## Sheet2
SiteCode | Key | CSG Type | Project Category | Implementation Scope | AE Implementation status: | AE Implementation Vendor: | RFS Date | Region | CSG uplink Port Capacity | EPOC Name | EPOC Down Link port | Service termination device | Handover Date | Integration Type
AJM0934 | Site 1854 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 45342 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/15 | AJM-0934-CSG-N540-LD-1 | 2024-02-17 | ZTP
IDX5806 | Site 712 | Passive | 5G | Passive patching | Passive Completed | XAD |  | DXB |  | DXB-DSO-CSG-IXR-E-1 | 1/1/26 | DXB-DSO-CSG-IXR-E-1 | 2024-02-19 | Passive site
IAJ5801 | Site 4339 | Passive | 5G+Migration | Passive patching | Passive Completed | SHAHID | 45336 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/51 | AJM-2450-SCSG-SR7B-1 | 2024-02-14 | Passive site
SHJ3310 | Site 11839 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45295 | SHJ | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | SHJ-3310-CSG-ASR920-LD-1 | 2024-01-03 | Manual
SHJ2104 | Site 11512 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45308 | SHJ | 10G | SHJ-2010-SCSG-IXR-R6D-1 | 1/5/c7/1 | SHJ-3104-CSG-ASR920-LD-1 | 2024-01-16 | Manual
SHJ2555 | Site 11709 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45308 | SHJ | 10G | SHJ-2010-SCSG-IXR-R6D-1 | 1/5/c8/1 | SHJ-2555-CSG-ASR920-LD-1 | 2024-01-16 | Manual
SHJ2522 | Site 11682 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45308 | SHJ | 10G | SHJ-2019-SCSG-IXR-R6D-1 | 1/5/c10/1 | SHJ-2522-CSG-ASR920-LD-1 | 2024-01-16 | Manual
SHJ2467 | Site 11652 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | SHJ | 10G | SHJ-2012-SCSG-IXR-R6D-1 | 1/5/c19/1 | SHJ-2467-CSG-ASR920-LD-1 | 2024-01-11 | Manual
SHJ2236 | Site 11548 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45303 | SHJ | 10G | SHJ-2019-SCSG-IXR-R6D-1 | 1/5/c9/1 | SHJ-2236-CSG-ASR920-LD-1 | 2024-01-11 | Manual
SHJ0689 | Site 3930 | Others | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45308 | SHJ | 10G | SHJ-2012-SCSG-IXR-R6D-1 | 1/5/c15/1 | SHJ-0689-CSG-N540-LD-1 | 2024-01-16 | Manual
SHJ0486 | Site 3389 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45301 | SHJ | 10G | SHJ-2226-SCSG-IXR-R6D-1 | 1/6/c6/1 | SHJ-0486-CSG-ASR920-LD-1 | 2024-01-08 | Manual
RAK3431 | Site 11308 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45306 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c14/1 | RAK-3431-CSG-N540-LD-1 | 2024-01-12 | Manual
RAK3235 | Site 11292 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45306 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c15/1 | RAK-3235-CSG-N540-LD-1 | 2024-01-12 | Manual
RAK3196 | Site 11289 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45307 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c16/1 | RAK-3196-CSG-N540-LD-1 | 2024-01-12 | Manual
RAK2892 | Site 11234 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | Ten0/0/0/41 | RAK-2892-CSG-ASR920-LD-1 | 2024-01-17 | Manual
RAK2743 | Site 11153 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | Ten0/0/0/31 | RAK-2743-CSG-N540-LD-1 | 2024-01-17 | Manual
RAK2726 | Site 11137 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | Ten0/0/0/42 | RAK-2726-CSG-ASR920-LD-1 | 2024-01-17 | Manual
RAK2381 | Site 11097 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45301 | RAK | 10G | RAK-2009-SCSG-IXR-R6D-1 | 1/5/c10/1 | RAK-2381-CSG-ASR920-LD-1 | 2024-01-08 | Manual
RAK2733 | Site 11144 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45303 | RAK | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | RAK-2105-CSG-ASR920-LD-1 | 2024-01-10 | Manual
DXN0965 | Site 3676 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/45 | DXN-0965-CSG-ASR920-LD-1 | 2024-01-17 | Manual
DXN0028 | Site 3471 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45303 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/5/c4 | DXN-0028-CSG-ASR920-LD-1 | 2024-01-10 | Manual
DXB3411 | Site 10417 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45308 | DXB | 10G | DXB-2302-SCSG-IXR-R6D-1 | 1/6/c10/1 | DXB-3411-CSG-N540-LD-1 | 2024-01-16 | Manual
DXB2589 | Site 9965 | Nokia SAR-M | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | DXB |  | DXB-1074-SCSG-IXR-R6D-1 | 1/6/c11 | DXB-2589-CSG-ASR920-LD-1 | 2024-01-18 | Manual
DXB1993 | Site 10178 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45303 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/5/c20 | DXB-1993-CSG-N540-LD-1 | 2024-01-10 | Manual
DXB1051 | Site 8583 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | DXB | 10G | DXB-3165-SCSG-IXR-R6D-2 | 1/6/c1 | DXB-1051-CSG-ASR920-LD-1 | 2024-01-18 | Manual
AUH3235 | Site 8210 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45303 | AUH | 10G | AUH-DC-AGGR-SR12e-1/AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUH-3235-CSG-ASR920-LD-1 | 2024-01-09 | Manual
AUH3192 | Site 7437 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45310 | AUH | 10G | AUH-2205-SCSG-IXR-R6D-1 | 1/3/c2/1 | AUH-3192-CSG-N540-LD-1 | 2024-01-18 | Manual
AUH2963 | Site 8169 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45302 | AUH | 10G | AUH-DC-AGGR-SR12e-1/AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUH-2963-CSG-ASR920-LD-1 | 2024-01-03 | Manual
AAN3418 | Site 6320 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45303 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c20/1 | AAN-3418-CSG-N540-LD-1 | 2024-01-09 | Manual
AAN3362 | Site 6290 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45299 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c13/1 | AAN-3362-CSG-N540-LD-1 | 2024-01-05 | Manual
AAN3361 | Site 6289 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45299 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c14/1 | AAN-3361-CSG-N540-LD-1 | 2024-01-05 | Manual
AAN3144 | Site 6182 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45299 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c15/1 | AAN-3144-CSG-N540-LD-1 | 2024-01-05 | Manual
AAN2802 | Site 6637 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45295 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c13/1 | AAN-2802-CSG-ASR920-LD-1 | 2024-01-03 | Manual
AAN2620 | Site 6099 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45299 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c16/1 | AAN-2620-CSG-N540-LD-1 | 2024-01-04 | Manual
AAN2605 | Site 6091 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45301 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c19/1 | AAN-2605-CSG-ASR920-LD-1 | 2024-01-08 | Manual
AAN2572 | Site 6079 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 45301 | AUH | 10G | AAN-2399-SCSG-IXR-R6D-1 | 1/6/c2/1 | AAN-2572-CSG-ASR920-LD-1 | 2024-01-08 | Manual
AJM0988 | Site 3961 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 45328 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/52 | AJM-0988-CSG-N540-LD-1 | 2024-02-02 | ZTP
DUB0883 | #N/A | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 45329 | DXB | 10G | DXB-0296A-PREAGG-SR7-1 | 2/1/4 | DUB-0883-CSG-IXR-E-1 | 2024-02-05 | ZTP
AAN3633 | #N/A | Cisco NCS540 | Migration | New CSG | RFSed | HOI-MEA | 45330 | AUH | 10G | AAN-3633-CSG0N540-LD-1 |  | AAN-3633-CSG-N540-LD-1 | 2024-02-08 | ZTP
DXB1949 | Site 9849 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 45328 | DXB | 10G | DXB-3155-SCSG-IXR-R6D-1 | 1/3/c4 | DXB-1949-CSG-N540-LD-1 | 2024-02-03 | ZTP
DXB1606 | Site 9777 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 45328 | DXB | 10G | DXB-6002-SCSG-IXR-R6D-1 | 1/3/c1 | DXB1606-CSG-N540-LD-1 | 2024-02-03 | ZTP
AAN3349 | Site 6278 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 45323 | AUH | 10G | AAN-2020-SCSG-IXR-R6-1 | Port 1/3/10 | AAN3349-CSG-N540-LD-1 | 2024-01-31 | ZTP
AUH3271 | Site 7476 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 45335 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | Port 2/2/2 | AUH-3271-CSG-N540-LD-1 | 2024-02-08 | ZTP
IAD5536 | Site 3614 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 45318 | AUH | 1G | AUH-1336-SCSG-SR7B-1 | esat-2/1/5 | AUH-1336-SCSG-SR7B-1 | 2024-01-26 | Passive site
AUH3501 | Site 7555 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 45330 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | esat-2/1/49 | AUH-3501-CSG-N540-LD-1 | 2024-01-31 | ZTP
AAN2077 | Site 5938 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 45327 | AUH |  | AAN-2006-PREAGG-SR7-1 | Port 5/1/5 | AAN-2077-CSG-IXR-E-1 | 2024-02-01 | ZTP
AAN2925 | Site 6151 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 45328 | AUH | 10G | AAN-2006-PREAGG-SR7-1 | Port 5/1/2 | AAN-2925-CSG-N540-LD-1 | 2024-02-01 | ZTP
AAN0009 | Site 2639 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 45325 | AUH |  | AAN-2038-CSG-SAR-X-1 | Port 1/2/5 | AAN-2038-CSG-SAR-X-1 | 2024-02-03 | Passive site
AUH6135 | Site 7953 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45335 | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-1/1/31 | AUH-6135-CSG-N540-LD-1 | 2024-02-09 | ZTP
AAN2941 | Site 6155 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45321 | AUH | 10G | AAN-2019-SCSG-IXR-R6-1 | Port 1/5/9 | AAN-2941-CSG-N540-LD-1 | 2024-01-26 | ZTP
FUJ1439 | Site 10672 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45323 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Te0/8/0/29 | FUJ-1439-CSG-N540-LD-1 | 2024-01-30 | ZTP
FUJ0677 | Site 4532 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45323 | FUJ | 10G | FUJ-6001-AGG-ASR9912-2 | Te0/8/0/30 | FUJ-0677-CSG-IXR-E-1 | 2024-01-31 | ZTP
AUH0861 | Site 3120 | Passive | Migration | Passive patching | Passive Completed | XAD | 45323 | AUH |  | AUH-2219-CSG-SAR-X-1 | Port 1/2/3 | AUH-2219-CSG-SAR-X-1 | 2024-02-17 | Passive site
ISH5212 | Site 5904 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 45309 | SHJ |  | SHJ-2580-SCSG-SR7B-1 | esat-1/1/14 | SHJ-2580-SCSG-SR7B-1 | 2024-01-18 | Passive site
IAD5561 | Site 3782 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 45323 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/43 | IAD-5501-CSG-N540-LD-1 | 2024-01-30 | ZTP
AUH2027 | Site 7745 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45313 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-1/1/50 | AUH-2027-CSG-IXR-E-1 | 2024-01-20 | ZTP
FUJ3403 | Site 10861 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 45336 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Te0/8/0/30 | FUJ-3403-CSG-IXR-E-1 | 2024-02-10 | ZTP
DXB2467 | Site 10338 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 45327 | DXB | 10G | DXB-DGPOP1-AGGR-SR12e-1 | esat-1/1/27 | DXB-2467-CSG-N540-LD-1 | 2024-02-02 | ZTP
AUH3566 | Site 7590 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 45328 | AUH | 10G | AUH-1090-SCSG-SR7B-1 | esat-1/1/48 | AUH-3566-CSG-N540-LD-1 | 2024-01-27 | ZTP
IAD5194 | Site 4950 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 45311 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-2/1/13 | AUH-1336-SCSG-SR7B-1 | 2024-01-19 | Passive site
FUJ3279 | Site 10853 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45322 | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/3 | FUJ-3279-CSG-IXR-E-1 | 2024-01-27 | ZTP
DXB2940 | Site 10021 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45320 | DXB | 10G | DXB-MIRDIFPOP-AGGR-SR12e-1 | esat-1/1/37 | DXB-2940-CSG-IXR-E-1 | 2024-01-25 | ZTP
AUH2096 | Site 7363 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 45334 | AUH | 10G | AUH-2054-PREAGG-SR7-1 | Port 4/1/4 | AUH-2096-CSG-IXR-E-1 | 2024-02-03 | ZTP
AUH2339 | Site 7497 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 45316 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/12 | AUH-2339-CSG-IXR-E-1 | 2024-01-24 | ZTP
AUH3339 | Site 7811 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45313 | AUH | 10G | AUH-1426-SCSG-SR7B-1 | esat-1/1/59 | AUH-3339-CSG-N540-LD-1 | 2024-01-18 | ZTP
AUH2496 | Site 7848 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45313 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/21 | AUH-2496-CSG-N540-LD-1 | 2024-01-19 | ZTP
UAQ1005 | Site 12018 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45316 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/12 | UAQ-1005-CSG-N540-LD-1 | 2024-01-22 | ZTP
DXB0019 | Site 1171 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 45306 | DXB | 10G | DXB-0296A-PREAGG-SR7-1 | 2/1/2 | DXB-0019B-CSG-IXR-E-1 | 2024-01-11 | ZTP
RAK1167 | Site 12166 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 45306 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-1 | Port 1/3/c11 | RAK1167-CSG-IXR-E-1 | 2024-01-11 | ZTP
AAN2316 | Site 5983 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | SHAHID | 45310 | AUH | 10G | AUH-5002-AGGR-SR7-2 | Port 5/2/4 | AAN-2316-CSG-IXR-E-1 | 2024-01-16 | ZTP
KFN2616 | Site 10960 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45296 | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#B03 OTN RK-1/NE516 C/03/TX15/RX15 | KFN-2616-CSG-IXR-E-1 | 2024-01-04 | ZTP
KFN3630 | Site 11041 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45301 | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#A4 OTN RK-1/NE516 C/03/TX4/R4 | KFN-3630-CSG-N540-LD-1 | 2024-01-05 | ZTP
ISH5168 | #N/A | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 45313 | SHJ | 10G | SHJ-2017-AGGR-SR7B-1 | esat-1/1/57 | ISH-5168-CSG-IXR-E-1 | 2024-01-18 | ZTP
DXB1659 | Site 8927 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | SHAHID | 45342 | DXB | 10G | DXB-MIRDIFPOP-SCSG-NCS57C3-1 | TF0/0/0/1 | DXB-1659-CSG-IXR-E-1 | 2024-02-19 | Manual
AUH0043 | #N/A | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 45328 | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/9 | AUH-0043-CSG-N540-LD-1 | 2024-02-01 | ZTP
AUH0897 | Site 1881 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45301 | AUH | 10G | AUH-2937-PREAGG-SR7-1 | 2/2/1 | AUH-0897-CSG-IXR-E-1 | 2024-01-08 | ZTP
IFU5616 | #N/A | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 45310 | FUJ |  | FUJ-3712-CSG-ASR920-LD-1 | Gi0/0/10 | FUJ-3712-CSG-ASR920-LD-1 | 2024-01-19 | Passive site
SHJ1630 | #N/A | Nokia IXR-E | Rollout + 5G | New CSG | RFSed | SHAHID | 45334 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/24 | SHJ-1630-CSG-IXR-E-1 | 2024-02-09 | ZTP
DXB0282 | Site 2669 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45314 | DXB | 10G | DXB-2268-SCSG-IXR-R6-1 | 1/1/3 | DXB-0282-CSG-IXR-E-1 | 2024-01-08 | ZTP
AUH6399 | Site 8454 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 45315 | AUH | 10G | AUH-2908-PREAGG-SR7-1 | Port 5/1/1 | AUH-6399-CSG-IXR-E-1 | 2024-01-22 | ZTP
AUH0408 | Site 2237 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 45324 | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/2 | AUH-0408-CSG-N540-LD-1 | 2024-01-22 | ZTP
IAD5306 | Site 3825 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 45299 | AUH |  | AUH-2223-SCSG-IXR-R6D-1 | 1G Port | AUH-2223-SCSG-IXR-R6D-1 | 2024-01-08 | Passive site