## owssvr - 2024-02-20T124028.917
Issue ID | Work Order No. | PO Number/Release Number | Project Code | Project Name | Site Code | CSG Type | Project Category | Implementation Scope | AE Implementation status: | AE Implementation Vendor: | RFS Date | Region | CSG uplink Port Capacity | EPOC Name | EPOC Down Link port | Service termination device | CSG Device Serial # | Update Mobile OD Status | 2G: (No. Of Services) | 3G: (No. Of Services): | 4G: (No. Of Services): | 5G: (No. Of Services): | AE Implementation Remark: | Assigned to | CR Actual Completion | Handover Date | SEB Ref # | SFP Type | Migration Vendor | Migration Status | Link Status | RFS Notification | Year | Created By | Project Created | GAID | Latitude | Longitude | Integration Type | Auto Generate WO IIB-CSG | Item Type | Path
2599 | WO- IIB-CSG-2024-Order # 2599 |  | AUH0039 |  | AUH0039 | Passive |  | Passive patching | PTW in progress | XAD |  | AUH | [5 empty] | 5 | [5 empty] | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2024 | Rogelio Pangilinan | 2024-02-20 09:02 |  | 24.447114 | 54.394981 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2598 | WO- IIB-CSG-2024-Order # 2598 |  | AUH0038 |  | AUH0038 | Passive |  | Passive patching | PTW in progress | XAD |  | AUH | [5 empty] | 5 | [5 empty] | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2024 | Rogelio Pangilinan | 2024-02-20 09:01 |  | 24.447036 | 54.394344 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2597 | WO- IIB-CSG-2024-Order # 2597 |  | AUH0037 |  | AUH0037 | Passive |  | Passive patching | PTW in progress | XAD |  | AUH | [5 empty] | 5 | [5 empty] | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2024 | Rogelio Pangilinan | 2024-02-20 08:59 |  | 24.44775 | 54.395333 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2596 | WO- IIB-CSG-2024-Order # 2596 |  | DXBZAFRAN |  | DXBZAFRAN |  | Migration |  |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-19 14:22 | DXB_E3278F_10305_001001002 | 25.18815 | 55.24982 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2595 | WO- IIB-CSG-2024-Order # 2595 |  | DXBKHAZNA |  | DXBKHAZNA |  | Migration |  |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-19 14:19 | DXB_E3278M_10098_001002010 | 25.17541 | 55.31798 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2594 | WO- IIB-CSG-2024-Order # 2594 |  | DXB6004 |  | DXB6004 |  | Migration |  |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-19 14:17 | DXB_E3178R_13163_001001001 | 25.1555 | 55.21152 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2593 | WO- IIB-CSG-2024-Order # 2593 |  | DXB6504 |  | DXB6504 |  | Migration |  |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-19 14:15 | DXB_E3176A_10003_001010006 | 25.02781 | 55.18508 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2592 | WO- IIB-CSG-2024-Order # 2592 |  | DXB6501 |  | DXB6501 |  | Migration |  |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-19 14:10 | DXB_E3077M_10006_001001003 | 25.071056 | 55.125750 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2591 | WO- IIB-CSG-2024-Order # 2591 |  | DXB6020 |  | DXB6020 |  | Migration |  |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-19 14:09 | DXB_E3177B_10710_001002001 | 25.111701 | 55.203026 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2590 | WO- IIB-CSG-2024-Order # 2590 |  | IADNR5153 |  | IADNR5153 | Passive | 5G | Passive patching | PTW in progress | XAD |  | AUH |  | IAD-5151-CSG-SAR-8-1 | 1/1/6 | IAD-5151-CSG-SAR-8-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-19 12:27 |  | 24.469106 | 54.375173 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2589 | WO- IIB-CSG-2024-Order # 2589 |  | IADNR5151 |  | IADNR5151 | Passive | 5G | Passive patching | PTW in progress | XAD |  | AUH |  | IAD-5151-CSG-SAR-8-1 | 1/2/6 | IAD-5151-CSG-SAR-8-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-19 12:25 |  | 24.469106 | 375173 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2588 | WO- IIB-CSG-2024-Order # 2588 |  | IADNR5203 |  | IADNR5203 | Passive | 5G | Passive patching | PTW in progress | XAD |  | AUH |  | IAD-5151-CSG-SAR-8-1 | 1/2/5 | IAD-5151-CSG-SAR-8-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-19 12:23 |  | 24.469106 | 54.375173 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2587 | WO- IIB-CSG-2024-Order # 2587 |  | IAD5474 |  | IAD5474 | Cisco NCS540 | Migration | New CSG | Survey in progress | SHAHID |  | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-1/1/9 | IAD5474-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 | Survey in progress | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-02-19 12:04 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2586 | WO- IIB-CSG-2024-Order # 2586 |  | IAD5449 |  | IAD5449 | Cisco NCS540 | Migration | New CSG | Survey in progress | SHAHID |  | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-1/1/6 | IAD5449-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 | Survey in progress | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-02-19 12:02 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2585 | WO- IIB-CSG-2024-Order # 2585 |  | SHJ3764 |  | SHJ3764 | Cisco NCS540 | BAU + 5G | New CSG | Survey in progress | SHAHID |  | SHJ |  | SHJ-2547-SCSG-SR7B-1 | esat-1/1/8 | SHJ3764-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 | Survey in progress | [5 empty] | Cisco |  |  | FALSE | 2024 | Munaim Abdul salam | 2024-02-19 11:35 |  | 25.2587 | 55.5816 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2584 | WO- IIB-CSG-2024-Order # 2584 |  | IDX0058T |  | IDX0058T | Passive | Migration | Passive patching | PTW in progress | SHAHID |  | DXB |  | DXB-FCPOP-SCSG-SR7B-2 | esat-1/1/18 | DXB-FCPOP-SCSG-SR7B-2 |  | 5 |  | 1 | 1 |  | PTW in progress | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-02-15 17:48 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2583 | WO- IIB-CSG-2024-Order # 2583 |  | AAN0090 |  | AAN0090 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 5/1/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 13:17 | AAN_E3568L_10002_001001001 | 24.27911 | 55.60543 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2582 | WO- IIB-CSG-2024-Order # 2582 |  | AUH3165 |  | AUH3165 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2142-SCSG-IXR-R6D-1 | 1/5/c1/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 13:15 | AUH_E2871V_10002_001001001 | 24.49947 | 54.91118 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2581 |  |  | IDX5354 |  | IDX5354 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-6501-AGGR-SR12e-1 | 7/1/17 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 13:12 | DXB_E3077N_10792_001002004 | 25.080243 | 55.120570 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2580 |  |  | SHJ2342 |  | SHJ2342 | Nokia IXR-E | Rollout |  |  | Nokia |  | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/2 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 13:08 | SHJ_E3480W_10002_001001001 | 25.322719 | 55.503915 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2579 |  |  | AUH0600 |  | AUH0600 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-MASDARCITY-PREAGG-SR7-1 | 3/1/4 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 13:05 | AUH_E2570L_10022_001001002 | 24.4332 | 54.61765 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2578 |  |  | DXN0702 |  | DXN0702 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-VH-SCSG-SR7B-1 | 1/2/c6/1 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 13:03 | DXB_E3177Q_11960_001011015 | 25.05594 | 55.20374 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2577 |  |  | AUH3908 |  | AUH3908 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/44 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 12:56 | AUH_E2469M_10534_001001001 | 24.34827 | 54.54494 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2576 |  |  | DXB2906 |  | DXB2906 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-PALMJ-AGGR-SR7B-2 | esat-1/1/36 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 12:51 | DXB_E3077J_10668_001001001 | 25.09679 | 55.15234 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2575 |  |  | DXT6523 |  | DXT6523 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-6504-AGGR-SR12e-1 | esat-1/1/2 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 12:47 | DXB_E3176P_10010_001001001 | 24.96619 | 55.17636 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2574 |  |  | AAN2588 |  | AAN2588 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 4/1/3 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 12:42 | AAN_E3367P_10001_001001001 | 24.15273 | 55.38235 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2573 |  |  | DXN0773 |  | DXN0773 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-VH-SCSG-SR7B-1 | esat-1/1/27 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-14 12:34 | DXB_E3177W_10039_001001004 | 25.03652 | 55.22074 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2572 | WO- IIB-CSG-2024-Order # 2572 |  | AAN2541 |  | AAN2541 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AAN-2049-SCSG-SR7B-1 | esat-1/1/51 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 11:10 | AAN_E3568R_10001_001001001 | 24.25587 | 55.6167 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2571 | WO- IIB-CSG-2024-Order # 2571 |  | KFN2626 |  | KFN2626 | Nokia IXR-E | Rollout |  |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Hu0/0/0/3 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 11:06 | FJR_E4183X_10001_001001001 | 25.6027 | 56.23216 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2570 | WO- IIB-CSG-2024-Order # 2570 |  | AAN2410 |  | AAN2410 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AAN-2495-PREAGG-SR7-1 | 2/2/2 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 11:04 | AAN_E3672M_10001_001001001 | 24.641532 | 55.708853 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2569 | WO- IIB-CSG-2024-Order # 2569 |  | DXB1365 |  | DXB1365 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-PALMJ-AGGR-SR7B-2 | esat-1/1/35 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 11:00 | DXB_E3077C_10323_001001001 | 25.11769 | 55.12025 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2568 | WO- IIB-CSG-2024-Order # 2568 |  | DXB1364 |  | DXB1364 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-PALMJ-AGGR-SR7B-2 | esat-1/1/34 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 10:56 | DXB_E3078X_10523_001001001 | 25.1255 | 55.13247 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2567 | WO- IIB-CSG-2024-Order # 2567 |  | SHJ2531 |  | SHJ2531 | Nokia IXR-E | Rollout |  |  | Nokia |  | SHJ | Others | SHJ-2226-SCSG-IXR-R6D-1 | 1/3/c1/1 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 10:53 | SHJ_E3379A_10190_001001001 | 25.30313 | 55.364356 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2566 | WO- IIB-CSG-2024-Order # 2566 |  | DXB0914 |  | DXB0914 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-3155-SCSG-IXR-R6D-1 | 1/3/c1/1 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 10:49 | DXB_E3278Q_10170_001001002 | 25.156 | 55.301 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2565 | WO- IIB-CSG-2024-Order # 2565 |  | AUH0593 |  | AUH0593 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-1048-PREAGG-SR7-1 | 5/1/3 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 10:46 | AUH_E2270A_10010_001002005 | 24.465723 | 54.307574 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2564 | WO- IIB-CSG-2024-Order # 2564 |  | RAK3193 |  | RAK3193 | Nokia IXR-E | Rollout |  |  | Nokia |  | RAK | 1G | UAQ-2806-PREAGG-SR7-1 | 2/1/19 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-02-14 10:43 | RKT_E3883G_10084_001001001 | 25.642735 | 55.889936 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2563 | WO- IIB-CSG-2024-Order # 2563 |  | AUH0637 |  | AUH0637 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2036-SCSG-IXR-R6-1 | 1/4/10 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:36 | AUH_E2570G_10019_001003001 | 24.465166 | 54.604346 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2562 | WO- IIB-CSG-2024-Order # 2562 |  | AUH0839 |  | AUH0839 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 5/1/2 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:31 | AUH_E2371P_10193_001006001 | 24.500828 | 54.38899 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2561 | WO- IIB-CSG-2024-Order # 2561 |  | AUH0838 |  | AUH0838 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 5/1/3 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:25 | AUH_E2371P_10194_001002001 | 24.501667 | 54.39014 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2560 | WO- IIB-CSG-2024-Order # 2560 |  | AUH0840 |  | AUH0840 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 5/1/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:22 | AUH_E2371P_10190_001017001 | 24.501667 | 54.39014 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2559 | WO- IIB-CSG-2024-Order # 2559 |  | AUH0837 |  | AUH0837 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 5/1/4 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:18 | AUH_E2371P_10192_001018001 | 24.502059 | 54.389141 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2558 | WO- IIB-CSG-2024-Order # 2558 |  | KFN2681 |  | KFN2681 | Nokia IXR-E | Rollout |  |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Hu0/0/0/3 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:14 | FJR_E4081T_10005_001001001 | 25.4241 | 56.1519 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2557 | WO- IIB-CSG-2024-Order # 2557 |  | AUH3865 |  | AUH3865 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-2 | esat-1/1/42 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:10 | AUH_E2570L_10084_001001001 | 24.44271 | 54.61495 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2556 | WO- IIB-CSG-2024-Order # 2556 |  | DXB1744 |  | DXB1744 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-1852-SCSG-IXR-R6D-2 | 1/6/c11/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:05 | DXB_E3579U_10037_001001001 | 25.23301 | 55.56268 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2555 | WO- IIB-CSG-2024-Order # 2555 |  | DXB1473 |  | DXB1473 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-DOZ-SCSG-SR7B-1 | esat-2/1/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 21:01 | DXB_E3377C_10049_001001001 | 25.11872 | 55.41108 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2554 | WO- IIB-CSG-2024-Order # 2554 |  | AUH2074 |  | AUH2074 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/23 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:58 | AUH_E2270O_11634_001001001 | 24.43036 | 54.37268 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2553 | WO- IIB-CSG-2024-Order # 2553 |  | DXB3331 |  | DXB3331 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-VILLAPOP-AGGR-SR12e-1 | 2/1/11 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:53 | DXB_E3378V_10002_001007001 | 25.14422 | 55.39617 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2552 | WO- IIB-CSG-2024-Order # 2552 |  | DXB3124 |  | DXB3124 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-3122-SCSG-SR7B-1 | esat-1/1/46 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:49 | DXB_E3279L_13067_001001001 | 25.26239 | 55.28756 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2551 | WO- IIB-CSG-2024-Order # 2551 |  | DXB0837 |  | DXB0837 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | TF0/0/0/14 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:43 | DXB_E3177Y_10570_001003003 | 25.0411 | 55.2516 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2550 |  |  | DXB2004 |  | DXB2004 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-VH-SCSG-SR7B-1 | 1/2/c8/1 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:38 | DXB_E3176C_10492_001001001 | 25.04321 | 55.23167 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2549 | WO- IIB-CSG-2024-Order # 2549 |  | DXB1710 |  | DXB1710 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-1156-SCSG-NCS57C3-1 | TF0/0/0/7 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:35 | DXB_E3177C_11906_001001001 | 25.1248 | 55.20875 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2548 | WO- IIB-CSG-2024-Order # 2548 |  | DXB1315 |  | DXB1315 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-6002-SCSG-IXR-R6D-1 | 1/5/c4/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:31 | DXB_E3278X_10001_001001001 | 25.13553 | 55.33622 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2547 | WO- IIB-CSG-2024-Order # 2547 |  | AUH0712 |  | AUH0712 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2184-SCSG-IXR-R6D-1 | 1/3/c15/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:26 | AUH_E2270H_10959_001004001 | 24.47637 | 54.35644 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2546 | WO- IIB-CSG-2024-Order # 2546 |  | DXB2757 |  | DXB2757 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-6501-SCSG-NCS57C3-1 | TF0/0/0/6 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:18 | DXB_E3077M_10013_001001001 | 25.07056 | 55.12483 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2545 | WO- IIB-CSG-2024-Order # 2545 |  | DXB1877 |  | DXB1877 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-2123-PREAGG-SR7-1 | 5/1/4 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 20:12 | DXB_E3378T_10006_001001001 | 25.15546 | 55.45788 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2544 | WO- IIB-CSG-2024-Order # 2544 |  | DXB0068 |  | DXB0068 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-3252-SCSG-SR7B-1 | esat-1/1/40 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:59 | DXB_E3279W_10856_001004004 | 25.2279 | 55.32046 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2543 | WO- IIB-CSG-2024-Order # 2543 |  | KFN2627 |  | KFN2627 | Nokia IXR-E | Rollout |  |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Hu0/0/0/3 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:55 | FJR_E4081T_10004_001001001 | 25.43243 | 56.14053 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2542 |  |  | SHJ5343 |  | SHJ5343 | Nokia IXR-E | Rollout |  |  | Nokia |  | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-3/1/28 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:50 | SHJ_E3380K_10005_001001002 | 25.344189 | 55.3759 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2541 | WO- IIB-CSG-2024-Order # 2541 |  | DXB1347 |  | DXB1347 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-0298-SCSG-NCS57C3-1 | TF0/0/0/31 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:43 | DXB_E3177A_11008_001001001 | 25.12331 | 55.18127 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2540 | WO- IIB-CSG-2024-Order # 2540 |  | DXB1001 |  | DXB1001 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-6501-SCSG-NCS57C3-1 | TF0/0/0/23 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:39 | DXB_E3077V_10370_001001001 | 25.039917 | 55.1064415 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2539 | WO- IIB-CSG-2024-Order # 2539 |  | AUH2347 |  | AUH2347 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2054-PREAGG-SR7-1 | 4/1/2 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:34 | AUH_E2370K_12708_001001001 | 24.43014 | 54.39341 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2538 | WO- IIB-CSG-2024-Order # 2538 |  | DXB1822 |  | DXB1822 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-1998-AGGR-SR12e-1 | 2/1/32 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:30 | DXB_E3379G_11010_001001001 | 25.27920 | 55.38520 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2537 | WO- IIB-CSG-2024-Order # 2537 |  | DXB0798 |  | DXB0798 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/25 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:23 | DXB_E3279N_11573_001001002 | 25.2561 | 55.3288 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2536 | WO- IIB-CSG-2024-Order # 2536 |  | DXB1257 |  | DXB1257 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/11 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:17 | DXB_E3279H_13327_001001001 | 25.272370 | 55.318100 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2535 | WO- IIB-CSG-2024-Order # 2535 |  | DXN0064 |  | DXN0064 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-DSO-DC-AGGR-SR7S-1 | esat-1/1/19 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-02-13 19:11 | DXB_E3377A_10203_001002001 | 25.11357 | 55.37304 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2534 | WO- IIB-CSG-2024-Order # 2534 |  | AUH6363 |  | AUH6363 | Nokia IXR-E | Rollout | New CSG | Commissioning in progress | XAD |  | AUH | 10G | AUH2934 MS OTN | AUH-KHAZNA-AGG-SR12e-1 RK1/SH-1 /Front Port# A02 OTN RK-1/NE787 C/03/TX01/RX01 | AUH-6363-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-13 11:43 |  | 23.1157 | 53.7946 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2533 | WO- IIB-CSG-2024-Order # 2533 |  | DUB0028 |  | DUB0028 | Passive | Rollout | Passive patching | PTW in progress | XAD |  | DXB |  | DXB-ZAFRAN-AGG-SR12E-2 | Port : 3/1/20 | DXB-ZAFRAN-AGG-SR12E-2 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-12 15:09 |  | 25.186667 | 55.257311 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2532 | WO- IIB-CSG-2024-Order # 2532 |  | RAK0523 |  | RAK0523 | Nokia IXR-E | 5G+Migration | New CSG | PTW in progress | XAD |  | RAK | 10G | NE506 (RAK2028-UAQDC) | RAK2028_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#B10 OTN RK-1/NE506 C/03/TX22/RX22 | RAK-0523-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-12 12:29 |  | 25.699922 | 55.782636 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2531 | WO- IIB-CSG-2024-Order # 2531 |  | AJM0933 |  | AJM0933 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | XAD | 2024-02-20 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/17 | AJM-0933-CSG-IXR-E-1 | NK224931398 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  | Y23-F117828 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-12 12:11 | AJM_E3580A_10152_001036018 | 25.39039 | 55.571870 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2530 | WO- IIB-CSG-2024-Order # 2530 |  | AJM0934 |  | AJM0934 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2024-02-20 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/15 | AJM-0934-CSG-N540-LD-1 | FOC2718N597 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-17 | Y23-F117824 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-12 11:49 | AJM_E3580A_10325_001037019 | 25.391001 | 55.572171 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2529 | WO- IIB-CSG-2024-Order # 2529 |  | IAD5356 |  | IAD5356 | Nokia IXR-E | Migration | New CSG | PTW in progress | SHAHID |  | AUH |  | AUH-2184-SCSG-IXR-R6D-1 | Port 1/3/c17/1 | IAD-5356-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 | [6 empty] | Nokia |  |  | FALSE | 2024 | Munaim Abdul salam | 2024-02-10 11:41 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2528 | WO- IIB-CSG-2024-Order # 2528 |  | IDXNR5806 |  | IDX5806 | Passive | 5G | Passive patching | Passive Completed | XAD |  | DXB |  | DXB-DSO-CSG-IXR-E-1 | 1/1/26 | DXB-DSO-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-19 |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-09 15:12 |  | 25.108047 | 55.376429 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2527 | WO- IIB-CSG-2024-Order # 2527 |  | DUB0434 |  | DUB0434 |  | Rollout | Passive patching | Transmission rack not available | HOI-MEA |  | DXB |  | DXB-1156-SCSG-NCS57C3-1 | TF0/0/0/10 | DXB-1156-SCSG-NCS57C3-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-08 15:08 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2526 | WO- IIB-CSG-2024-Order # 2526 |  | DUB0514 |  | DUB0514 |  | Rollout | Passive patching | Transmission rack not available | HOI-MEA |  | DXB |  | DXB-DGPOP2-SCSG-NCS57C3-1 | TF0/0/0/7 | DXB-DGPOP2-SCSG-NCS57C3-1 |  | 5 |  |  |  |  | * | [5 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-08 15:07 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2525 | WO- IIB-CSG-2024-Order # 2525 |  | DUB0457 |  | DUB0457 |  | Rollout | Passive patching | Passive Completed | HOI-MEA | 2024-02-15 | DXB | 10G | DXB-1022-CSG-SAR-X-1 | 1/3/4 | DXB-1022-CSG-SAR-X-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-08 15:05 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2524 | WO- IIB-CSG-2024-Order # 2524 |  | ISH5247 |  | ISH5247 |  | BAU | Passive patching | Transmission rack not available | HOI-MEA |  | SHJ |  | SHJ-2580-SCSG-SR7B-1 | esat-2/1/42 | SHJ-2580-SCSG-SR7B-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-08 15:02 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2523 | WO- IIB-CSG-2024-Order # 2523 |  | RAK0526 |  | RAK0526 | Nokia IXR-E | 5G+Migration | New CSG | Commissioning in progress | HOI-MEA |  | RAK |  | RAK2028_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#B09 OTN RK-1/NE506 C/03/TX21/RX21 | OTN Link |  |  | 5 | [13 empty] | FALSE | 2024 | Syed Shahzaib | 2024-02-08 14:59 |  |  |  | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2522 | WO- IIB-CSG-2024-Order # 2522 |  | SHJ6255 |  | SHJ6255 | Nokia IXR-E | BAU | New CSG | Commissioning in progress | HOI-MEA |  | SHJ | 10G | SHJ-2547-SCSG-SR7B-1 | esat-1/1/7 | SHJ-6255-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-08 14:56 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2521 |  |  | DXB0838 |  | DXB0838 |  | Migration | Passive patching | Passive Completed | HOI-MEA | 2024-02-07 | DXB |  | DXB-0837-CSG-IXR-E-1 | 1/1/12 | DXB-0837-CSG-IXR-E-1 | [12 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-08 14:52 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2520 | WO- IIB-CSG-2024-Order # 2520 |  | IAJ5801 |  | IAJ5801 | Passive | 5G+Migration | Passive patching | Passive Completed | SHAHID | 2024-02-14 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/51 | AJM-2450-SCSG-SR7B-1 |  | 5 |  | 1 | 1 | 1 | Passive Completed |  |  | 2024-02-14 | [5 empty] | FALSE | 2024 | Munaim Abdul salam | 2024-02-06 09:50 |  | 25.3902 | 55.57259 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2519 | WO- IIB-CSG-2024-Order # 2519 |  | SHJ3889 _ 1 X CSG_Rehoming (Migration) |  | SHJ3889 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | SHJ | 10G | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c1/1 | SHJ-3889-CSG-ASR920-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-21 | Y23-F113968 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 18:11 | SHJ_E3379E_10030_001001001 | 25.29818995 | 55.46017783 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2518 | WO- IIB-CSG-2024-Order # 2518 |  | SHJ3723 _ 1 X CSG_Rehoming (Migration) |  | SHJ3723 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | SHJ | 10G | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c3/1 | SHJ-3723-CSG-ASR920-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-21 | Y23-F113976 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 18:07 | SHJ_E3379E_10032_001001001 | 25.3079281 | 55.45282243 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2517 |  |  | SHJ3310 _ 1 X CSG_Rehoming (Migration) |  | SHJ3310 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-04 | SHJ | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | SHJ-3310-CSG-ASR920-LD-1 | CAT2427U3WN |  |  | 1 | 1 |  |  | Tasif Maqbool;#267 |  | 2024-01-03 | Y23-F114770 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 18:02 | SHJ_E3380W_10016_001001001 | 25.31177655 | 55.41771621 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2516 | WO- IIB-CSG-2024-Order # 2516 |  | SHJ3104 _ 1 X CSG_Rehoming (Migration) |  | SHJ3104 | Cisco ASR920 | Migration | Rollout Passive Patching | RFSed | Cisco | 2024-01-17 | SHJ | 10G | SHJ-2010-SCSG-IXR-R6D-1 | 1/5/c7/1 | SHJ-304-CSG-ASR920-LD-1 | CAT2343U3CK | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-16 | Y23-F115522 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:55 | SHJ_E3380O_10005_001001001 | 25.34900815 | 55.45418472 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2515 |  |  | SHJ2555 _ 1 X CSG_Rehoming (Migration) |  | SHJ2555 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-17 | SHJ | 10G | SHJ-2010-SCSG-IXR-R6D-1 | 1/5/c8/1 | SHJ-2555-CSG-ASR920-LD-1 | CAT2343U3CC |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-16 | Y23-F115524 |  | Nokia |  |  | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:52 | SHJ_E3480P_10002_001001001 | 25.34275227 | 55.4608262 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2514 |  |  | SHJ2543 _ 1 X CSG_Rehoming (Migration) |  | SHJ2543 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-04 | SHJ | 10G | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c4/1 | SHJ-2543-CSG-ASR920-LD-1 | CAT2334U55N |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-28 | Y23-F114453 |  | Nokia |  |  | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:48 | SHJ_E3380Y_10003_001001001 | 25.32421 | 55.45625968 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2513 |  |  | SHJ2522 _ 1 X CSG_Rehoming (Migration) |  | SHJ2522 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-17 | SHJ | 10G | SHJ-2019-SCSG-IXR-R6D-1 | 1/5/c10/1 | SHJ-2522-CSG-ASR920-LD-1 | CAT2339U1Y8 |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-16 | Y23-F115526 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:45 | SHJ_E3380H_10006_001001001 | 25.36426182 | 55.41338051 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2512 |  |  | SHJ2509 _ 1 X CSG_Rehoming (Migration) |  | SHJ2509 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | SHJ | 10G | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c5/1 | SHJ-2509-CSG-ASR920-LD-1 | CAT2343U3BK |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-21 | Y23-F113949 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:40 | SHJ_E3380Y_10002_001001001 | 25.3180443918 | 55.45036283 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2511 |  |  | SHJ2467 _ 1 X CSG_Rehoming (Migration) |  | SHJ2467 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | SHJ | 10G | SHJ-2012-SCSG-IXR-R6D-1 | 1/5/c19/1 | SHJ-2467-CSG-ASR920-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-11 | Y23-F115255 |  | Nokia | Completed |  | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:36 | SHJ_E3380M_10009_001001001 | 25.35099 | 55.40400729 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2510 |  |  | SHJ2282 _ 1 X CSG_Rehoming (Migration) |  | SHJ2282 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | SHJ | 10G | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c6/1 | SHJ-2282-CSG-ASR920-LD-1 | CAT2343U3A0 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-21 | Y23-F113955 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:32 | SHJ_E3380Y_10012_001001001 | 25.3242767 | 55.44955064 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2509 |  |  | SHJ2236 _ 1 X CSG_Rehoming (Migration) |  | SHJ2236 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | SHJ | 10G | SHJ-2019-SCSG-IXR-R6D-1 | 1/5/c9/1 | SHJ-2236-CSG-ASR920-LD-1 | CAT2419U1KW | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-11 | Y23-F115256 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:26 | SHJ_E3380H_10009_001001001 | 25.37558 | 55.40337339 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2508 |  |  | SHJ2210 _ 1 X CSG_Rehoming (Migration) |  | SHJ2210 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-26 | SHJ | 10G | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c7/1 | SHJ-2210-CSG-ASR920-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-25 | Y23-F114212 |  | Nokia | Completed |  | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:22 | SHJ_E3379D_10019_001001001 | 25.29032 | 55.43887699 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2507 |  |  | SHJ0732 _ 1 X CSG_Rehoming (Migration) |  | SHJ0732 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-09 | SHJ | 10G | SHJ-2226-SCSG-IXR-R6D-1 | 1/6/c3/1:111 | SHJ-0732-CSG-ASR920-LD-1 | CAT2439U0U2 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-07 | Y23-F111265 |  | Cisco | Completed |  | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:18 | SHJ_E3379A_10441_001001002 | 25.30315511 | 55.37812543 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2506 |  |  | SHJ0689 _ 1 X CSG_Rehoming (Migration) |  | SHJ0689 | Others | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-17 | SHJ | 10G | SHJ-2012-SCSG-IXR-R6D-1 | 1/5/c15/1 | SHJ-0689-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  |  |  | 2024-01-16 | Y23-F115521 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:04 | SHJ_E3380Q_10431_001001002 | 25.33695658 | 55.40010521 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2505 |  |  | SHJ0670 _ 1 X CSG_Rehoming (Migration) |  | SHJ0670 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-09 | SHJ | 10G | SHJ-2226-SCSG-IXR-R6D-1 | 1/6/c4/1:111 | SHJ-0670-CSG-ASR920-LD-1 | CAT2439U0KC |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-07 | Y23-F111267 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 17:00 | SHJ_E3379A_10436_001001007 | 25.304097 | 55.37857 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2504 |  |  | SHJ0572 _ 1 X CSG_Rehoming (Migration) |  | SHJ0572 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-09 | SHJ | 10G | SHJ-2226-SCSG-IXR-R6D-1 | 1/6/c5/1:111 | SHJ-0572-CSG-ASR920-LD-1 | CAT2439U0ET |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-07 | Y23-F111269 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 16:57 | SHJ_E3379A_10615_001001001 | 25.30390606 | 55.37899227 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2503 |  |  | SHJ0494 _ 1 X CSG_Rehoming (Migration) |  | SHJ0494 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-26 | SHJ |  | SHJ-2508-SCSG-IXR-R6D-1 | 1/5/c8/1 | SHJ-0494-CSG-ASR920-LD-1 | CAT2343U3CU |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-25 | Y23-F114216 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 16:53 | SHJ_E3379J_10518_001001001 | 25.28914 | 55.44861457 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2502 |  |  | DUB0260 |  | DUB0260 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-02-09 | DXB |  | DUB-0289-CSG-N540-LD-1 | 0/0/0/13 | DUB-0289-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-05 16:52 |  | 25.173249 | 55.298727 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2501 |  |  | SHJ0486 _ 1 X CSG_Rehoming (Migration) |  | SHJ0486 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-10 | SHJ | 10G | SHJ-2226-SCSG-IXR-R6D-1 | 1/6/c6/1 | SHJ-0486-CSG-ASR920-LD-1 | CAT2402U1NZ |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-08 | Y23-F115040 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 16:48 | SHJ_E3379A_10457_001001001 | 25.2999699 | 55.3795792 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2500 | WO- IIB-CSG-2024-Order # 2500 |  | KFN2956 |  | KFN2956 | Nokia IXR-E | 5G Upgrade | New CSG | Commissioning in progress | XAD |  | FUJ | 10G | NE516 (RAK2722-Kalba) |  | KFN-2956-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-05 16:46 |  | 25.41864 | 56.15578 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2499 |  |  | RAK3746 _ 1 X CSG_Rehoming (Migration) |  | RAK3746 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | RAK |  | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | RAK-3746-CSG-ASR920-LD-1 | CAT2350U0ZY |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-08-08 | Y23-F104336 |  | Nokia | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 14:23 | RKT_E4086F_10001_001001001 | 25.91968191 | 56.05195108 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2498 |  |  | RAK3431 _ 1 X CSG_Rehoming (Migration) |  | RAK3431 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-15 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c14/1 | RAK-3431-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-12 | Y23-F115258 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 14:19 | FJR_E3983W_10001_001001001 | 25.59725835 | 56.00004753 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2497 |  |  | RAK3489 _ 1 X CSG_Rehoming (Migration |  | RAK3489 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c12/1 | RAK-3489-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-01 | Y23-F112821 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 14:12 | RKT_E3884Y_10001_001001001 | 25.68716911 | 55.94583 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2496 |  |  | RAK3357 _ 1 X CSG_Rehoming (Migration) |  | RAK3357 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c13/1 | RAK-3357-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-01 | Y23-F112822 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 14:09 | RKT_E3980A_10002_001001001 | 25.38728947 | 55.9722 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2495 |  |  | RAK3235 _ 1 X CSG_Rehoming (Migration) |  | RAK3235 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-15 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c15/1 | RAK-3235-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-12 | Y23-F115261 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 14:05 | FJR_E3982S_10001_001001001 | 25.51916538 | 56.02400914 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2494 |  |  | RAK3196 _ 1 X CSG_Rehoming (Migration) |  | RAK3196 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-16 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c16/1 | RAK-3196-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-12 | Y23-F115270 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 14:01 | FJR_E4082K_10001_001001001 | 25.54180429 | 56.06217399 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2493 |  |  | RAK3124 _ 1 X CSG_Rehoming (Migration) |  | RAK3124 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | RAK | 10G | UAQ-DC-AGGR-SR7S-1 /UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | RAK-3124-CSG-ASR920-LD-1 | CAT2439U05Q |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-06-09 | Y23-F100637 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:58 | RKT_E3784S_10005_001001001 | 25.69616734 | 55.82153611 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2492 |  |  | RAK2892 _ 1 X CSG_Rehoming (Migration) |  | RAK2892 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | Ten0/0/0/41 | RAK-2892-CSG-ASR920-LD-1 | CAT2439U05S |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-17 | Y23-F115619 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:55 | RKT_E4087B_10002_001001001 | 26.02232 | 56.08655 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2491 |  |  | RAK2860 _ 1 X CSG_Rehoming (Migration) |  | RAK2860 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-03 | RAK | 10G | RAK-2000-SCSG-SR7B-1 | esat-1/1/49 | RAK-2860-CSG-ASR920-LD-1 | CAT2318U076 |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-28 | Y23-F114438 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:51 | RKT_E3884M_10002_001001001 | 25.72409965 | 55.90254 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2490 |  |  | RAK2767 _ 1 X CSG_Rehoming (Migration) |  | RAK2767 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-26 | RAK | 10G | RAK-2759-SCSG-IXR-R6D-1 | 1/6/c11/1 | RAK-2767-CSG-ASR920-LD-1 | CAT2425U36Q |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-25 |  |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:47 | RKT_E3985K_10002_001001001 | 25.8079 | 55.95495 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2489 |  |  | RAK2761 _ 1 X CSG_Rehoming (Migration) |  | RAK2761 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | RAK |  | RAK-2026-SCSG-IXR-R6D-2 | 1/6/c9/1 | RAK-2761-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-01 | Y23-F112820 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:44 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2488 |  |  | RAK2743 _ 1 X CSG_Rehoming (Migration) |  | RAK2743 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | Ten0/0/0/31 | RAK-2743-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-17 | Y23-F115623 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:40 | RKT_E4087D_10001_001001001 | 26.03372384 | 56.11379148 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2487 |  |  | RAK2726 _ 1 X CSG_Rehoming (Migration) |  | RAK2726 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | Ten0/0/0/42 | RAK-2726-CSG-ASR920-LD-1 | CAT2439U04B |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-17 | Y23-F115618 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:35 | RKT_E4087B_10001_001001001 | 26.02941 | 56.08701 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2486 |  |  | RAK2717 _ 1 X CSG_Rehoming (Migration) |  | RAK2717 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-28 | RAK | 10G | RAK-2759-SCSG-IXR-R6D-1 | 1/6/c12/1 | RAK-2717-CSG-ASR920-LD-1 | CAT2439U0KB |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-25 | Y23-F114203 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:31 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2485 |  |  | RAK2706 _ 1 X CSG_Rehoming (Migration) |  | RAK2706 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-04 | RAK | 10G | RAK-2000-SCSG-SR7B-1 | esat-1/1/50 | RAK-2706-CSG-ASR920-LD-1 | CAT2341U2LN |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-05-04 | Y23-F79571 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 13:27 | RKT_E3884J_10001_001001001 | 25.74438774 | 55.93462644 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2484 |  |  | RAK2381 _ 1 X CSG_Rehoming (Migration) |  | RAK2381 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-10 | RAK | 10G | RAK-2009-SCSG-IXR-R6D-1 | 1/5/c10/1 | RAK-2381-CSG-ASR920-LD-1 | CAT2439U0PV |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-08 | Y23-F115039 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 12:59 | RKT_E3884E_10001_001001001 | 25.762264 | 55.948869 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2483 |  |  | RAK2105 _ 1 X CSG_Rehoming (Migration) |  | RAK2105 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | RAK | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | RAK-2105-CSG-ASR920-LD-1 | CAT2341U2KY |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-10 | Y23-F115183 |  | Cisco |  | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 12:16 | RKT_E3784R_10001_001001001 | 25.69568079 | 55.7974739 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2482 |  |  | IDX5782 _ 1 X CSG_Rehoming (Migration) |  | IDX5782 | Cisco ASR920 |  | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-30 | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-1 | 1/6/c1/1 | IDX-5782-CSG-ASR920-LD-1 | CAT2439U0GR | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-30 | Y23-F112736 |  | Nokia | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 12:09 | DXB_E3278A_11671_001001003 | 25.201198 | 55.280789 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2481 |  |  | IDX5250 _ 1 X CSG_Rehoming (Migration) |  | IDX5250 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | DXB | 10G | DXB-1635-SCSG-NCS57C3-2 | Ten0/0/0/37 | IDX-5250-CSG-ASR920-LD-1 | FOC2511NAPZ | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-20 | Y23-F113908 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 12:02 | DXB_E3177V_10999_001001210 | 25.03976124 | 55.19738692 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2480 |  |  | IDX5249 _ 1 X CSG_Rehoming (Migration) |  | IDX5249 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-23 | DXB | 10G | DXB-3165-SCSG-IXR-R6D-2 | 1/6/c3/1 | IDX-5249-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-28 | Y23-F112655 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:35 | DXB_E3279N_10351_001001002 | 25.269298 | 55.328309 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2479 |  |  | IDX5115 _ 1 X CSG_Rehoming (Migration) |  | IDX5115 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-21 | DXB | 10G | DXB-Zafran-SCSG-IXR-R6D-1 | 1/5/c3/1 | IDX-5115-CSG-ASR920-LD-1 | CAT2419U1YY |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-27 | Y23-F112512 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:24 | DXB_E3278G_10239_001013002 | 25.1965101282 | 55.2846052259 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2478 |  |  | IDX0939C _ 1 X CSG_Rehoming (Migration) |  | IDX0939C | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-28 | DXB | 10G | DXB-2302-SCSG-IXR-R6D-1 | 1/5/c2/1 | IDX-0939C-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-27 | Y23-F114362 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:14 | DXB_E3378U_10007_001001001 | 25.12940136 | 55.36336712 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2477 |  |  | IAD5353 _ 1 X CSG_Rehoming (Migration) |  | IAD5353 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-28 | AUH | 10G | AUH-1437-SCSG-SR7B-1 | esat-1/1/7:111 | IAD-5353-CSG-ASR920-LD-1 | CAT2433U0FD |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  |  | Y23-F81065 |  | Nokia | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:11 | AUH_E2571P_10005_001001001 | 24.504491 | 54.591524 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2476 |  |  | DXN0975 _ 1 X CSG_Rehoming (Migration) |  | DXN0975 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-20 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/38 | DXN-0975-CSG-ASR920-LD-1 | CAT2419U1S1 |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-01 | Y23-F113902 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:06 | DXB_E3177S_10270_001001013 | 25.057159 | 55.227787 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2475 |  |  | DXN0965 _ 1 X CSG_Rehoming (Migration) |  | DXN0965 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/45 | DXN-0965-CSG-ASR920-LD-1 | CAT2419U1ZH |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-17 | Y23-F115624 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:03 | DXB_E3177S_10259_001001014 | 25.05697298 | 55.22843828 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2474 |  |  | DXN0952 _ 1 X CSG_Rehoming (Migration) |  | DXN0952 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-11 | DXB | 10G | DXB-3252-SCSG-SR7B-1 | esat-1/1/20 | DXN-0952-CSG-ASR920-LD-1 | CAT2419U1WE |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-06 | Y21-F37765 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 11:00 | DXB_E3279X_10656_001003004 | 25.2268659107877 | 55.3401462904477 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2473 |  |  | DXN0627 _ 1 X CSG_Rehoming (Migration) |  | DXN0627 |  | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-21 | DXB | 10G | DXB-Zafran-SCSG-IXR-R6D-1 | 1/6/c8/1 | DXN-0627-CSG-ASR920-LD-1 | CAT2343U3C9 |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-27 | Y23-F112511 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:57 | DXB_E3278F_10703_001044007 | 25.193352116 | 55.2810989184 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2472 | WO- IIB-CSG-2024-Order # 2472 |  | DXN0500 _ 1 X CSG_Rehoming (Migration) |  | DXN0500 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-28 | DXB | 10G | DXB-Zafran-SCSG-IXR-R6D-1 | 1/6/c6 | DXN-0500-CSG-ASR920-LD-1 | CAT2419U1XC | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-27 | Y23-F112510 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:53 | DXB_E3278F_10705_001002002 | 25.191558 | 55.269454 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2471 | WO- IIB-CSG-2024-Order # 2471 |  | DXN0418 _ 1 X CSG_Rehoming (Migration) |  | DXN0418 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/42 | DXN-0418-CSG-ASR920-LD-1 | CAT2239U098 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-20 | Y23-F113896 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:49 | DXB_E3177S_10258_001002002 | 25.06461794 | 55.23912785 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2470 | WO- IIB-CSG-2024-Order # 2470 |  | DXN0380 _ 1 X CSG_Rehoming (Migration) |  | DXN0380 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/43 | DXN-0380-CSG-ASR920-LD-1 | CAT2402U1WB | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-20 | Y23-F113893 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:46 | DXB_E3177S_10252_001001043 | 25.06233 | 55.23277 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2469 | WO- IIB-CSG-2024-Order # 2469 |  | DXN0235 _ 1 X CSG_Rehoming (Migration) |  | DXN0235 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/40 | DXN-0235-CSG-ASR920-LD-1 | CAT2419U1TW | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-20 | Y23-F113887 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:43 | DXB_E3177E_10632_001001002 | 25.11276987 | 55.24616758 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2468 | WO- IIB-CSG-2024-Order # 2468 |  | DXN0234 _ 1 X CSG_Rehoming (Migration) |  | DXN0234 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | DXB |  | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Te0/0/0/39 | DXN-0234-CSG-ASR920-LD-1 | CAT2419U1RD | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-20 | Y23-F113878 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:39 | DXB_E3177E_10637_001001001 | 25.11415248 | 55.24643516 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2467 | WO- IIB-CSG-2024-Order # 2467 |  | DXN0113 _ 1 X CSG_Rehoming (Migration) |  | DXN0113 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | DXB | 10G | DXB-ZAFRAN-SCSG-IXR-R6D-1 | 1/6/c7/1 | DXN-0113-CSG-ASR920-LD-1 | CAT2419U1WC | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-29 | Y23-F112735 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:35 | DXB_E3278F_10394_001002015 | 25.1911371 | 55.2820675 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2466 | WO- IIB-CSG-2024-Order # 2466 |  | DXN0034 _ 1 X CSG_Rehoming (Migration) |  | DXN0034 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-29 | DXB | 10G | DXB-6501-AGGR-SR12e-1 | 2/1/35 | DXN-0034-CSG-ASR920-LD-1 | CAT2433U0EQ | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-27 | Y23-F114361 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:31 | DXB_E3176V_10009_001009001 | 24.94830831 | 55.20286921 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2465 | WO- IIB-CSG-2024-Order # 2465 |  | DXN0028 _ 1 X CSG_Rehoming (Migration) |  | DXN0028 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/5/c4 | DXN-0028-CSG-ASR920-LD-1 | CAT2402U1SH | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-10 | Y23-F115181 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:28 | DXB_E3478Q_10004_001001001 | 25.15587473 | 55.50030381 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2464 | WO- IIB-CSG-2024-Order # 2464 |  | DXB3526 _ 1 X CSG_Rehoming (Migration) |  | DXB3526 | Cisco NCS540 | Migration | Preagg Pending | RFSed | Cisco | 2023-11-30 | DXB |  | DXB-2302-SCSG-IXR-R6D-1 | 1/6/c9/1 | DXB-3526-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-30 | Y23-F112737 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:22 | DXB_E3378P_11114_001001001 | 25.1500071 | 55.3700368 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2463 | WO- IIB-CSG-2024-Order # 2463 |  | DXB3411 _ 1 X CSG_Rehoming (Migration) |  | DXB3411 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-17 | DXB | 10G | DXB-2302-SCSG-IXR-R6D-1 | 1/6/c10/1 | DXB-3411-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-16 | Y23-F115520 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:19 | DXB_E3378U_10015_001001001 | 25.1323057 | 55.3633976 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2462 | WO- IIB-CSG-2024-Order # 2462 |  | DXB3366 _ 1 X CSG_Rehoming (Migration) |  | DXB3366 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-28 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/5/c8 | DXB-3366-CSG-ASR920-LD-1 | CAT2419U1VE | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-27 | Y23-F112509 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:16 | DXB_E3479X_10528_001001001 | 25.2284854129 | 55.5311365549 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2461 | WO- IIB-CSG-2024-Order # 2461 |  | DXB3184 _ 1 X CSG_Rehoming (Migration) |  | DXB3184 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-12 | DXB | 10G | DXB-2282-SCSG-IXR-R6D-1 | 1/6/c2/1 | DXB-3184-CSG-ASR920-LD-1 | CAT2436U3LA | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-12 | Y23-F113338 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:12 | DXB_E3279J_11731_001001001 | 25.28344509 | 55.35557194 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2460 | WO- IIB-CSG-2024-Order # 2460 |  | DXB2589 _ 1 X CSG_Rehoming (Migration) |  | DXB2589 | Nokia SAR-M | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | DXB |  | DXB-1074-SCSG-IXR-R6D-1 | 1/6/c11 | DXB-2589-CSG-ASR920-LD-1 | CAT2343U38K | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-18 | Y23-F115672 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 10:08 | DXB_E3076N_10297_001002001 | 24.98323815 | 55.1381938 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2459 | WO- IIB-CSG-2024-Order # 2459 |  | DXB2117 _ 1 X CSG_Rehoming (Migration) |  | DXB2117 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-12 | DXB | 10G | DXB-2282-SCSG-IXR-R6D-1 | 1/6/c3/1 | DXB-2117-CSG-ASR920-LD-1 | CAT2427U3ZW | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-12 | Y23-F113337 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 09:59 | DXB_E3279E_10906_001001001 | 25.29339147 | 55.35590968 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2458 | WO- IIB-CSG-2024-Order # 2458 |  | DXB1993 _ 1 X CSG_Rehoming (Migration) |  | DXB1993 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/5/c20 | DXB-1993-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-10 | Y23-F115187 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-05 09:56 | DXB_E3478M_10041_001001001 | 25.18041209 | 55.51256804 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2457 | WO- IIB-CSG-2024-Order # 2457 |  | AUG4431 |  | AUG4431 | Nokia IXR-E | Migration | New CSG | Commissioning in progress | XAD |  | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/3/c12 | AUG-4431-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-05 09:19 |  | 24.20083 | 54.68416 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2456 | WO- IIB-CSG-2024-Order # 2456 |  | AUH6621 |  | AUH6621 | Cisco NCS540 | Migration | New CSG | Transmission rack not available | HOI-MEA |  | AUH | 10G | AUH-6005-AGGR-SR12e-1 | Port 2/1/35 |  |  | 5 |  |  |  |  | RACK SPAce Issue | [5 empty] | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-02-05 09:07 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2455 | WO- IIB-CSG-2024-Order # 2455 |  | DXB1904 _ 1 X CSG_Rehoming (Migration) |  | DXB1904 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-30 | DXB | 10G | DXB-1096-SCSG-IXR-R6D-1 | 1/5/c3 | DXB-1904-CSG-ASR920-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-30 | Y23-F112738 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:56 | DXB_E3379A_10199_001001001 | 25.292262 | 55.37321 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2454 | WO- IIB-CSG-2024-Order # 2454 |  | DXB1849 _ 1 X CSG_Rehoming (Migration) |  | DXB1849 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-28 | DXB | 10G | DXB-3724-AGGR-SR12e-1 | 2/1/5 | DXB-1849-CSG-ASR920-LD-1 | CAT2402U1PG | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-23 | Y23-F112310 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:53 | DXB_E3379T_11238_001001001 | 25.24410714 | 55.45001271 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2453 | WO- IIB-CSG-2024-Order # 2453 |  | DXB1315 _ 1 X CSG_Rehoming (Migration) |  | DXB1315 | Cisco NCS540 | Migration |  | CSG not available | Cisco |  | DXB | 10G | DXB-6002-SCSG-IXR-R6D-2 | 1/6/C6/1:111 | DXB-1315-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-09-15 | Y23-F107618 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:41 | DXB_E3278X_10001_001001001 | 25.13559044 | 55.33619855 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2452 | WO- IIB-CSG-2024-Order # 2452 |  | DXB1092 _ 1 X CSG_Rehoming (Migration) |  | DXB1092 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | DXB | 10G | DXB-3165-SCSG-IXR-R6D-1 | 1/6/c4 | DXB-1092-CSG-ASR920-LD-1 | CAT2402U1ME | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-27 | Y23-F112513 |  | Cisco | Completed |  | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:37 | DXB_E3279I_10219_001001001 | 25.277148934 | 55.3277491422 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2451 | WO- IIB-CSG-2024-Order # 2451 |  | DXB1051 _ 1 X CSG_Rehoming (Migration) |  | DXB1051 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | DXB | 10G | DXB-3165-SCSG-IXR-R6D-2 | 1/6/c1 | DXB-1051-CSG-ASR920-LD-1 | CAT2439U01W | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-18 | Y23-F115674 |  | Nokia | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:34 | DXB_E3279J_11017_001001001 | 25.27569669 | 55.34488547 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2450 | WO- IIB-CSG-2024-Order # 2450 |  | AUH6564 _ 1 X CSG_Rehoming (Migration) |  | AUH6564 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-29 | AUH | 10G | AUH-1405-SCSG-IXR-R6D-1 | 1/6/c13/1 | AUH-6564-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-29 | Y23-F112658 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:29 | AUH_E2568I_10612_001001001 | 24.2801079 | 54.64613179 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2449 | WO- IIB-CSG-2024-Order # 2449 |  | AUH6522 _ 1 X CSG_Rehoming (Migration) |  | AUH6522 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-11 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 /AUH-KHAZNA-AGG-SR12e-2 | 6/1/c5/1 | AUH-6522-CSG-ASR920-LD-1 | CAT2436U38P | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-07 | Y23-F113081 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:25 | AUH_E0566B_10308_001001001 | 24.067108 | 52.64591 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2448 | WO- IIB-CSG-2024-Order # 2448 |  | AUH6474 _ 1 X CSG_Rehoming (Migration) |  | AUH6474 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-21 | AUH | 10G | AUH-DC-AGGR-SR12e-1 /AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUH-6474-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-19 | Y23-F113834 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-04 13:09 | AUH_E1562X_10148_001001001 | 23.65993197 | 53.67902787 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2447 | WO- IIB-CSG-2024-Order # 2447 |  | AUH3826 _ 1 X CSG_Rehoming (Migration) |  | AUH3826 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-19 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/6/8/1 | AUH3826-CSG-ASR920-LD-1 | CAT2419U1TS | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-18 | Y23-F113717 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 20:06 | AUH_E2568R_10031_001001001 | 24.23627467 | 54.63446861 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2446 | WO- IIB-CSG-2024-Order # 2446 |  | AUH3718 _ 1 X CSG_Rehoming (Migration) |  | AUH3718 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-29 | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | 1/6/c1/1 | AUH-3718-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-20 | Y23-F112717 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 19:35 | AUH_E2667W_10001_001001001 | 24.13983414 | 54.74484328 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2445 | WO- IIB-CSG-2024-Order # 2445 |  | AUH3549 _ 1 X CSG_Rehoming (Migration) |  | AUH3549 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-29 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/6/c9/1 | AUH-3549-CSG-ASR920-LD-1 | CAT2341U2JS | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-27 | Y23-F114364 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 19:30 | AUH_E2568X_10114_001001001 | 24.2297398 | 54.65581037 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2444 | WO- IIB-CSG-2024-Order # 2444 |  | AUH3235 _ 1 X CSG_Rehoming (Migration) |  | AUH3235 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | AUH | 10G | AUH-DC-AGGR-SR12e-1/AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUH-3235-CSG-ASR920-LD-1 | CAT2433U0QD | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-09 | Y23-F115116 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 19:26 | AUH_E1562Y_10614_001001001 | 23.6571 | 53.7065 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2443 | WO- IIB-CSG-2024-Order # 2443 |  | AUH3218 _ 1 X CSG_Rehoming (Migration) |  | AUH3218 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-12 | AUH | 10G | AUH-2223-SCSG-IXR-R6D-1 | 1/6/c1 | AUH-3218-CSG-ASR920-LD-1 | CAT2439U0FQ | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-12 | Y23-F113335 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 19:14 | AUH_E2470Y_10250_001001001 | 24.400521 | 54.570025 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2442 | WO- IIB-CSG-2024-Order # 2442 |  | AUH3192 _ 1 X CSG_Rehoming (Migration) |  | AUH3192 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-19 | AUH | 10G | AUH-2205-SCSG-IXR-R6D-1 | 1/3/c2/1 | AUH-3192-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-18 | Y23-F115675 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:58 | AUH_E2470U_10954_001001001 | 24.3986469 | 54.48757976 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2441 | WO- IIB-CSG-2024-Order # 2441 |  | AUH3058 _ 1 X CSG_Rehoming (Migration) |  | AUH3058 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | AUH | 10G | AUH-2784-SCSG-IXR-R6D-1 | 1/6/c1/1 | AUH-3058-CSG-ASR920-LD-1 | CAT2439U0SQ | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-01 | Y23-F112818 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:54 | AUH_E2670M_10010_001001001 | 24.43712377 | 54.73688 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2440 | WO- IIB-CSG-2024-Order # 2440 |  | AUH3057 _ 1 X CSG_Rehoming (Migration) |  | AUH3057 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | AUH | 10G | AUH-2784-SCSG-IXR-R6D-1 | 1/6/c2/1 | AUH-3057-CSG-ASR920-LD-1 | CAT2439U0CV | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-01 | Y23-F112819 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:48 | AUH_E2670N_10002_001001001 | 24.44378 | 54.73866 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2439 | WO- IIB-CSG-2024-Order # 2439 |  | AUH2985 _ 1 X CSG_Rehoming (Migration) |  | AUH2985 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-29 | AUH | 10G | AUH-2836-PREAGG-SR7-1 | 5/1/4 | AUH-2985-CSG-ASR920-LD-1 | CAT2439U0B6 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-16 | Y23-F111888 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:44 | AUH_E1561D_10337_001001001 | 23.65252332 | 53.68993268 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2438 | WO- IIB-CSG-2024-Order # 2438 |  | AUH2963 _ 1 X CSG_Rehoming (Migration) |  | AUH2963 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-11 | AUH | 10G | AUH-DC-AGGR-SR12e-1/AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUH-2963-CSG-ASR920-LD-1 | CAT2427U3S5 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-03 | Y23-F114760 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:40 | AUH_E1366H_10273_001001001 | 24.06951335 | 53.46794367 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2437 | WO- IIB-CSG-2024-Order # 2437 |  | AUH2909 _ 1 X CSG_Rehoming (Migration) |  | AUH2909 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-07 | AUH | 10G | AUH-DC-AGGR-SR12e-1/AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUH-2909-CSG-ASR920-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-06 | Y23-F113017 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:32 | AUH_E1066O_10001_001001001 | 24.0592 | 53.2081 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2436 | WO- IIB-CSG-2024-Order # 2436 |  | AUH2675 _ 1 X CSG_Rehoming (Migration) |  | AUH2675 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-19 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/6/c12/1 | AUH-2675-CSG-ASR920-LD-1 | CAT2341U2H7 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-18 | Y23-F113719 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:26 | AUH_E2568V_10057_001001001 | 24.22777326 | 54.61518884 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2435 | WO- IIB-CSG-2024-Order # 2435 |  | AUH2636 _ 1 X CSG_Rehoming (Migration) |  | AUH2636 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-07 | AUH | 10G | AUH-6005-AGGR-SR12e-1 | 2/1/5 | AUH-2636-CSG-ASR920-LD-1 | CAT2402U1TP | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-06 | Y23-F113016 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:05 | AUH_E2271Y_11541_001005002 | 24.49267831 | 54.3689772 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2434 | WO- IIB-CSG-2024-Order # 2434 |  | AUH2442 _ 1 X CSG_Rehoming (Migration) |  | AUH2442 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-01 | AUH | 10G | AUH-1316-SCSG-IXR-R6D-1 | 1/6/c16/1 | AUH-2442-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-01 | Y23-F112817 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 18:00 | AUH_E2270C_11027_001001001 | 24.46422952 | 54.34533 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2433 | WO- IIB-CSG-2024-Order # 2433 |  | AUH2406 _ 1 X CSG_Rehoming (Migration) |  | AUH2406 |  | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-19 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/6/c13/1 | AUH-2406-CSG-ASR920-LD-1 | CAT2425U38C | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-18 | Y23-F113730 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 17:56 | AUH_E2568X_10115_001001001 | 24.22394516 | 54.65959708 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2432 | WO- IIB-CSG-2024-Order # 2432 |  | AUH2061 _ 1 X CSG_Rehoming (Migration) |  | AUH2061 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-26 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/6/c14/1 | AUH-2061-CSG-ASR920-LD-1 | CAT2350U1A3 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-25 | Y23-F114208 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 17:52 | AUH_E2568X_10112_001001001 | 24.2269785699 | 54.6489653671 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2431 | WO- IIB-CSG-2024-Order # 2431 |  | AUG6088 _ 1 X CSG_Rehoming (Migration) |  | AUG6088 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-21 | AUH | 10G | AUH-DC-AGGR-SR12e-1 /AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUG-6088-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-19 | Y23-F113820 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 17:47 | AUH_E1463Q_10001_001001001 | 23.7682 | 53.55384074 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2430 | WO- IIB-CSG-2024-Order # 2430 |  | AUG6025 _ 1 X CSG_Rehoming (Migration) |  | AUG6025 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-21 | AUH | 10G | AUH-DC-AGGR-SR12e-1 /AUH-DC-AGGR-SR12e-2 | 6/1/c3/1 | AUG-6025-CSG-ASR920-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-19 | Y23-F113829 |  | Cisco |  |  | TRUE | 2024 | Alaa Khaled | 2024-02-03 17:38 | AUH_E1561J_10591_001001001 | 23.6354 | 53.70276 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2429 | WO- IIB-CSG-2024-Order # 2429 |  | AJM2463 _ 1 X CSG_Rehoming (Migration) |  | AJM2463 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-30 | AJM |  | AJM-6001-SCSG-SR7B-1 | esat-2/1/9 | AJM-2463-CSG-ASR920-LD-1 | CAT2425U340 | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-29 | Y23-F112656 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 17:35 | AJM_E3381T_10245_001001001 | 25.4169 | 55.44037 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2428 | WO- IIB-CSG-2024-Order # 2428 |  | AJM2304 _ 1 X CSG_Rehoming (Migration) |  | AJM2304 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-12 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/57 | AJM-2304-CSG-ASR920-LD-1 | CAT2417U0SH | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-08 | Y23-F113144 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 17:26 | AJM_E3480G_11969_001001001 | 25.38084368 | 55.49666057 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2427 | WO- IIB-CSG-2024-Order # 2427 |  | AAN3418 _ 1 X CSG_Rehoming (Migration) |  | AAN3418 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-12 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c20/1 | AAN-3418-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-09 | Y23-F115115 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 15:15 | AAN_E3666L_10006_001001001 | 24.08718817 | 55.70472756 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2426 | WO- IIB-CSG-2024-Order # 2426 |  | AAN3362 _ 1 X CSG_Rehoming (Migration) |  | AAN3362 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-08 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c13/1 | AAN-3362-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-05 | Y23-F114841 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 15:12 | AAN_E3666L_10008_001001001 | 24.09141379 | 55.7069567 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2425 | WO- IIB-CSG-2024-Order # 2425 |  | AAN3361 _ 1 X CSG_Rehoming (Migration) |  | AAN3361 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-08 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c14/1 | AAN-3361-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-05 | Y23-F114840 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 15:08 | AAN_E3666L_10007_001001001 | 24.09749872 | 55.71100751 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2424 | WO- IIB-CSG-2024-Order # 2424 |  | AAN3307 _ 1 X CSG_Rehoming (Migration) |  | AAN3307 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-19 | AUH | 10G | AAN-2021-PREAGG-SR7-1 | 4/2/3 | AAN-3307-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-19 | Y23-F113798 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 14:51 | AAN_E3867F_10003_001001001 | 24.20304307 | 55.86959471 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2423 | WO- IIB-CSG-2024-Order # 2423 |  | AAN3144 _ 1 X CSG_Rehoming (Migration) |  | AAN3144 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-08 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c15/1 | AAN-3144-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-05 | Y23-F114839 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 14:35 | AAN_E3666L_10004_001001001 | 24.09293956 | 55.70154 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2422 | WO- IIB-CSG-2024-Order # 2422 |  | AAN2829 _ 1 X CSG_Rehoming (Migration) |  | AAN2829 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-28 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c10 | AAN-2829-CSG-ASR920-LD-1 | CAT2425U32X | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-22 | Y23-F112251 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 14:26 | AAN_E3666F_10004_001001001 | 24.114415 | 55.68253 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2421 | WO- IIB-CSG-2024-Order # 2421 |  | AAN2802 _ 1 X CSG_Rehoming (Migration) |  | AAN2802 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-04 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c13/1 | AAN-2802-CSG-ASR920-LD-1 | CAT2239U0DQ | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-03 | Y23-F114767 |  | Nokia |  |  | TRUE | 2024 | Alaa Khaled | 2024-02-03 14:20 | AAN_E3666O_10002_001001001 | 24.09288 | 55.75729 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2420 | WO- IIB-CSG-2024-Order # 2420 |  | AAN2800 _ 1 X CSG_Rehoming (Migration) |  | AAN2800 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-11-29 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c15/1 | AAN-2800-CSG-ASR920-LD-1 | CAT2214U4LZ | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-11-29 | Y23-F112657 |  | Cisco |  |  | TRUE | 2024 | Alaa Khaled | 2024-02-03 14:13 | AAN_E3666J_10001_001001001 | 24.10236 | 55.75994 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2419 | WO- IIB-CSG-2024-Order # 2419 |  | AAN2620 _ 1 X CSG_Rehoming (Migration) |  | AAN2620 | Cisco NCS540 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-08 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/6/c16/1 | AAN-2620-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-04 | Y23-F114838 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 13:07 | AAN_E3666X_10002_001001001 | 24.06342272 | 55.7357049 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2418 |  |  | AAN2605 _ 1 X CSG_Rehoming (Migration) |  | AAN2605 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-10 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c19/1 | AAN-2605-CSG-ASR920-LD-1 | CAT2324U14Y |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-08 | Y23-F115033 |  | Cisco |  | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 13:00 | AAN_E3666G_10002_001001001 | 24.11026082 | 55.69494478 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2417 |  |  | AAN2572 _ 1 X CSG_Rehoming (Migration) |  | AAN2572 |  | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2024-01-10 | AUH | 10G | AAN-2399-SCSG-IXR-R6D-1 | 1/6/c2/1 | AAN-2572-CSG-ASR920-LD-1 | CAT2427U3XJ |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2024-01-08 | Y23-F115025 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 12:54 | AAN_E3766S_10002_001001001 | 24.07016698 | 55.83512535 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2416 |  |  | AAN2491 _ 1 X CSG_Rehoming (Migration) |  | AAN2491 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-19 | AUH | 10G | AAN-5002-AGGR-SR12-1 | 5/1/3 | AAN-2491-CSG-ASR920-LD-1 | CAT2427U432 |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-18 | Y23-F113721 |  | Cisco |  |  | TRUE | 2024 | Alaa Khaled | 2024-02-03 12:48 | AAN_E3270I_10001_001001001 | 24.46212922 | 55.3337375 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2415 |  |  | AAN2346 _ 1 X CSG_Rehoming (Migration) |  | AAN2346 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-25 | AUH | 10G | AAN-2088-PREAGG-SR7-1 | 4/1/5 | AAN-2346-CSG-ASR920-LD-1 | CAT2402U1VV |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-21 | Y23-F113946 |  | Cisco |  | Not Muted | FALSE | 2024 | Alaa Khaled | 2024-02-03 12:05 | AAN_E3767R_10001_001001001 | 24.16406135 | 55.81034686 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2414 |  |  | AAN2060 _ 1 X CSG_Rehoming (Migration) |  | AAN2060 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade | RFSed | Cisco | 2023-12-12 | AUH | 10G | AAN-2058-PREAGG-SR7-1 | 2/2/4 | AAN-2060-CSG-ASR920-LD-1 | CAT2439U04W |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-12 | Y23-F113336 |  | Cisco |  | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 12:00 | AUH_E2768U_10001_001001001 | 24.22734 | 54.7854 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2413 |  |  | AAN0098 _ 1 X CSG_Rehoming (Migration) |  | AAN0098 | Cisco ASR920 |  |  | RFSed | Cisco | 2023-12-19 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c17/1 | AAN-0098-CSG-ASR920-LD-1 | CAT2419U1SZ |  |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-18 | Y23-F113745 |  | Cisco | Completed | Not Muted | TRUE | 2024 | Alaa Khaled | 2024-02-03 11:51 |  | 24.12601767 | 55.66043283 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2412 | WO- IIB-CSG-2024-Order # 2412 |  | DUB0178 |  | DUB0178 |  | Rollout | Passive patching | Transmission rack not available | HOI-MEA |  | DXB |  | DXB-3257-CSG-IXR-E-1 | 1/1/18 | DXB-3257-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-02-03 11:35 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2411 | WO- IIB-CSG-2024-Order # 2411 |  | DUB0252 |  | DUB0252 | Passive | Rollout | Passive patching | Osp cores full | XAD |  | DXB |  | DXB-3173-SCSG-SR7B-1 | esat-2/1/1 | DXB-3173-SCSG-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-02 11:16 |  | 25.240156 | 55.296409 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2410 | WO- IIB-CSG-2024-Order # 2410 |  | AUH0086 |  | AUH0086 | Passive | Rollout | Passive patching | Transmission rack not available | XAD |  | AUH |  | AUH-5004-SCSG-SR7B-1 | esat-2/1/45 | AUH-5004-SCSG-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-02-02 11:06 |  | 24.70278 | 54.79035 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2409 |  |  | AAN0097 _ 1 X CSG_Rehoming (Migration) |  | AAN0097 | Cisco ASR920 | Migration | Ring Break/Card Exp/Upgrade |  |  | 2023-12-19 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c18/1 | AAN-0097-CSG-ASR920-LD-1 | CAT2419U1XG | 5 |  | 1 | 1 | 1 |  | Tasif Maqbool;#267 |  | 2023-12-18 | Y23-F113742 |  | Nokia | Completed |  | TRUE | 2024 | Alaa Khaled | 2024-02-01 17:29 | AAN_E3566E_10002_001001001 | 24.12183637 | 55.65668957 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2408 |  |  | AJMNR0988 |  | AJMNR0988 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2024-02-06 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/52 | AJM-0988-CSG-N540-LD-1 | FOC2718N5MQ | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-02 | Y23-F116738 |  | Cisco |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-31 11:58 | AJM_E3580G_10851_001002001 | 25.380878 | 55.586015 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2407 |  |  | DUB0883 |  | DUB0883 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2024-02-07 | DXB | 10G | DXB-0296A-PREAGG-SR7-1 | 2/1/4 | DUB-0883-CSG-IXR-E-1 | NK231133454 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-05 | Y23-F116887 |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-30 13:06 | DXB_E3279T_11712_001001001 | 25.24444 | 55.359113 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2406 |  |  | IAD5165 |  | IAD5165 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-31 | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-1/1/26 | AUH-6003-AGGR-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-30 10:50 |  | 24.486768 | 54.363957 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2405 | WO- IIB-CSG-2024-Order # 2405 |  | DXN0091 |  | DXN0091 | Passive | Rollout | Passive patching | Site Not Ready | XAD |  | DXB |  | DXB-0296A-PREAGG-SR7-1 | 1/2/6 | DXB-0296A-PREAGG-SR7-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-29 14:57 |  | 25.247742 | 55.360887 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2404 |  |  | DUB0502 |  | DUB0502 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-27 | DXB | 1G | DUB-0289-CSG-N540-LD-1 | Port 0/0/0/11 | DUB-0289-CSG-N540-LD-1 | [12 empty] | Cisco |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-27 12:46 |  | 25.171284 | 55.304621 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2402 |  |  | AAN3633 |  | AAN3633 | Cisco NCS540 | Migration | New CSG | RFSed | HOI-MEA | 2024-02-08 | AUH | 10G | AAN-3633-CSG0N540-LD-1 |  | AAN-3633-CSG-N540-LD-1 | FOC2718N5DH | 5 | [7 empty] | 2024-02-08 | Y23-F117113 |  |  |  |  | FALSE | 2024 | Syed Shahzaib | 2024-01-26 10:06 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2401 | WO- IIB-CSG-2024-Order # 2401 |  | DXB2655 |  | DXB2655 | Cisco NCS540 | Migration | New CSG | OSP Issue | SHAHID |  | DXB |  | DXB-DGPOP2-SCSG-NCS57C3-1 | TF0/0/0/6 | DXB-2655-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | additional 2 cores required from DXB 3564 to DG pop2 as only 1 core is free on site/existing cabinet is full /No space for new CSG | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-25 19:23 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2400 |  |  | DXB1949 |  | DXB1949 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2024-02-06 | DXB | 10G | DXB-3155-SCSG-IXR-R6D-1 | 1/3/c4 | DXB-1949-CSG-N540-LD-1 | FOC2720N8S7 | 5 |  | 1 | 1 |  | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-02-03 | Y23-F116800 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-25 19:21 | DXB_E3278Q_10337_001001001 | 25.15254 | 55.295735 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2399 |  |  | DXB1606 |  | DXB1606 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2024-02-06 | DXB | 10G | DXB-6002-SCSG-IXR-R6D-1 | 1/3/c1 | DXB1606-CSG-N540-LD-1 | FOC2718N58N | 5 |  | 1 | 1 |  | HOD Submitted |  |  | 2024-02-03 | Y23-F116795 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-25 19:18 | DXB_E3278O_11135_001001001 | 25.177542 | 55.36425 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2398 | WO- IIB-CSG-2024-Order # 2398 |  | IDX0059T |  | IDX0059T | Passive | Migration | New CSG | PTW in progress | SHAHID |  | DXB |  | DXB-FCPOP-SCSG-SR7B-2 | esat-1/1/18 | DXB-FCPOP-SCSG-SR7B-2 |  | 5 |  | 1 | 1 |  | As per BM Access will provide after 25/2/2024 | [5 empty] | Nokia | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-25 19:13 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2397 |  |  | AAN3349 |  | AAN3349 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2024-02-01 | AUH | 10G | AAN-2020-SCSG-IXR-R6-1 | Port 1/3/10 | AAN3349-CSG-N540-LD-1 | FOC2718N55N | 5 |  | 1 | 1 | 1 | Site RFS (ACR),Comarch not showing |  |  | 2024-01-31 | Y23-F116516 |  | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 16:06 | AAN_E3667G_10003_001001001 | 24.205423 | 55.7086 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2396 |  |  | AUH3271 |  | AUH3271 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 2024-02-13 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | Port 2/2/2 | AUH-3271-CSG-N540-LD-1 | FOC2720N8VV | 5 |  | 1 | 1 | 1 | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-02-08 | Y23-F117103 |  | Cisco | IIB not ready |  | TRUE | 2024 | Munaim Abdul salam | 2024-01-23 16:01 | AUH_E2469G_11367_001001001 | 24.358571 |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2395 |  |  | IAD5218 |  | IAD5218 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2024-02-05 | AUH |  | AUH-2410-SCSG-IXR-R6-1 | Port 1/5/c17 | AUH-2410-SCSG-IXR-R6-1 |  | 5 |  | 1 | 1 |  | Passive Completed/Migration pending | [5 empty] | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:54 |  | 24.453728, | 54.614413 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2394 |  |  | AAN0024 |  | AAN0024 | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | AUH | 1G | AAN-2038-CSG-SAR-X-1 | Port 1/3/5 | AAN-2038-CSG-SAR-X-1 |  | 5 |  | 1 | 1 |  | Migartion pending | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:50 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2393 |  |  | IAD5536 |  | IAD5536 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2024-01-27 | AUH | 1G | AUH-1336-SCSG-SR7B-1 | esat-2/1/5 | AUH-1336-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  | Passive Completed/Migration pending |  |  | 2024-01-26 |  |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:44 |  | 24.475857, | 54.374485 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2392 |  |  | AUH3501 |  | AUH3501 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 2024-02-08 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | esat-2/1/49 | AUH-3501-CSG-N540-LD-1 | FOC2624KMZF | 5 |  | 1 | 1 | 1 | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-01-31 | Y23-F116521 |  | Cisco | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:39 | AUH_E2569P_10092_001001001 | 24.331134 | 54.590028 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2391 | WO- IIB-CSG-2024-Order # 2391 |  | AUH0436 |  | AUH0436 | Passive | Migration | Passive patching | Access Issues | SHAHID |  | AUH |  | AUH-2039-PREAGG-SR7-1 | Port 3/2/8 | AUH-2039-PREAGG-SR7-1 |  | 5 |  | 1 | 1 |  | BM required to shift the GSM site from existing location/Mail shared on 16/2/2024 | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:32 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2390 | WO- IIB-CSG-2024-Order # 2390 |  | IAD5161 |  | IAD5161 | Cisco NCS540 | Migration | New CSG | Handover | SHAHID |  | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | Port 1/4/c16 | IAD-5161-CSG-N540-LD-1 | FOC2718N577 | 5 |  | 1 | 1 |  | HOD Submitted/LAR not approved |  |  | 2024-02-15 | Y23-F117131 |  | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:26 | AUH_E2667W_10002_001001001 | 24.136949 | 54.741444 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2389 |  |  | AAN2077 |  | AAN2077 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2024-02-05 | AUH |  | AAN-2006-PREAGG-SR7-1 | Port 5/1/5 | AAN-2077-CSG-IXR-E-1 | NK224931305 | 5 | 1 | 1 | 1 | 1 | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-02-01 | Y23-F116695 |  | Nokia | IIB not ready |  | TRUE | 2024 | Munaim Abdul salam | 2024-01-23 15:20 | AAN_E3667N_10001_001001001 | 24.179807 | 55.742937 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2388 |  |  | AAN2925 |  | AAN2925 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2024-02-06 | AUH | 10G | AAN-2006-PREAGG-SR7-1 | Port 5/1/2 | AAN-2925-CSG-N540-LD-1 | FOC2718N581 | 5 |  | 1 | 1 | 1 | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-02-01 | Y23-F116662 |  | Cisco | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:09 | AAN_E3667N_10003_001001001 | 24.175917 | 55.745098 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2387 |  |  | AAN0009 |  | AAN0009 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2024-02-03 | AUH |  | AAN-2038-CSG-SAR-X-1 | Port 1/2/5 | AAN-2038-CSG-SAR-X-1 |  | 5 |  | 1 | 1 |  | Passive Patching completed/Migration Pending |  |  | 2024-02-03 |  |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-23 15:00 |  | 24.195755, | 55.647975 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2386 | WO- IIB-CSG-2024-Order # 2386 |  | AAN2420 |  | AAN2420 | Nokia IXR-E | Migration | New CSG | Handover | XAD |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | Pot 5/1/2 | AAN-2420-CSG-IXR-E-1 | NK224931287 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-29 | Y23-F116379 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 14:49 | AAN_E3368C_10001_001001001 | 24.310686 | 55.423337 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2385 | WO- IIB-CSG-2024-Order # 2385 |  | IAD5539 |  | IAD5539 | Cisco NCS540 | 5G Upgrade | New CSG | Handover | HOI-MEA |  | AUH | 10G | AUH-1437-SCSG-SR7B-1 | esat-1/1/54 | IAD-5539-CSG-N540-LD-1 | FOC2718N5A8 | 5 | [10 empty] | Cisco | In progress |  | FALSE | 2024 | Syed Shahzaib | 2024-01-23 14:42 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2384 | WO- IIB-CSG-2024-Order # 2384 |  | AUH6615 |  | AUH6615 | Nokia IXR-E | Migration | New CSG | Commissioning in progress | XAD |  | AUH | 10G | NE789 (AUH2938-AUH DC) | AUH-KHAZNA-AGG-SR12e-1 RK1/SH-1 /Front Port# A10 OTN RK-1/NE787 C/03/TX11/RX11 | AUH-6615-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 14:41 |  | 23.66484 | 53.43065 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2383 | WO- IIB-CSG-2024-Order # 2383 |  | DUB0372 |  | DUB0372 |  | Rollout |  | Transmission rack not available | HOI-MEA |  | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-1 | 1/5/c14 | DXB-ZAFRAN-SCSG-IXR-R6D-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Syed Shahzaib | 2024-01-23 14:40 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2382 | WO- IIB-CSG-2024-Order # 2382 |  | DUB0492 |  | DUB0492 |  | Rollout |  | Transmission rack not available | HOI-MEA |  | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/19 | DXB-1516-SCSG-SR7B-1 |  | 5 | [13 empty] | FALSE | 2024 | Syed Shahzaib | 2024-01-23 14:38 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2381 |  |  | AUH6135 |  | AUH6135 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-02-13 | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-1/1/31 | AUH-6135-CSG-N540-LD-1 | FOC2718N5F2 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-09 | Y23-F117162 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 14:35 | AUH_E2270D_10401_001001001 | 24.47694 | 54.35100 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2380 |  |  | AAN3551 |  | AAN3551 | Passive | Migration | Passive patching | Passive Completed | XAD | 2024-01-26 | AUH |  | AAN-2033-SCSG-SR7B-1 | esat-1/1/48 ¦ esat-1/1/49 | AAN-2033-SCSG-SR7B-1 |  | 5 |  |  |  | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 14:24 |  | 24.3138 | 55.8038 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2379 |  |  | AUH3375 |  | AUH3375 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2149-SCSG-SR7B-1 | esat-1/1/57 | AUH-3375-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 13:37 | AUH_E2571H_10535_001001001 | 24.546348 | 54.626870 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2378 |  |  | AAN2941 |  | AAN2941 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-01-30 | AUH | 10G | AAN-2019-SCSG-IXR-R6-1 | Port 1/5/9 | AAN-2941-CSG-N540-LD-1 | FOC2718N5CU | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2024-01-26 | Y23-F116264 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 13:30 | AAN_E3767P_10003_001001001 | 24.162348 | 55.77102 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2377 |  |  | KFN2681 |  | KFN2681 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold | XAD |  | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#B05 OTN RK-1/NE516 C/03/TX17/R17 | KFN-2681-CSG-IXR-E-1 |  | 5 |  |  |  |  | site integrated by other vendor | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-23 10:53 |  | 25.4241 | 56.1519 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2376 |  |  | FUJ1439 |  | FUJ1439 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-02-01 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Te0/8/0/29 | FUJ-1439-CSG-N540-LD-1 | FOC2718N5G7 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-30 | Y23-F116464 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-22 14:04 | FJR_E4278T_10599_001001001 | 25.1581142 | 56.3439378 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2375 |  |  | KFN0716 |  | KFN0716 | Cisco NCS540 | Migration | New CSG | No OSP | XAD |  | FUJ | 10G | NE522 (FUJ2022-KALBA) | FUJ2022_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#B04 OTN RK-1/NE522 C/03/TX16/RX16 | KFN-0716-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-22 14:01 | SHJ_E4279D_10001_001001001 | 25.314316 | 56.331545 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2374 |  |  | DXN0588 |  | DXN0588 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-25 | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-2 | 1/5/c15 | DXB-ZAFRAN-SCSG-IXR-R6D-2 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-19 14:13 |  | 25.196373 | 55.283484 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2373 |  |  | FUJ0677 |  | FUJ0677 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-02-01 | FUJ | 10G | FUJ-6001-AGG-ASR9912-2 | Te0/8/0/30 | FUJ-0677-CSG-IXR-E-1 | NK231134527 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-31 |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-19 14:09 | FJR_E4278T_10597_001001001 | 25.16193333 | 56.3453889 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2372 |  |  | CSG Link Shifting-Upgrade-Ring Break |  | CSG Link Shifting-Upgrade-Ring Break |  | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  |  | 10G | list attached | list attached | [16 empty] | FALSE | 2024 | Omer Ikram | 2024-01-19 10:45 | NA | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2371 | WO- IIB-CSG-2024-Order # 2371 |  | DXB1118 |  | DXB1118 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-3165-SCSG-IXR-R6D-2 | 1/3/c2/1 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-01-19 10:45 | DXB_E3279N_10154_001001001 | 25.2673 | 55.32745 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2370 | WO- IIB-CSG-2024-Order # 2370 |  | SHJ2289 |  | SHJ2289 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | SHJ-3612-SCSG-SRa8-1 | 2/3/1 |  |  | 5 | [13 empty] | FALSE | 2024 | Hafiz Umar | 2024-01-19 10:41 | SHJ_E3778U_10001_001001001 | 25.13372 | 55.7705 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2369 | WO- IIB-CSG-2024-Order # 2369 |  | DXB2278 |  | DXB2278 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-ZAFRAN-SCSG-IXR-R6D-2 | 1/6/c7/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 04:32 | DXB_E3278F_10649_001001001 | 25.1893 | 55.27078 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2368 | WO- IIB-CSG-2024-Order # 2368 |  | DXB1782A |  | DXB1782A | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-ZAFRAN-SCSG-IXR-R6D-2 | 1/6/c6/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 04:29 | DXB_E3278G_10168_001023002 | 25.19003 | 55.284474 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2367 | WO- IIB-CSG-2024-Order # 2367 |  | SHJ2582 |  | SHJ2582 | Nokia IXR-E | Rollout |  |  | Nokia |  | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-3/1/31 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 04:26 | SHJ_E3380P_10021_001001001 | 25.32686 | 55.37707 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2366 | WO- IIB-CSG-2024-Order # 2366 |  | DXB1282 |  | DXB1282 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-1088-SCSG-SR7B-1 | esat-1/1/50 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 04:22 | DXB_E3279M_10966_001001001 | 25.26619 | 55.31111 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2365 | WO- IIB-CSG-2024-Order # 2365 |  | IAD5333 |  | IAD5333 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | esat-1/1/44 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:57 | AUH_E2570L_10030_001001001 | 24.43411 | 54.6198 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2364 |  |  | SHJ2532 |  | SHJ2532 | Nokia IXR-E | Rollout |  |  | Nokia |  | SHJ | Others | SHJ-6501-SCSG-IXR-R6D-1 | 1/3/c1/1 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:54 | SHJ_E3379A_10277_001001001 | 25.3072 | 55.3709 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2363 |  |  | FUJ2436 |  | FUJ2436 | Nokia IXR-E | Rollout |  |  | Nokia |  | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/41 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:51 | SHJ_E4275M_10001_001001001 | 24.90844 | 56.30152 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2362 |  |  | DXB2814 |  | DXB2814 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-3/1/18 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:47 | DXB_E3279M_11347_001004002 | 25.264193 | 55.304317 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2361 |  |  | DXB1392 |  | DXB1392 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-FCPOP-SCSG-SR7B-1 | 1/2/c1/1 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:44 | DXB_E3277U_10934_001001001 | 25.051361 | 55.284611 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2360 |  |  | DXB3211 |  | DXB3211 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | Others | DXB-2770-SCSG-IXR-R6D-1 | 1/3/c6/1 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:40 | DXB_E3177L_10274_001001001 | 25.073307 | 55.18578 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2359 |  |  | AUH2858 |  | AUH2858 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | 1/5/c14/1 | [16 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:36 | AUH_E2769C_10001_001001001 | 24.39517 | 54.84003 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2358 |  |  | AUH3726 |  | AUH3726 | Nokia IXR-E | Rollout |  |  | Nokia |  | AUH | 10G | AUH-2204-SCSG-IXR-R6-1 | Port 1/6/c11/1 |  |  | 5 | [13 empty] | TRUE | 2024 | Hafiz Umar | 2024-01-19 03:32 | AUH_E2568O_10562_001001001 | 24.26893 | 54.67236 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2357 | WO- IIB-CSG-2024-Order # 2357 |  | KFN3674 |  | KFN3674 | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | FUJ | 10G | NE518 (KFN2611-Kalba) | KFN2611/Huawei ODF RK-1/SH-1 /Front Port#D01 OTN RK-1/NE518 C/10/TX13/RX13 | KFN-3674-CSG-N540-LD-1 | NK231133454 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-05 | Y23-F116893 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-18 11:01 | FJR_E4183X_10002_001001001 | 25.595211 | 56.22619 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2356 | WO- IIB-CSG-2024-Order # 2356 |  | DXB2630 |  | DXB2630 |  | 5G+Migration | New CSG | Commissioning in progress | HOI-MEA |  | DXB | [5 empty] | 5 | [5 empty] | Syed Shahzaib;#1735 |  |  |  |  | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-01-18 09:40 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2355 | WO- IIB-CSG-2024-Order # 2355 |  | DXB2121 |  | DXB2121 |  | 5G+Migration | New CSG | CSG not available | HOI-MEA |  | DXB | [5 empty] | 5 |  |  |  |  | Waiting for plan from Zakria | Syed Shahzaib;#1735 |  |  |  |  | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-01-18 09:36 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2354 | WO- IIB-CSG-2024-Order # 2354 |  | DXB1495 |  | DXB1495 |  | 5G+Migration |  | Commissioning in progress | HOI-MEA |  | DXB | [5 empty] | 5 | [5 empty] | Syed Shahzaib;#1735 |  |  |  |  | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-01-18 09:35 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2353 | WO- IIB-CSG-2024-Order # 2353 |  | DXB3452 |  | DXB3452 |  | 5G+Migration | New CSG | Commissioning in progress | HOI-MEA |  | DXB | [5 empty] | 5 | [5 empty] | Syed Shahzaib;#1735 |  |  |  |  | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-01-18 09:33 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2352 | WO- IIB-CSG-2024-Order # 2352 |  | AUH2342 |  | AUH2342 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | HOI-MEA | 2024-02-06 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-1/1/53 | AUH-2342-CSG-IXR-E-1 |  | 5 |  | 1 | 1 |  | DF Requested to Nokiaa | Syed Shahzaib;#1735 |  |  | Y23-F116866 |  | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-01-18 09:32 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2351 | WO- IIB-CSG-2024-Order # 2351 |  | AUH6112 |  | AUH6112 | Nokia IXR-E | 5G+Migration | New CSG | Handover | HOI-MEA |  | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-2/1/13 | AUH-6112-CSG-IXR-E-1 |  | 5 |  |  |  |  | DF Requested to Nokiaa | Syed Shahzaib;#1735 |  |  |  |  | HOI-MEA | IIB not ready |  | FALSE | 2024 | Syed Shahzaib | 2024-01-18 09:23 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2350 | WO- IIB-CSG-2024-Order # 2350 |  | AUH0861 |  | AUH0861 | Passive | Migration | Passive patching | Passive Completed | XAD | 2024-02-01 | AUH |  | AUH-2219-CSG-SAR-X-1 | Port 1/2/3 | AUH-2219-CSG-SAR-X-1 |  | 5 | [7 empty] | 2024-02-17 |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 18:48 |  | 24.417808 | 54.440865 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2349 | WO- IIB-CSG-2024-Order # 2349 |  | AUH3730 |  | AUH3730 | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | AUH | 10G | AUH-6005-AGGR-SR12e-1 | Port 2/1/16 | AUH-3730-CSG-N540-LD-1 | FOC2718N56E | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-01 |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 18:45 | AUH_E2271T_11097_001001001 | 24.503406 | 54.374764 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2348 | WO- IIB-CSG-2024-Order # 2348 |  | AAN2624 |  | AAN2624 | Nokia IXR-E | Migration | New CSG | Handover | XAD |  | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 | Port 1/3/c16 | AAN-2624-CSG-N540-LD-1 | NK224931238 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-26 | Y23-F116181 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 18:38 | AAN_E3666S_10002_001001001 | 24.08274002 | 55.73868012 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2347 | WO- IIB-CSG-2024-Order # 2347 |  | AUH0680 |  | AUH0680 | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | AUH | 10G | AUH-2134-PREAGG-SR7-1 | Port 4/2/1 | AUH-0680-CSG-N540-LD-1 | FOC2718N5A9 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-31 | Y23-F116573 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 18:28 | AUH_E2569U_10251_001001001 | 24.317509 | 54.605561 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2346 |  |  | AUH5811A |  | AUH5811A | Passive | Migration | Passive patching | Access Issues | XAD |  | AUH | 1G | AUH-2118-SCSG-SR7B-1 | esat-1/1/47 | AUH-2118-SCSG-SR7B-1 |  | 5 | [10 empty] | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 18:19 |  | 24.357482 | 54.476066 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2345 | WO- IIB-CSG-2024-Order # 2345 |  | AAN2050 |  | AAN2050 | Nokia IXR-E | Migration | New CSG | Handover | XAD |  | AUH | 10G | AAN-2049-SCSG-SR7B-1 | esat-1/1/57 | AAN-2050-CSG-IXR-E-1 | NK224931187 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-26 | Y23-F116210 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 18:04 | AAN_E3568M_10001_001001001 | 24.26742 | 55.6203 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2344 | WO- IIB-CSG-2024-Order # 2344 |  | AAN0039 |  | AAN0039 | Nokia IXR-E | Migration | New CSG | Handover | XAD |  | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/59 | AAN-0039-CSG-IXR-E-1 | NK224931207 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-05 | Y23-F116891 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 17:52 | AAN_E3567I_10006_001001001 | 24.194416 | 55.646385 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2343 |  |  | AAN2541 |  | AAN2541 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold | XAD |  | AUH | 10G | AAN-2049-SCSG-SR7B-1 | esat-1/1/56 | AAN-2541-CSG-IXR-E-1 |  | 5 |  |  |  |  | 1/27/2024 cancelled from XAD | [5 empty] | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-17 17:32 |  | 24.25599 | 55.61826 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2342 |  |  | IBS-FTK-22-4625 |  | ISH5212 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2024-01-18 | SHJ |  | SHJ-2580-SCSG-SR7B-1 | esat-1/1/14 | SHJ-2580-SCSG-SR7B-1 |  | 5 | 0 | 1 | 1 | 0 | Site Completed |  |  | 2024-01-18 |  |  | Nokia |  |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 15:54 |  | 25.3176 | 55.377 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2341 | WO- IIB-CSG-2024-Order # 2341 |  | IAD5304 |  | IAD5304 | Passive | Migration | Passive patching | Payment Issue | SHAHID |  | AUH |  | AUH-1090-SCSG-SR7B-1 | esat-1/1/47 | AUH-1090-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  | Access issue for DU due to payment issue /Mail update given to Mr Siraj on 18/01/2024 | [5 empty] | Shahid Tech |  |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 12:31 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2340 | WO- IIB-CSG-2024-Order # 2340 |  | AUH6485 |  | AUH6485 | Cisco NCS540 | Migration | New CSG | Site Not Ready | SHAHID |  | AUH |  | AUH-2937-PREAGG-SR7-1 | tbd | AUH-6485-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 | Uplink port not confirmed due to card upfradation required for CSG uplink port | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 12:28 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2339 | WO- IIB-CSG-2024-Order # 2339 |  | AUH2800 |  | AUH2800 | Nokia IXR-E | Migration | New CSG | Handover | SHAHID |  | AUH |  | AUH-1416-AGGR-SR12E-2 | esat-2/1/46 | AUH-2800-CSG-IXR-E-1 | NK224931418 | 5 | 1 | 1 | 1 | 1 |  |  |  | 2024-02-17 | Y23-F117833 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 12:21 | AUH_E2569K_10039_001001001 |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2338 |  |  | IAD5561 |  | IAD5561 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2024-02-01 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/43 | IAD-5501-CSG-N540-LD-1 | FOC2718N55K | 5 |  | 1 | 1 |  | Site RFS (ACR),Comarch not showing |  |  | 2024-01-30 | Y23-F116440 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 12:11 | AUH_E2271X_10610_002021004 | 24.488072 | 54.360202 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2337 |  |  | IAD5602 |  | IAD5602 | Cisco NCS540 | Migration | New CSG | No OSP | SHAHID |  | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/42 | IAD-5602-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | Site Visited on 22/01/2024/OSP terminated in different building-Mail share to Mr Shafaat on 22/1/2024 | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 12:08 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2336 | WO- IIB-CSG-2024-Order # 2336 |  | IAD5954 |  | IAD5954 | Cisco NCS540 | SRAN + 5G | New CSG | Dewa/Sewa Power not available | SHAHID |  | AUH | 10G | AUH-2134-SCSG-NCS57C3-1 | TenGigE0/0/2/10 | IAD-5954-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | Rectifier not energized,ETC lead site /NO ECD for power up as per last mailfrom Paul (NOKIA) | [8 empty] | FALSE | 2024 | Munaim Abdul salam | 2024-01-17 12:04 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2335 |  |  | KFN2616 |  | KFN2616 | Nokia IXR-E | 5G+Migration | New CSG | Cancelled/on Hold | XAD |  | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#B03 OTN RK-1/NE516 C/03/TX15/RX15 | KFN-2616-CSG-IXR-E-1 |  | 5 |  |  |  |  | site is already RFSed. duplicate entry | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Aris Dumma | 2024-01-16 11:50 |  | 25.44405 | 56.12702 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2334 | WO- IIB-CSG-2024-Order # 2334 |  | AJM0983 |  | AJM0983 | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | AJM | 10G | SHJ-2035-SCSG-SR7B-1 | esat-1/1/4 | AJM-0983-CSG-N540-LD-1 | FOC2718N5FX | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-22 | Y23-F115863 |  | XAD |  |  | FALSE | 2024 | Aris Dumma | 2024-01-16 11:46 | AJM_E3480A_12308_001001001 | 25.390472 | 55.473044 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2333 |  |  | UAQ2002 |  | UAQ2910 | Passive | 5G Upgrade |  | Cancelled/on Hold | XAD |  | UAQ |  | UAQ-2911-CSG-ASR920-LD-1 | TE 0/0/0/14 | UAQ-2911-CSG-ASR920-LD-1 |  | 5 |  |  |  |  | site with Shahidtech | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Aris Dumma | 2024-01-16 11:42 |  | 25.575870 | 55.558130 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2332 |  |  | AUH2027 |  | AUH2027 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-22 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-1/1/50 | AUH-2027-CSG-IXR-E-1 | NK224931129 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-20 | Y23-F115750 |  | XAD |  |  | FALSE | 2024 | Aris Dumma | 2024-01-16 11:34 | AUH_E2270E_12851_001001001 | 24.477383 | 54.374969 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2331 |  |  | SHJ0478 |  | SHJ0478 | Passive | Migration | Passive patching | Passive Completed | XAD | 2024-01-27 | SHJ |  | SHJ-2084-SCSG-SR7B-1 | esat-3/1/4 | SHJ-2084-SCSG-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Aris Dumma | 2024-01-16 11:30 |  | 25.337396 | 55.375573 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2330 |  |  | KFN2626 |  | KFN2116 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold | XAD |  | FUJ | 10G | NE518 (KFN2611-Kalba) | KFN2611/Huawei ODF RK-1/SH-1 /Front Port#D03 OTN RK-1/NE518 C/10/TX15/RX15 | KFN-2626-CSG-IXR-E-1 |  | 5 |  |  |  |  | site integrated by other vendor | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Aris Dumma | 2024-01-16 11:22 |  | 25.6027 | 56.23216 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2329 |  |  | FUJ3403 |  | FUJ3403 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 2024-02-14 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Te0/8/0/30 | FUJ-3403-CSG-IXR-E-1 | NK224931214 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-02-10 | Y23-F117264 |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 17:06 | FJR_E4178T_10001_001001001 | 25.15398 | 56.24177 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2328 |  |  | DXB2467 |  | DXB2467 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2024-02-05 | DXB | 10G | DXB-DGPOP1-AGGR-SR12e-1 | esat-1/1/27 | DXB-2467-CSG-N540-LD-1 | FOC2718N5FG | 5 |  | 1 | 1 | 1 | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-02-02 | Y23-F116739 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:35 | DXB_E3076B_10529_001001001 | 25.019121 | 55.103599 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2327 | WO- IIB-CSG-2024-Order # 2327 |  | AUH3746 |  | AUH3746 |  | 5G Upgrade | Passive patching | Cancelled/on Hold |  |  | AUH |  | NA |  |  |  | 5 |  | 1 | 1 | 1 | Dropped from Shahid -Site inside Zayed Militry city | [8 empty] | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:31 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2326 |  |  | AUH3566 |  | AUH3566 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2024-02-06 | AUH | 10G | AUH-1090-SCSG-SR7B-1 | esat-1/1/48 | AUH-3566-CSG-N540-LD-1 | FOC2718N5ZS | 5 |  | 1 | 1 | 1 | HOD Submitted |  |  | 2024-01-27 | Y23-F116258 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:28 | AUH_E2569C_10078_001001001 | 24.430295 | 54.444169 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2325 | WO- IIB-CSG-2024-Order # 2325 |  | AUH3867 |  | AUH3867 | Nokia IXR-E | 5G Upgrade | New CSG | Handover | SHAHID |  | AUH | 10G | AUH-1416-AGGR-SR12E-2 | esat-2/1/48 | AUH-3867-CSG-IXR-E-1 | NK224931227 | 5 |  | 1 | 1 |  | HOD Submitted |  |  | 2024-02-17 | Y23-F117849 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:25 | AUH_E2569C_10078_001001001 |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2324 |  |  | IAD5194 |  | IAD5194 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2024-01-20 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-2/1/13 | AUH-1336-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  | Survey completed/ISP required/Material Requesed/ |  |  | 2024-01-19 |  |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:21 |  | 24.4641193 | 54.375563 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2323 | WO- IIB-CSG-2024-Order # 2323 |  | AUH3519 |  | AUH3519 | Cisco NCS540 | Migration | New CSG | Handover | SHAHID |  | AUH | 10G | AUH-1437-SCSG-SR7B-1 | esat-1/1/60 | AUH-3519-CSG-N540-LD-1 | FOC2718N5NK | 5 |  | 1 | 1 | 1 | HOD Submitted/LAR not approved |  |  | 2024-02-17 | Y23-F117827 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:14 | AUH_E2571O_10901_001001001 | 24.5298 | 54.6703 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2322 |  |  | AUH0422 |  | AUH0422 | Nokia IXR-E | Migration | New CSG | No OSP | SHAHID |  | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-1/1/63 | AUH-0422-CSG-IXR-E-1 |  | 5 |  | 1 | 1 |  | NO OSP on Site/OSP request sharedto Mr Shaffat on 17/01/2024 | [5 empty] | Shahid Tech |  |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 16:05 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2321 |  |  | FUJ3279 |  | FUJ3279 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-31 | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/3 | FUJ-3279-CSG-IXR-E-1 | NK224931284 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-27 | Y23-F116257 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 16:01 | SHJ_E4276N_10002_001001001 | 25.0054 | 56.3341 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2320 | WO- IIB-CSG-2024-Order # 2320 |  | AUH2195 |  | AUH2195 | Nokia IXR-E | Migration | New CSG | Integrated | SHAHID |  | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/44 | AUH-2195-CSG-IXR-E-1 |  | 5 |  | 1 | 1 |  | HOD in progress | [5 empty] | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 15:58 |  | 24.485398 | 54.359951 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2319 | WO- IIB-CSG-2024-Order # 2319 |  | UAQ2910 |  | UAQ2910 | Nokia IXR-E | 5G Upgrade | New CSG | Handover | SHAHID |  | UAQ |  | NE510 (UAQ2012-UAQDC) | UAQ2012_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#B04 OTN RK-1/NE510 C/03/TX16/RX16 | UAQ-2911-CSG-IXR-E-1 | NK224931396 | 5 |  |  |  | 1 | HOD Submitted |  |  | 2024-02-19 | Y23-F117983 |  | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 15:53 | UAQ_E3582A_10002_001001001 | 25.576646 | 55.557683 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2318 |  |  | DXB2940 |  | DXB2940 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-29 | DXB | 10G | DXB-MIRDIFPOP-AGGR-SR12e-1 | esat-1/1/37 | DXB-2940-CSG-IXR-E-1 | NK224931286 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-25 | Y23-F116097 |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 15:52 | DXB_E3379X_11913_001001001 | 25.22775 | 55.43632 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2317 | WO- IIB-CSG-2024-Order # 2317 |  | DXB1122 |  | DXB1122 | Nokia IXR-E | 5G+Migration | Passive patching | Handover | SHAHID |  | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/20 | DXB-1122-CSG-IXR-E-1 | NK224931264 | 5 |  | 1 | 1 |  | HOD Submitted/LAR not approved |  |  | 2024-02-01 |  |  | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 15:47 | DXB_E3279M_11347_001004001 | 25.2631 | 55.307 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2316 |  |  | AUH2096 |  | AUH2096 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2024-02-12 | AUH | 10G | AUH-2054-PREAGG-SR7-1 | Port 4/1/4 | AUH-2096-CSG-IXR-E-1 | NK224931271 | 5 |  | 1 | 1 |  | Site RFS (ACR),Comarch not showing/Migration pending |  |  | 2024-02-03 | Y23-F116780 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 15:40 | AUH_E2370L_13053_001001001 | 24.429512 | 54.414932 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2315 | WO- IIB-CSG-2024-Order # 2315 |  | SHR3413 |  | SHR3413 | Nokia IXR-E | Migration | New CSG | Handover | SHAHID |  | SHJ | 10G | SHJ-5001-SCSG-SR7B-1 | esat-1/1/55 | SHR-3413-CSG-IXR-E-1 | NK224931147 | 5 | 1 | 1 | 1 |  | HOD Submitted |  |  | 2024-02-03 | Y23-F116834 |  | Shahid Tech | IIB not ready |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 15:40 | SHJ_E3878J_10001_001001001 | 25.1912 | 55.9519 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2314 |  |  | AUH2339 |  | AUH2339 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2024-01-25 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/12 | AUH-2339-CSG-IXR-E-1 | NK224931299 | 5 |  | 1 | 1 |  | Migartion pending |  |  | 2024-01-24 | Y23-F116023 |  | Shahid Tech | In progress |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-15 15:36 | AUH_E2270J_12010_001001001 | 24.44836 | 54.36652 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2313 | WO- IIB-CSG-2024-Order # 2313 |  | DXB1447 |  | DXB1447 | Nokia IXR-E | Migration | New CSG | Commissioning in progress | XAD |  | DXB | 10G | DXB-1852-PREAGG-SR7-1 | 5/2/8 | DXB-1447-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 15:20 |  | 25.1069 | 55.57027 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2312 |  |  | FUJ2436 |  | FUJ2436 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold | XAD |  | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/41 | FUJ-2436-CSG-IXR-E-1 |  | 5 |  |  |  |  | with nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 15:14 |  | 24.90844 | 56.30152 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2311 |  |  | KFN2627 |  | KFN2627 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold | XAD |  | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#A14 OTN RK-1/NE516 C/03/TX14/RX14 | KFN-2627-CSG-IXR-E-1 |  | 5 | 1 | 1 | 1 |  | site integrated by other vendor | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-15 15:11 |  | 25.43243 | 56.14053 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2310 |  |  | AUH0712 |  | AUH0712 | Passive | Migration |  | Passive Completed | HOI-MEA | 2024-01-11 | AUH |  | AUH-1048-PREAGG-SR7-1 | Port 4/2/14 | AUH-1048-PREAGG-SR7-1 |  | 5 |  | 1 | 1 | [7 empty] | Nokia |  |  | FALSE | 2024 | Mohamed Abussalah | 2024-01-13 15:17 |  | 24.4543 | 54.3319 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2309 |  |  | IAD5685 |  | IAD5685 | Passive | Migration | Passive patching | Passive Completed | XAD | 2024-01-16 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-2/1/22 | AUH-1336-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-13 11:32 |  | 24.475399 | 54.374303 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2308 |  |  | AUH3339 |  | AUH3339 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-01-22 | AUH | 10G | AUH-1426-SCSG-SR7B-1 | esat-1/1/59 | AUH-3339-CSG-N540-LD-1 | FOC2718N56T | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2024-01-18 | Y23-F115668 |  | Shahid Tech |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-13 11:29 | AUH_E2769P_10001_001001001 | 24.33546 | 54.79065 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2307 |  |  | AUH2496 |  | AUH2496 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-01-22 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/21 | AUH-2496-CSG-N540-LD-1 | FOC2718N57B | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2024-01-19 | Y23-F115710 |  | Cisco |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-13 11:21 | AUH_E2270E_12872_001001001 | 24.467996125834926 | 54.37937934800444 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2306 | WO- IIB-CSG-2024-Order # 2306 |  | IAD5659 |  | IAD5659 | Passive | Migration | Passive patching | PTW in progress | XAD |  | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-2/1/19 | AUH-1336-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-13 11:13 |  | 24.4731 | 54.3671 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2305 |  |  | UAQ1005 |  | UAQ1005 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-01-25 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/12 | UAQ-1005-CSG-N540-LD-1 | FOC2718N5AU | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2024-01-22 | Y23-F115840 |  | Cisco |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-12 11:00 | UAQ_E3681B_10001_001001001 | 25.47351 | 55.69676 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2304 | WO- IIB-CSG-2024-Order # 2304 |  | DXB0857 |  | DXB0857 | Nokia IXR-E | Rollout | New CSG | Handover | SHAHID |  | DXB | 10G | DXB-3164-SCSG-NCS57C3-1 | Te 0/0/0/22 | DXB-0857-CSG-IXR-E-1 | NK231134490 | 5 |  | 1 | 1 | 1 | HOD Submitted/LAR not approved |  |  | 2024-02-08 | Y23-F117127 |  | Shahid Tech | IIB not ready |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-11 17:27 | DXB_E3379K_11790_001001001 | 25.254833 | 55.381943 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2303 |  |  | DUB0571 |  | DUB0571 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-17 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/39 | DXB-VH-SCSG-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-11 16:57 |  | 25.052241 | 55.218892 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2302 |  |  | DUB0309 |  | DUB0309 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-17 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/38 | DXB-VH-SCSG-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-11 16:53 |  | 25.04895 | 55.206668 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2301 |  |  | DXBNR0069 |  | DXB0069 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-25 | DXB |  | DXB-0068-CSG-IXR-E-1 | 1/1/15 | DXB-0068-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-11 13:02 |  | 25.22793 | 55.320480 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2300 |  |  | DXB0019B |  | DXB0019B | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 2024-01-15 | DXB | 10G | DXB-0296A-PREAGG-SR7-1 | 2/1/2 | DXB-0019B-CSG-IXR-E-1 | NK231134693 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-11 | Y23-F115234 |  | Nokia |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-10 14:28 | DXB_E3279T_10298_001001003 | 25.249382 | 55.352372 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2299 |  |  | RAK1167 |  | RAK1167 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2024-01-15 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-1 | Port 1/3/c11 | RAK1167-CSG-IXR-E-1 | NK224931132 | 5 | 0 | 1 | 1 | 0 | Site Completed |  |  | 2024-01-11 | Y23-F115191 |  | Nokia |  |  | FALSE | 2024 | Munaim Abdul salam | 2024-01-05 15:17 | RKT_E3984P_10006_001001001 | 25.7014 | 55.9685 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2298 | WO- IIB-CSG-2024-Order # 2298 |  | AUH3131 |  | AUH3131 | Cisco NCS540 | Migration | New CSG | Commissioning in progress | XAD |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | Port 2/3/3 | AUH-3131-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2024 | Rogelio Pangilinan | 2024-01-04 12:25 |  | 24.230106 | 54.485479 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2297 |  |  | AAN2316 |  | AAN2316 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | SHAHID | 2024-01-19 | AUH | 10G | AUH-5002-AGGR-SR7-2 | Port 5/2/4 | AAN-2316-CSG-IXR-E-1 | NK224931125 | 5 | 1 | 1 | 1 | 1 | Migartion Pending |  |  | 2024-01-16 | Y23-F115604 |  | Shahid Tech |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-12-26 15:01 | AUH_E3066A_10026_001001001 | 24.12953 | 55.094101 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2296 |  |  | AAN3627 |  | AAN3627 | Cisco NCS540 | BAU | New CSG | RFSed | SHAHID | 2024-01-02 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/8 | AAN-3627-CSG-N540-LD-1 | FOC2720N8T9 | 5 | 0 | 1 | 1 | 0 | Boarding Status : Boarded (ACR) |  |  | 2023-12-30 | Y23-F114541 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-12-26 13:26 | AAN_E3668Y_10266_001001001 | 24.23245391 | 55.761772 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2295 |  |  | AUH0078 |  | AUH0078 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-12-27 | AUH |  | AUH-2536-CSG-SAR-X-1 | Port 1/2/6 | AUH-2536-CSG-SAR-X-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-26 13:15 |  | 24.264946 | 54.458765 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2294 |  |  | AAN3261 |  | AAN3261 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-12-28 | AUH |  | AAN-2019-SCSG-IXR-R6-1 | Port 1/4/6 | AAN-3261-CSG-N540-LD-1 | FOC2624KMEZ | 5 | 0 | 1 | 1 | 1 | Site Completed |  |  | 2023-12-27 | Y23-F114347 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-12-26 10:49 | AAN_E3667I_10007_001001001 | 24.20095 | 55.737099 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2293 |  |  | SHJ0406 |  | SHJ0406 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:46 |  | 25.299020 | 55.373910 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2292 |  |  | FUJ2137 |  | FUJ2137 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:44 |  | 25.169230 | 56.095460 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2291 |  |  | SHJ2642 |  | SHJ2642 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:41 |  | 25.251110 | 55.833580 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2290 |  |  | AUH0561 |  | AUH0561 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:38 |  | 24.483769 | 54.361067 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2289 |  |  | DXB0092 |  | DXB0092 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:34 | DXB_E3279M_11330_001005001 | 25.251289 | 55.301465 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2288 |  |  | DXB0947 |  | DXB0947 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:27 |  | 25.252600 | 55.301970 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2287 |  |  | AUH2385 |  | AUH2385 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:24 |  | 24.333270 | 54.534490 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2286 |  |  | AUH2471 |  | AUH2471 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:17 |  | 24.326440 | 54.532160 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2285 |  |  | FUJ2965 |  | FUJ2965 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-25 10:14 |  | 25.008654 | 56.102004 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2284 |  |  | IFU5632 |  | IFU5632 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-12-28 | FUJ |  | FUJ-6001-CSG-ASR920-LD-1 | Gi0/0/8 | FUJ-6001-CSG-ASR920-LD-1 |  | 5 | 0 | 1 | 1 | 0 | Site Completed |  |  | 2023-12-28 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-12-25 10:02 |  | 25.121742 | 56.351385 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2283 |  |  | IADNR5332 |  | IAD5332 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-12-28 | AUH |  | IAD-5330-CSG-IXR-E-1 | 1/1/15 | IAD-5330-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-23 10:55 |  | 24.455179 | 54.616619 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2282 | WO- IIB-CSG-2023-Order # 2282 |  | IADNR5162 |  | IADNR5162 | Passive | 5G | Passive patching | PTW in progress | XAD |  | AUH |  | AUH-MASDARCITY-PREAGG-SR7-1 | 1/2/18 | AUH-MASDARCITY-PREAGG-SR7-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-23 10:53 |  | 24.43561 | 54.619683 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2281 | WO- IIB-CSG-2023-Order # 2281 |  | IADNR5163 |  | IADNR5163 | Passive | 5G | Passive patching | PTW in progress | XAD |  | AUH |  | AUH-MASDARCITY-PREAGG-SR7-1 | 1/2/17 | AUH-MASDARCITY-PREAGG-SR7-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-23 10:51 |  | 24.43561 | 54.619683 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2280 |  |  | AUHNR0709 |  | AUH0709 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-12-26 | AUH |  | AUH-0705-CSG-IXR-E-1 | 1/1/18 | AUH-0705-CSG-IXR-E-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-23 10:49 |  | 24.429747 | 54.427776 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2279 |  |  | IADNR5824 |  | IAD5824 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-12-28 | AUH |  | AUH-2036-SCSG-IXR-R6-1 | 1/4/9 | AUH-2036-SCSG-IXR-R6-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-23 10:44 |  | 24.481259 | 54.619896 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2278 |  |  | FUJ2141 |  | FUJ2141 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | [5 empty] | 5 | [13 empty] | FALSE | 2023 | Wesam Asran | 2023-12-22 18:05 |  | 25.147500 | 56.027880 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2277 |  |  | DUB0688 |  | DUB0688 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-27 | DXB | 1G | DXB-PALMJ-CSG-IXR-E-2 | 1/1/21 | DXB-PALMJ-CSG-IXR-E-2 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-22 10:24 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2276 |  |  | DUB0431 |  | DUB0431 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-20 | DXB | 1G | DXB-2605-CSG-IXR-E-1 | 1/1/13 | DXB-2605-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-22 10:23 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2275 |  |  | DUB0788 |  | DUB0788 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-22 | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/17 | DXB-1516-SCSG-SR7B-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-22 10:21 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2274 |  |  | DUB0684 |  | DUB0684 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-22 | DXB | 1G | DXB-DMTC-SCSG-SR7B-1 | esat-1/1/6 | DXB-DMTC-SCSG-SR7B-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-22 10:19 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2273 |  |  | AUH3040 |  | AUH3040 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2024-01-02 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/3/c18 | AUH-3040-CSG-N540-LD-1 | FOC2718N59H | 5 | [8 empty] | Y23-F114294 |  | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-22 10:17 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2272 | WO- IIB-CSG-2023-Order # 2272 |  | IBS-FTK-22-0285 |  | SHJ0169 | Nokia IXR-E | BAU + 5G | New CSG | Cancelled/on Hold | SHAHID |  | SHJ |  | SHJ-2012-SCSG-IXR-R6D-1 | Port 1/5/c2 | SHJ-0169-CSG-IXR-E-1 |  | 5 | 0 | 1 | 1 | 1 | IXR-E Dismantled on 31/01/2024 as per the Instruction from Mr Izzat from planning team.. | [5 empty] | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-12-21 16:08 |  | 25.3518 | 55.3852 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2271 |  |  | SHJ2260 |  | SHJ2260 | Passive | 5G | Passive patching | Passive Completed | SHAHID | 2023-12-22 | SHJ | 10G | SHJ-0402-CSG-SAR-X-1 | 1/3/7 | SHJ-0402-CSG-SAR-X-1 |  | 5 |  |  |  | 1 | Site Completed | [5 empty] | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-12-21 12:00 |  | 25.337665 | 55.375743 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2270 |  |  | SHJ2225 |  | SHJ2225 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | [18 empty] | FALSE | 2023 | Omer Ikram | 2023-12-20 17:08 |  | 25.312682 | 55.376049 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2269 |  |  | SHJ0135 |  | SHJ0135 |  | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-12-20 17:05 |  | 25.313050 | 55.378120 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2268 |  |  | SHJ0151 |  | SHJ0151 | Nokia IXR-E | Migration | New CSG | RFSed | Nokia |  | SHJ | 10G | SHJ-2580-SCSG-SR7B-1 | esat-1/1/33 | [11 empty] | Y23-F79449 |  |  | Completed |  | TRUE | 2023 | Omer Ikram | 2023-12-20 16:45 | SHJ_E3380U_10002_001002001 | 25.312215 | 55.37741 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2267 |  |  | DXB1159 |  | DXB1159 | Nokia IXR-E | Migration | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-2302-SCSG-IXR-R6D-1 | Port 1/3/c5/1 | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-12-20 16:32 | DXB_E3278S_10476_001001001 | 25.15146 | 55.34045 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2266 |  |  | DUB0499 |  | DUB0499 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-29 | DXB |  | DUB-0405-CSG-N540-LD-1 | Te0/0/0/16 | DUB-0405-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 12:15 |  | 25.172511 | 55.306226 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2265 |  |  | DUB0288 |  | DUB0288 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-29 | DXB |  | DUB-0405-CSG-N540-LD-1 | Te0/0/0/15 | DUB-0405-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 12:13 |  | 25.1738 | 55.3004 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2264 |  |  | DUB0743 |  | DUB0743 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-29 | DXB |  | DUB-0405-CSG-N540-LD-1 | Te0/0/0/14 | DUB-0405-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 12:12 |  | 25.1738 | 55.3004 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2263 |  |  | DUB0746 |  | DUB0746 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-29 | DXB |  | DUB-0405-CSG-N540-LD-1 | Te0/0/0/13 | DUB-0405-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 12:11 |  | 25.1738 | 55.3004 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2262 |  |  | DUB0738 |  | DUB0738 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-29 | DXB |  | DUB-0501-CSG-N540-LD-1 | Te0/0/0/12 | DUB-0501-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 12:09 |  | 25.17196 | 55.3004 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2261 |  |  | DUB0495 |  | DUB0495 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-29 | DXB |  | DUB-0405-CSG-N540-LD-1 | Te0/0/0/12 | DUB-0405-CSG-N540-LD-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 12:07 |  | 25.17343 | 55.306919 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2260 |  |  | DUB0405 |  | DUB0405 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-23 | DXB | 10G | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/8 | DUB-0405-CSG-N540-LD-1 | FOC2720N8TD | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-22 | Y23-F114037 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 11:49 | DXB_E3278M_10370_001014001 | 25.173534 | 55.304493 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2258 |  |  | ISH5229 |  | ISH5229 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-12-29 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/28 | ISH-5229-CSG-N540-LD-1 | FOC2718N5CT | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-28 | Y23-F114407 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 10:21 | SHJ_E3480V_10063_001001002 | 25.32168 | 55.483134 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2257 |  |  | ISH5228 |  | ISH5228 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2024-01-03 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/27 | ISH-5228-CSG-N540-LD-1 | FOC2718N5FM | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-28 | Y23-F114405 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 10:18 | SHJ_E3480V_10060_001001002 | 25.32168 | 55.483134 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2254 |  |  | DXB2685 |  | DXB2685 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | DXB | [17 empty] | Completed |  | FALSE | 2023 | Wesam Asran | 2023-12-20 10:07 | DXB_E3177J_12962_001001001 | 25.09806 | 55.24483 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2253 |  |  | DXB0358 |  | DXB0358 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | DXB | [17 empty] | Completed |  | FALSE | 2023 | Wesam Asran | 2023-12-20 10:05 | DXB_E3076J_10839_001002003 | 25.004483 | 55.154367 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2252 |  |  | DXB3365 |  | DXB3365 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | DXB | [17 empty] | Completed |  | FALSE | 2023 | Wesam Asran | 2023-12-20 10:02 | DXB_E3479X_10537_001001001 | 25.2367 | 55.5346 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2251 | WO- IIB-CSG-2023-Order # 2251 |  | DXN0271 |  | DXN0271 | Passive | Rollout | Passive patching | PTW in progress | XAD |  | DXB |  | DXB-2688-SCSG-SR7B-1 | esat-1/1/4 | DXB-2688-SCSG-SR7B-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 10:01 |  | 24.893474 | 55.142034 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2250 | WO- IIB-CSG-2023-Order # 2250 |  | DUB0213 |  | DUB0213 | Passive | Rollout | Passive patching | PTW in progress | XAD |  | DXB |  | DXB-1103-SCSG-IXR-R6D-1 | 1/6/c11 | DXB-1103-SCSG-IXR-R6D-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 09:56 |  | 25.202635 | 55.276030 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2249 |  |  | RAK3109 |  | RAK3109 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | RAK | [19 empty] | FALSE | 2023 | Wesam Asran | 2023-12-20 09:55 | RKT_E3884N_10003_001001001 | 25.7100 | 55.9235 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2247 |  |  | DXB1721 |  | DXB1721 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Wesam Asran | 2023-12-20 09:48 | DXB_E3279W_10927_001001001 | 25.217220 | 55.302780 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2245 |  |  | DXB2686 |  | DXB2686 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | DXB | [17 empty] | Completed |  | FALSE | 2023 | Wesam Asran | 2023-12-20 09:38 | DXB_E3175P_10153_001001001 | 24.878500 | 55.176700 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2244 |  |  | DXN0090 |  | DXN0090 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-26 | DXB | 1G | DXB-6020-PREAGG-SR7-1 | 2/1/4 | DXN-0090-CSG-N540-LD-1 | FOC2720N8WA | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-25 | Y23-F114141 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-20 09:37 | DXB_E3177F_11132_001026003 | 25.094617 | 55.173745 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2241 |  |  | AUH2725 |  | AUH2725 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AUH-2170-SCSG-NCS57C3-1 | Ten0/0/0/42 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-19 17:44 | AUH_E2569O_10015_001001001 | 25.25822 | 55.29343 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2240 |  |  | DXB2931 |  | DXB2931 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-3/1/11 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:39 | DXB_E3279L_11260_001001001 | 25.25779 | 55.27318 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2238 |  |  | RAK3521 |  | RAK3521 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:31 | RKT_E3784W_10009_001001001 | 25.29797 | 55.39755 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2237 |  |  | DXB2540 |  | DXB2540 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | 10G | DXB-1346-SCSG-IXR-R6D-1 | 1/3/c1/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:29 | DXB_E3379B_11401_001001001 | 25.29856 | 55.35417 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2236 |  |  | AAN0004 |  | AAN0004 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/52 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:26 | AAN_E3767A_10011_001003091 | 24.22654 | 55.74920 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2235 |  |  | AAN2454 |  | AAN2454 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AAN-2065-PREAGG-SR7-1 | 4/1/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:23 | AAN_E3667E_10007_001001001 | 24.22556 | 55.73362 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2234 |  |  | DXB2979 |  | DXB2979 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/6/c20/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:21 | DXB_E3478D_10178_001001001 | 25.20423 | 55.50340 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2233 |  |  | RAK3526A |  | RAK3526A | Nokia IXR-E | Migration |  |  | Nokia |  | RAK | 10G | FUJ-6001-AGG-ASR9912-1 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:17 | RKT_E3982G_10002_001001001 | 25.55409 | 55.95882 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2232 |  |  | UAQ3132 |  | UAQ3132 | Nokia IXR-E | Migration |  |  | Nokia |  | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/11 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:13 | UAQ_E3581C_10075_001001001 | 25.47562 | 55.61289 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2231 |  |  | AUH3500 |  | AUH3500 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/22 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:09 | AUH_E2469O_10180_001001001 | 24.35802 | 54.57409 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2230 |  |  | AUH3498 |  | AUH3498 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/21 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:07 | AUH_E2469O_10182_001001001 | 24.33851 | 54.56018 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2229 |  |  | SHJ2378 |  | SHJ2378 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | 10G | SHJ-2058-SCSG-IXR-R6-1 | 1/6/6 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:04 | SHJ_E3380L_10040_001003001 | 25.35712 | 55.38034 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2228 |  |  | DXB1587 |  | DXB1587 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | 10G | DXB-6501-AGGR-SR12e-1 | 2/1/32 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 17:02 | DXB_E3077S_10158_001009001 | 25.06727 | 55.12766 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2227 |  |  | AUH2652 |  | AUH2652 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 16:59 | AUH_E2771U_10002_001001001 | 24.49718 | 54.77500 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2226 |  |  | AUH2310 |  | AUH2310 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-1/1/27 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 16:55 | AUH_E2270D_11812_001001001 | 24.47442 | 54.35031 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2225 |  |  | AAN2938 |  | AAN2938 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AAN-2019-SCSG-IXR-R6-1 | 1/6/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 16:53 | AAN_E3667E_10014_001001001 | 24.21752 | 55.75287 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2224 |  |  | AAN3141 |  | AAN3141 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/38 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 16:49 | AAN_E3672T_10236_001001001 | 24.61073 | 55.755827 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2222 |  |  | SHJ0300 |  | SHJ0300 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2580-SCSG-SR7B-1 | [17 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 16:33 |  | 25.298800 | 55.375000 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2221 |  |  | AUH2786 |  | AUH2786 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6005-AGGR-SR12e-2 | 2/1/15 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 16:23 |  | 24.5420 | 54.4800 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2220 |  |  | AUH2253 |  | AUH2253 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6005-AGGR-SR12e-2 | 2/1/17 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 16:19 | AUH_E2471K_10001_001001001 | 24.52861 | 54.49882 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2219 |  |  | AUH2389 |  | AUH2389 | Nokia IXR-E | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2122-SCSG-SR7B-1 | esat-1/1/18 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 16:04 | AUH_E2369T_10348_001001001 | 24.336928 | 54.481736 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2218 |  |  | FUJ2142 |  | FUJ2142 | Nokia SAR-X |  | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2398-PREAGG-SRa8-1 | 1/1/8 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:55 | RKT_E4078T_10001_001001001 | 25.1665 | 56.1368 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2217 |  |  | DXB5003 |  | DXB5003 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | AAN-6001-AGGR-SR7S-2 | esat-1/1/57 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:51 |  | 24.94511 | 55.51055 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2216 |  |  | AAN5004 |  | AAN5004 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-2/1/64 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:46 |  | 24.690700 | 55.631570 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2215 |  |  | AJM2304 |  | AJM2304 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AJM | 10G | UAQ-DC-AGGR-SR7S-1 | [17 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:26 | AJM_E3480G_11969_001001001 | 25.380874 | 55.496677 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2214 |  |  | AJM2305 |  | AJM2305 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AJM | 10G | UAQ-DC-AGGR-SR7S-1 | esat-1/1/50 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:19 | AJM_E3480B_12722_001001001 | 25.397122 | 55.492847 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2213 |  |  | SHJ2482 |  | SHJ2482 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-5001-SCSG-SR7B-1 | [17 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:13 |  | 25.278889 | 55.693610 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2212 |  |  | AUH2065 |  | AUH2065 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6003-AGGR-SR7B-1 | [17 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:07 |  | 24.48745 | 54.36391 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2211 |  |  | DXB0010 |  | DXB0010 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-3173-PREAGG-SR7B-1 | [17 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 15:00 |  | 25.254130 | 55.303610 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2210 |  |  | DXB0341 |  | DXB0341 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB |  | DXB-1025-PREAGG-SR7-1 | [17 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:49 |  | 25.252270 | 55.308510 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2209 |  |  | DXB0487 |  | DXB0487 | Nokia SAR-X | Rollout Upgrade |  |  |  |  | DXB |  | DXB-3173-PREAGG-SR7B-1 | esat-2/1/10 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:42 |  | 25.246930 | 55.308950 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2208 |  |  | AUH2208 |  | AUH2208 | Nokia IXR-E | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-1/1/52 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:35 |  | 24.32935 | 54.5371 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2207 |  |  | AUH2469 |  | AUH2469 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/10 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:31 |  | 24.3249 | 54.5355 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2206 |  |  | FUJ2130 |  | FUJ2130 | Nokia SAR-8 | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2437-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:20 |  | 25.118615 | 55.961030 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2205 |  |  | RAK2151 |  | RAK2151 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | RAK-2026-SCSG-IXR-R6D-1 | 1/5/c6/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:15 |  | 25.697260 | 55.962160 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2204 |  |  | AUH2647 |  | AUH2647 | Nokia IXR-E | Migration | Card Exp - Rollout Passive Patching |  | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-1/1/54 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-12-19 14:11 | AUH_E2468E_10342_001001001 | 24.30177 | 54.57138 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2203 |  |  | FUJ0608 |  | FUJ0608 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-2 | Te0/8/0/11 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 14:02 |  | 25.122510 | 56.327070 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2202 |  |  | FUJ0633 |  | FUJ0633 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G |  | Te0/8/0/10 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 13:57 |  | 25.122460 | 56.324790 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2201 |  |  | FUJ0642 |  | FUJ0642 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ |  | FUJ-6001-AGG-ASR9912-2 | Te0/8/0/9 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 13:31 |  | 25.122475 | 56.324337 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2200 |  |  | FUJ3747 |  | FUJ3747 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2398-PREAGG-SRa8-1 | 1/1/7 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 12:06 | FJR_E4178R_10001_001001001 | 25.15386 | 56.206903 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2199 |  |  | FUJ3239 |  | FUJ3239 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2398-PREAGG-SRa8-1 | 1/1/6 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 12:02 | RKT_E4178P_10002_001001001 | 25.156892 | 56.160073 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2198 |  |  | FUJ2154 |  | FUJ2154 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2437-PREAGG-SR7-1 | 1/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 11:48 |  | 25.064716 | 56.048348 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2197 |  |  | FUJ2966 |  | FUJ2966 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 1G | FUJ-2437-PREAGG-SR7-1 | 2/1/14 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 11:44 |  | 25.031487 | 56.081944 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2196 |  |  | FUJ3272 |  | FUJ3272 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ |  | FUJ-2437-PREAGG-SR7-1 | 4/1/5 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 11:35 |  | 24.864800 | 56.085900 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2195 |  |  | FUJ3273 |  | FUJ3273 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2437-PREAGG-SR7-1 | 2/1/9 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-12-19 11:31 |  | 24.883781 | 56.094302 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2194 | WO- IIB-CSG-2023-Order # 2194 |  | FUJ3985 |  | FUJ3985 | Nokia IXR-E | Migration | New CSG | Handover | XAD |  | FUJ | 10G | FUJ-5002-SCSG-SR7-1 | Port 4/1/2 | FUJ-3985-CSG-IXR-E-1 | NK224931278 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-02 | Y23-F114647 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 17:26 | FJR_E4277N_10001_001001001 | 25.084367 | 56.3176499 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2193 |  |  | IFU5626 |  | IFU5626 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-12-22 | FUJ | 10G | FUJ-5002-SCSG-SR7-1 | 4/1/1 | IFU-5626-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-12-21 | Y23-F113958 |  | Shahid Tech | In progress |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 16:24 | FJR_E4277A_10003_001001001 | 25.12502 | 56.27312 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2192 |  |  | KFN2616 |  | KFN2616 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-05 | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#B03 OTN RK-1/NE516 C/03/TX15/RX15 | KFN-2616-CSG-IXR-E-1 | NK224931190 | 5 | 2 | 3 | 3 | 3 |  | Rogelio Pangilinan;#1712 |  | 2024-01-04 | Y23-F114791 |  | XAD |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 16:21 | FJR_E4081N_10003_001001001 | 25.44405 | 56.12702 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2191 |  |  | AJM0952 |  | AJM0952 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-12-29 | AJM | 1G | AJM-6001-SCSG-SR7B-1 | esat-2/1/53 | AJM-0952-CSG-N540-LD-1 | FOC2718N5NB | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-12-28 | Y23-F114383 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 16:09 | AJM_E3480F_12341_001001001 | 25.379795 | 55.459848 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2190 | WO- IIB-CSG-2023-Order # 2190 |  | FUJ0632 |  | FUJ0632 | Nokia IXR-E | Migration | New CSG | Transmission rack not available | XAD |  | FUJ | 10G | FUJ-5002-SCSG-SR7-1 | Port 4/1/3 | FUJ-0632-CSG-IXR-E-1 |  | 5 | 1 | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 16:03 | FJR_E4277A_10001_001001001 | 25.126596 | 56.269903 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2189 |  |  | KFN3630 |  | KFN3630 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-01-10 | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#A4 OTN RK-1/NE516 C/03/TX4/R4 | KFN-3630-CSG-N540-LD-1 | FOC2718N5EC | 5 |  | 2 | 2 |  |  | Rogelio Pangilinan;#1712 |  | 2024-01-05 | Y23-F114882 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 15:52 | FJR_E4081J_10002_001001001 | 25.458932° | 56.137245° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2188 |  |  | IAD5375 |  | IAD5375 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-12-29 | AUH |  | IAD-5333-CSG-SAR-X-1 | 1/3/6 | IAD-5333-CSG-SAR-X-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 15:31 |  | 24.434113 | 54.619809 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2187 | WO- IIB-CSG-2023-Order # 2187 |  | DXB1761 |  | DXB1761 | Cisco NCS540 | Upgrade from SARX to IXR-E |  | Transmission rack not available | HOI-MEA |  | DXB | 10G | DXB-1852-SCSG-IXR-R6D-2 | 1/6/c8 | DXB-1761-CSG-N540-LD-1 |  | 5 |  |  |  |  | Rack space full | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-12-14 13:11 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2186 |  |  | AUH1085 |  | AUH1085 |  | SRAN + 5G |  | Passive Completed | HOI-MEA | 2024-01-22 | AUH |  | AUH-1426-SCSG-SR7B-1 | esat-1/1/45 | AUH-1426-SCSG-SR7B-1 |  | 5 |  |  |  |  | plan changed to passive | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-12-14 13:08 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2185 | WO- IIB-CSG-2023-Order # 2185 |  | FUJ3410 |  | FUJ3410 | Nokia IXR-E | BAU + 5G |  | Installed & Power up | HOI-MEA |  | FUJ |  | NE522 (FUJ2022-KALBA) |  | FUJ-3410-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-14 13:06 |  |  |  | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2184 |  |  | DXB3734 |  | DXB3734 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-12-25 | DXB | 10G | DXB-DFC-SCSG-SR7B-1 | esat-1/1/7 | DXB-3734-CSG-N540-LD-1 | FOC2720N8Y3 | 5 | [8 empty] | Y23-F113557 |  | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-14 13:04 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2183 |  |  | SHJ3173 |  | SHJ3173 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-12-19 | SHJ |  | SHJ-3827-CSG-IXR-E-1 | 1/1/15 | SHJ-3827-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-14 11:33 |  | 25.32543 | 55.38591 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2182 |  |  | IBS-SS-21-3359 |  | ISH5168 | Nokia IXR-E | BAU | New CSG | RFSed | SHAHID | 2024-01-22 | SHJ | 10G | SHJ-2017-AGGR-SR7B-1 | esat-1/1/57 | ISH-5168-CSG-IXR-E-1 | NK224931202 | 5 |  | 1 | 1 |  | Site Completed |  |  | 2024-01-18 | Y23-F115627 |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-12-13 16:26 | SHJ_E3379A_10352_001001001 | 25.3017 | 55.3683 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2181 | WO- IIB-CSG-2023-Order # 2181 |  | DXB1659 |  | DXB1659 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | SHAHID | 2024-02-20 | DXB | 10G | DXB-MIRDIFPOP-SCSG-NCS57C3-1 | TF0/0/0/1 | DXB-1659-CSG-IXR-E-1 | NK224931375 | 5 |  | 1 | 1 | 1 | Site RFS(ACR) Comarch not showing |  |  | 2024-02-19 | Y23-F117886 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-12-12 20:37 | DXB_E3378I_10248_001001001 | 25.18225 | 55.43214 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2180 |  |  | RAK1441 |  | RAK1441 | Cisco NCS540 | 5G | New CSG | No OSP | SHAHID |  | RAK | 10G | RAK-2727-SCSG-NCS57C3-1 | TenGigE0/0/2/0 | RAK-1441-CSG-NCS540-LD-1 |  |  |  | 1 | 1 | 1 | OSP ECD is 25Dec23 | [5 empty] | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-12-12 14:44 |  | 25.908131 | 56.059258 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2179 |  |  | AUH0066 |  | AUH0066 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | XAD | 2023-12-25 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/45 | AUH-0066-CSG-IXR-E-1 | NK231134543 | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-22 | Y23-F114027 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-11 15:38 | AUH_E2271X_10772_001010001 | 24.485142 | 54.352433 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2178 | WO- IIB-CSG-2023-Order # 2178 |  | KFN3082 |  | KFN3082 | Nokia IXR-E | 5G Upgrade | New CSG | Handover | XAD |  | FUJ | 10G | NE522 (FUJ2022-KALBA) | TBC | KFN-3082-CSG-IXR-E-1 | NK224931306 | 5 | 1 | 2 | 2 |  |  | Rogelio Pangilinan;#1712 |  | 2023-12-29 | Y23-F114484 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-11 14:58 | SHJ_E4279E_10016_001001001 | 25.31178 | 56.34322 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2177 |  |  | AJM0975 |  | AJM0975 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-12-14 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-2/1/52 | AJM-0975-CSG-N540-LD-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-12-14 | Y23-F113476 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-07 11:42 | AJM_E3380E_14326_001001001 | 25.387068 | 55.453741 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2176 |  |  | IDX5187 |  | IDX5187 | Passive | Rollout | Passive patching | Cancelled/on Hold | XAD |  | DXB |  | DXB-0296A-PREAGG-SR7-1 | 3/2/9 | DXB-0296A-PREAGG-SR7-1 | [6 empty] | plan changed to MW 12-7-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-06 15:50 |  | 25.25641 | 55.342601 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2175 |  |  | SHJ3788 |  | SHJ3788 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-12-12 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/47 | SHJ-3788-CSG-IXR-E-1 | NK224931288 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-12 | Y23-F113343 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-06 15:15 | SHJ_E3579D_10013_001001001 | 25.306399 | 55.630007 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2174 |  |  | DUB0413 |  | DUB0413 |  | Rollout |  | Passive Completed | HOI-MEA | 2024-01-13 | DXB | 1G | DXB-1036-SCSG-IXR-R6-1 | 1/5/6 | DXB-1036-SCSG-IXR-R6-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:34 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2173 |  |  | DUB0725 |  | DUB0725 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-21 | DXB | 1G | DXB-DSO-CSG-IXR-E-1 | 1/1/11 | DXB-DSO-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:32 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2172 |  |  | AUH3375 |  | AUH3375 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-12-13 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-1/1/29 | AUH-3375-CSG-N540-LD-1 | FOC2720N8XC | 5 | [8 empty] | Y23-F113384 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:30 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2171 |  |  | SHJ1213 |  | SHJ1213 | Nokia IXR-E | BAU + 5G |  | RFSed | HOI-MEA | 2023-12-21 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/53 | SHJ-1213-CSG-IXR-E-1 | NK224931358 | 5 | [8 empty] | Y23-F113821 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:27 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2170 | WO- IIB-CSG-2023-Order # 2170 |  | FUJ1497 |  | FUJ1497 |  | BAU |  | OSP Issue | HOI-MEA |  | FUJ | 1G | FUJ-2433-SCSG-SR7-1 | Port 2/1/8 |  |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:26 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2169 |  |  | AJM3980 |  | AJM3980 | Cisco NCS540 | BAU + 5G |  | RFSed | HOI-MEA | 2023-12-14 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/60 | AJM-3980-CSG-N540-LD-1 | FOC2720N8K6 | 5 | [8 empty] | Y23-F113461 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:25 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2168 |  |  | AJM1461 |  | AJM1461 | Cisco NCS540 | BAU + 5G |  | RFSed | HOI-MEA | 2023-12-14 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/59 | AJM-1461-CSG-N540-LD-1 | FOC2720N8WP | 5 | [8 empty] | Y23-F113473 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:24 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2167 |  |  | SHJ1173 |  | SHJ1173 | Cisco NCS540 | BAU + 5G |  | RFSed | HOI-MEA | 2024-01-04 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/51 | SHJ-1173-CSG-IXR-E-1 | NK224931320 | 5 | [8 empty] | Y23-F114684 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-12-06 14:22 |  | 25.1789958418228 | 55.803566921433 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2165 |  |  | AUH2053 |  | AUH2053 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-16 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | Port esat-2/1/40 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:59 | AUH_E2270E_11206_001001001 | 24.47855 | 54.36579 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2164 |  |  | AUH6521 |  | AUH6521 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-24 | AUH | 10G | AUH-2420-SCSG-SR7B-1 | Port esat-1/1/19 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:55 | AUH_E2669F_10104_001001001 | 24.36252 | 54.69578 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2163 |  |  | DXB0214 |  | DXB0214 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-24 | DXB | 10G | DXB-3122-SCSG-SR7B-1 | Port esat-2/1/22 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:47 | DXB_E3279L_11740_001004001 | 25.253542 | 55.281631 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2162 |  |  | AUH3270 |  | AUH3270 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-17 | AUH | 10G | AUH-2118-SCSG-SR7B-1 | Port esat-1/1/8 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:35 | AUH_E2469Q_10417_001001001 | 24.32469 | 54.51827 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2161 |  |  | AUH2928 |  | AUH2928 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-22 | AUH | 10G | AUH-2929-PREAGG-SRa8-1 | Port 2/1/10 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:29 | AUH_E2054A_10105_001001001 | 23.02865 | 54.12914 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2160 |  |  | DXB3194 |  | DXB3194 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-14 | DXB | 10G | DXB-JPPOP-AGGR-SR12e-1 | Port esat-1/1/45 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:23 | DXB_E3177P_14252_001001002 | 25.062111 | 55.170113 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2159 |  |  | AUH0484 |  | AUH0484 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-13 | AUH | 10G | AUH-1090-SCSG-SR7B-1 | esat-1/1/7 | [16 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:18 | AUH_E2370L_13031_001002006 | 24.434359 | 54.413059 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2158 |  |  | DXB3593 |  | DXB3593 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-11-10 | DXB | 10G | DXB-ICPOP-SCSG-IXR-R6D-1 | Port 1/5/c7/1 | [10 empty] | 2023-11-03 | [5 empty] | TRUE | 2023 | Hafiz Umar | 2023-12-06 02:09 | DXB_E3378F_10714_001001001 | 25.182603 | 55.376131 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2157 |  |  | IAJ5863 |  | IAJ5863 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-12-08 | AJM |  | AJM-2310-CSG-ASR920-LD-1 | Gi0/0/10 | AJM-2310-CSG-ASR920-LD-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-05 12:34 |  | 25.403608 | 55.506531 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2156 |  |  | AUH0043 |  | AUH0043 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2024-02-06 | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/9 | AUH-0043-CSG-N540-LD-1 | FOC2718N5KC | 5 |  | 1 | 1 |  | Site Completed |  |  | 2024-02-01 | Y23-F116617 |  |  |  |  | FALSE | 2023 | Mohammed Faris | 2023-12-05 09:52 | AUH_E2370N_10498_001001002 | 24.43003 | 54.463462 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2155 |  |  | IAD5279 |  | IAD5279 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-22 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-1/1/29 | IAD-5279-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-21 | Y23-F113942 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-05 09:45 | AUH_E2271X_10402_001004001 | 24.48787 | 54.352030 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2154 |  |  | DUB0719 |  | DUB0719 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-07 | DXB |  | DXB-BB-SCSG-NCS57C3-2 | TF0/0/0/49 | DXB-BB-SCSG-NCS57C3-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-01 11:07 |  | 25.182127 | 55.276134 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2153 |  |  | AUH6134 |  | AUH6134 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-13 | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | 1/4/c1 | AUH-6134-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-12 | Y23-F113391 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-01 10:47 |  | 24.18824 | 54.6697 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2152 |  |  | AUH6571 |  | AUH6571 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-11 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | esat-1/1/48 | AUH-6571-CSG-N540-LD-1 | FOC2720N8X5 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-08 | Y23-F113178 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-01 10:45 | AUH_E2469F_11173_001001001 | 24.374603000 | 54.504376002 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2151 |  |  | AUH2519 |  | AUH2519 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-13 | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | Port 1/4/c15 | AUH-2519-CSG-N540-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-12 | Y23-F113394 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-12-01 10:35 |  | 24.383702° | 54.888585° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2150 |  |  | KFN1170 |  | KFN1170 | Nokia IXR-E | BAU + 5G | New CSG | No OSP | XAD |  | FUJ | 10G | NE522 (FUJ2022-KALBA) | To be confirmed | KFN-1170-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-30 11:55 |  | 25.367650 | 56.346945 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2149 |  |  | FUJ3410 |  | FUJ3410 | Nokia IXR-E | BAU + 5G | New CSG | Cancelled/on Hold |  |  | FUJ | 10G | NE522 (FUJ2022-KALBA) | To be confirmed | FUJ-3410-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-30 11:53 |  | 25.220416 | 56.353591 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2148 |  |  | RAK1239 |  | RAK1239 | Nokia IXR-E | BAU + 5G | New CSG | RFSed | XAD | 2023-12-15 | RAK | 10G | NE508 (UAQ2016-UAQDC) | UAQ2016/MW RACK 2/SH-1 /Front Port#B5 OTN RK-1/NE508 C/03/TX17/RX17 | RAK-1239-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-14 |  |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-11-30 11:49 | RKT_E3683E_10009_001001001 | 25.655503 | 55.750648 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2147 |  |  | UAQ3722 |  | UAQ3722 | Nokia IXR-E | BAU + 5G | New CSG | RFSed | XAD | 2023-12-15 | UAQ | 10G | NE508 (UAQ2016-UAQDC) | UAQ2016/MW RACK 2/SH-1 /Front Port#B4 OTN RK-1/NE508 C/03/TX16/RX16 | UAQ-3722-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-14 |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-30 11:46 | UAQ_E3683N_10001_001001001 | 25.63541 | 55.72616 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2146 |  |  | FUJ1407 |  | FUJ1407 | Nokia IXR-E | BAU + 5G | New CSG | RFSed | XAD | 2023-12-27 | FUJ | 10G | FUJ-5003-PREAGG-SRa8-1 | Port 2/1/7 | FUJ-1407-CSG-IXR-E-1 | NK224931177 | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-12-25 | Y23-F114200 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-30 11:44 | FJR_E4079N_10001_001001001 | 25.275574 | 56.121129 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2145 |  |  | SHJ0326 |  | SHJ0326 | Passive | 5G+Migration | Passive patching | Passive Completed | XAD | 2023-12-05 | SHJ |  | SHJ-0682-CSG-IXR-E-1 | Port 1/1/10 3G Port 1/1/6 LTE & Port 1/1/7 5G | SHJ-0682-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD | Completed |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-30 11:02 |  | 25.302428 | 55.38406 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2144 |  |  | FUJ1472 |  | FUJ1472 | Cisco NCS540 | BAU | New CSG | RFSed | SHAHID | 2023-12-13 | FUJ | 1G | FUJ-2433-SCSG-SR7-1 | Port 2/1/7 | FUJ-1472-CSG-N540-LD-1 | FOC2720N8WK |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-12-13 | Y23-F113424 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-11-30 10:31 | RKT_E4175X_10002_001001001 | 24.880082 | 56.218549 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2143 |  |  | SHJ1274 |  | SHJ1274 | Nokia IXR-E | BAU + 5G | New CSG | RFSed | SHAHID | 2023-12-08 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/50 | SHJ-1274-CSG-IXR-E-1 | NK224931351 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-12-08 | Y23-F113151 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-11-30 10:20 | SHJ_E3679N_10001_001001001 | 25.2688262 | 55.727744 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2142 |  |  | SHJ6256 |  | SHJ6256 | Cisco NCS540 | BAU | New CSG | RFSed | SHAHID | 2023-12-08 | SHJ | 10G | SHJ-3612-SCSG-SRa8-1 | Port 2/3/3 | SHJ-6256-CSG-N540-LD-1 | FOC2720N8JG |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-12-08 | Y23-F113158 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-11-30 10:13 | SHJ_E3677I_10001_001001001 | 25.095292 | 55.726193 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2141 |  |  | UAQ1406 |  | UAQ1406 | Nokia IXR-E | BAU | New CSG | RFSed | SHAHID | 2023-12-08 | UAQ | 10G | SHJ-5001-SCSG-SR7B-1 | esat-1/1/52 | UAQ-1406-CSG-IXR-E-1 | NK224931370 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-12-08 | Y23-F113170 |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-11-30 10:07 | SHJ_E3879E_10001_001001001 | 25.312749 | 55.950381 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2140 |  |  | UAQ1105 |  | UAQ1105 | Cisco NCS540 | BAU + 5G | New CSG | RFSed | SHAHID | 2023-12-18 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-1/1/54 | UAQ-1105-CSG-N540-LD-1 | FOC2720N8TB |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-12-15 | Y23-F113567 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-11-30 09:56 | UAQ_E3582W_10079_001001001 | 25.49876973 | 55.59877361 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2139 |  |  | DUB0067 |  | DUB0067 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-19 | DXB | 10G | DXB-VILLAPOP-AGGR-SR12e-2 | 7/1/5 | DUB-0067-CSG-N540-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-15 | Y23-F113591 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-29 16:37 | DXB_E3377K_10710_001001001 | 25.086044 | 55.382122 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2138 |  |  | Cisco WO-6 PAC-183 |  | Cisco WO-6 PAC-183 |  | Migration |  |  | Cisco |  | DXB | [11 empty] | Cisco;#707 | [5 empty] | Completed |  | FALSE | 2023 | Mary Blanch Honey Quilino | 2023-11-29 14:44 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2137 |  |  | Cisco WO-6 PAC-182 |  | Cisco WO-6 PAC-182 |  | Migration |  |  | Cisco |  | DXB | [11 empty] | Cisco;#707 | [5 empty] | Completed |  | FALSE | 2023 | Mary Blanch Honey Quilino | 2023-11-29 14:42 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2136 |  |  | Cisco WO-6 PAC-181 |  | Cisco WO-6 PAC-181 |  | Migration |  |  | Cisco |  | SHJ | [11 empty] | Cisco;#707 | [5 empty] | Completed |  | FALSE | 2023 | Mary Blanch Honey Quilino | 2023-11-29 14:35 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2135 |  |  | Cisco WO 1 PAC 191 |  | Cisco WO 1 PAC 191 |  | Migration |  |  | Cisco | [13 empty] | Cisco;#707 | [5 empty] | Completed |  | FALSE | 2023 | Mahmoud Hagag | 2023-11-29 13:44 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2134 | WO- IIB-CSG-2023-Order # 2134 |  | IDX0980B |  | IDX0980B |  | Rollout |  | Commissioning in progress | HOI-MEA |  | DXB |  | DXB-6504-AGGR-SR12e-2 | esat-1/1/4 |  |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:17 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2133 |  |  | DUB0236 |  | DUB0236 |  | Rollout |  | Passive Completed | HOI-MEA | 2024-01-17 | DXB | 1G | DXB-PALMJ-CSG-IXR-E-1 | 1/1/5 | DXB-PALMJ-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:16 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2132 |  |  | DXN0779 |  | DXN0779 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-15 | DXB |  | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | TF0/0/0/3 | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:14 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2131 |  |  | DUB0637 |  | DUB0637 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-22 | DXB | 1G | DXB-2282-SCSG-IXR-R6D-1 | 1/5/c17 | DXB-2282-SCSG-IXR-R6D-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:13 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2130 |  |  | DXN0173 |  | DXN0173 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-12-26 | DXB | 10G | DXB-6504-AGGR-SR12e-2 | esat-1/1/5 | DXN-0173-CSG-N540-LD-1 | FOC2720N8RJ | 5 | [8 empty] | Y23-F114045 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:11 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2129 |  |  | DUB0163 |  | DUB0163 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-29 | DXB |  | DXB-BB-SCSG-NCS57C3-2 | Gig0/0/0/51 | DXB-BB-SCSG-NCS57C3-2 |  | 5 |  |  |  |  | OSP Issue resolved at 23 DEC 2023 | [5 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:10 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2128 | WO- IIB-CSG-2023-Order # 2128 |  | ISH5008 |  | ISH5008 |  | BAU |  | Site Not Ready | HOI-MEA |  | SHJ | 10G | SHJ-2017-AGGR-SR7b-1 | esat-1/1/56 |  |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:08 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2127 |  |  | IFU5634 |  | IFU5634 |  | BAU |  | Passive Completed | HOI-MEA | 2023-12-27 | FUJ | 1G | FUJ-6001-CSG-ASR920-LD-1 | Gig0/0/9 | FUJ-6001-CSG-ASR920-LD-1 |  | 5 |  |  |  |  | Patching completed but high power due to SFP | [5 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:04 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2126 |  |  | IDX0962B |  | IDX0962B |  | Rollout |  | No OSP | HOI-MEA |  | DXB |  | Waiting for Plan | Waiting for Plan | Waiting for Plan | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:02 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2125 |  |  | DUB0468 |  | DUB0468 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-05 | DXB |  | DXB-BB-SCSG-NCS57C3-2 | Gig0/0/0/48 | DXB-BB-SCSG-NCS57C3-2 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 08:01 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2124 |  |  | DUB0150 |  | DUB0150 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-11-27 | DXB |  | DXB-6501-SCSG-NCS57C3-2 | Gig0/0/0/1 | DXB-6501-SCSG-NCS57C3-2 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-29 07:59 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2123 |  |  | DUB0573 |  | DUB0573 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-16 | DXB |  | DXB-2728-CSG-IXR-E-1 | 1/1/13 | DXB-2728-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-28 16:56 |  | 25.048563 | 55.203996 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2122 |  |  | DXB5236J |  | DXB5236J | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-12-16 | DXB |  | DXB-2728-CSG-IXR-E-1 | 1/1/14 | DXB-2728-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-28 16:54 |  | 25.031223 | 55.217861 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2121 |  |  | AJM3156 |  | AJM3156 | Nokia IXR-E | BAU + 5G | New CSG | RFSed | SHAHID | 2023-12-07 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/58 | AJM-3156-CSG-IXR-E-1 | NK224931403 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-12-06 | Y23-F113028 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-11-28 10:16 | AJM_E3480J_10761_001001001 | 25.37661 | 55.54926 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2120 |  |  | AUH0897 |  | AUH0897 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-10 | AUH | 10G | AUH-2937-PREAGG-SR7-1 | 2/2/1 | AUH-0897-CSG-IXR-E-1 | NK231134559 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-08 | Y23-F114974 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-27 11:31 | AUH_E1562X_10051_001001002 | 23.658548 | 53.680119 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2119 |  |  | AUH0097 |  | AUH0097 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-11-28 | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-1/1/55 | AUH-6003-AGGR-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-27 11:21 |  | 24.47780355 | 54.3690933 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2118 |  |  | DXB0041 |  | DXB0041 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-12-01 | DXB | 10G | DXB-1023-SCSG-IXR-R6-1 | 1/1/3 | DXB-0041-CSG-N540-LD-1 | FOC2720N8K2 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-11-28 | Y23-F112586 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-24 12:53 | DXB_E3279P_11007_001001001 | 25.23717 | 55.27428 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2117 |  |  | DUB0616 |  | DUB0616 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-11-27 | DXB | 1G | DXB-VH-SCSG-SR7B-1 | esat-2/1/63 | DXB-VH-SCSG-SR7B-1 |  |  | 1 | 1 |  |  | Site Completed |  |  | 2023-11-27 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-11-24 10:25 |  | 25.064107 | 55.217447 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2116 |  |  | DUB0397 |  | DUB0397 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD |  | DXB | 10G | DXB-SiteC-Abdullah-AGG-ASR9912-1 | Te0/8/0/7 | DUB-0397-CSG-N540-LD-1 | FOC2720N8SQ | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-12-25 | Y23-F114145 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-24 09:09 | DXB_E3177F_10294_001002013 | 25.093673 | 55.17427 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2115 |  |  | IFU5616 |  | IFU5616 | Passive | Parity | Passive patching | Passive Completed | SHAHID | 2024-01-19 | FUJ |  | FUJ-3712-CSG-ASR920-LD-1 | Gi0/0/10 | FUJ-3712-CSG-ASR920-LD-1 |  | 5 |  |  | 1 | 1 | Passive Completed |  |  | 2024-01-19 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-11-24 08:47 |  | 25.1304 | 56.295267 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2114 |  |  | ISH5222 |  | ISH5222 | Passive | BAU + 5G | Passive patching | Passive Completed | SHAHID | 2023-11-24 | SHJ | 1G | KLB-DC-SCSG-SR7B-1 | esat-1/1/57 | KLB-DC-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-11-24 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-11-23 15:05 |  | 25.0787 | 56.3605 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2113 | WO- IIB-CSG-2023-Order # 2113 |  | ISH5134 |  | ISH5134 | Passive | SRAN + 5G | Passive patching | Site Not Ready | SHAHID |  | SHJ | 1G | SHJ-2084-SCSG-SR7B-1 | esat-2/1/55 | SHJ-2084-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  | ETC DAS not ready as per the mail on 02/01/2024 from Mr Mohaned | [5 empty] | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-11-23 15:02 |  | 25.33228 | 55.361094 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2112 | WO- IIB-CSG-2023-Order # 2112 |  | IAJ5851 |  | IAJ5851 | Cisco NCS540 | Rollout | New CSG | Site Not Ready | SHAHID |  | AJM | 10G | SHJ-2540-SCSG-SR7B-1 | esat-1/1/52 | IAJ-5851-CSG-N540-LD-1 |  | 5 |  |  | 1 | 1 | ECD for RFM is 2/10/2024 mentioned in mail on 12/12/2023 shared by Mr Mohaned | [5 empty] | Cisco |  |  | FALSE | 2023 | Mohammed Faris | 2023-11-23 09:47 |  | 25.39115 | 55.433757 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2111 |  |  | support for cisco migration by nokia (Batch 5) |  | support for cisco migration by nokia (Batch 5) |  | Migration |  |  | Nokia | [21 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-20 15:26 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2110 |  |  | DXB5342G |  | DXB5342G | Passive | Rollout | Passive patching | Passive Completed | XAD | 2024-01-11 | DXB |  | DXB-1828-SCSG-IXR-R6D-1 | 1/6/c5 | DXB-1828-SCSG-IXR-R6D-1 |  | 5 |  | 1 | 1 |  | Site assigned to XAD for new EPOC. |  |  | 2023-12-01 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-11-20 11:06 |  | 25.266638 | 55.388635 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2109 |  |  | IDX5715 |  | IDX5715 |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:16 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2108 |  |  | IAD0989A |  | IAD0989A |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:13 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2107 |  |  | AUH2567 |  | AUH2567 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:12 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2106 |  |  | IAD5848 |  | IAD5848 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:10 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2105 |  |  | IAD5424 |  | IAD5424 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:09 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2104 |  |  | IAD5254 |  | IAD5254 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:08 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2103 |  |  | IAD5538 |  | IAD5538 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:06 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2102 |  |  | IAD5548 |  | IAD5548 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:04 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2101 |  |  | IDX0372 |  | IDX0372 |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:03 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2100 |  |  | IAD0992E |  | IAD0992E |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 05:01 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2099 |  |  | AJM5999 |  | AJM5999I/AJM5999J |  | Migration |  |  | Nokia |  | AJM | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:59 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2098 |  |  | DXB5237G |  | DXB5237G |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:57 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2097 |  |  | IDX0963D |  | IDX0963D |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:54 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2096 |  |  | IAD5700 |  | IAD5700 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:52 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2095 |  |  | IDX0183T |  | IDX0183T |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:50 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2094 |  |  | IAD5394 |  | IAD5394 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:48 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2093 |  |  | IAD5579 |  | IAD5579 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:46 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2092 |  |  | AUH2281 |  | AUH2281 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:44 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2091 |  |  | IAD5589 |  | IAD5589 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:38 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2090 |  |  | IAD5630 |  | IAD5630 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:37 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2089 |  |  | AUH0581 |  | AUH0581 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:35 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2088 |  |  | IDX0808 |  | IDX0808 |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:33 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2087 |  |  | AAN3405 |  | AAN3405 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:32 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2086 |  |  | IAD5778 |  | IAD5778 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:27 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2085 |  |  | IAD5601 |  | IAD5601 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:25 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2084 |  |  | AAN3296 |  | AAN3296 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:23 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2083 |  |  | AUH0660 |  | AUH0660 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:22 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2082 |  |  | AUH3227 |  | AUH3227 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:20 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2081 |  |  | AUH5458D |  | AUH5458D |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-18 04:18 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2080 |  |  | IAD5820 |  | IAD5820 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:47 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2079 |  |  | IDX5669 |  | IDX5669 |  | Migration | Passive patching |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:44 |  | 25.088220 | 55.303060 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2078 |  |  | IAD5658 |  | IAD5658 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:40 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2077 |  |  | SHJ5191C |  | SHJ5191C |  | Migration | Passive patching |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:38 |  | 25.296136 | 55.488993 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2076 |  |  | DXN0274 |  | DXN0274 |  | Migration | Passive patching |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:35 |  | 25.243584 | 55.280514 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2075 |  |  | AJM6001 |  | AJM6001 |  | Migration | Passive patching |  | Nokia |  | AJM | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:32 |  | 25.387820 | 55.459130 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2074 |  |  | AUH0722 |  | AUH0722 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:30 |  | 22.900375 | 54.33669 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2073 |  |  | IAD5492 |  | IAD5492 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:27 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2072 |  |  | SHJ0660 |  | SHJ0660 |  | Migration | Passive patching |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 18:24 |  | 25.305400 | 55.380500 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2071 |  |  | AAN5398E |  | AAN5398E |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 17:16 |  | 24.164235 | 55.898119 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2070 |  |  | DXS6074 |  | DXS6074 |  | Migration | Passive patching |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 17:10 |  | 25.246850 | 55.340819 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2069 |  |  | IAD5712 |  | IAD5712 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 17:07 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2068 |  |  | IAD5581 |  | IAD5581 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 17:02 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2067 |  |  | ISH0497A |  | ISH0497A |  | Migration | Passive patching |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:59 |  | 25.332302 | 55.390368 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2066 |  |  | ISH0496 |  | ISH0496A,ISH0496B,ISH0496C,ISH0496D |  | Migration | Passive patching |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:39 |  | 25.285230 | 55.461398 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2065 |  |  | IAD5753 |  | IAD5753 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:22 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2064 |  |  | AAN5397F |  | AAN5397F |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:19 |  | 24.24427 | 55.72551 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2063 |  |  | IAD5899 |  | IAD5899 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:14 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2062 |  |  | AUH5403C |  | AUH5403C |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:11 |  | 24.354604 | 54.484136 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2061 |  |  | DXN0089 |  | DXN0089 |  | Migration | Passive patching |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 16:06 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2060 |  |  | AUH0621 |  | AUH0621 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-17 15:57 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2059 |  |  | AUH6387 |  | AUH6387 |  | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-17 15:54 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2058 |  |  | ISH0497C |  | ISH0497C |  | Migration |  |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-17 15:43 | SHJ_E3380U_10038_001001007 | 25.31084 | 55.37248 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2057 |  |  | IAD5564 |  | IAD5564 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 15:33 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2056 |  |  | IAD0996E |  | IAD0996E |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 15:31 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2055 |  |  | IAD5637 |  | IAD5637 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 15:27 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2054 |  |  | IAD5288 |  | IAD5288 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 15:19 |  | NA | Na | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2053 |  |  | AAN0122 |  | AAN0122 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 14:48 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2052 |  |  | IDX0843 |  | IDX0843 |  | Migration | Passive patching |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 14:44 |  | 25.124014 | 55.377646 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2051 |  |  | IAD5443 |  | IAD5443 |  | Migration | Passive patching |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 14:41 |  | NA | NA | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2050 |  |  | DXB5148I |  | DXB5148I |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 14:37 |  | 25.123528 | 55.402578 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2049 |  |  | DXN0445 |  | DXN0445 |  | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 14:35 |  | 25.219518 | 55.364668 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2048 |  |  | DUB0002 |  | DUB0002 |  | Migration | Passive patching |  |  |  | DXB | 10G | [18 empty] | FALSE | 2023 | Omer Ikram | 2023-11-17 14:31 |  | 25.295400 | 55.375200 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2046 |  |  | DUB0577 |  | DUB0577 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-12-21 | DXB | 1G | DXB-DSO-CSG-IXR-E-2 | 1/1/11 | DXB-DSO-CSG-IXR-E-2 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-17 00:33 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2045 |  |  | DXB3410 |  | DXB3410 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-12-14 | DXB | 10G | DXB-BB-SCSG-NCS57C3-1 | Te0/0/2/2 | DXB-3410-CSG-N540-LD-1 | FOC2720N8UH | 5 | [8 empty] | Y23-F113428 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-17 00:31 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2044 |  |  | AJM1266 |  | AJM1266 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2023-11-24 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-1/1/56 | AJM-1266-CSG-IXR-E-1 | NK224931298 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-11-23 | Y23-F112323 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-11-16 15:43 | AJM_E3480C_13623_001001001 | 25.3872 | 55.5149 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2043 |  |  | DXNNR0272 |  | DXNNR0272 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-11-24 | DXB | 10G | DXB-1096-SCSG-IXR-R6D-1 | 1/5/c7 | DXN-0272-CSG-N540-LD-1 | FOC2720N8J5 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-11-22 | Y23-F112240 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-16 08:29 | DXB_E3379B_11562_001017002 | 25.293 | 55.3937 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2042 |  |  | DUB0883 |  | DUB0883 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-29 | DXB |  | DXB-0296A-PREAGG-SR7-1 | 3/2/11 | DXB-0296A-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-16 08:19 |  | 25.24444 | 55.359113 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2041 |  |  | AUH1717 |  | AUH1717 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-23 | AUH |  | AUH-KHAZNA-AGG-SR12e-1 | esat-1/1/47 | AUH-1717-CSG-N540-LD-1 | FOC2720N8UF | 5 | [8 empty] | Y23-F112112 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-14 18:19 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2040 |  |  | AAN3119 |  | AAN3119 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-12-07 | AUH | 10G | AAN-5002-AGGR-SR12-1 | 5/1/4 | AAN-3119-CSG-IXR-E-1 | NK224931335 | 5 | [8 empty] | Y23-F113029 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-14 18:18 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2039 |  |  | AAN2625 |  | AAN2625 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-12-14 | AUH | 10G | AAN-2302-SCSG-IXR-R6D-1 |  | AAN-2625-CSG-IXR-E-1 | NK224931259 | 5 | [8 empty] | Y23-F113018 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-14 18:16 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2038 |  |  | AAN3321 |  | AAN3321 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-21 | AUH | 10G | AAN-2059-PREAGG-SR7-1 | Port 2/2/4 | AAN-3321-CSG-IXR-E-1 | NK224931170 | [9 empty] | Y23-F111762 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-14 18:14 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2037 |  |  | DUB0586 |  | DUB0586 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-11-21 | DXB |  | DXB-DGPOP2-SCSG-NCS57C3-2 | TF0/0/0/0 | DXB-DGPOP2-SCSG-NCS57C3-2 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-11-21 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-11-14 15:13 | NA | 25.018185 | 55.125294 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2036 |  |  | DXB0897 |  | DXB0897 | Nokia IXR-E | Migration | New CSG | No OSP | XAD |  | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/49 | DXB-0897-CSG-IXR-E-1 | [6 empty] | incorrect OSP in portal | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-14 12:00 |  | 25.252328 | 55.335300 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2032 |  |  | IAD5901 |  | IAD5901 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-12-01 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | esat-1/1/46 | IAD-5901-CSG-N540-LD-1 | FOC2720N8Z7 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-11-22 | Y23-F112228 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-13 12:53 | AUH_E2570Q_10037_001001001 | 24.430332 | 54.620414 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2031 |  |  | AUH3944 |  | AUH3944 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-17 | AUH | 10G | AUH-2918-PREAGG-SR7-1 | 4/1/5 | AUH-3944-CSG-IXR-E-1 | NK224931218 | [9 empty] | Y23-F111673 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-13 12:36 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2030 |  |  | RAK1286 |  | RAK1286 | Cisco NCS540 | BAU + 5G | New CSG | RFSed | SHAHID | 2023-11-22 | RAK | 10G | RAK-2026-SCSG-IXR-R6D-1 | Port 1/5/c19 | RAK-1286-CSG-N540-LD-1 | FOC2720N8YL |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-11-21 | Y23-F112135 |  | Cisco |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-11-10 14:46 | RKT_E3983H_10002_001001001 | 25.6433 | 55.9981 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2029 | WO- IIB-CSG-2023-Order # 2029 |  | SHJ1631 |  | SHJ1631 | Nokia IXR-E | BAU + 5G | New CSG | Site Not Ready | SHAHID |  | SHJ |  | SHJ-2049-AGGR-SR7b-1 | esat-2/1/26 | New CSG Integration |  | 5 |  | 1 | 1 | 1 | Sites are not ready. Civil still going on./NO ECD shared | [5 empty] | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-11-07 16:49 |  | 25.312 | 55.454 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2028 | WO- IIB-CSG-2023-Order # 2028 |  | SHJ1628 |  | SHJ1628 | Nokia IXR-E | BAU + 5G | New CSG | Site Not Ready | SHAHID |  | SHJ |  | SHJ-2049-AGGR-SR7b-1 | esat-2/1/25 | New CSG Integration |  | 5 |  | 1 | 1 | 1 | Sites are not ready. Civil still going on./NO ECD shared | [5 empty] | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-11-07 16:46 |  | 25.3058 | 55.4553 | Manual | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
2027 |  |  | DXN0899 |  | DXN0899 | Passive | Rollout | New CSG | Passive Completed | XAD | 2023-12-13 | DXB | 10G | DXB-0019B-CSG-SAR-X-1 | 1/2/7 SRAN and 1/3/7 5G | DXB-0019B-CSG-SAR-X-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-07 13:15 |  | 25.252649 | 55.353995 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2026 |  |  | SHJ1630 |  | SHJ1630 | Nokia IXR-E | BAU + 5G | New CSG | RFSed | SHAHID | 2024-02-12 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/24 | SHJ-1630-CSG-IXR-E-1 | NK224931263 | 5 |  | 1 | 1 | 1 | RFS(ACR)/Comarch not showing |  |  | 2024-02-09 | Y23-F117171 |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-11-07 12:25 | SHJ_E3380Y_10082_001001001 | 25.3121 | 55.4513 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2025 |  |  | DUB0766 |  | DUB0766 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-07 | DXB |  | DXB-DIFC-TER-2-CSG-IXR-E-1 | 1/1/5 | DXB-DIFC-TER-2-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-07 09:47 |  | 25.20691 | 55.275800 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2024 |  |  | AAN3423 |  | AAN3423 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-17 | AUH | 10G | AAN-6001-AGGR-SR7S-2 | esat-1/1/59 | AAN-3423-CSG-IXR-E-1 | NK224632224 | [9 empty] | Y23-F111728 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-06 11:22 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2023 |  |  | DUB0242 |  | DUB0242 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-11-06 | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/16 | DXB-1516-SCSG-SR7B-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-06 09:30 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2022 |  |  | AAN2400 |  | AAN2400 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | Port 10/1/2 | [10 empty] | 2023-10-26 | Y23-F110317 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-11-03 16:15 | AAN_E3166B_10001_001001001 | 24.12386 | 55.20728 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2021 |  |  | AAN2947 |  | AAN2947 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-07 | AUH |  | AAN-2009-SCSG-IXR-R6D-1 | 1/5/c15 | AAN-2947-CSG-IXR-E-1 | NK224931399 | [9 empty] | Y23-F111195 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-03 15:03 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2020 |  |  | AAN3646 |  | AAN3646 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-07 | AUH | 10G | AAN-2033-SCSG-SR7B-1 | esat-1/1/29 | AAN-3646-CSG-IXR-E-1 | NK224931155 | [9 empty] | Y23-F111165 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-11-03 15:02 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2019 |  |  | KFN3678 |  | KFN3678 | Cisco NCS540 | BAU + 5G | New CSG | RFSed | XAD | 2023-11-16 | FUJ | 10G | NE516 (RAK2722-Kalba) | RAK2722/TXN RK/SH-1 /Front Port#A13 OTN RK-1/NE516 C/03/TX13/RX13 | KFN-3678-CSG-N540-LD-1 | FOC2720N8MQ |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-11-14 | Y23-F111671 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-03 13:56 | RKT_E4081W_10001_001001001 | 25.4218 | 56.0969 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2018 |  |  | DXB1684 |  | DXB1684 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | Others | DXB-1096-SCSG-IXR-R6D-2 | Port 1/3/c2/1 | [10 empty] | 2023-10-27 | Y23-F110567 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-11-03 05:20 | DXB_E3279T_10021_001002002 | 25.247807 | 55.345497 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2017 |  |  | SHJ2218 |  | SHJ2218 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:54 | SHJ_E3380C_10003_001001001 | 25.3861 | 55.4127 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2016 |  |  | DXB1426 |  | DXB1426 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:53 | DXB_E3178Q_11536_001001001 | 25.14477 | 55.20342 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2015 |  |  | DXB2559 |  | DXB2559 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:51 | DXB_E3077X_10028_001011002 | 25.04736 | 55.13075 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2014 |  |  | DXB2108 |  | DXB2108 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:49 | DXB_E3478Q_10003_001002001 | 25.159861 | 55.487305 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2013 |  |  | DXB1179 |  | DXB1179 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:46 | DXB_E3177K_11559_001001001 | 25.0734 | 55.16675 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2012 |  |  | AUH2086 |  | AUH2086 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:45 | AUH_E2270J_12006_001001001 | 24.45962 | 54.37259 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2011 |  |  | DXB1593 |  | DXB1593 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:43 | DXB_E3379G_11249_001002001 | 25.283806 | 55.388615 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2010 |  |  | DXB3216 |  | DXB3216 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:40 | DXB_E3177P_14254_001001001 | 25.05631 | 55.17622 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2009 |  |  | DXB3210 |  | DXB3210 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:38 | DXB_E3177U_12624_001001001 | 25.050749 | 55.181725 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2008 |  |  | RAK2872 |  | RAK2872 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:35 | RKT_E3884D_10002_001001001 | 25.75941 | 55.91884 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2007 |  |  | RAK2100 |  | RAK2100 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-03 04:32 | RKT_E3985G_10004_001001001 | 25.81945 | 55.98603 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2006 |  |  | SHJ0179 |  | SHJ0179 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 20:13 | SHJ_E3379A_10206_001003012 | 25.297216 | 55.372331 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2005 |  |  | DXB2334 |  | DXB2334 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 20:10 | DXB_E3277Q_10536_001001001 | 25.0585 | 55.28502 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2004 |  |  | DXB0113 |  | DXB0113 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 20:08 | DXB_E3279X_10028_002002001 | 25.23258 | 55.32314 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2003 |  |  | AAN2026 |  | AAN2026 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 20:06 | AAN_E3668Y_10001_001001001 | 24.2325 | 55.76822 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2002 |  |  | SHJ2673 |  | SHJ2673 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 20:04 | SHJ_E3479H_10001_001001001 | 25.275 | 55.5029 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2001 |  |  | DXB1094 |  | DXB1094 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 20:01 | DXB_E3279I_15587_001001001 | 25.279249 | 55.334747 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
2000 |  |  | DXB1066 |  | DXB1066 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | TRUE | 2023 | Hafiz Umar | 2023-11-02 19:59 | DXB_E3177U_12626_001001001 | 25.048332 | 55.172279 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1999 |  |  | DXB1055 |  | DXB1055 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 19:43 | DXB_E3279L_12594_001001001 | 25.26022 | 55.29861 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1998 |  |  | DXB3214 |  | DXB3214 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 19:39 | DXB_E3077T_13243_001001001 | 25.05882 | 55.16119 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1997 |  |  | RAK2738 |  | RAK2738 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 19:37 | FJR_E4082V_10001_001001001 | 25.5077 | 56.07566 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1996 |  |  | SHJ0399 |  | SHJ0399 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 19:27 | SHJ_E3379A_10206_001001001 | 25.29798 | 55.37197 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1995 |  |  | KFN2677 |  | KFN2677 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 19:21 | FJR_E4281T_10001_001001001 | 25.42871 | 56.35086 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1994 |  |  | KFN2624 |  | KFN2624 | Nokia IXR-E | Migration |  |  | Nokia | [21 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 18:33 | FJR_E4282J_10001_001001001 | 25.55483 | 56.34695 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1993 |  |  | SHJ2361 |  | SHJ2361 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 18:30 | SHJ_E3380C_10002_001001001 | 25.3883 | 55.4158 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1992 |  |  | DXB1889 |  | DXB1889 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 18:24 | DXB_E3379H_11019_001001001 | 25.28354 | 55.40894 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1991 |  |  | DXB1324 |  | DXB1324 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 18:20 | DXB_E3379F_10185_001001001 | 25.2874 | 55.37106 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1990 |  |  | AUH2275 |  | AUH2275 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:32 | AUH_E2774O_10007_001001001 | 24.798112 | 54.860856 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1989 |  |  | DXB1293 |  | DXB1293 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:28 | DXB_E3279I_14829_001001001 | 25.27375 | 55.33143 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1988 |  |  | DXB2504 |  | DXB2504 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:24 | DXB_E3479W_10366_001001001 | 25.22098 | 55.51294 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1987 |  |  | DXB2078 |  | DXB2078 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:21 | DXB_E3177P_12158_001001001 | 25.0543 | 55.1715 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1986 |  |  | DXB2805 |  | DXB2805 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:18 | DXB_E3077Y_11622_001001001 | 25.0499 | 55.1464 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1985 |  |  | DXB1068 |  | DXB1068 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:15 | DXB_E3177P_14253_001001001 | 25.064804 | 55.184807 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1984 |  |  | IDX5197 |  | IDX5197 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:11 | DXB_E3077W_11010_001001139 | 25.044755 | 55.119421 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1983 |  |  | IDX5025 |  | IDX5025 | Nokia IXR-E | Rollout |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:08 | DXB_E3077O_11071_001014002 | 25.08738 | 55.15127 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1982 |  |  | IDX5153 |  | IDX5153 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:04 | DXB_E3278A_11661_001011001 | 25.199899 | 55.282951 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1981 |  |  | AUH2220 |  | AUH2220 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 17:00 | AUH_E2370M_12380_001001001 | 24.43846 | 54.42833 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1980 |  |  | AUH3123 |  | AUH3123 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 16:51 | AUH_E2771K_10001_001001001 | 24.54085 | 54.78882 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1979 |  |  | AUH3565 |  | AUH3565 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 16:47 | AUH_E1655M_10001_001001001 | 23.062828 | 53.776832 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1978 |  |  | AUH6483 |  | AUH6483 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 16:42 | AUH_E2154J_10001_001001001 | 23.008509 | 54.307284 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1977 |  |  | SHJ2636 |  | SHJ2636 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 16:35 |  | 25.320990 | 55.659760 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1976 |  |  | DXB2279 |  | DXB2279 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-02 16:28 | DXB_E3279D_12671_001001001 | 25.2900829 | 55.3278046 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1975 |  |  | KFN2108 |  | KFN2108 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 16:22 | SHJ_E4280T_10002_001001001 | 25.34508 | 56.34381 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1974 |  |  | AJM2321 |  | AJM2321 | Nokia IXR-E | Migration |  |  | Nokia |  | AJM | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 16:02 | AJM_E3381T_13921_001001001 | 25.41976 | 55.44970 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1973 |  |  | AUH2891 |  | AUH2891 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 15:59 | AUH_E2667X_10001_001001001 | 24.139726 | 54.758084 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1972 |  |  | AUH0460 |  | AUH0460 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 15:54 | AUH_E2270E_12846_001003001 | 25.05505 | 55.15886 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1971 |  |  | RAK2772 |  | RAK2772 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK | [19 empty] | FALSE | 2023 | Hafiz Umar | 2023-11-02 15:42 | RKT_E3985M_10001_001001001 | 25.801596 | 56.00038 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1970 |  |  | DXB2272 |  | DXB2272 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-01 17:28 | DXB_E3279W_10078_001003001 | 25.23411 | 55.31161 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1969 |  |  | DXB2343 |  | DXB2343 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-01 17:24 | DXB_E3279Q_12264_001001001 | 25.2393995 | 55.2881619 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1968 |  |  | DXB1590 |  | DXB1590 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-01 17:21 | DXB_E3379K_11769_001001001 | 25.257413 | 55.380469 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1967 |  |  | IAD5066 |  | IAD5066 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [19 empty] | FALSE | 2023 | Omer Ikram | 2023-11-01 17:18 | AUH_E2370S_10282_001007001 | 24.416117 | 54.453591 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1966 |  |  | AUH2799 |  | AUH2799 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [17 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-11-01 17:13 |  | 24.343 | 54.57585 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1965 | WO- IIB-CSG-2023-Order # 1965 |  | IRK5526 |  | IRK5526 | Cisco NCS540 | BAU | New CSG | Site Not Ready | SHAHID |  | RAK |  | RAK-2000-SCSG-SR7B-1 | esat-1/1/19 | RAK-2000-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  | Access not ready for GSM site as per the mail on 02/01/2024 from Mr Mohaned | [5 empty] | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-11-01 16:45 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1964 |  |  | DXB3176 |  | DXB3176 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-11-10 | DXB | 10G | DXB-1074-SCSG-IXR-R6-1 | 1/6/1 | DXB-3176-CSG-N540-LD-1 | FOC2720N8VF |  |  | 1 | 1 |  | Site Completed |  |  | 2023-11-08 | Y23-F111327 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-11-01 16:42 | DXB_E3076N_10380_001001001 | 24.98984 | 55.14292 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1963 |  |  | SHJ2344 |  | SHJ2344 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ | [17 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-11-01 16:42 | SHJ_E3479I_10001_001001001 | 25.2817 | 55.5223 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1962 |  |  | AUH0425 |  | AUH0425 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [17 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-11-01 16:38 | AUH_E2271X_10400_001002001 | 24.48849 | 54.35274 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1961 |  |  | AUH3940 |  | AUH3940 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH | [17 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-11-01 16:32 |  | 24.334041 | 54.537409 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1960 |  |  | AAN0026 |  | AAN0026 |  | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-11-01 16:28 |  | 24.23281 | 55.73054 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1959 |  |  | AUH6501 |  | AUH6501 | Nokia SAR-8 | Rollout | New CSG | RFSed | Nokia |  | AUH | 10G | AUH-6501-AGGR-SR12e-1 | Port 7/1/8 | [11 empty] | Y23-F109620 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-11-01 14:27 | AUH_E2369J_10069_001001001 | 24.36676 | 54.48445 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1958 |  |  | DXB0604 |  | DXB0604 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [11 empty] | Y23-F109871 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-11-01 14:21 | DXB_E3077J_10603_001002002 | 25.0889 | 55.1581 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1957 |  |  | DXB0608 |  | DXB0608 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-6504-AGGR-SR12e-1 | Port 1/2/c3/1 | [11 empty] | Y23-F109544 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-11-01 14:15 | DXB_E3077W_11006_001002002 | 25.0467 | 55.1175 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1956 |  |  | DXB0594 |  | DXB0594 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [11 empty] | Y23-F109490 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-11-01 14:11 | DXB_E3279V_10054_001002003 | 25.2247 | 55.285 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1955 |  |  | DUB0419 |  | DUB0419 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-04 | DXB |  | DXB-3230-SCSG-IXR-R6-1 | 1/5/6 | DXB-3230-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-01 14:00 |  | 25.177211 | 55.234184 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1954 |  |  | AUH2815 |  | AUH2815 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-11-27 | AUH | 10G | AUH-2402-SCSG-IXR-R6D-1 | 1/3/c15 | AUH-2815-CSG-IXR-E-1 | NK224931317 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-11-23 | Y23-F112280 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-01 11:28 | AUH_E2567A_10001_001001001 | 24.19643 | 54.58858 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1953 |  |  | DXN0442 |  | DXN0442 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-04 | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/15 | DXB-1516-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-11-01 10:00 |  | 25.21107 | 55.31803 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1952 |  |  | DXB0596 |  | DXB0596 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F109502 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-31 16:16 | DXB_E3278A_11617_001002004 | 25.2111 | 55.2756 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1951 |  |  | DUB0818 |  | DUB0818 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-03 | DXB |  | DXB-DSO-CSG-IXR-E-2 | 1/1/16 | DXB-DSO-CSG-IXR-E-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-31 15:14 |  | 25.118911 | 55.395955 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1950 |  |  | DXB0606 |  | DXB0606 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-6504-AGGR-SR12e-1 | Port 1/2/c3/1 | [10 empty] | 2023-10-19 | Y23-F109968 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-31 14:48 | DXB_E3077N_10712_001002003 | 25.0708 | 55.1386 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1949 |  |  | DXB0604 |  | DXB0604 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F109871 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-31 14:43 | DXB_E3077J_10603_001002002 | 25.0889 | 55.1581 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1948 |  |  | DXB0591 |  | DXB0591 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F109977 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-31 14:38 | DXB_E3279M_11335_001003047 | 25.2547 | 55.3042 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1947 |  |  | DXB0589 |  | DXB0589 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F109975 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-31 14:32 | DXB_E3279N_11571_001002002 | 25.2633 | 55.3242 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1946 |  |  | IBS-SS-21-3855 |  | ISH5223 | Cisco NCS540 | BAU + 5G | New CSG | RFSed | SHAHID | 2023-11-20 | SHJ | 10G | SHJ-5001-SCSG-SR7B-1 | esat-1/1/5 | ISH-5223-CSG-N540-LD-1 | FOC2720N8X4 |  | 0 | 1 | 1 | 0 | Site Completed |  |  | 2023-11-09 | Y23-F111362 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-31 12:08 | SHJ_E3879H_10003_001001001 | 25.289 | 55.8981 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1945 |  |  | DXB0593 |  | DXB0593 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [11 empty] | Y23-F109974 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 20:13 | DXB_E3279V_10053_001002003 | 25.2336 | 55.2922 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1944 |  |  | DXB0605 |  | DXB0605 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-6504-AGGR-SR12e-1 | Port 1/2/c3/1 | [11 empty] | Y23-F109969 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 19:55 | DXB_E3077O_11061_001002003 | 25.08 | 55.1475 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1943 |  |  | DXB0296 |  | DXB0296 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F109973 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 19:44 | DXB_E3279T_11659_001005001 | 25.24877 | 55.35219 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1942 |  |  | Dxb2685 |  | Dxb2685 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | Port Te0/0/0/50 | [10 empty] | 2023-10-19 | [5 empty] | TRUE | 2023 | Hafiz Umar | 2023-10-30 19:28 | DXB_E3177J_12962_001001001 | 25.09806 | 55.24483 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1941 |  |  | DXB0586 |  | DXB0586 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F110067 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 19:16 | DXB_E3279T_10007_001002002 | 25.2483 | 55.3525 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1940 |  |  | DXB0584 |  | DXB0584 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F110063 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 18:59 | DXB_E3379P_10549_001001002 | 25.2411 | 55.3658 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1939 |  |  | DXB0583 |  | DXB0583 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-20 | Y23-F110061 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 18:52 | DXB_E3379V_14249_001002003 | 25.2303 | 55.3911 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1938 |  |  | DXB0588 |  | DXB0588 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F110059 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 18:42 | DXB_E3279N_11570_001001003 | 25.2542 | 55.33 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1937 |  |  | DXN0371 |  | DXN0371 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-DUBAIOTECH-AGGR-SR12e-1 | Port 2/1/13 | [10 empty] | 2023-10-19 | Y23-F110065 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 18:21 | DXB_E3177R_11519_001014003 | 25.05867 | 55.22328 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1936 |  |  | DXB0592 |  | DXB0592 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F109976 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 18:06 | DXB_E3279Q_12256_001002003 | 25.2444 | 55.2983 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1935 |  |  | DXB0587 |  | DXB0587 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-26 | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-19 | Y23-F110145 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 17:57 | DXB_E3279S_10299_001002004 | 25.2494 | 55.34 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1934 |  |  | DXB0590 |  | DXB0590 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-26 | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 6/1/c2/1 | [10 empty] | 2023-10-21 | Y23-F110146 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-30 17:51 | DXB_E3279M_11334_001003041 | 25.2664 | 55.3139 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1933 |  |  | DUB0156 |  | DUB0156 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-10-31 | DXB |  | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/4 | DXB-BB-SCSG-NCS57C3-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-30 15:20 |  | 25.181593 | 55.270578 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1932 |  |  | RAK0567 |  | RAK0567 | Cisco NCS540 | Parity | New CSG | RFSed | SHAHID | 2023-11-10 | RAK | 10G | RAK-6001-AGGR-SR7S-2 | esat-1/1/9 | RAK-0567-CSG-N540-LD-1 | FOC2718N60M |  | 0 | 1 | 1 | 0 | Site Completed |  |  | 2023-11-07 | Y23-F111214 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-30 15:08 | RKT_E3985Q_10035_001001001 | 25.7837 | 55.988696 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1931 |  |  | DUB0420 |  | DUB0420 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-12-13 | DXB | 10G | DXB-5008-AGGR-SR2S-1 | esat-1/1/23 | DUB-0420-CSG-N540-LD-1 | FOC2720N8Z4 | [9 empty] | Y23-F113155 |  | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-28 12:12 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1930 |  |  | DUB0063 |  | DUB0063 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-11-07 | DXB | 10G | DXB-6504-AGGR-SR12e-1 | 2/1/7 | DUB-0063-CSG-N540-LD-1 | FOC2720N8PC | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-11-04 | Y23-F111066 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-27 14:48 | DXB_E3176A_10179_001001003 | 25.024604 | 55.183189 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1929 |  |  | IAD5884 |  | IAD5884 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-04 | AUH |  | AUH-2410-SCSG-IXR-R6D-1 | port 1/5/c18 | AUH-2410-SCSG-IXR-R6D-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-27 11:46 |  | 24.455686° | 54.616216° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1928 |  |  | DUB0547 |  | DUB0547 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-1516-SCSG-SR7B-1 | esat-3/1/14 | DXB-1516-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-31 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-27 10:33 |  | 25.253804 | 55.337492 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1927 |  |  | AUH2271 |  | AUH2271 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2142-SCSG-IXR-R6D-1 | TBD | AUH-2271-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 | site inside Zayed military city | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-26 11:29 |  | 24.52848 | 54.992232 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1926 |  |  | AUH3937 |  | AUH3937 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-11-16 | AUH |  | AUH-6558-CSG-IXR-E-1 | 1/1/11SRAN ¦ 1/1/12 5G | AUH-6558-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-26 11:26 |  | 24.068716700 | 52.663479500 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1925 |  |  | AUH3939 |  | AUH3939 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-11-07 | AUH | 10G | AUH-1416-AGGR-SR12E-2 | esat-2/1/1 | AUH-3939-CSG-IXR-E-1 | NK224931355 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-31 | Y23-F110841 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-26 11:07 | AUH_E2569L_10103_001001001 | 24.340519991 | 54.610540001 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1924 |  |  | SHJ1462 |  | SHJ1462 | Cisco NCS540 | BAU | New CSG | RFSed | XAD | 2023-11-02 | SHJ | 10G | SHJ-2022-AGGR-SR7b-1 | esat-1/1/27 | SHJ-1462-CSG-N540-LD-1 | FOC2720N8S8 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-11-01 | Y23-F110916 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-25 14:45 | SHJ_E3380S_10026_001001001 | 25.336606 | 55.425581 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1923 |  |  | DXB1438 |  | DXB1438 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-11-13 | DXB | 10G | DXB-DSO-DC-AGGR-SR7S-1 | esat-1/1/18 | DXB-1438-CSG-N540-LD-1 | FOC2720N8QZ |  |  | 1 | 1 |  | Site Completed |  |  | 2023-11-02 | Y23-F110965 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-25 13:09 | DXB_E3378K_11021_001001001 | 25.163371759076 | 55.3821706551555 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1922 |  |  | SHJ3255 |  | SHJ3255 | Nokia SAR-X | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | UAQ-DC-AGGR-SR7S-1 and 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-25 11:10 |  | 25.306137 | 55.424105 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1921 |  |  | AUH3589 |  | AUH3589 | Nokia IXR-E | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 5/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-25 11:05 | AUH_E1362J_10001_001001001 | 23.661669 | 53.698249 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1920 |  |  | AUH2905 |  | AUH2905 | Nokia IXR-E | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2904-PREAGG-SR7-1 | Port 2/2/4 |  |  | 5 | [13 empty] | FALSE | 2023 | Omer Ikram | 2023-10-25 11:02 | AUH_E1666S_10001_001001001 | 24.0468 | 53.7717 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1919 |  |  | AAN2286 |  | AAN2286 | Nokia IXR-E | Rollout Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2058-PREAGG-SR7-1 | Port 4/1/5 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-25 10:59 | AAN_E3667E_10005_001007001 | 24.22459 | 55.76309 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1918 |  |  | AUH0087 |  | AUH0087 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-10-31 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | esat-1/1/43 | AUH-0087-CSG-N540-LD-1 | FOC2720N8RC |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-10-30 | Y23-F110736 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-25 08:55 | AUH_E2570Q_10036_001001001 | 24.42998 | 54.62154 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1917 |  |  | DUB0955 |  | DUB0955 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-27 | DXB |  | DXB-3155-SCSG-IXR-R6D-2 | 1/5/c5 | DXB-3155-SCSG-IXR-R6D-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:21 |  | 25.157454 | 55.295125 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1916 |  |  | DXB0041 |  | DXB0041 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-28 | DXB |  | DXB-1023-SCSG-IXR-R6-1 | 1/1/3 | DXB-1023-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:19 |  | 25.237170 | 55.274280 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1915 |  |  | DXN0852 |  | DXN0852 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-27 | DXB |  | DXB-3155-SCSG-IXR-R6D-2 | 1/5/c4 | DXB-3155-SCSG-IXR-R6D-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:17 |  | 25.158353° | 55.295234° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1914 |  |  | DXN0466 |  | DXN0466 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-11-06 | DXB |  | DXB-3257-CSG-IXR-E-1 | 1/1/6 | DXB-3257-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:12 |  | 25.259615 | 55.306165 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1913 |  |  | DXN0430 |  | DXN0430 | Passive | Migration | Passive patching | Access Issues | XAD |  | DXB |  | DXB-2113-CSG-SAR-X-1 | 1/2/4 | DXB-2113-CSG-SAR-X-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:09 |  | 25.24696 | 55.41723 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1912 |  |  | DXB2464 |  | DXB2464 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-30 | DXB |  | DXB-1914-CSG-SAR-X-1 | 1/3/6 | DXB-1914-CSG-SAR-X-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:07 |  | 25.015923° | 55.658373° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1911 | WO- IIB-CSG-2023-Order # 1911 |  | DXB3879 |  | DXB3879 | Nokia IXR-E | Migration | New CSG | Transmission rack not available | XAD |  | DXB | 10G | DXB-DGPOP1-AGGR-SR12e-1 | esat-1/1/26 | DXB-3879-CSG-IXR-E-1 |  | 5 |  |  |  |  | site is ATOM no rack and rectifier available | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:04 |  | 24.92068 | 55.00901 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1910 |  |  | DXB0282 |  | DXB0282 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-23 | DXB | 10G | DXB-2268-SCSG-IXR-R6-1 | 1/1/3 | DXB-0282-CSG-IXR-E-1 | NK231233690 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-08 | Y23-F115004 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 16:01 | DXB_E3278A_11563_001003001 | 25.210424 | 55.270957 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1909 |  |  | DXB0033 |  | DXB0033 | Nokia IXR-E | Migration | New CSG | No OSP | XAD |  | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/3 | DXB-0033-CSG-IXR-E-1 | [6 empty] | no OSP , no rectifier , no rackspace | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 15:56 |  | 25.220695 | 55.280454 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1908 |  |  | DXB2955 |  | DXB2955 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-11-28 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-2 | esat-1/1/4 | DXB-2955-CSG-N540-LD-1 | FOC2720N8W2 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-11-02 | Y23-F110966 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-24 09:30 | DXB_E3277V_10944_001001001 | 25.040856 | 55.290564 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1907 |  |  | RAK3109 |  | RAK3109 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | RAK | 10G | RAK-2000-SCSG-SR7B-1 | Port esat-1/1/18 | [10 empty] | 2023-10-17 | Y23-F109784 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 16:06 | RKT_E3884N_10003_001001001 | 25.7100 | 55.9235 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1906 |  |  | KFN2601 |  | KFN2601 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-09 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 and 2 | Hu0/0/0/3 | [10 empty] | 2023-05-02 | Y23-F79405 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 16:03 | SHJ_E4280T_10001_001001001 | 25.33951 | 56.34911 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1905 |  |  | DXB1721 |  | DXB1721 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-13 | DXB | 10G | DXB-3249-PREAGG-SR7-1 | Port 1/1/4 | [10 empty] | 2023-10-13 | Y23-F109580 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:50 | DXB_E3279W_10927_001001001 | 25.21722 | 55.30278 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1904 |  |  | DXB1591 |  | DXB1591 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-17 | DXB | 10G | DXB-2282-SCSG-IXR-R6D-1 | Port 1/3/c4/1 | [10 empty] | 2023-10-17 | Y23-F109709 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:46 | DXB_E3379A_10110_001001001 | 25.29024 | 55.37175 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1903 |  |  | DXB2686 |  | DXB2686 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-17 | DXB | 10G | DXB-2688-SCSG-SR7B-1 | Port esat-1/1/30 | [10 empty] | 2023-10-17 | Y23-F109710 |  |  | Completed |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:41 | DXB_E3175P_10153_001001001 | 24.8785 | 55.1767 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1902 |  |  | DXB2700 |  | DXB2700 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-09 | DXB | 10G | DXB-1090-SCSG-SR7B-1 | Port esat-1/1/16 | [10 empty] | 2023-10-05 | Y23-F109037 |  |  | Completed |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:38 | DXB_E3279G_10459_001001001 | 25.27105 | 55.2979 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1901 |  |  | DXB0607 |  | DXB0607 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-13 | Y23-F109546 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:34 | DXB_E3077S_10416_001003005 | 25.0581 | 55.1272 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1900 |  |  | DXB0603 |  | DXB0603 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-12 | Y23-F109509 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:31 | DXB_E3177F_11011_001002003 | 25.1022 | 55.1739 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1899 |  |  | DXB0602 |  | DXB0602 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-13 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 14:28 | DXB_E3177B_10704_001002003 | 25.1147 | 55.1908 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1898 |  |  | DXB0601 |  | DXB0601 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-17 | Y23-F109711 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:25 | DXB_E3177B_10716_001002003 | 25.1211 | 55.2006 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1897 |  |  | DXB0600 |  | DXB0600 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-17 | Y23-F109713 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:21 | DXB_E3178W_11681_001003001 | 25.12674 | 55.20301 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1896 |  |  | DXB0599 |  | DXB0599 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-17 | Y23-F109712 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:16 | DXB_E3178S_11207_001002003 | 25.1556 | 55.2286 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1895 |  |  | DXB0598 |  | DXB0598 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-13 | Y23-F109547 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 14:12 | DXB_E3178J_11971_001002003 | 25.1914 | 55.2603 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1894 |  |  | DXB0597 |  | DXB0597 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-BB-AGGR-SR12e-1 and 2 | Port 6/1/c2/1 | [10 empty] | 2023-10-04 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 13:52 | DXB_E3278A_11618_001002003 | 55.2694 | Ring3 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1893 |  |  | DXB0596 |  | DXB0596 |  | Rollout | New CSG | RFSed | Nokia | 2023-10-19 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-12 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 13:47 | DXB_E3278A_11617_001002004 | 25.2111 | 55.2756 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1892 |  |  | DXB0595 |  | DXB0595 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-12 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 13:44 | DXB_E3279U_15619_001002003 | 25.2172 | 55.2797 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1891 |  |  | DXB0594 |  | DXB0594 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-19 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-12 | Y23-F109490 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 13:41 | DXB_E3279V_10054_001002003 | 25.2247 | 55.285 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1890 |  |  | DXB0611 |  | DXB0611 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-12 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 13:36 | DXB_E3076Q_10021_001002003 | 24.97734 | 55.09099 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1889 |  |  | DXB0610 |  | DXB0610 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-18 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-12 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 13:33 | DXB_E3076G_10589_001002001 | 25.0014 | 55.0958 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1888 |  |  | DXB0609 |  | DXB0609 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-19 | DXB | 10G | DXB-6504-AGGR-SR12e-1 and 2 | Port 1/2/c3/1 | [10 empty] | 2023-10-13 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-10-23 13:28 | DXB_E3076B_10518_001002001 | 25.0264 | 55.1008 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1887 |  |  | DXB0608 |  | DXB0608 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-19 | DXB | 10G | DXB-6504-AGGR-SR12e-2 | Port 1/2/c3/1 | [10 empty] | 2023-10-13 | Y23-F109544 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 13:23 | DXB_E3077W_11006_001002002 | 25.0467 | 55.1175 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1886 |  |  | DXB0425 |  | DXB0425 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-11 | DXB | 10G | DXB-JBR-BAHAR-SCSG-IXR-R6-1 | 1/4/8 | [10 empty] | 2022-03-08 | Y21-F51571 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 13:17 | DXB_E3077N_10085_001001001 | 25.07688 | 55.13613 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1885 |  |  | AUH3600 |  | AUH3600 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-20 | AUH | 10G | AUH-2908-PREAGG-SR7-1 | Port 3/2/7 | [10 empty] | 2023-05-02 | Y23-F79454 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-10-23 13:13 | AUH_E1366M_10667_001001001 | 24.060483 | 53.4529 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1884 |  |  | AAN3613 |  | AAN3613 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-10-30 | AUH | 10G | AAN-2033-SCSG-SR7B-1 | esat-1/1/28 | AAN-3613-CSG-N540-LD-1 | FOC2720N8RQ | [9 empty] | Y23-F110613 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-10-21 15:45 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1883 |  |  | AAN3635 |  | AAN3635 |  | SRAN + 5G |  | Passive Completed | HOI-MEA | 2023-10-24 | AUH |  | AAN-2055-CSG-SAR-8-1 | Port 1/2/6 & Port 1/3/7 | AAN-2055-CSG-SAR-8-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:44 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1882 |  |  | AAN3305 |  | AAN3305 |  | SRAN + 5G |  | Passive Completed | HOI-MEA | 2023-10-24 | AUH |  | AAN-0132-CSG-IXR-E-1 | Port 1/1/11 & Port 1/1/12 | AAN-0132-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:42 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1881 |  |  | AAN3400 |  | AAN3400 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-20 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/56 | AAN-3400-CSG-N540-LD-1 | FOC2720N8Z3 | 5 | [8 empty] | Y23-F111896 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:41 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1880 |  |  | AAN3588 |  | AAN3588 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-10-31 | AUH | 10G | AAN-2495-PREAGG-SR7-1 | Port 2/2/3 | AAN-3588-CSG-N540-LD-1 | FOC2720N8W0 | [9 empty] | Y23-F110716 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:39 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1879 |  |  | AAN3446 |  | AAN3446 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-17 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/55 | AAN-3446-CSG-N540-LD-1 | FOC2720N8TV | 5 | [8 empty] | Y23-F111895 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:38 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1878 |  |  | AAN3292 |  | AAN3292 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-10-30 | AUH | 10G | AAN-2301-AGGR-SR7B-1 | esat-1/1/25 | AAN-3292-CSG-N540-LD-1 | FOC2720N8U9 | [9 empty] | Y23-F110756 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:36 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1877 |  |  | IAD5527 |  | IAD5527 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2024-01-19 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/39 | IAD-5527-CSG-IXR-E-1 | NK230930723 | 5 | [8 empty] | Y23-F114654 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-21 15:35 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1876 |  |  | DUB0501 |  | DUB0501 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-11-01 | DXB | 10G | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/10 | DUB-0501-CSG-IXR-E-1 | FOC2720N8KV | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-31 | Y23-F110824 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-19 15:11 | DXB_E3278M_10389_001011002 | 25.171704 | 55.306224 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1875 |  |  | FUJ5700E |  | FUJ5700E |  | BAU + 5G |  | Passive Completed | HOI-MEA | 2023-10-23 | FUJ | 1G | KLB-DC-SCSG-SR7B-1 | esat-1/1/2 | KLB-DC-SCSG-SR7B-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-19 14:48 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1874 |  |  | AUH6403 |  | AUH6403 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-16 | DXB | 10G | AUH-2904-PREAGG-SR7-1 | Port 2/2/3 | AUH-6403-CSG-IXR-E-1 | NK224931327 | 5 | [8 empty] | Y23-F111273 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-19 14:45 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1873 |  |  | AUH3347 |  | AUH3347 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-28 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | Port 2/1/38 | AUH-3347-CSG-N540-LD-1 | FOC2720N8K5 | 5 | [8 empty] | Y23-F112399 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-19 14:42 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1872 |  |  | DUB0548 |  | DUB0548 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-10-23 | DXB | 1G | DXB-2268-CSG-IXR-E-1 | 1/1/6 | DXB-2268-CSG-IXR-E-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-19 14:40 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1871 | WO- IIB-CSG-2023-Order # 1871 |  | AUH6452 |  | AUH6452 |  | SRAN + 5G |  | Transmission rack not available | HOI-MEA |  | AUH | 10G | AUH-2929-PREAGG-SRa8-1 | 1/1/9 |  |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-10-19 14:39 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1870 |  |  | AAN3585 |  | AAN3585 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-10-26 | AUH | 10G | AAN-5002-AGGR-SR12-1 | Port 4/1/2 | AAN-3585-CSG-N540-LD-1 | FOC2720N8YS | [9 empty] | Y23-F110322 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-19 14:37 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1869 |  |  | IRK5525 |  | IRK5525 | Nokia IXR-E | BAU |  | RFSed | HOI-MEA | 2023-11-03 | RAK | 10G | RAK-2000-SCSG-SR7B-1 | esat-1/1/32 | IRK-5525-CSG-IXR-E-1 | NK231134707 | [9 empty] | Y23-F110895 |  | Nokia |  |  | TRUE | 2023 | Syed Shahzaib | 2023-10-19 14:35 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1868 |  |  | DXB3585 |  | DXB3585 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-11-01 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-2 | esat-1/1/54 | DXB-3585-CSG-N540-LD-1 | FOC2720N8KT |  |  | 1 | 1 |  | Site Competed |  |  | 2023-10-30 | Y23-F110707 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-19 10:09 | DXB_E3277S_10607_001001001 | 25.0624128268548 | 55.3252655661853 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1867 |  |  | DXB3887 |  | DXB3887 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-12-12 | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-3/1/13 | DXB-3887-CSG-N540-LD-1 | FOC2720NBHR |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-27 | Y23-F110549 |  | Cisco |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-18 10:27 | DXB_E3279M_11347_001004003 | 25.25947 | 55.309858 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1866 |  |  | AUH3270 |  | AUH3270 | Cisco NCS540 | SRAN + 5G | New CSG | Cancelled/on Hold | XAD |  | AUH | 10G | AUH-2118-SCSG-SR7B-1 | esat-1/1/8 | AUH-3270-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 | site RFSED by nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 13:37 | AUH_E2469Q_10417_001001001 | 24.32469 | 54.51827 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1865 |  |  | AUH3499 |  | AUH3499 | Nokia IXR-E | SRAN + 5G | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/19 | AUH-3499-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 | Site is with Nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 13:33 | AUH_E2469O_10181_001001001 | 24.34768 | 54.58188 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1864 |  |  | AUH6418 |  | AUH6418 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | XAD | 2023-11-27 | AUH | 10G | AUH-2908-PREAGG-SR7-1 | Port 2/2/3 | AUH-6418-CSG-IXR-E-1 | NK224931276 |  |  | 1 | 1 | 1 | site power not ready | Rogelio Pangilinan;#1712 |  | 2023-11-25 | Y23-F112431 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 13:28 | AUH_E1366F_10001_001001001 | 24.06584 | 53.41871 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1863 |  |  | AUH3552 |  | AUH3552 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | Port 5/1/3 | AUH-3552-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 | Site is with Nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 13:22 |  | 24.527735 | 54.991423 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1862 |  |  | AUH2432 |  | AUH2432 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | Port 5/1/5 | AUH-2432-CSG-IXR-E-1 |  |  | 1 | 1 | 1 | 1 | Site is with Nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 13:05 |  | 24.530707 | 54.851006 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1861 |  |  | AUH2094 |  | AUH2094 | Nokia IXR-E | 5G+Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/29 | AUH-2094-CSG-IXR-E-1 |  |  | 1 | 1 | 1 | 1 | Site is with Nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 12:56 |  | 24.41884 | 54.43333 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1860 |  |  | DXN0392 |  | DXN0392 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-10-18 | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-2 | 1/6/c5 | DXB-ZAFRAN-SCSG-IXR-R6D-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 12:24 |  | 25.194682 | 55.271654 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1859 |  |  | AUH6212 |  | AUH6212 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 5/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-17 10:37 |  | 23.68209 | 53.70767 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1858 |  |  | AUH6212 |  | AUH6212 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 5/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-17 10:36 |  | 23.68209 | 53.70767 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1857 |  |  | AUH2325 |  | AUH2325 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-1093-PREAGG-SR7-1 | Port 3/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-17 10:30 | AUH_E2370M_12400_001001001 | 24.435107 | 54.43841 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1856 |  |  | SHJ2031 |  | SHJ2031 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | UAQ-DC-AGGR-SR7S-1 and 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-17 10:25 | SHJ_E3380X_10001_001001003 | 25.31427 | 55.42508 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1855 |  |  | SHJ2506 |  | SHJ2506 | Nokia SAR-8 | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | UAQ-DC-AGGR-SR7S-1 and 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-17 10:19 |  | 25.325547 | 55.39077 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1854 |  |  | SHJ2506 |  | SHJ2506 | Nokia SAR-8 | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | UAQ-DC-AGGR-SR7S-1 and 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-17 10:19 |  | 25.325547 | 55.39077 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1853 |  |  | DUB0417 |  | DUB0417 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-1828-PREAGG-SR7-1 | Port 2/1/7 | DXB-1828-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-18 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-17 10:06 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1852 |  |  | IAD5934 |  | IAD5934 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-10-18 | AUH |  | AUH-1437-SCSG-SR7B-1 | esat-1/1/50 | AUH-1437-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-17 08:52 |  | 24.539361 | 54.67459 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1851 |  |  | AUH3258 |  | AUH3258 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-10-25 | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | 1/3/c8 | AUH-3258-CSG-IXR-E-1 | NK224931395 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-21 | Y23-F110148 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-16 17:16 | AUH_E2767F_10001_001001001 | 24.19412 | 54.78919 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1850 |  |  | DXN0058 |  | DXN0058 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-11-02 | DXB | 10G | DXB-VH-SCSG-SR7B-1 | esat-1/1/58 | DXN-0058-CSG-N540-LD-1 | FOC2720N8PB |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-10-31 | Y23-F110859 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-16 16:12 | DXB_E3177Q_11950_001045004 |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1849 |  |  | DUB0003 |  | DUB0003 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-11-01 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-1 | esat-1/1/42 | DUB-0003-CSG-N540-LD-1 | FOC2718N594 |  |  | 1 | 1 | 1 | Site Competed |  |  | 2023-10-31 | Y23-F110809 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-16 16:09 | DXB_E3176D_10103_001001012 | 25.024669 | 55.243152 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1848 |  |  | FUJ1273 |  | FUJ1273 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-10-31 | FUJ | 10G | FUJ-5002-SCSG-SR7-1 | Port 2/2/2 | FUJ-1273-CSG-IXR-E-1 | NK224931294 |  | 0 | 1 | 1 | 1 | Site Completed |  |  | 2023-10-28 | Y23-F110646 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-16 15:48 | FJR_E4277S_10065_001001001 | 25.0783 | 56.3159 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1847 | WO- IIB-CSG-2023-Order # 1847 |  | AUH3981 |  | AUH3981 | Nokia IXR-E | Rollout | New CSG | Commissioning in progress | XAD |  | AUH | 10G | AUH2934 MS OTN | AUH-KHAZNA-AGG-SR12e-1 RK1/SH-1 /Front Port# A10 OTN RK-1/NE787 C/03/TX11/RX11 | AUH-3981-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-12 11:34 |  | 22.95939 | 53.81969 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1846 |  |  | AUH3943 |  | AUH3943 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-10-23 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | 2/1/35 | AUH-3943-CSG-N540-LD-1 | FOC2720N8U4 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-20 | Y23-F110091 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-12 11:30 | AUH_E2569G_10161_001001001 | 24.36643 | 54.61102 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1845 |  |  | AUH3813 |  | AUH3813 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-10-26 | AUH | 10G | AUH-1437-SCSG-SR7B-1 | esat-1/1/48 | AUH-3813-CSG-N540-LD-1 | FOC2720N8RC |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-25 | Y23-F110360 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-12 11:19 | AUH_E2571Q_10437_001001001 | 24.504757 | 54.613114 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1844 |  |  | AUH3361 |  | AUH3361 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-10-23 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | 2/1/34 | AUH-3361-CSG-N540-LD-1 | FOC2718N5X4 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-19 | Y23-F110042 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-12 11:15 | AUH_E2569K_10066_001001001 | 24.3549 | 54.59946 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1843 |  |  | SHJ2579 |  | SHJ2579 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | UAQ-DC-AGGR-SR7S-1 and 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-11 10:04 | SHJ_E3380U_10016_001002001 | 25.309600 | 55.378800 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1842 |  |  | AUH3285 |  | AUH3285 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 5/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-11 10:00 | AUH_E1162N_10001_001001001 | 23.697153 | 53.2907 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1841 |  |  | AUH3285 |  | AUH3285 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 5/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-11 09:59 | AUH_E1162N_10001_001001001 | 23.697153 | 53.2907 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1840 |  |  | FUJ3984 |  | FUJ3984 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-10-26 | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/1 | FUJ-3984-CSG-N540-LD-1 | FOC2720N8YU |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-23 | Y23-F110250 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-10 14:08 | SHJ_E4277X_10001_001001001 | 25.05426 | 56.32398 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1839 | WO- IIB-CSG-2023-Order # 1839 |  | SHJ0403 |  | SHJ0403 | Passive | Migration | Passive patching | Passive in Progress | XAD |  | SHJ |  | SHJ-2084-SCSG-SR7B-1 | esat-2/1/25 | SHJ-2084-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-10 14:05 |  | 25.33315 | 55.375596 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1838 |  |  | RAK3525 |  | RAK3525 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-11-27 | RAK | 10G | UAQ-DC-AGGR-SR7S-1 | esat-1/1/39 | RAK-3525-CSG-IXR-E-1 | NK224931267 |  |  | 2 | 2 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-11-17 | Y23-F111905 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-10 14:01 | RKT_E3985O_10002_001001001 | 25.81111 | 56.0408 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1837 |  |  | AUH6561 |  | AUH6561 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-10-13 | AUH | 10G | AUH-1372-PREAGG-SR7-1 | 5/1/5 | AUH-6561-CSG-N540-LD-1 | FOC2614N0GB |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-12 | Y23-F109527 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-09 11:30 | AUH_E2469H_11250_001001001 | 24.36615° | 54.53731° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1836 |  |  | DXN0589 |  | DXN0589 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-10-20 | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-1 | 1/3/c1 | DXB-ZAFRAN-SCSG-IXR-R6D-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:15 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1835 |  |  | DXB3497 |  | DXB3497 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-11-17 | DXB | 10G | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/3 | DXB-3497-CSG-N540-LD-1 | FOC2720N8NW | 5 | [8 empty] | Y23-F111898 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:14 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1834 |  |  | DUB0904 |  | DUB0904 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-10-12 | DXB |  | DXB-6501-SCSG-NCS57C3-1 | TF0/0/0/1 | DXB-6501-SCSG-NCS57C3-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:12 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1833 |  |  | SHJ1405 |  | SHJ1405 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-10-17 | SHJ | 10G | SHJ-5001-SCSG-SR7B-1 | esat-1/1/57 | SHJ-1405-CSG-IXR-E-1 | NK224931172 | [9 empty] | Y23-F109472 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:11 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1832 |  |  | ISH5239 |  | ISH5239 |  | BAU |  | Passive Completed | HOI-MEA | 2023-10-23 | SHJ |  | ISH-5234-CSG-IXR-E-1 | 1/1/6 | ISH-5234-CSG-IXR-E-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:09 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1831 |  |  | ISH5238 |  | ISH5238 |  | BAU |  | Passive Completed | HOI-MEA | 2023-10-20 | SHJ |  | ISH-5234-CSG-IXR-E-1 | 1/1/7 | ISH-5234-CSG-IXR-E-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:08 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1830 |  |  | ISH5237 |  | ISH5237 |  | BAU |  | Passive Completed | HOI-MEA | 2023-10-20 | SHJ |  | ISH-5234-CSG-IXR-E-1 | 1/1/4 | ISH-5234-CSG-IXR-E-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:06 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1829 |  |  | ISH5235 |  | ISH5235 |  | BAU |  | Passive Completed | HOI-MEA | 2023-10-19 | SHJ |  | ISH-5234-CSG-IXR-E-1 | Port 1/1/3 | ISH-5234-CSG-IXR-E-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-10-09 10:05 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1828 |  |  | ISH5234 |  | ISH5234 | Nokia IXR-E | BAU |  | RFSed | HOI-MEA | 2023-10-23 | SHJ |  | SHJ-2049-AGGR-SR7b-1 | esat-2/1/23 | ISH-5234-CSG-IXR-E-1 | NK223433863 | [9 empty] | Y23-F109996 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-10-09 10:03 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1827 |  |  | DXN0760 |  | DXN0760 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-JI-POP-SCSG-IXR-R6-1 | 1/4/5 | DXB-JI-POP-SCSG-IXR-R6-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-23 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 17:31 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1826 |  |  | DUB0406 |  | DUB0406 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-DGPOP2-SCSG-NCS57C3-1 | Tf0/0/0/5 | DXB-DGPOP2-SCSG-NCS57C3-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-14 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 17:28 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1825 |  |  | DUB0144 |  | DUB0144 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-6501-SCSG-NCS57C3-1 | Tf0/0/0/2 | DXB-6501-SCSG-NCS57C3-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-23 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 17:26 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1824 |  |  | DUB0781 |  | DUB0781 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-11-01 | DXB | 10G | DXB-VILLAPOP-AGGR-SR12e-1 | Port 7/1/11 | DUB-0781-CSG-N540-LD-1 | FOC2720N8W7 |  |  | 1 | 1 |  | Site Competed |  |  | 2023-10-30 | Y23-F110752 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-06 17:24 | DXB_E3377K_10705_001004069 | 25.0891245253209 | 55.3776714098425 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1823 |  |  | DUB0905 |  | DUB0905 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-6020-CSG-IXR-E-1 | 1/1/9 | DXB-6020-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-13 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 17:21 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1822 |  |  | DUB0685 |  | DUB0685 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-1022-CSG-SAR-X-1 | Port 1/2/6 | DXB-1022-CSG-SAR-X-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-17 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 17:16 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1821 |  |  | DUB0914 |  | DUB0914 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-VH-SCSG-SR7B-1 | esat-1/1/55 | DXB-VH-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-12 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 17:10 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1820 |  |  | DUB0842 |  | DUB0842 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-12-20 | DXB | 10G | DXB-JPPOP-AGGR-SR12e-1 | esat-1/1/44 | DUB-0842-CSG-N540-LD-1 | FOC2720N8VL |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-31 | Y23-F110798 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-06 17:07 | DXB_E3177R_11326_001001005 | 25.060441 | 55.216284 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1819 |  |  | DUB0530 |  | DUB0530 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-DGPOP2-SCSG-NCS57C3-1 | Tf0/0/0/4 | DXB-DGPOP2-SCSG-NCS57C3-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-13 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 15:58 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1818 |  |  | DUB0004 |  | DUB0004 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-11-01 | DXB | 10G | DXB-6504-AGGR-SR12e-1 | Port 2/1/13 | DUB-0004-CSG-N540-LD-1 | FOC2720N964 |  |  | 1 | 1 |  | Site Competed |  |  | 2023-10-30 | Y23-F110729 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-10-06 15:44 | DXB_E3176A_10182_001001003 | 25.024238 | 55.183092 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1817 |  |  | DXN0167 |  | DXN0167 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-11-10 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/41 | DXB-VH-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-11-10 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-06 15:41 |  | 25.0615 | 55.2024 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1816 |  |  | AUH6356 |  | AUH6356 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 and 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-06 11:16 | AUH_E1561O_10150_001001001 | 23.610065 | 53.716113 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1815 |  |  | DXB1535 |  | DXB1535 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-JPPOP-AGGR-SR12e-1 | Port 2/1/30 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-06 11:14 |  | 25.057100 | 55.213770 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1814 |  |  | AUH3605 |  | AUH3605 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 and 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-06 11:11 | AUH_E1561B_10001_001001001 | 23.654 | 53.65375 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1813 |  |  | AUH6426 |  | AUH6426 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 and 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-05 16:43 | AUH_E1661F_10209_001001001 | 23.65224 | 53.71442 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1812 |  |  | AUH6355 |  | AUH6355 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 and 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-05 16:39 | AUH_E1561O_10151_001001001 | 23.603499 | 53.703794 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1811 |  |  | IDX0016T |  | IDX0016T | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-11-07 | DXB |  | DXB-1866-SCSG-IXR-R6-2 | 1/5/9 | DXB-1866-SCSG-IXR-R6-2 | [6 empty] | IIB Passive and migration both done by XAD | [5 empty] | Nokia | Completed |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-05 13:26 |  | 25.263906 | 55.386199 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1810 |  |  | RAK3444 |  | RAK3444 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-10-16 | RAK | 10G | UAQ-2806-PREAGG-SR7-1 | 2/2/1 | RAK-3444-CSG-N540-LD-1 | FOC2633NBYP |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-10-11 | Y23-F109368 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-05 13:05 | RKT_E3883B_10880_001001001 | 25.665379 | 55.880853 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1809 |  |  | IDX0948C |  | IDX0948C | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-10-11 | DXB | 1G | DXB-DGPOP2-SCSG-NCS57C3-1 | Tf0/0/0/1 | IDX-0948C-CSG-N540-LD-1 | FOC2631N0BM | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-10 | Y23-F109335 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-05 11:45 | DXB_E2975G_10001_001002002 | 24.920548 | 55.008658 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1808 |  |  | IAD5984 |  | IAD5984 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-10-27 | AUH |  | AUH-ADAC-PREAGG-SR7-1 | Port 3/2/4 - SRAN and Port 4/1/1 5G | AUH-ADAC-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-04 17:01 |  | 24.430499 | 54.645621 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1807 |  |  | IAD5983 |  | IAD5983 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-10-24 | AUH |  | AUH-MCR2-CSG-IXR-E-1 | Port 1/1/13-SRAN ¦ 1/1/12-5G | AUH-MCR2-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-04 16:59 |  | 24.441531 | 54.647513 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1806 |  |  | IAD5045 |  | IAD5045 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-10-08 | AUH |  | AUH-MCR1-CSG-IXR-E-1 | Port 1/1/12 SRAN ¦ 1/1/13 5G | AUH-MCR1-CSG-IXR-E-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-04 16:54 |  | 24.45279 | 54.63869 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1805 |  |  | AUH0010 |  | AUH0010 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-10-07 | AUH |  | AUH-MCR1-CSG-IXR-E-1 | Port 1/1/11 5G and Port 1/1/15 SRAN | AUH-MCR1-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-04 16:53 |  | 24.44973237 | 54.6319336 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1804 |  |  | DUB0219 |  | DUB0219 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-10-06 | DXB |  | DXB-1346-SCSG-IXR-R6D-1 | 1/5/c18 | DXB-1346-SCSG-IXR-R6D-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-04 11:11 |  | 25.295831 | 55.362018 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1803 |  |  | AUH3587 |  | AUH3587 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 and 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-04 10:08 |  | 23.64161 | 53.69406 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1802 |  |  | AUH2837 |  | AUH2837 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 and 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-04 10:05 | AUH_E1662U_10522_001001001 | 23.65915 | 53.73182 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1801 |  |  | DUB0267 |  | DUB0267 | Nokia IXR-E | Rollout |  | RFSed | Nokia | 2023-10-03 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | Port Te0/0/0/51 | [11 empty] | Y23-F108462 |  |  | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 23:00 | DXB_E3177E_10669_001006020 | 25.11254 | 55.24885 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1800 |  |  | DXB0913 |  | DXB0913 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-03 | DXB | Others | DXB-3155-SCSG-IXR-R6D-2 | Port 1/3/c1/1 | [11 empty] | Y23-F108372 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 22:54 | DXB_E3278Q_10170_001001001 | 25.156 | 55.301 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1799 |  |  | AAN2026 |  | AAN2026 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | AUH | 10G | AAN-2065-PREAGG-SR7-1 | Port 4/1/4 | [11 empty] | Y23-F107878 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 22:31 | AAN_E3668Y_10001_001001001 | 24.2325 | 55.76822 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1798 |  |  | DXB2108 |  | DXB2108 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | DXB | Others | DXB-1852-SCSG-IXR-R6D-1 | Port 1/3/c2/1 | [11 empty] | Y23-F106786 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 22:23 | DXB_E3478Q_10003_001002001 | 25.159861 | 55.487305 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1797 |  |  | DXB0113 |  | DXB0113 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | DXB | 10G | DXB-3252-SCSG-SR7B-1 | Port esat-1/1/42 | [11 empty] | Y23-F106899 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 22:06 | DXB_E3279X_10028_002002001 | 25.23258 | 55.32314 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1796 |  |  | SHJ2218 |  | SHJ2218 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | SHJ | 10G | SHJ-2059-SCSG-NCS57C3-1 | Port Ten0/0/0/33 | [11 empty] | Y23-F105376 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 21:53 | SHJ_E3380C_10003_001001001 | 25.386158 | 55.412701 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1795 |  |  | SHJ0179 |  | SHJ0179 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | SHJ | 10G | SHJ-6501-PREAGG-SR7-1 | Port 4/1/2 | [11 empty] | Y23-F105618 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 21:47 | SHJ_E3379A_10206_001003012 | 25.297216 | 55.372331 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1794 |  |  | DXB2334 |  | DXB2334 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-1 | Port esat-1/1/11 | [11 empty] | Y23-F107636 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 21:30 | DXB_E3277Q_10536_001001001 | 25.0585 | 55.28502 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1793 |  |  | AUH2086 |  | AUH2086 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-27 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | Port esat-2/1/7 | [11 empty] | Y23-F105068 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 21:18 | AUH_E2270J_12006_001001001 | 24.45962 | 54.37259 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1792 |  |  | AAN2548 |  | AAN2548 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-28 | AUH | 10G | AAN-2033-SCSG-SR7B-1 | Port esat-1/1/27 | [11 empty] | Y23-F107959 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 21:02 | AAN_E3768B_10002_001001001 | 24.3147 | 55.79781 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1791 |  |  | DXB0916 |  | DXB0916 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | Others | DXB-3155-SCSG-IXR-R6D-1 | Port 1/3/c2/1 | [11 empty] | Y23-F108371 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 20:47 | DXB_E3278Q_10170_001001003 | 25.156 | 55.301 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1790 |  |  | DXB1404 |  | DXB1404 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | 10G | DXB-3129-SCSG-SR7B-1 | Port esat-1/1/34 | [11 empty] | Y23-F108494 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 20:32 | DXB_E3178Y_10742_001002001 | 25.1347 | 55.25556 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1789 |  |  | DXB1007 |  | DXB1007 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | Others | DXB-2302-SCSG-IXR-R6D-1 | Port 1/3/c2/1 | [11 empty] | Y23-F108493 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 20:21 | DXB_E3378U_10004_001001001 | 25.1435 | 55.3706 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1788 |  |  | DXB2840 |  | DXB2840 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | Others | DXB-2302-SCSG-IXR-R6D-1 | Port 1/3/c3/1 | [11 empty] | Y23-F108491 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 20:01 | DXB_E3278Y_10029_001001001 | 25.144048 | 55.348533 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1787 |  |  | DXB2153 |  | DXB2153 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | Others | DXB-2302-SCSG-IXR-R6D-1 | Port 1/3/c1/1 | [11 empty] | Y23-F108489 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 19:52 | DXB_E3278N_10984_001001001 | 25.16994 | 55.34192 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1786 |  |  | DXB3140 |  | DXB3140 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | Others | DXB-1635-SCSG-NCS57C3-1 | Port TF0/0/0/10 | [11 empty] | Y23-F108488 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 19:37 | DXB_E3076E_10814_001001001 | 25.02538 | 55.16305 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1785 |  |  | DXB3213 |  | DXB3213 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | DXB | Others | DXB-2770-SCSG-IXR-R6D-1 | Port 1/3/c5/1 | [11 empty] | Y23-F105495 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 19:27 | DXB_E3077T_13396_001001001 | 25.069473 | 55.157417 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1784 |  |  | DUB0351 |  | DUB0351 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-10-11 | DXB |  | DXB-DUBAIOTECH-AGGR-SR12e-1 | 3/1/2 | DXB-DUBAIOTECH-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-03 15:20 |  | 25.0647302 | 55.2440663 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1783 |  |  | IRK5522 |  | IRK5522 | Nokia IXR-E | BAU | New CSG | RFSed | XAD | 2023-10-20 | RAK | 10G | RAK-2000-SCSG-SR7B-1 | esat-2/1/3 | IRK-5522-CSG-IXR-E-1 | NK231134713 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-10 | Y23-F109328 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-03 14:42 | RKT_E3885Y_10029_001001001 | 25.7823 | 55.9414 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1782 |  |  | RAK0530 |  | RAK0530 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 and UAQ-DC-AGGR-SR7S-2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 11:07 | RKT_E3683E_10006_001001001 | 25.66188 | 55.74944 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1781 |  |  | SHJ2265 |  | SHJ2265 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2019-SCSG-IXR-R6D-1 | 1/6/c1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 11:04 |  | 25.371970 | 55.403316 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1780 |  |  | AUH3006 |  | AUH3006 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2178-PREAGG-SR7-1 | Port 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 10:58 | AUH_E2875V_10064_001001001 | 24.8678 | 54.8971 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1779 |  |  | DXB1340 |  | DXB1340 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-2123-PREAGG-SR7-1 | Port 5/2/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 10:54 | DXB_E3478A_10072_001001001 | 25.21383 | 55.47418 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1778 |  |  | DXB2651 |  | DXB2651 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-2123-PREAGG-SR7-1 | Port 5/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 10:50 | DXB_E3479U_10418_001001001 | 25.22761 | 55.46753 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1777 |  |  | DXB2495 |  | DXB2495 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-2123-PREAGG-SR7-1 | Port 5/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 10:45 | DXB_E3478B_10346_001001001 | 25.21679 | 55.49843 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1776 |  |  | DXB2599 |  | DXB2599 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-2123-PREAGG-SR7-1 | 5/2/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-03 10:41 | DXB_E3478B_10347_001001001 | 25.20929 | 55.49179 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1775 |  |  | KFN2603 |  | KFN2603 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-10-02 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1/FUJ-6001-AGG-ASR9912-2 | Hu0/0/0/3 | [11 empty] | Y23-F105501 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-10-03 04:22 | FJR_E4282E_10001_001001001 | 25.57821 | 56.34870 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1774 |  |  | AUH3542 |  | AUH3542 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2170-PREAGG-SR7-1 | 5/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-10-02 16:48 | AUH_E2669P_10303_001001001 | 24.326781 | 54.695994 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1773 |  |  | IDXNR5199 |  | IDXNR5199 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | XAD | 2023-11-08 | DXB | 10G | DXB-DGPOP2-SCSG-NCS57C3-2 | TF0/0/0/4 | IDX-5199-CSG-N540-LD-1 | FOC2720N8J8 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-18 | Y23-F109895 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-02 11:55 | DXB_E3077W_11010_001002083 | 25.04575 | 55.118980 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1772 |  |  | DXB1986 |  | DXB1986 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | XAD | 2023-10-17 | DXB | 10G | DXB-1090-SCSG-SR7B-1 | esat-1/1/47 | DXB-1986-CSG-N540-LD-1 | FOC2720N8T4 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-16 | Y23-F109764 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-10-02 11:49 | DXB_E3279H_12762_001001001 | 25.27487 | 55.30224 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1771 |  |  | DXN0120 |  | DXN0120 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-DGPOP1-CSG-IXR-E-1 | 1/1/16 | DXB-DGPOP1-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-12 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-10-02 11:33 |  | 25.033823 | 55.146663 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1770 |  |  | AUH0895 |  | AUH0895 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2937-PREAGG-SR7-1 | 1/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:45 | AUH_E1561E_10438_001001001 | 23.64055 | 53.70805 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1769 |  |  | SHJ0365 |  | SHJ0365 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ |  | SHJ-2226-PREAGG-SR7-1 | 4/1/14 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:42 | SHJ_E3379A_10213_001002001 | 25.300272 | 55.372418 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1768 |  |  | AUH2921 |  | AUH2921 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2923-PREAGG-SRa8-1 | 1/1/7 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:39 | AUH_E2365B_10001_001001001 | 24.01831 | 54.41476 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1767 |  |  | AUH2921 |  | AUH2921 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2923-PREAGG-SRa8-1 | 1/1/7 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:38 | AUH_E2365B_10001_001001001 | 24.01831 | 54.41476 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1766 |  |  | AUH2998 |  | AUH2998 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2923-PREAGG-SRa8-1 | 1/1/5 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:34 | AUH_E2367Q_10002_001001001 | 24.148864° | 54.429780° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1765 |  |  | AAN3147 |  | AAN3147 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2302-PREAGG-SR7-1 | 5/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:30 | AAN_E3666L_10001_001001001 | 24.0976 | 55.70579 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1764 |  |  | AAN2303 |  | AAN2303 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2302-PREAGG-SR7-1 | 5/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:24 | AAN_E3666M_10001_001001001 | 24.09386 | 55.71827 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1763 |  |  | AAN3146 |  | AAN3146 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2302-PREAGG-SR7-1 | 5/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:15 | AAN_E3666L_10003_001001001 | 24.093711 | 55.693819 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1762 |  |  | DXN0824 |  | DXN0824 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-3724-AGGR-SR12e-1 | 7/1/17 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:11 | DXB_E3379F_10526_001001001 | 25.280009 | 55.367455 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1761 |  |  | DXB1891 |  | DXB1891 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-3129-SCSG-SR7B-1 | esat-1/1/20 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:06 | DXB_E3178Y_10805_001001001 | 25.1451111 | 55.222332 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1760 |  |  | DXB1702 |  | DXB1702 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-3129-SCSG-SR7B-1 | esat-1/1/13 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:04 | DXB_E3177E_10059_001001001 | 25.1219 | 55.2451 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1759 |  |  | AAN2026 |  | AAN2026 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2065-PREAGG-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 16:01 | AAN_E3668Y_10001_001001001 | 24.2325 | 55.76822 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1758 |  |  | AUG6453 |  | AUG6453 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | 1/3/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:58 | AUH_E2367L_10001_001001001 | 24.157876 | 54.428808 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1757 |  |  | AUH2293 |  | AUH2293 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2099-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:54 | AUH_E2370Y_10218_001002001 | 24.399740 | 54.47333 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1756 |  |  | AUH2145 |  | AUH2145 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2039-PREAGG-SR7-1 | 3/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:51 | AUH_E2271X_10305_001001001 | 24.4817 | 54.36268 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1755 |  |  | AAN2023 |  | AAN2023 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2058-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:48 | AAN_E3667E_10436_001002001 | 24.2182 | 55.75958 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1754 |  |  | AAN2285 |  | AAN2285 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2058-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:45 | AAN_E3767A_10047_001001001 | 24.22267 | 55.768 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1753 |  |  | AAN3295 |  | AAN3295 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2005-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:43 | AAN_E3667L_10002_001001001 | 24.18475 | 55.69311 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1752 |  |  | AAN3264 |  | AAN3264 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2005-PREAGG-SR7-1 | 2/2/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:40 | AAN_E3667Q_10003_001001001 | 24.167087 | 55.694221 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1751 |  |  | SHJ3171 |  | SHJ3171 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2020-PREAGG-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:36 | SHJ_E3379C_12180_001002001 | 25.296605 | 55.408993 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1750 |  |  | SHJ3250 |  | SHJ3250 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2020-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:22 | SHJ_E3379C_12181_001002001 | 25.295700 | 55.4061 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1749 |  |  | SHJ2505 |  | SHJ2505 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2040-PREAGG-SR7-1 | 1/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:19 | SHJ_E3380I_10008_001001001 | 25.3776 | 55.4233 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1748 |  |  | AUH3780 |  | AUH3780 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | 1/3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:16 | AUH_E2369Y_10092_001001001 | 24.303412 | 54.486824 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1747 |  |  | DXB1895 |  | DXB1895 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1946-PREAGG-SR7-1 | 4/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:13 | DXB_E3379N_10523_001001001 | 25.2695274 | 55.4325829 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1746 |  |  | DXB2328 |  | DXB2328 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1828-PREAGG-SR7-1 | 5/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:09 | DXB_E3379F_10447_001001001 | 25.2757 | 55.3814 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1745 |  |  | FUJ3710 |  | FUJ3710 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2013-SCSG-SR7-1 | 4/1/5 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:05 | FJR_E4277J_10466_001001001 | 25.1124 | 56.3421 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1744 |  |  | FUJ3572 |  | FUJ3572 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2013-SCSG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-30 15:03 | FJR_E4277E_11387_001001001 | 25.11788 | 56.34854 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1743 |  |  | FUJ2405 |  | FUJ2405 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2022-SCSG-SR7-1 | 1/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:58 | FJR_E4278Y_10495_001001001 | 25.15239 | 56.33882 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1742 |  |  | AUH3200 |  | AUH3200 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 1/1/5 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:54 | AUH_E2271Y_11192_001017009 | 24.492867 | 54.376826 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1741 |  |  | AUH3714 |  | AUH3714 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2054-PREAGG-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:50 | AUH_E2370R_11138_001001001 | 24.412896 | 54.426831 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1740 |  |  | AUH3245 |  | AUH3245 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:45 | AUH_E2271X_10752_001001001 | 24.49091 | 54.363133 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1739 |  |  | AUH3068 |  | AUH3068 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2138-PREAGG-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:42 | AUH_E2670M_10241_001001001 | 24.445282 | 54.723959 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1738 |  |  | AUH3107 |  | AUH3107 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | 1/3/7 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:39 | AUH_E2469U_10089_001001001 | 24.31277 | 54.49697 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1737 |  |  | FUJ3058 |  | FUJ3058 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-5003-PREAGG-SRa8-1 | 2/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:31 | RKT_E4179K_10001_001001001 | 25.27132 | 56.1756 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1736 |  |  | FUJ3052 |  | FUJ3052 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2433-SCSG-SR7-1 | 5/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:26 | HAT_E4074Y_10378_001001001 | 24.7842 | 56.1421 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1735 |  |  | SHJ0402 |  | SHJ0402 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-1/1/27 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:22 | SHJ_E3380P_10019_001001001 | 25.33613 | 55.375352 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1734 |  |  | AUH3585 |  | AUH3585 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | 5/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:18 | AUH_E1562S_10083_001001001 | 23.680109 | 53.692158 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1733 |  |  | AUH2207 |  | AUH2207 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-1372-PREAGG-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:14 | AUH_E2469H_11239_001001001 | 24.37013 | 54.53471 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1732 |  |  | AUH2711 |  | AUH2711 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2178-PREAGG-SR7-1 | 2/2/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:11 | AUH_E2875V_10063_001001001 | 24.859523 | 54.900193 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1731 |  |  | DXB1850 |  | DXB1850 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1946-PREAGG-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:08 | DXB_E3379O_11109_001001001 | 25.254895 | 55.450145 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1730 |  |  | DXB2861 |  | DXB2861 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-2123-PREAGG-SR7-1 | 5/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:05 | DXB_E3379Y_10572_001001001 | 25.233052 | 55.460487 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1729 |  |  | DXB2781 |  | DXB2781 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1946-PREAGG-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 15:01 | DXB_E3379T_11239_001001001 | 25.24853 | 55.45689 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1728 |  |  | AUH2901 |  | AUH2901 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH |  | AUH-2713-PREAGG-SRa8-1 | 1/3/6 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:34 | AUH_E2367A_10001_001001001 | 24.20538 | 54.40673 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1727 |  |  | AUH3146 |  | AUH3146 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | 1/3/9 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:31 | AUH_E2267M_10001_001001001 | 24.157257° | 54.347230° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1726 |  |  | AUH3179 |  | AUH3179 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | 1/3/10 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:27 | AUH_E2067X_10001_001001001 | 24.122352° | 54.164147° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1725 |  |  | SHJ3011 |  | SHJ3011 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-3612-SCSG-SRa8-1 | 1/3/9 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:23 | SHJ_E3776O_10001_001001001 | 25.00366 | 55.84129 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1724 |  |  | SHJ3010 |  | SHJ3010 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-3612-SCSG-SRa8-1 | 1/3/8 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:18 | SHJ_E3776E_10001_001001001 | 25.03237 | 55.84062 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1723 |  |  | FUJ3701 |  | FUJ3701 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-2014-PREAGG-SR7-1 | 4/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:13 | SHJ_E4276I_10002_001001001 | 25.012715 | 56.324546 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1722 |  |  | FUJ3703 |  | FUJ3703 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/17 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:09 | SHJ_E4276N_10001_001001001 | 24.997351 | 56.325064 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1721 |  |  | FUJ5001 |  | FUJ5001 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-5002-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 14:06 | FJR_E4079H_10004_001001001 | 25.29243 | 56.10468 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1720 |  |  | AUH2652 |  | AUH2652 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 12:03 | AUH_E2771U_10002_001001001 | 24.49915 | 54.79859 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1719 |  |  | AUH2776 |  | AUH2776 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 2/2/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 12:00 | AUH_E2871Y_10001_001001001 | 24.50284 | 54.971849 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1718 |  |  | AUH3101 |  | AUH3101 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:56 | AUH_E2771J_10001_001001001 | 24.552996 | 54.859903 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1717 |  |  | AUH3109 |  | AUH3109 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:52 | AUH_E2871W_10002_001001001 | 24.497011 | 54.934841 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1716 |  |  | AUH3110 |  | AUH3110 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:47 | AUH_E2771S_10001_001001001 | 24.51304 | 54.85349 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1715 |  |  | AAN2833 |  | AAN2833 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2009-PREAGG-SR7-1 | 1/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:42 | AAN_E3567W_10002_001001001 | 24.1411 | 55.62543 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1714 |  |  | AAN3621 |  | AAN3621 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-2009-PREAGG-SR7-1 | 3/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:38 | AAN_E3667P_10005_001001001 |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1713 |  |  | SHJ3022 |  | SHJ3022 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2038-AGGR-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:33 | SHJ_E3380I_10009_001001001 | 25.371940 | 55.420530° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1712 |  |  | SHJ2240 |  | SHJ2240 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | SHJ-2038-AGGR-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:29 | SHJ_E3380I_10004_001001001 | 25.36867 | 55.42764 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1711 |  |  | AUH2463 |  | AUH2463 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2178-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:25 |  | 24.888440 | 54.866740 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1710 |  |  | AUH3590 |  | AUH3590 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2962-PREAGG-SR7-1 | 4/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:20 | AUH_E0664D_10285_001001001 | 23.897302 | 52.799408 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1709 |  |  | AUH2957 |  | AUH2957 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2962-PREAGG-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:15 | AUH_E0664T_10463_001001001 | 23.84346 | 52.81089 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1708 |  |  | DXB1319 |  | DXB1319 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1153-PRAGG-SR7-1 | 5/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:10 | DXB_E3379T_11236_001001001 | 25.24154 | 55.44449 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1707 |  |  | AUH6211 |  | AUH6211 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2962-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:06 | AUH_E0763F_10002_001001001 | 23.79385 | 52.83851 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1706 |  |  | DXB1512 |  | DXB1512 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1153-PRAGG-SR7-1 | 4/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 11:01 | DXB_E3379T_11237_001001001 | 25.2363892 | 55.4473915 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1705 |  |  | AUG4370 |  | AUG4370 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2170-PREAGG-SR7-1 | 5/1/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:55 | AUH_E2568B_10271_001001001 | 24.33027 | 54.69018 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1704 |  |  | AUH2468 |  | AUH2468 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2360-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:52 | AUH_E2469I_10504_001001001 | 24.365439 | 54.559376 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1703 |  |  | AUH2361 |  | AUH2361 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2360-PREAGG-SR7-1 | 4/1/5 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:47 | AUH_E2469C_10349_001001001 | 24.38069 | 54.54135 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1702 |  |  | AUH3429 |  | AUH3429 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2170-PREAGG-SR7-1 | 5/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:44 | AUH_E2569N_10963_001001001 | 24.356308 | 54.649647 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1701 |  |  | AUH2214 |  | AUH2214 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2360-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:41 | AUH_E2469N_10597_001001001 | 24.3558 | 54.56493 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1700 |  |  | AUH2377 |  | AUH2377 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-1372-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:37 | AUH_E2469M_10515_001001001 | 24.34316 | 54.53125 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1699 |  |  | AUH3279 |  | AUH3279 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-1372-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:33 | AUH_E2469M_10280_001010001 | 24.344032 | 54.535641 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1698 |  |  | AUH0445 |  | AUH0445 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-1372-PREAGG-SR7-1 | 2/2/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:30 | AUH_E2469M_10520_001001002 | 24.345985 | 54.539258 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1697 |  |  | AUG6085 |  | AUG6085 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2134-PREAGG-SR7-1 | 1/1/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:27 | AUH_E2569L_10090_001001001 | 24.351638° | 54.610986° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1696 |  |  | AUG4360 |  | AUG4360 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-2134-PREAGG-SR7-1 | 1/1/2 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:23 | AUH_E2569R_10757_001001001 | 24.3271 | 54.6303 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1695 |  |  | SHJ2473 |  | SHJ2473 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 10:18 | SHJ_E3479F_10001_001001001 | 25.2783 | 55.4754 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1694 |  |  | SHJ2274 |  | SHJ2274 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | SHJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 09:43 | SHJ_E3479G_10003_001001001 | 25.276605 | 55.483148 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1693 |  |  | KFN2842 |  | KFN2842 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 09:38 | FJR_E4381F_10001_001001001 | 25.472286 | 56.361268 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1692 |  |  | FUJ3208 |  | FUJ3208 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 09:34 | FJR_E4279J_10006_001001001 | 25.2881 | 56.3506 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1691 |  |  | KFN1149 |  | KFN1149 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-29 09:28 | FJR_E4382U_10001_001003001 | 25.50201 | 56.36061 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1690 |  |  | KFN3161 |  | KFN3161 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 18:00 | FJR_E4281O_10001_001001001 | 25.44556 | 56.35086 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1689 |  |  | FUJ3088 |  | FUJ3088 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:56 | FJR_E4279O_10003_001001001 | 25.263643 | 56.350475 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1688 |  |  | KFN2957 |  | KFN2957 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:52 | SHJ_E4280T_10005_001001001 | 25.347533 | 56.348609 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1687 |  |  | KFN2110 |  | KFN2110 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:49 | FJR_E4379A_10049_001001001 | 25.29726 | 56.358 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1686 |  |  | FUJ3275 |  | FUJ3275 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:38 | FJR_E4379F_11237_001001001 | 25.2861 | 56.3543 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1685 |  |  | FUJ3059 |  | FUJ3059 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:33 | FJR_E4379K_11354_001001001 | 25.2618 | 56.3666 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1684 |  |  | KFN3776 |  | KFN3776 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:22 | SHJ_E4280O_10002_001001001 | 25.358400° | 56.348840° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1683 |  |  | KFN2838 |  | KFN2838 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:17 | SHJ_E4380A_10001_001001001 | 25.403336° | 56.358610° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1682 |  |  | FUJ3637 |  | FUJ3637 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:11 | FJR_E4277D_10458_001001001 | 25.12772 | 56.33079 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1681 |  |  | DXB0358 |  | DXB0358 | Nokia IXR-E | Rollout |  | RFSed | HOI-MEA | 2023-10-16 | DXB |  | DXB-1583-SCSG-IXR-R6D-1 | 1/5/c2 | DXB-0358-CSG-IXR-E-1 | NK22393A796 | [9 empty] | Y23-F109474 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-28 17:08 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1680 |  |  | DUB0079 |  | DUB0079 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-10-04 | DXB |  | DXB-VILLAPOP-AGGR-SR12e-2 | 3/2/10 | DXB-VILLAPOP-AGGR-SR12e-2 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-28 17:07 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1679 |  |  | IDX5372 |  | IDX5372 |  | Migration |  | Passive Completed | HOI-MEA | 2023-09-28 | DXB |  | DXB-2583-SCSG-SR7B-1 | esat-2/1/16 & esat-2/1/17 | DXB-2583-SCSG-SR7B-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-28 17:05 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1678 |  |  | UAQ2810 |  | UAQ2810 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:05 | SHJ_E3879I_10001_001001001 | 25.289370° | 55.921950° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1677 |  |  | KFN2612 |  | KFN2612 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 17:01 | SHJ_E4280Y_10001_001001001 | 25.3307 | 56.3429 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1676 |  |  | KFN1182 |  | KFN1182 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 16:57 | FJR_E4381A_10005_001001001 | 25.49491 | 56.36053 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1675 |  |  | KFN2629 |  | KFN2629 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 16:53 | FJR_E4381K_10001_001001001 | 25.44658 | 56.35832 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1674 |  |  | KFN2604 |  | KFN2604 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 16:49 | FJR_E4281T_10002_001001001 | 25.4351 | 56.344 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1673 |  |  | KFN2604 |  | KFN2604 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 16:48 | FJR_E4281T_10002_001001001 | 25.4351 | 56.344 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1672 |  |  | DUB0546 |  | DUB0546 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-10-10 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/6/c9 | DUB-0546-CSG-N540-LD-1 | FOC2624KMJ2 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-06 | Y23-F109106 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-09-28 16:03 | DXB_E3478Q_10009_001001001 | 25.150677 | 55.498990 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1671 |  |  | FUJ3267 |  | FUJ3267 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:57 | FJR_E4278Y_00007_001001001 | 25.135265 | 56.35357 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1670 |  |  | DUB0197 |  | DUB0197 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/2 | DXB-BB-SCSG-NCS57C3-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-07 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-09-28 15:55 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1669 |  |  | KFN2792 |  | KFN2792 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:54 | FJR_E4282T_10002_001001001 | 25.5154208 | 56.3374675 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1668 |  |  | KFN3633 |  | KFN3633 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:49 | FJR_E4282O_10003_001001001 | 25.540989 | 56.33517 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1667 |  |  | KFN3632 |  | KFN3632 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:44 | FJR_E4282O_10002_001001001 | 25.53829 | 56.34224 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1666 |  |  | FUJ2492 |  | FUJ2492 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 & 2 | Hu0/0/0/3 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:40 | FJR_E4279O_10002_001001001 | 25.2757 | 56.3521 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1665 |  |  | RAK2940 |  | RAK2940 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:34 | RKT_E3986X_10004_001001001 | 25.87192 | 56.024881 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1664 |  |  | RAK3522 |  | RAK3522 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:30 | RKT_E3784M_10001_001001001 | 25.712540° | 55.795440° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1663 |  |  | RAK3490 |  | RAK3490 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:26 | RKT_E3784S_10004_001001001 | 25.701207 | 55.817133 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1662 |  |  | RAK2735 |  | RAK2735 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:20 | RKT_E3784Q_10003_001001001 | 25.70434 | 55.78835 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1661 |  |  | RAK2785 |  | RAK2785 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:13 | RKT_E3784W_10001_001001001 | 25.6788 | 55.7954 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1660 |  |  | RAK3356 |  | RAK3356 | Nokia IXR-E | Upgrade from SARX to IXR-E | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:05 | RKT_E3784N_10001_001001001 | 25.7097 | 55.8277 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1659 |  |  | RAK3483 |  | RAK3483 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 15:02 | RKT_E3784S_10002_001001001 | 25.694900° | 55.828700° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1658 |  |  | RAK3123 |  | RAK3123 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:58 | RKT_E3784T_10002_001001001 | 25.703621 | 55.84994 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1657 |  |  | RAK2979 |  | RAK2979 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:51 | RKT_E3784T_10001_001001001 | 25.705171 | 55.834156 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1656 |  |  | RAK2789 |  | RAK2789 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:42 | RKT_E3784Q_10001_001001001 | 25.70109 | 55.79243 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1655 |  |  | UAQ2816 |  | UAQ2816 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:38 | UAQ_E3683U_10001_001001001 | 25.5845 | 55.6594 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1654 |  |  | RAK3977 |  | RAK3977 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:29 | RKT_E3986T_10007_001001001 | 25.88927 | 56.04399 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1653 |  |  | RAK2497 |  | RAK2497 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:26 | RKT_E3986T_10001_001001001 | 25.88447 | 56.04555 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1652 |  |  | RAK2382 |  | RAK2382 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:19 | RKT_E3984B_10001_001001001 | 25.76155 | 55.9756 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1651 |  |  | RAK2874 |  | RAK2874 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:16 | RKT_E3985C_10002_001001001 | 25.844320° | 55.996690° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1650 |  |  | RAK2383 |  | RAK2383 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:12 | RKT_E3784N_10002_001001001 | 25.71306 | 55.81626 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1649 |  |  | RAK2647 |  | RAK2647 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:10 | RKT_E3986X_10001_001001001 | 25.867043 | 56.012112 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1648 |  |  | UAQ2933 |  | UAQ2933 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 14:03 | UAQ_E3582Q_00001_001001001 | 25.5224 | 55.5947 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1647 |  |  | RAK2844 |  | RAK2844 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 11:20 | RKT_E3985I_10003_001001001 | 25.81938 | 56.03098 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1646 |  |  | DXN0393 |  | DXN0393 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-10-11 | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-1 | 1/5/c12 | DXB-ZAFRAN-SCSG-IXR-R6D-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-28 11:11 |  | 25.194682 | 55.271654 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1645 |  |  | RAK3971 |  | RAK3971 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 11:04 | RKT_E3986S_10003_001001001 | 25.87365477 | 56.015122 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1644 |  |  | RAK2775 |  | RAK2775 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 10:55 | RKT_E3986T_10002_001001001 | 25.8778 | 56.0337 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1643 |  |  | RAK3187 |  | RAK3187 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 10:51 | RKT_E3985L_10007_001001001 | 25.815 | 55.974 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1642 |  |  | RAK2982 |  | RAK2982 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 10:45 | RKT_E3985Q_10006_001001001 | 25.7956 | 55.9736 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1641 |  |  | RAK2865 |  | RAK2865 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | RAK | 10G | UAQ-DC-AGGR-SR7S-1 & 2 | 1/x1/2/c2/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 10:40 | RKT_E3985G_10002_001001001 | 25.8192 | 55.9805 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1640 |  |  | AUH6592 |  | AUH6592 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 & 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-28 10:35 | AUH_E1267Y_10001_001001001 | 24.10657 | 53.39893 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1639 |  |  | DUB0717 |  | DUB0717 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-3160-PREAGG-SR7-1 | Port 3/2/18 | DXB-3160-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-12 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-09-28 10:08 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1638 |  |  | DXB1426 |  | DXB1426 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-22 | DXB | 10G | DXB-3230-SCSG-IXR-R6-1 | Port 1/5/5 | [10 empty] | 2023-09-22 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-09-27 14:45 | DXB_E3178Q_11536_001001001 | 25.143656 | 55.203233 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1637 |  |  | AAN2026 |  | AAN2026 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | AUH | 10G | AAN-2065-PREAGG-SR7-1 | Port 4/1/4 | [10 empty] | 2023-09-19 | Y23-F107878 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 14:35 | AAN_E3668Y_10001_001001001 | 24.2325 | 55.76822 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1636 |  |  | DXB2334 |  | DXB2334 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-1 | Port esat-1/1/11 | [10 empty] | 2023-09-15 | Y23-F107636 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 14:30 | DXB_E3277Q_10536_001001001 | 25.0585 | 55.28502 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1635 |  |  | AUH6566 |  | AUH6566 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-21 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | Port esat-1/1/52 | [10 empty] | 2023-09-18 | Y23-F107748 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 14:25 | AUH_E2469B_10639_001001001 | 24.37731 | 54.51149 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1634 |  |  | AUH2690 |  | AUH2690 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-21 | AUH | 10G | AUH-2036-SCSG-IXR-R6D-1 | Port 1/5/c15/1 | [10 empty] | 2023-09-18 | Y23-F107749 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 14:20 | AUH_E2570E_10085_001001001 | 24.46999 | 54.66408 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1633 |  |  | DXB2559 |  | DXB2559 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-22 | DXB | Others | DXB-DGPOP2-SCSG-NCS57C3-1 | Port TF0/0/0/3 | [10 empty] | 2023-09-08 | Y23-F107080 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 14:08 | DXB_E3077X_10028_001011002 | 25.04736 | 55.13075 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1632 |  |  | DXB0113 |  | DXB0113 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | DXB | 10G | DXB-3252-SCSG-SR7B-1 | Port esat-1/1/42 | [10 empty] | 2023-09-07 | Y23-F106899 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 14:00 | DXB_E3279X_10028_002002001 | 25.23258 | 55.32314 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1631 |  |  | SHJ0179 |  | SHJ0179 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | SHJ | 10G | SHJ-6501-PREAGG-SR7-1 | Port 4/1/2 | [10 empty] | 2023-08-24 | Y23-F105618 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 13:55 | SHJ_E3379A_10206_001003012 | 25.297216 | 55.372331 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1630 |  |  | DXB2108 |  | DXB2108 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | DXB | Others | DXB-1852-SCSG-IXR-R6D-1 | Port 1/3/c2/1 | [10 empty] | 2023-09-05 | Y23-F106786 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 13:48 | DXB_E3478Q_10003_001002001 | 25.159861 | 55.487305 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1629 |  |  | DXB1179 |  | DXB1179 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-12 | DXB | 10G | DXB-2770-SCSG-IXR-R6D-2 | Port 1/3/c3/1 | [10 empty] | 2023-08-10 | Y23-F104551 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-27 13:42 | DXB_E3177K_11559_001001001 | 25.0734 | 55.16675 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1628 |  |  | SHJ2218 |  | SHJ2218 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-25 | SHJ | 10G | SHJ-2059-SCSG-NCS57C3-1 | Ten0/0/0/33 | [10 empty] | 2023-08-21 | Y23-F105376 |  |  |  |  | FALSE | 2023 | Omer Ikram | 2023-09-27 13:32 | SHJ_E3380C_10003_001001001 | 25.386158 | 55.412701 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1627 |  |  | AUH3666 |  | AUH3666 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-DC-AGGR-SR12e-1 & 2 | 6/1/c3/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 12:09 | AUH_E1366M_10668_001001001 | 24.05135 | 53.467595 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1626 |  |  | AUH3619 |  | AUH3619 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:59 | AUH_W0467F_10001_001001001 | 24.11018 | 51.66006 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1625 |  |  | AUH2917 |  | AUH2917 | Nokia IXR-E | Upgrade from SARX to IXR-E | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:54 | AUH_W0065F_10001_001001001 | 23.9437 | 52.0546 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1624 |  |  | AUH2960 |  | AUH2960 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:50 | AUH_E0767R_10001_001001001 | 24.109583 | 52.859889 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1623 |  |  | AUH3144 |  | AUH3144 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:46 | AUH_E0567V_10667_001001001 | 24.0810806 | 52.66305 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1622 |  |  | AUH6374 |  | AUH6374 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:42 | AUH_E0566B_10314_001001001 | 24.071521 | 52.655602 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1621 |  |  | AUH3599 |  | AUH3599 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:38 | AUH_E0567W_10087_001001001 | 24.086331 | 52.6757194 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1620 |  |  | AUH3148 |  | AUH3148 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:23 | AUH_E0665X_10182_001001001 | 23.90849 | 52.79646 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1619 |  |  | AUH2897 |  | AUH2897 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:17 | AUH_E0666L_10004_001001001 | 24.042159 | 52.75349 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1618 |  |  | AUH2886 |  | AUH2886 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 11:07 | AUH_E0566B_10306_001001001 | 24.07527 | 52.658 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1617 |  |  | AUH2956 |  | AUH2956 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 10:55 | AUH_E0665H_10001_001001001 | 23.96762 | 52.78493 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1616 |  |  | AUH6460 |  | AUH6460 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-27 10:46 | AUH_E0566B_10321_001001001 | 24.070833 | 52.645986 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1615 |  |  | AUH6478 |  | AUH6478 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:42 |  | 24.06482 | 52.65357 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1614 |  |  | AUH3618 |  | AUH3618 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:39 |  | 24.071922 | 52.676090 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1613 |  |  | AUH2883 |  | AUH2883 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:32 | AUH_E0567V_10664_001001001 | 24.089331 | 52.644914 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1612 |  |  | AUH6401 |  | AUH6401 | Nokia IXR-E | Upgrade from SARX to IXR-E | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:26 | AUH_E0567V_10668_001001001 | 24.085924 | 52.649115 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1611 |  |  | AUG6455 |  | AUG6455 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ready For 5G |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:22 | AUH_E0664Y_10374_001001001 | 23.8286 | 52.81128 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1610 |  |  | AUH2913 |  | AUH2913 | Nokia IXR-E | Upgrade from SARX to IXR-E | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:16 | AUH_E0567A_10287_001001001 | 24.16539 | 52.63596 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1609 |  |  | AUH6464 |  | AUH6464 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 14:00 | AUH_E0566B_10311_001001001 | 24.071864 | 52.648421 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1608 |  |  | AUH2863 |  | AUH2863 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:55 |  | 24.08478 | 52.65656 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1607 |  |  | AUH6455 |  | AUH6455 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:50 |  | 24.019102 | 52.41057 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1606 |  |  | AUG6060 |  | AUG6060 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:46 | AUH_E0567V_10665_001001001 | 24.08135 | 52.65049 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1605 |  |  | AUH6400 |  | AUH6400 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:41 |  | 24.08174 | 52.66809 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1604 |  |  | AUH6400 |  | AUH6400 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:40 |  | 24.08174 | 52.66809 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1603 |  |  | AUH2899 |  | AUH2899 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:37 | AUH_E0666L_10001_001001001 | 24.03153 | 52.75871 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1602 |  |  | AUH2898 |  | AUH2898 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-26 13:33 | AUH_E0666M_10001_001001001 | 24.03781 | 52.76466 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1601 |  |  | KFN3946 |  | KFN3946 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | FUJ | 10G | FUJ-5003-PREAGG-SRa8-1 | 2/1/5 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:53 | RKT_E4179H_10003_001001001 | 25.28231 | 56.20012 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1600 |  |  | SHJ2290 |  | SHJ2290 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | SHJ | 10G | SHJ-3612-SCSG-SRa8-1 | 1/3/10 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:49 | SHJ_E3776H_10001_001001001 | 25.004947 | 55.805188 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1599 |  |  | AUH3791 |  | AUH3791 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:45 | AUH_E2671E_10001_001001001 | 24.5711 | 54.762578 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1598 |  |  | AUH3792 |  | AUH3792 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 4/1/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:41 | AUH_E2770E_10001_001001001 | 24.487732 | 54.87805 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1597 |  |  | AUH3600 |  | AUH3600 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2908-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:35 | AUH_E1366M_10667_001001001 | 24.060483 | 53.4529 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1596 |  |  | AAN3131 |  | AAN3131 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 10/2/5 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:29 | AAN_E3568V_10001_001001001 | 24.22734 | 55.59593 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1595 |  |  | AUH6077 |  | AUH6077 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:24 | AUH_E2771E_10002_001001001 | 24.56455 | 54.86075 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1594 |  |  | AUH3206 |  | AUH3206 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-MariaIsland-PREAGG-SR7-1 | 3/1/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:20 | AUH_E2271Y_10206_001003001 | 24.48732 | 54.365722 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1593 |  |  | AUH0415 |  | AUH0415 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-1/1/59 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:13 | AUH_E2270D_12023_001001001 | 24.47677 | 54.3537 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1592 |  |  | AUH3366 |  | AUH3366 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | 4/1/5 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:07 | AUH_E1561A_10538_001001001 | 23.6487 | 53.62462 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1591 |  |  | AUH3588 |  | AUH3588 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 03:02 | AUH_E1562Y_10617_001001001 | 23.661564 | 53.698257 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1590 |  |  | AUH3465 |  | AUH3465 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | 4/1/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 02:56 | AUH_E1562Y_10618_001001001 | 23.67048 | 53.70101 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1589 |  |  | AUH6111 |  | AUH6111 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2836-PREAGG-SR7-1 | 4/1/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 02:44 | AUH_E1363Y_10004_001001001 | 23.74545 | 53.5084 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1588 |  |  | AUH3061 |  | AUH3061 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2784-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 02:39 | AUH_E2670G_10014_001001001 | 24.456311 | 54.717269 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1587 |  |  | AUH3643 |  | AUH3643 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2784-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 02:35 | AUH_E2670X_10691_001001001 | 24.41122 | 54.751829 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1586 |  |  | AUH2779 |  | AUH2779 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2674-PREAGG-SR7-1 | 2/2/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 02:29 | AUH_E2768D_10001_001001001 | 24.29198 | 54.85646 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1585 |  |  | AUH2777 |  | AUH2777 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2674-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-26 02:23 | AUH_E2869J_10001_001001001 | 24.37361 | 54.97304 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1584 |  |  | AUH2177 |  | AUH2177 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2674-PREAGG-SR7-1 | 2/2/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:53 | AUH_E2867A_10038_001001001 | 24.21113 | 54.901040 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1583 |  |  | AUH2180 |  | AUH2180 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-1359-PREAGG-SR7-1 | 3/1/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:49 | AUH_E2469C_10348_001003001 | 24.377011 | 54.530093 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1582 |  |  | AUH2321 |  | AUH2321 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-1316-PREAGG-SR7-1 | 4/1/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:45 | AUH_E2270D_12839_001001001 | 24.470473 | 54.359305 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1581 |  |  | AUH0720 |  | AUH0720 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-1316-PREAGG-SR7-1 | 4/1/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:38 | AUH_E2270D_11598_001012007 | 24.47941 | 54.35427 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1580 |  |  | AUH3838 |  | AUH3838 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-1048-PREAGG-SR7-1 | 5/1/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:34 | AUH_E2270G_10197_001001001 | 24.0766 | 55.66194 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1579 |  |  | AAN3148 |  | AAN3148 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 100G | AAN-2005-SCSG-IXR-R6D-1 | 1/3/c6/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:29 | AAN_E3567W_10003_001001001 | 24.145470 | 55.631100 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1578 |  |  | AAN2562 |  | AAN2562 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 10/1/6 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:12 | AAN_E3471G_10002_001001001 | 24.55366 | 55.5074 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1577 |  |  | AAN3165 |  | AAN3165 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/1/10 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:07 | AAN_E3471Q_10001_001001001 | 24.51634 | 55.50632 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1576 |  |  | AUH6087 |  | AUH6087 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | 4/1/5 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 21:01 | AUH_E2771X_10001_001001001 | 24.50643 | 54.84874 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1575 |  |  | AAN2893 |  | AAN2893 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/1/8 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 20:49 | AAN_E3468X_10004_001001001 | 24.22754 | 55.54336 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1574 |  |  | AAN3216 |  | AAN3216 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/1/7 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 20:44 | AAN_E3267R_10001_001001001 | 24.159029 | 55.334050 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1573 |  |  | AAN3281 |  | AAN3281 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/2/8 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 20:40 | AAN_E3571K_10001_001001001 | 24.535967 | 55.587202 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1572 |  |  | AAN2503 |  | AAN2503 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/2/7 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 20:35 | AAN_E3467E_10001_001001001 | 24.21787 | 55.55795 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1571 |  |  | AAN2496 |  | AAN2496 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/2/6 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 20:29 | AAN_E3571N_10001_001001001 | 24.5387 | 55.63624 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1570 |  |  | AAN2492 |  | AAN2492 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/2/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 20:24 | AAN_E3369L_10001_001001001 | 24.35088 | 55.40031 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1569 |  |  | AUH6416 |  | AUH6416 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:58 | AUH_E0666M_10002_001001001 | 24.030492 | 52.778725 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1568 |  |  | AUH2867 |  | AUH2867 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:50 |  | 24.07598 | 52.7519 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1567 |  |  | AUH2866 |  | AUH2866 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:45 | AUH_E0666B_11085_001001001 | 24.0835 | 52.75871 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1566 |  |  | AUH2865 |  | AUH2865 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:29 | AUH_E0566B_10046_001001001 | 24.07965 | 52.65715 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1565 |  |  | AUH6392 |  | AUH6392 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:25 | AUH_E0566B_10310_001001001 | 24.0657 | 52.64886 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1564 |  |  | AUH3231 |  | AUH3231 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:21 | AUH_E0566B_10307_001002001 | 24.0721111 | 52.653 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1563 |  |  | AUH3751 |  | AUH3751 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:16 | AUH_E0566C_10374_001001001 | 24.07146 | 52.66751 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1562 |  |  | AUH3878 |  | AUH3878 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:08 | AUH_E0567U_10220_001001001 | 24.092236 | 52.642516 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1561 |  |  | AUH2885 |  | AUH2885 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1-Port 6/1/c5/1 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 14:03 | AUH_E0566B_10312_001001001 | 24.0752 | 52.65127 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1560 |  |  | AUH6456 |  | AUH6456 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1:517-Port 6/1/c5/1:518 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 13:57 | AUH_E0466K_10001_001001001 | 24.03932 | 52.543661 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1559 |  |  | AUH6456 |  | AUH6456 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1:517-Port 6/1/c5/1:518 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 13:56 | AUH_E0466K_10001_001001001 | 24.03932 | 52.543661 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1558 |  |  | AUH6456 |  | AUH6456 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1:517-Port 6/1/c5/1:518 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 13:55 | AUH_E0466K_10001_001001001 | 24.03932 | 52.543661 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1557 |  |  | AUH6456 |  | AUH6456 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1:517-Port 6/1/c5/1:518 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 13:54 | AUH_E0466K_10001_001001001 | 24.03932 | 52.543661 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1556 |  |  | AUH3593 |  | AUH3593 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | Port 6/1/c5/1:515-Port 6/1/c5/1:516 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-25 13:49 | AUH_E0665X_10184_001001001 | 23.917131 | 52.7953611 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1555 |  |  | AAN3403 |  | AAN3403 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/2/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 05:33 | AAN_E3267F_10001_001001001 | 24.204950 | 55.280940 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1554 |  |  | AAN3427 |  | AAN3427 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/1/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 05:27 | AAN_E3468T_10005_001001001 | 24.244 | 55.559 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1553 |  |  | AAN2589 |  | AAN2589 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 4/1/5 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 05:22 | AAN_E3467C_10002_001001001 | 24.22169 | 55.52886 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1552 |  |  | AAN2348 |  | AAN2348 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 1/2/10 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 05:18 | AAN_E3267I_10002_001001001 | 24.20063 | 55.336601 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1551 |  |  | AAN2890 |  | AAN2890 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 4/1/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 05:13 | AAN_E3067L_10381_001001001 | 24.168995 | 55.105214 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1550 |  |  | AAN3138 |  | AAN3138 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/1/9 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 05:07 | AAN_E3270H_10145_001001001 | 24.46183 | 55.323430 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1549 |  |  | AAN3353 |  | AAN3353 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/1/8 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 04:56 | AAN_E3468X_10005_001001001 | 24.22984 | 55.5509 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1548 |  |  | AAN3425 |  | AAN3425 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/1/7 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 04:48 | AAN_E3471S_10001_001001001 | 24.518000 | 55.535300 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1547 |  |  | AAN2604 |  | AAN2604 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/1/8 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 04:42 | AAN_E3468Y_10002_001001001 | 24.230749 | 55.56786 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1546 |  |  | AAC4348 |  | AAC4348 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/2/6 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 04:35 | AAN_E3267M_10002_001001001 | 25.17362 | 55.41778 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1545 |  |  | AAN2027 |  | AAN2027 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/2/10 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 04:25 | AAN_E3467D_10001_001001001 | 24.223 | 55.53597 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1544 |  |  | AAN3118 |  | AAN3118 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/2/9 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 04:04 | AAN_E3270A_10001_001001001 | 24.48745 | 55.282910 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1543 |  |  | AAN2539 |  | AAN2539 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/2/8 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 03:54 | AAN_E3467D_10002_001001001 | 24.2196 | 55.54849 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1542 |  |  | AAN3217 |  | AAN3217 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/2/4 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 03:42 | AAN_E3467I_10003_001001001 | 24.20077 | 55.543801 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1541 |  |  | AAN2052 |  | AAN2052 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/2/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 03:33 | AAN_E3468Y_10001_001001001 | 24.22713 | 55.557389 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1540 |  |  | AAN2415 |  | AAN2415 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/1/6 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 03:21 | AAN_E3467D_10004_001001001 | 25.77224, | 55.96797 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1539 |  |  | AAN2567 |  | AAN2567 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/1/10 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 03:06 | AAN_E3467I_10002_001001001 | 24.197780 | 55.533000 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1538 |  |  | AAN3136 |  | AAN3136 | Nokia IXR-E | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | 1/2/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 02:55 | AAN_E3171Y_10002_001001001 | 24.49526 | 55.25701 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1537 |  |  | AUH3525 |  | AUH3525 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2402-PREAGG-SR7-1 | 2/2/3 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 02:45 | AUH_E2568M_10005_001001001 | 25.25917 | 54.629890 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1536 |  |  | AUH2669 |  | AUH2669 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2402-PREAGG-SR7-1 | 2/2/2 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 02:25 | AUH_E2568N_10170_001001001 | 24.25558 | 54.65324 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1535 |  |  | AUH2683 |  | AUH2683 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-2402-PREAGG-SR7-1 | 2/2/1 | [16 empty] | FALSE | 2023 | Hafiz Umar | 2023-09-25 02:12 | AUH_E2568I_10607_001001001 | 24.27325 | 54.65553 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1534 |  |  | AUH3616 |  | AUH3616 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1:513- Port 6/1/c5/1:514 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 16:09 | AUH_E0566B_10313_001002001 | 24.0678889 | 52.6551889 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1533 |  |  | AUH3191 |  | AUH3191 | Nokia IXR-E | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 & 2 | 6/1/c5/1:511-6/1/c5/1:512 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 16:05 | AUH_E0566B_10309_001001001 | 24.072717 | 52.647208 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1532 |  |  | AUH2234 |  | AUH2234 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | AUH | 10G | AUH-1097-SCSG-SR7B-1 | esat-1/1/4 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 15:58 | AUH_E2470W_10286_001000000 | 24.39848 | 54.54117 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1531 |  |  | DXB2941 |  | DXB2941 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-3159-SCSG-SR7B-1 | esat-1/1/50 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 15:53 | DXB_E3178X_12252_001001001 | 25.14547 | 55.24242 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1530 |  |  | DXB2943 |  | DXB2943 | Nokia SAR-X | 5G+CSG Uplink Upgrade |  |  | Nokia |  | DXB | 10G | DXB-3159-SCSG-SR7B-1 | esat-1/1/51 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 15:46 | DXB_E3178S_11218_001001001 | 25.1487 | 55.2335 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1529 |  |  | DXB1151 |  | DXB1151 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-3/1/10 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 15:41 |  | 25.196900 | 55.296200 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1528 |  |  | AUH2009 |  | AUH2009 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6005-AGGR-SR12e-1 | 7/1/26 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 14:51 | AUH_E2271Y_11664_001008001 | 24.490820 | 54.368490 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1527 |  |  | AUH2009 |  | AUH2009 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6005-AGGR-SR12e-1 | 7/1/26 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 14:50 | AUH_E2271Y_11664_001008001 | 24.490820 | 54.368490 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1526 |  |  | AUH2144 |  | AUH2144 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6005-AGGR-SR12e-1 | 7/1/25 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 14:45 | AUH_E2271Y_11381_001010003 | 24.49351 | 54.38118 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1525 |  |  | AUH2006 |  | AUH2006 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AUH-6005-AGGR-SR12e-1 | 7/1/24 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 14:39 |  | 24.4953 | 54.3726 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1524 |  |  | AAN2549 |  | AAN2549 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 10/2/9 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 14:18 | AAN_E3468X_10002_001001001 | 24.234630 | 55.551100 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1523 |  |  | AAN2323 |  | AAN2323 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 10/1/8 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 14:12 | AAN_E3467H_10001_001001001 | 24.19145 | 55.52063 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1522 |  |  | AAN2298 |  | AAN2298 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | AUH | 10G | AAN-5002-AGGR-SR12-2 | 10/1/7 | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-24 14:08 | AAN_E3468T_10001_001001001 | 24.246454 | 55.569996 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1521 |  |  | DXB1443 |  | DXB1443 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-DUBAIOTECH-AGGR-SR12e-1 | 7/1/12 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 13:52 | DXB_E3074L_10023_001001001 | 24.81578 | 55.10911 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1520 |  |  | DXB1448 |  | DXB1448 | Nokia SAR-X | 5G+CSG Uplink Upgrade | Ring Break/Card Exp/Upgrade |  | Nokia |  | DXB | 10G | DXB-1153-SCSG-NCS57C3-2 | Te0/0/0/33:111 | [16 empty] | FALSE | 2023 | Omer Ikram | 2023-09-24 13:47 | DXB_E3379Y_10565_001001001 | 25.233000 | 55.442700 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1519 |  |  | AUH2857 |  | AUH2857 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-23 11:00 | AUH_E2469F_11154_001001001 | 24.374125 | 54.487786 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1518 |  |  | FUJ3261 |  | FUJ3261 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-23 06:14 | FJR_E4079A_10001_001001001 | 25.07718 | 55.16366 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1517 |  |  | FUJ2490 |  | FUJ2490 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 18:07 | MSF_E3975V_10002_001001001 | 24.8776185641371 | 55.9872440264714 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1516 |  |  | DXB2774 |  | DXB2774 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 18:02 | DXB_E3277G_10005_001001001 | 25.0908778872509 | 55.3020902799967 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1515 |  |  | IDX5901 |  | IDX5901 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:59 | DXB_E3075X_10845_001009001 | 24.8671183638 | 55.147033394 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1514 |  |  | DXB2788 |  | DXB2788 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:56 | DXB_E3177V_11057_001001001 | 25.0410734543 | 55.1937079522 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1513 |  |  | SHJ2352 |  | SHJ2352 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:52 | SHJ_E3379B_11396_001002001 | 25.3043698668 | 55.394743429 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1512 |  |  | DXB2165 |  | DXB2165 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:48 | DXB_E3177M_10656_001001001 | 25.0864806786 | 55.2084146775 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1511 |  |  | AAN2315 |  | AAN2315 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-09-22 17:45 | AAN_E3266B_10001_001001001 | 24.1318318181 | 55.3094632761 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1510 |  |  | MCR2 |  | MCR2 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:43 | AUH_E2570I_10082_001001001 | 24.4466653339 | 54.646085833 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1509 |  |  | MCR1 |  | MCR1 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:41 | AUH_E2570I_10082_001001002 | 24.4466653339 | 54.646085833 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1508 |  |  | AUH3567 |  | AUH3567 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-09-22 17:39 | AUH_E2271Y_11962_001003001 | 24.4905924209 | 54.3742988854 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1507 |  |  | SHJ0292 |  | SHJ0292 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:37 | SHJ_E3380U_10156_001030001 | 25.314559 | 55.375324 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1506 |  |  | SHJ2246 |  | SHJ2246 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:35 | SHJ_E3479D_10002_001001001 | 25.2917784693 | 55.529343851 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1505 |  |  | RAK0520 |  | RAK0520 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:32 | RKT_E3784V_10002_001002002 | 25.6830128865 | 55.7818416339 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1504 |  |  | SHJ0017 |  | SHJ0017 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-09-22 17:29 | SHJ_E3380P_10014_001001002 | 25.3287 | 55.3771 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1503 |  |  | KFN3947 |  | KFN3947 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-09-22 17:27 | RKT_E4179H_10002_001001001 | 25.286823 | 56.201683 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1502 |  |  | AUG6084 |  | AUG6084 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 17:24 | AUH_E2569L_10091_001001001 | 24.34746 | 54.61787 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1501 |  |  | RAK3745 |  | RAK3745 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:24 | SHJ_E3980K_10001_001001001 | 25.3591628208899 | 55.9616760404582 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1500 |  |  | AUH2425 |  | AUH2425 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:23 | AUH_E2670W_11000_001001001 | 24.40826 | 54.73079 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1499 |  |  | RAK0532 |  | RAK0532 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:21 | RKT_E3683E_10004_001001001 | 25.6695907223 | 55.743946596 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1498 |  |  | AAN2506 |  | AAN2506 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 17:21 | AAN_E3866N_10001_001001001 | 24.08629 | 55.93044 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1497 |  |  | AUH3053 |  | AUH3053 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:19 | AUH_E2469R_10442_001005001 | 24.33659 | 54.53801 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1496 |  |  | AUH2857 |  | AUH2857 | Nokia IXR-E | Migration |  |  |  |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 17:18 | AUH_E2469F_11154_001001001 | 24.374125 | 54.487786 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1495 |  |  | UAQ2812 |  | UAQ2812 | Nokia IXR-E | Migration |  |  | Nokia |  | UAQ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:17 | SHJ_E3980P_10001_001001001 | 25.3331446330512 | 55.9624102215084 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1494 |  |  | AUH2569 |  | AUH2569 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:16 | AUH_E2271T_11086_001001001 | 24.5048 | 54.3715 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1493 |  |  | FUJ2962 |  | FUJ2962 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:14 | RKT_E4076J_10001_001001001 | 25.016945042265 | 56.1457815270034 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1492 |  |  | AUH2564 |  | AUH2564 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:14 | AUH_E2470O_10086_001001001 | 24.43556 | 54.57587 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1491 |  |  | AUH2124 |  | AUH2124 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:13 | AUH_E2370R_11119_001001001 | 24.41102 | 54.43525 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1490 |  |  | AUH2083 |  | AUH2083 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:11 | AUH_E2370G_10188_001001001 | 24.44591 | 54.4095 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1489 |  |  | SHJ0290 |  | SHJ0290 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:11 | SHJ_E3380U_10177_001001002 | 25.30890449 | 55.36896424 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1488 |  |  | AUH2044 |  | AUH2044 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:09 | AUH_E2270E_12623_001001001 | 24.476600 | 54.3712 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1487 |  |  | AUH0740 |  | AUH0740 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:08 | AUH_E2370F_11316_001002001 | 24.456139 | 54.400905 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1486 |  |  | AUH2915 |  | AUH2915 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:06 | AUH_E0366L_10001_001001001 | 24.037799 | 52.464266 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1485 |  |  | DXB2167 |  | DXB2167 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 17:05 | DXB_E3077X_10736_001001001 | 25.0404102578 | 55.1374277323 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1484 |  |  | AUH2604 |  | AUH2604 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 17:04 | AUH_E2770M_10013_001001001 | 24.436003 | 54.833577 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1483 |  |  | AUH0448 |  | AUH0448 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 17:02 | AUH_E2271Y_11473_001014002 | 24.492318 | 54.375486 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1482 |  |  | IDX5023 |  | IDX5023 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-09-22 17:01 | DXB_E3279J_10950_001002002 | 25.2781661322 | 55.3574196823 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1481 |  |  | AUH0705 |  | AUH0705 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 17:00 | AUH_E2370M_11441_001010001 | 24.42907 | 54.42734 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1480 |  |  | DXB2339 |  | DXB2339 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:58 | DXB_E3574K_10175_001001001 | 24.8203621 | 55.5802231 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1479 |  |  | DXB2786 |  | DXB2786 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:57 | DXB_E3478P_10025_001001001 | 25.161022 | 55.466107 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1478 |  |  | KFN3100 |  | KFN3100 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:55 | FJR_E4379F_11239_001001001 | 25.2931 | 56.36648 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1477 |  |  | FUJ2904 |  | FUJ2904 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:53 | FJR_E4179A_10028_001001001 | 25.30415 | 56.16811 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1476 |  |  | KFN2607 |  | KFN2607 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:51 | FJR_E4282T_10001_001001001 | 25.5203 | 56.3464 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1475 |  |  | IDX5198 |  | IDX5198 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Hafiz Umar | 2023-09-22 16:50 | DXB_E3077W_11010_001001140 | 25.0454295424 | 55.1192869016 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1474 |  |  | SHJ2214 |  | SHJ2214 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:49 | SHJ_E3380H_10016_001001001 | 25.3628 | 55.4197 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1473 |  |  | RAK3717 |  | RAK3717 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:48 | RKT_E3783C_10005_001001001 | 25.67777 | 55.81065 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1472 |  |  | AUH3330 |  | AUH3330 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 16:47 | AUH_E2669X_10001_001001001 | 24.324438 | 54.76062 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1471 |  |  | RAK3114 |  | RAK3114 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:46 | RKT_E3884S_10002_001001001 | 25.696124 | 55.915912 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1470 |  |  | RAK2889 |  | RAK2889 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:45 | RKT_E3784W_10002_001001001 | 25.67777 | 55.81065 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1469 |  |  | AUH0519 |  | AUH0519 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 16:44 | AUH_E2271X_10755_001001002 | 24.4863247 | 54.3574702 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1468 |  |  | RAK2719 |  | RAK2719 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:43 | RKT_E3985H_10001_001001001 | 25.8295 | 55.99343 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1467 |  |  | RAK2833 |  | RAK2833 | Nokia IXR-E | Migration |  |  | Nokia |  | RAK |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:41 | RKT_E3985U_10005_001003001 | 25.77224 | 55.96797 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1466 |  |  | DXB3132 |  | DXB3132 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 16:41 | DXB_E3177L_10276_001001001 | 25.0831916092 | 55.186372362 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1465 |  |  | AUH3435 |  | AUH3435 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:40 | AUH_E2469R_10975_001001001 | 24.327144 | 54.534657 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1464 |  |  | DXB1065 |  | DXB1065 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:38 | DXB_E3177P_14265_001001001 | 25.0688 | 55.1732 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1463 |  |  | DXB1016 |  | DXB1016 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 16:36 | DXB_E3178N_12503_001001001 | 25.1734161 | 55.2283058 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1462 |  |  | DXN0087 |  | DXN0087 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 16:16 | DXB_E3075L_10002_001001002 | 24.9061194798 | 55.1050116495 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1461 |  |  | AUH0471 |  | AUH0471 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 16:11 | AUH_E2271X_10680_001022001 | 24.49085121 | 54.36042677 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1460 |  |  | AUH6558 |  | AUH6558 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 16:03 | AUH_E0566A_10011_001001001 | 24.072367513209 | 52.6339365066331 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1459 |  |  | KFN2837 |  | KFN2837 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | TRUE | 2023 | Omer Ikram | 2023-09-22 15:59 | FJR_E4282O_10001_001001001 | 25.53269 | 56.34197 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1458 |  |  | AUH3448 |  | AUH3448 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:56 | AUH_E2270B_10027_001003001 | 24.4629 | 54.325475 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1457 |  |  | DXB1043 |  | DXB1043 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:54 |  | 25.2547 | 55.3051 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1456 |  |  | FUJ2960 |  | FUJ2960 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:51 |  | 25.048493 | 56.144001 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1455 |  |  | FUJ2128 |  | FUJ2128 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:50 |  | 25.040120 | 56.150760 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1454 |  |  | DXB1845 |  | DXB1845 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 15:49 | DXB_E3076U_10073_001001001 | 24.9475058435 | 55.0744123589 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1453 |  |  | DXT1983 |  | DXT1983 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:48 |  | 24.953600 | 55.133630 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1452 |  |  | DUB0804 |  | DUB0804 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-09-25 | DXB |  | DXB-1346-SCSG-IXR-R6D-1 | 1/5/c16 | DXB-1346-SCSG-IXR-R6D-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-22 15:25 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1451 |  |  | DXB1642 |  | DXB1642 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:25 |  | 25.071974 | 55.565556 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1450 |  |  | AUH2720 |  | AUH2720 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:21 | AUH_E2469W_10146_001001001 | 24.304274 | 54.53678 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1449 |  |  | DXB1561 |  | DXB1561 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:19 |  | 25.2609 | 55.3045 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1448 |  |  | DXN0955 |  | DXN0955 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:18 |  | 25.258988 | 55.321836 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1447 |  |  | DXB2043 |  | DXB2043 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:16 |  | 25.09059 | 55.405018 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1446 |  |  | DUB0633 |  | DUB0633 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-09-22 | DXB |  | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | Gig0/0/0/49 | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-22 15:14 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1445 |  |  | DXB0806 |  | DXB0806 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:14 |  | 25.237730 | 55.272840 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1444 |  |  | DXN0798 |  | DXN0798 |  | 5G |  | Passive Completed | HOI-MEA | 2023-09-22 | DXB |  | DXB-DUBAIOTECH-AGGR-SR12e-2 | 7/1/24 | DXB-DUBAIOTECH-AGGR-SR12e-2 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-22 15:13 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1443 |  |  | FUJ2138 |  | FUJ2138 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:11 |  | 25.076100 | 56.138600 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1442 |  |  | AUH3366 |  | AUH3366 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:05 | AUH_E1561A_10538_001001001 | 23.6487 | 53.62462 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1441 |  |  | AUH3605 |  | AUH3605 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:03 | AUH_E1561B_10001_001001001 | 23.654 | 53.65375 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1440 |  |  | DXB0730 |  | DXB0730 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 15:01 | DXB_E3279X_10608_001003024 | 25.21895 | 55.338953 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1439 |  |  | DXB0728 |  | DXB0728 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 14:58 | DXB_E3279X_10606_001005017 | 25.2309 | 55.32286 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1438 |  |  | DXB0726 |  | DXB0726 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 14:57 | DXB_E3279L_13060_001003024 | 25.25832 | 55.29737 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1437 |  |  | DXB0725 |  | DXB0725 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 14:55 | DXB_E3279L_13059_001003024 | 25.26511 | 55.28896 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1436 |  |  | DXB0722 |  | DXB0722 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 14:52 | DXB_E3279M_11337_001003020 | 25.269438 | 55.307606 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1435 |  |  | DXN0857 |  | DXN0857 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:32 | DXB_E3279V_11041_001014033 | 25.219866 | 55.28546 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1434 |  |  | DXB0027 |  | DXB0027 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:29 | DXB_E3279H_10599_001004002 | 25.2790676205 | 55.304833245 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1433 |  |  | SHJ2244 |  | SHJ2244 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:25 | SHJ_E3380Q_10015_001001001 | 25.3421413028 | 55.3859779558 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1432 |  |  | SHJ0310 |  | SHJ0310 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:22 | SHJ_E3380L_10042_001017002 | 25.3603972438 | 55.3940584282 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1431 |  |  | DXB2268 |  | DXB2268 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:20 | DXB_E3279U_15626_001001001 | 25.21734 | 55.27204 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1430 |  |  | SHJ0066 |  | SHJ0066 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:16 | SHJ_E3380U_10170_001049011 | 25.3190127104 | 55.3750564176 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1429 |  |  | FUJ2824 |  | FUJ2824 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:05 | SHJ_E4275F_10001_001001001 | 24.9201570309 | 56.273611802 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1428 |  |  | DXB0720 |  | DXB0720 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 12:04 | DXB_E3279N_11572_001005017 | 25.270903 | 55.332978 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1427 |  |  | DXB0719 |  | DXB0719 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 12:01 | DXB_E3279J_11721_001003018 | 25.275244 | 55.346275 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1426 |  |  | DXB2275 |  | DXB2275 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 12:00 | DXB_E3279R_11481_001001001 | 25.2365888965588 | 55.3139664430996 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1425 |  |  | SHJ2096 |  | SHJ2096 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:57 | SHJ_E3380K_10023_001001001 | 25.34527268 | 55.38012186 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1424 |  |  | AAN2347 |  | AAN2347 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:54 | AAN_E3167L_10001_001001001 | 24.1786200496 | 55.2006628372 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1423 |  |  | AAN2435 |  | AAN2435 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:50 | AAN_E3867H_10001_001001001 | 24.19813 | 55.92149 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1422 |  |  | AAN2525 |  | AAN2525 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:46 | AAN_E3167R_10001_001001001 | 24.1681928721 | 55.2237889032 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1421 |  |  | DXB0718 |  | DXB0718 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:43 | DXB_E3279J_11720_001005018 | 25.277666 | 55.352764 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1420 |  |  | UAQ2919 |  | UAQ2919 | Nokia IXR-E | Migration |  |  | Nokia |  | UAQ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:41 | UAQ_E3582V_10001_001001001 | 25.4950533193 | 55.5834819812 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1419 |  |  | DXB0717 |  | DXB0717 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:41 | DXB_E3379F_10810_001004027 | 25.277806 | 55.361575 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1418 |  |  | DXB0716 |  | DXB0716 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:39 | DXB_E3379F_10811_001003025 | 25.273276 | 55.369336 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1417 |  |  | DXB0715 |  | DXB0715 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:36 | DXB_E3379K_11744_001003024 | 25.269928 | 55.375011 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1416 |  |  | DXB0714 |  | DXB0714 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:34 | DXB_E3379L_12613_001002025 | 25.262361 | 55.38773 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1415 |  |  | DXB0713 |  | DXB0713 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:32 | DXB_E3379L_12614_001003030 | 25.25473 | 55.400996 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1414 |  |  | DXB0729 |  | DXB0729 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:30 | DXB_E3279X_10607_001003026 | 25.22497 | 55.33367 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1413 |  |  | DXB0727 |  | DXB0727 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:28 | DXB_E3279R_11441_001004019 | 25.24361 | 55.31596 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1412 |  |  | DXB0724 |  | DXB0724 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:27 | DXB_E3279L_13058_001003018 | 25.26889 | 55.293772 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1411 |  |  | DXB0723 |  | DXB0723 | Nokia IXR-E | Migration |  | RFSed | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:24 |  | 25.276192 | 55.301771 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1410 |  |  | DXB0721 |  | DXB0721 | Nokia IXR-E | Migration |  | RFSed | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:23 | DXB_E3279M_11336_001003030 | 25.270345 | 55.320678 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1409 |  |  | FUJ3564 |  | FUJ3564 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:20 | FJR_E4379F_11238_001001001 | 25.2791 | 56.3604 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1408 |  |  | DXB1046 |  | DXB1046 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:20 | DXB_E3279H_10201_001001001 | 25.2724412215 | 55.3095038815 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1407 |  |  | DXB0187 |  | DXB0187 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:19 | DXB_E3279R_10911_001001001 | 25.24454 | 55.31839 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1406 |  |  | DXB2884 |  | DXB2884 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:17 | DXB_E3378M_10859_001008002 | 25.167555 | 55.404808 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1405 |  |  | DXB2884 |  | DXB2884 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:16 | DXB_E3378M_10859_001008002 | 25.167555 | 55.404808 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1404 |  |  | FUJ2166 |  | FUJ2166 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:15 | SHJ_E4275A_10001_001001001 | 24.9412845419 | 56.2671480515 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1403 |  |  | AUG4340 |  | AUG4340 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:11 | AUH_E2370N_10358_001001001 | 24.436498 | 54.45909 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1402 |  |  | AJM0914 |  | AJM0914 | Nokia IXR-E | Migration |  |  | Nokia |  | AJM |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:11 | AJM_E3480A_12264_001012011 | 25.3931018171 | 55.4676953852 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1401 |  |  | AUH2158 |  | AUH2158 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:09 |  | 24.37005 | 54.50853 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1400 |  |  | AUH2463 |  | AUH2463 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:08 | AUH_E2775O_10147_001001001 | 24.8884097631 | 54.8667307073 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1399 |  |  | AUH3866 |  | AUH3866 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | Na | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:07 | AUH_E2570L_10079_001001001 | 24.43681 | 54.60357 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1398 |  |  | SHJ0682 |  | SHJ0682 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Omer Ikram | 2023-09-22 11:04 | SHJ_E3379B_11438_001001001 | 25.30251 | 55.38493 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1397 |  |  | DXB0513 |  | DXB0513 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:04 | DXB_E3279M_11427_001004002 | 25.2596216466573 | 55.3188827568272 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1396 |  |  | AUH3229 |  | AUH3229 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 11:01 | AUH_E2469E_10008_001001001 | 24.3938186784876 | 54.5772993626614 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1395 |  |  | FUJ3261 |  | FUJ3261 | Nokia IXR-E | Migration |  |  | Nokia |  | FUJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 10:58 | FJR_E4079A_10001_001001001 | 25.3048536964 | 56.066512608 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1394 |  |  | DXB0748 |  | DXB0748 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-22 10:53 | DXB_E3077N_10701_001001002 | 25.07559 | 55.13249 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1393 |  |  | DXB0138 |  | DXB0138 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 20:12 | DXB_E3075T_10045_001001001 | 24.884454 | 55.164851 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1392 |  |  | DXB0927 |  | DXB0927 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 20:09 | DXB_E3278A_11609_001005002 | 25.202328 | 55.272616 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1391 |  |  | DXB0212 |  | DXB0212 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 20:05 | DXB_E3178J_11970_001005002 | 25.188839 | 55.262921 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1390 |  |  | DXB0544 |  | DXB0544 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 20:01 | DXB_E3279N_10890_001002002 | 25.257139 | 55.326664 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1389 |  |  | DXB3148 |  | DXB3148 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:56 | DXB_E3076J_10827_001001001 | 25.00283 | 55.14816 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1388 |  |  | DXB3148 |  | DXB3148 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:55 | DXB_E3076J_10827_001001001 | 25.00283 | 55.14816 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1387 |  |  | SHJ3287 |  | SHJ3287 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:51 | SHJ_E3775F_10001_001001001 | 24.91464 | 55.77557 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1386 |  |  | AUH3533 |  | AUH3533 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:42 | AUH_E2967K_10224_001001001 | 24.18311 | 54.99484 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1385 |  |  | DXB2318 |  | DXB2318 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:38 | DXB_E3076P_10620_001001001 | 24.9766121 | 55.0785828 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1384 |  |  | AAN0069 |  | AAN0069 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:34 | AAN_E3668W_10002_001001122 | 24.246021 | 55.726835 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1383 |  |  | AAN3303 |  | AAN3303 | Nokia IXR-E | Migration |  |  | Nokia |  | AUH |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:30 | AAN_E3567X_10005_001001001 | 24.146443 | 55.649436 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1382 |  |  | DXB2147 |  | DXB2147 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:22 | DXB_E3075C_10001_001001001 | 24.93798 | 55.11038 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1381 |  |  | DXB2147 |  | DXB2147 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:21 | DXB_E3075C_10001_001001001 | 24.93798 | 55.11038 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1380 |  |  | DXB2147 |  | DXB2147 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:20 | DXB_E3075C_10001_001001001 | 24.93798 | 55.11038 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1379 |  |  | DXB2147 |  | DXB2147 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:20 | DXB_E3075C_10001_001001001 | 24.93798 | 55.11038 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1378 |  |  | DXB2287 |  | DXB2287 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:15 | DXB_E3379R_11328_001001001 | 25.25314 | 55.41428 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1377 |  |  | SHJ2632 |  | SHJ2632 | Nokia IXR-E | Migration |  |  | Nokia |  | SHJ |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 19:00 | SHJ_E3580W_10001_001001001 | 25.3161 | 55.6187 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1376 |  |  | DXB3356 |  | DXB3356 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 18:43 | DXB_E3077I_10095_001001001 | 25.094 | 55.1341 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1375 |  |  | DXN0946 |  | DXN0946 | Nokia IXR-E | Migration |  |  | Nokia |  | DXB |  | NA | NA | [14 empty] | Completed |  | FALSE | 2023 | Hafiz Umar | 2023-09-21 18:37 | DXB_E3278A_11664_001007003 | 25.203824 | 55.265732 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1373 |  |  | SHJ2673 |  | SHJ2673 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | SHJ | 10G | SHJ-2508-PREAGG-SR7-1 | Port 4/1/1 | [10 empty] | 2023-09-01 | Y23-F106468 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 18:05 | SHJ_E3479H_10001_001001001 | 25.275 | 55.5029 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1372 |  |  | DXB2201 |  | DXB2201 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | 10G | DXB-6501-SCSG-NCS57C3-1 | Port Te0/0/0/30 | [10 empty] | 2023-08-21 | Y23-F105379 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 17:54 | DXB_E3077W_10529_001003001 | 25.0470543 | 55.1248856 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1371 |  |  | DXB1593 |  | DXB1593 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | Others | DXB-1096-SCSG-IXR-R6D-1 | Port 1/3/c3/1 | [10 empty] | 2023-08-24 | Y23-F105620 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 17:48 | DXB_E3379G_11249_001002001 | 25.283806 | 55.388615 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1370 |  |  | RAK2872 |  | RAK2872 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | FUJ | 10G | RAK-2711-SCSG-IXR-R6D-1 | Port 1/5/c3/1 | [10 empty] | 2023-08-21 | Y23-F105386 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 17:41 |  | 25.75941 | 55.91884 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1369 |  |  | DXB1094 |  | DXB1094 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | Others | DXB-3165-SCSG-IXR-R6D-2 | Port 1/3/c1/1 | [10 empty] | 2023-08-24 | Y23-F105619 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 17:40 | DXB_E3279I_15587_001001001 | 25.279249 | 55.334747 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1368 |  |  | RAK2100 |  | RAK2100 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | FUJ | 10G | RAK-2759-SCSG-IXR-R6D-1 | Port 1/5/c1/1 | [10 empty] | 2023-08-24 | Y23-F105617 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 17:36 | RKT_E3985G_10004_001001001 | 25.81945 | 55.98603 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1367 |  |  | DXB3216 |  | DXB3216 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | Others | DXB-2770-SCSG-IXR-R6D-1 | Port 1/3/c2/1 | [10 empty] | 2023-08-23 | Y23-F105493 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 17:31 | DXB_E3177P_14254_001001001 | 25.05631 | 55.17622 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1366 |  |  | SHJ0399 |  | SHJ0399 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | SHJ | 10G | SHJ-6501-PREAGG-SR7-1 | Port 4/1/3 | [10 empty] | 2023-09-01 | Y23-F106467 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 17:26 | SHJ_E3379A_10206_001001001 | 25.29798 | 55.37197 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1365 |  |  | KFN2677 |  | KFN2677 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1/FUJ-6001-AGG-ASR9912-2 | Port Hu0/0/0/3-Port Hu0/0/0/3 | [10 empty] | 2023-08-01 | Y23-F103907 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 17:21 | FJR_E4281T_10001_001001001 | 25.42871 | 56.35086 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1364 |  |  | DXB1066 |  | DXB1066 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | Others | DXB-2770-SCSG-IXR-R6D-2 | Port 1/3/c6/1 | [10 empty] | 2023-08-23 | Y23-F105498 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 17:03 | DXB_E3177U_12626_001001001 | 25.048332 | 55.172279 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1363 |  |  | DXB3210 |  | DXB3210 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | Others | DXB-2770-SCSG-IXR-R6D-1 | Port 1/3/c7/1 | [10 empty] | 2023-08-24 | Y23-F105613 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 16:54 | DXB_E3177U_12624_001001001 | 25.050749 | 55.181725 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1362 |  |  | KFN2108 |  | KFN2108 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1/FUJ-6001-AGG-ASR9912-2 | Port Hu0/0/0/3-Port Hu0/0/0/3 | [10 empty] | 2023-07-07 | Y23-F102268 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 16:50 | SHJ_E4280T_10002_001001001 | 25.34508 | 56.34381 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1361 |  |  | DXB1055 |  | DXB1055 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | 10G | DXB-DMC-PREAGG-SR7-1 | Port 5/1/2 | [10 empty] | 2023-07-05 | Y23-F102116 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 16:47 | DXB_E3279L_12594_001001001 | 25.26022 | 55.29861 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1360 |  |  | RAK2772 |  | RAK2772 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | RAK | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | Port 1/x1/2/c2/1-Port 1/x1/2/c2/1 | [10 empty] | 2023-08-09 | Y23-F104380 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 16:46 | RKT_E3985M_10001_001001001 | 25.801596 | 56.00038 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1359 |  |  | DXB3214 |  | DXB3214 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-08 | DXB | Others | DXB-2770-SCSG-IXR-R6D-1 | Port 1/3/c3/1 | [10 empty] | 2023-09-01 | Y23-F106466 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 16:32 | DXB_E3077T_13243_001001001 | 25.058832 | 55.161198 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1358 |  |  | RAK2738 |  | RAK2738 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | RAK | 10G | KFN-2115-SCSG-SR7-1 | Port 5/1/1 | [10 empty] | 2023-08-21 | Y23-F105377 |  |  |  |  | TRUE | 2023 | Hafiz Umar | 2023-09-21 16:17 | FJR_E4082V_10001_001001001 | 25.5077 | 56.07566 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1357 |  |  | KFN2624 |  | KFN2624 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | Hu0/0/0/3 | [10 empty] | 2023-08-23 | Y23-F105502 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 15:40 | FJR_E4282J_10001_001001001 | 25.55483 | 56.34695 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1356 |  |  | RAK3521 |  | RAK3521 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | RAK | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | Port 1/x1/2/c2/1-Port 1/x1/2/c2/1 | [10 empty] | 2023-07-06 | Y23-F102211 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 15:33 | RKT_E3784W_10009_001001001 | 25.68766 | 55.80621 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1355 |  |  | RAK2718 |  | RAK2718 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | RAK | 10G | UAQ-DC-AGGR-SR7S-1/UAQ-DC-AGGR-SR7S-2 | Port 1/x1/2/c2/1-Port 1/x1/2/c2/1 | [10 empty] | 2023-08-04 | Y23-F104079 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:45 | RKT_E3985L_10001_001001001 | 25.813368 | 55.982717 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1354 |  |  | SHJ2361 |  | SHJ2361 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | SHJ | 10G | SHJ-2059-SCSG-NCS57C3-1 | Port Ten0/0/0/32 | [10 empty] | 2023-08-08 | Y23-F104378 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:40 | SHJ_E3380C_10002_001001001 | 25.390061 | 55.416545 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1353 |  |  | DXB1889 |  | DXB1889 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-2282-SCSG-IXR-R6D-1 | Port 1/3/c1/1 | [10 empty] | 2023-09-01 | Y23-F106314 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:35 | DXB_E3379H_11019_001001001 | 25.28354 | 55.40894 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1352 |  |  | DXB1324 |  | DXB1324 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-2282-SCSG-IXR-R6D-1 | Port 1/3/c2/1 | [10 empty] | 2023-09-05 | Y23-F106783 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:29 |  | 25.2874 | 55.37106 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1351 |  |  | AUH2275 |  | AUH2275 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | AUH | 10G | AUH-2178-PREAGG-SR7-1 | Port 2/2/1 | [10 empty] | 2023-08-24 | Y23-F105615 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:19 | AUH_E2774O_10007_001001001 | 24.798112 | 54.860856 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1350 |  |  | DXB2540 |  | DXB2540 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | 10G | DXB-1346-SCSG-IXR-R6D-1 | Port 1/3/c1/1 | [10 empty] | 2023-09-01 | Y23-F106344 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:12 | DXB_E3379B_11401_001001001 | 25.29875 | 55.38053 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1349 |  |  | DXT2543 |  | DXT2543 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | 10G | DXB-6501-SCSG-NCS57C3-1 | Port Te0/0/0/29 | [10 empty] | 2023-08-21 | Y23-F105378 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 14:03 | DXB_E3279U_10885_001001001 | 25.04798 | 55.11791 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1348 |  |  | DXB1293 |  | DXB1293 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-3165-SCSG-IXR-R6D-1 | Port 1/3/c1/1 | [10 empty] | 2023-09-05 | Y23-F106785 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 13:56 | DXB_E3279I_14829_001001001 | 25.27375 | 55.33143 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1347 |  |  | DXB2504 |  | DXB2504 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-1852-SCSG-IXR-R6D-2 | Port 1/3/c1/1 | [10 empty] | 2023-09-01 | Y23-F106462 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 13:50 | DXB_E3479W_10366_001001001 | 25.22098 | 55.51294 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1346 |  |  | DXB2078 |  | DXB2078 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-2770-SCSG-IXR-R6D-2 | Port 1/3/c2/1 | [10 empty] | 2023-08-21 | Y23-F105385 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 13:44 |  | 25.0543 | 55.1715 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1345 |  |  | DXB2805 |  | DXB2805 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-2770-SCSG-IXR-R6D-2 | Port 1/3/c1/1 | [10 empty] | 2023-08-21 | Y23-F105384 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 13:39 | DXB_E3077Y_11622_001001001 | 25.0499 | 55.1464 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1344 |  |  | DXB1068 |  | DXB1068 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | Others | DXB-2770-SCSG-IXR-R6D-2 | Port 1/3/c5/1 | [10 empty] | 2023-08-23 | Y23-F105496 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 13:32 | DXB_E3177P_14253_001001001 | 25.064804 | 55.184807 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1343 |  |  | IDX5197 |  | IDX5197 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | 10G | DXB-3183-PREAGG-SR7-1 | Port 5/1/2 | [10 empty] | 2023-08-18 | Y23-F105183 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 13:22 | DXB_E3077W_11010_001001139 | 25.044755 | 55.119421 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1342 |  |  | AUH3909 |  | AUH3909 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-10-04 | AUH |  | AUH-2116-CSG-SAR-8-1 | 1/2/2 (3G LTE) ¦ 1/2/5 (5G) | AUH-2116-CSG-SAR-8-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-21 12:26 |  | 24.35134 | 54.5216 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1341 |  |  | IDX5025 |  | IDX5025 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | 10G | DXB-1003-SCSG-SR7B-1 | esat-1/1/21 | [10 empty] | 2023-07-05 | Y23-F102111 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 12:05 |  | 25.08738 | 55.15127 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1340 |  |  | DXB0311 |  | DXB0311 | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-0311-IBS-SAR-M-1 | Port 1/1/4 | DXB-0311-IBS-SAR-M-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-11 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-09-21 12:03 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1339 |  |  | DXB3315 |  | DXB3315 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-09-28 | DXB | 10G | DXB-DFC-SCSG-SR7B-1 | esat-1/1/5 | DXB-DFC-SCSG-SR7B-1 | NK224931524 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-09-27 | Y23-F108468 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-09-21 12:00 | DXB_E3379P_10448_001002002 | 25.236631 | 55.37052 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1338 |  |  | IDX5153 |  | IDX5153 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | DXB | 10G | DXB-ZAFRAN-SCSG-IXR-R6D-1 | Port 1/6/c3/1 | [10 empty] | 2023-08-04 | Y23-F104131 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 11:51 | DXB_E3278A_11661_001011001 | 25.199899 | 55.282951 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1337 |  |  | AUH2220 |  | AUH2220 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | AUH | 10G | AUH-1090-SCSG-SR7B-1 | esat-1/1/45 | [10 empty] | 2023-08-24 | Y23-F105614 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 11:46 | AUH_E2370M_12380_001001001 | 24.43846 | 54.42833 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1336 |  |  | AUH2161 |  | AUH2161 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 3/2/4 | [10 empty] | 2023-08-21 | Y23-F105380 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 11:39 | AUH_E2771I_10001_001001001 | 24.55381 | 54.84563 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1335 |  |  | AUH3123 |  | AUH3123 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 2/1/9 | [10 empty] | 2023-09-01 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-09-21 11:34 | AUH_E2771K_10001_001001001 | 24.54085 | 54.78882 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1334 |  |  | AUH3565 |  | AUH3565 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/13 | [10 empty] | 2023-08-07 | Y23-F104301 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 11:25 | AUH_E1655M_10001_001001001 | 23.06238 | 53.77681 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1333 |  |  | AUH6483 |  | AUH6483 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-07 | AUH | 10G | AUH-2925-PREAGG-SRa8-1 | Port 1/1/5 | [10 empty] | 2023-09-05 | Y23-F106784 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-21 11:12 |  | 23.0085 | 54.307284 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1332 |  |  | DUB0787 |  | DUB0787 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2023-10-13 | DXB |  | DXB-VILLAPOP-AGGR-SR12e-2 | Port 2/1/28 | DUB-0787-CSG-IXR-E-1 | NK231134769 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-10-13 | Y23-F109468 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-09-21 10:20 | DXB_E3377F_10473_001001003 | 25.103688 | 55.369808 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1331 |  |  | DXN0188 |  | DXN0188 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-1516-SCSG-SR7B-1 | esat-3/1/12 | DXB-1516-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed on 21/09/2023 |  |  | 2023-09-21 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-09-20 10:24 |  | 25.209798 | 55.320298 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1330 |  |  | AAN3643 |  | AAN3643 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-10-23 | AUH | 10G | AAN-5002-AGGR-SR12-1 | 4/1/5 | AAN-3643-CSG-N540-LD-1 | FOC2624KMES |  |  |  |  | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-09-26 | Y23-F108328 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-09-19 11:07 | AAN_E3467S_10001_001001001 | 24.16953 | 55.54007 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1329 |  |  | SHJ1262 |  | SHJ1262 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-09-25 | SHJ | 10G | SHJ-2035-SCSG-SR7B-1 | esat-1/1/3 | SHJ-1262-CSG-IXR-E-1 | NK224931292 | [9 empty] | Y23-F108073 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-09-18 12:25 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1328 |  |  | DUB0424 |  | DUB0424 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-09-22 | DXB | 1G | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/1 | DXB-BB-SCSG-NCS57C3-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-18 11:25 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1327 |  |  | AAN2429 |  | AAN2429 | Passive | 5G Upgrade | Passive patching | No OSP | XAD |  | AUH |  | AAN-2399-SCSG-IXR-R6D-1 | 1/5/c10 | AAN-2399-SCSG-IXR-R6D-1 | [5 empty] | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-18 09:52 |  | 24.03254 | 55.65231 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1326 |  |  | DUB0047 |  | DUB0047 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-09-20 | DXB | 1G | DXB-JBR-BAHAR-SCSG-IXR-R6-1 | 1/5/2 | DXB-JBR-BAHAR-SCSG-IXR-R6-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-16 12:23 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1325 | WO- IIB-CSG-2023-Order # 1325 |  | AAN2059 |  | AAN2059 | Passive | 5G Upgrade | Passive patching | OSP Issue | XAD |  | AUH |  | AAN-6001-AGGR-SR7S-2 | esat-2/1/24 | AAN-6001-AGGR-SR7S-2 |  | 5 |  |  |  |  | OSP link is 16km++ | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-16 10:48 |  | 24.210111508 | 55.777743013 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1324 | WO- IIB-CSG-2023-Order # 1324 |  | AAN2534 |  | AAN2534 | Passive | 5G Upgrade | Passive patching | OSP Issue | XAD |  | AUH |  | AAN-6001-AGGR-SR7S-2 | esat-2/1/25 | AAN-6001-AGGR-SR7S-2 |  | 5 |  |  |  |  | OSP is 13++km | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-16 10:29 |  | 24.211560 | 55.795670 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1323 |  |  | IAD5764 |  | IAD5764 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-21 | AUH |  | AUH-2185-CSG-IXR-E-1 | 1/1/17 | AUH-2185-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-15 12:53 |  | 24.458589 | 54.382107 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1322 |  |  | AAN3360 |  | AAN3360 | Passive | 5G Upgrade | New CSG | Passive Completed | XAD | 2023-09-19 | AUH |  | AAN-2049-SCSG-SR7B-1 | esat-1/1/55 | AAN-2049-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-14 11:25 |  | 24.20189 | 55.56548 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1321 |  |  | AAN3100 |  | AAN3100 | To Be Confirmed |  | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AAN-2005-SCSG-IXR-R6D-1 | 1/5/c16 | [7 empty] | site has existing 5G 10GE | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-14 11:20 |  | 24.140363 | 55.64168 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1320 |  |  | AUH3194 |  | AUH3194 | Nokia IXR-E | SRAN + 5G |  | RFSed | HOI-MEA | 2023-11-06 | AUH | 10G | AUH-2149-SCSG-SR7B-1 | esat-1/1/36 | AUH-3194-CSG-IXR-E-1 | NK224931216 | 5 | [8 empty] | Y23-F109591 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-14 11:16 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1319 |  |  | SHJ0264 |  | SHJ0264 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-09-28 | SHJ | 10G | SHJ-2016-SCSG-SR7B-1 | esat-1/1/56 | SH-0264-CSG-IXR-E-1 | NK223433793 | [9 empty] | Y23-F108178 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-09-14 11:14 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1318 | WO- IIB-CSG-2023-Order # 1318 |  | AAN3218 |  | AAN3218 | To Be Confirmed | 5G | New CSG | OSP Issue | XAD |  | AUH | 10G | AAN-5002-AGGR-SR12-1 | To be assigned |  |  | 5 |  |  |  |  | OSP Highloss | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-14 11:12 |  | 24.213625° | 55.544182° | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1317 |  |  | AUH0008 |  | AUH0008 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-11-17 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | esat-1/1/42 | AUH-0008-CSG-N540-LD-1 | FOC2720N8WW | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-11-14 | Y23-F111667 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-14 08:50 | AUH_E2570R_10018_001001001 | 24.420671 | 54.623344 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1316 | WO- IIB-CSG-2023-Order # 1316 |  | IDX0960A |  | IDX0960A | Cisco NCS540 | Rollout | New CSG | Transmission rack not available | XAD |  | DXB | 1G | DXB-3155-SCSG-IXR-R6D-1 | 1/3/c4 | IDX-0960-CSG-N540-LD-1 |  | 5 |  |  |  |  | no TX rack no rectifier avaialable on site | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-13 13:43 |  | 25.166187 | 55.304250 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1313 |  |  | IAD5139 |  | IAD5139 | Passive | Parity | Passive patching | No OSP | XAD |  | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-2/1/37 | AUH-6003-AGGR-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-11 16:37 |  | 24.461593 | 54.323536 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1312 |  |  | DXB2279 |  | DXB2279 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-31 | DXB | 10G | DXB-1090-SCSG-SR7B-1 | esat-1/1/29 | [10 empty] | 2023-08-28 | Y23-F106029 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 18:19 | DXB_E3279D_12671_001001001 | 25.290083 | 55.327805 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1311 |  |  | DXB2272 |  | DXB2272 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-05 | DXB | 10G | DXB-3145-PREAGG-SR7-1 | Port 5/1/5 | [10 empty] | 2023-08-30 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-09-08 18:13 | DXB_E3279W_10078_001003001 | 25.23411 | 55.31161 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1310 |  |  | DXB2343 |  | DXB2343 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-31 | DXB | 10G | DXB-3173-SCSG-SR7B-1 | esat-2/1/14 | [10 empty] | 2023-08-29 | Y23-F106126 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 18:06 |  | 25.2394 | 55.2881 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1309 |  |  | DXB1590 |  | DXB1590 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-28 | DXB | 10G | DXB-3164-PREAGG-SR7-1 | Port 5/1/9 | [10 empty] | 2023-08-18 | Y23-F105182 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 18:00 | DXB_E3379K_11769_001001001 | 25.25757 | 55.38058 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1308 |  |  | AUH3353 |  | AUH3353 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-29 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | Port 2/1/27 | [10 empty] | 2023-08-28 | Y23-F106009 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 17:51 |  | 24.37448 | 54.62302 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1307 |  |  | AUH3350 |  | AUH3350 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | AUH | 10G | AUH-1416-AGGR-SR12E-1 | Port 2/1/26 | [10 empty] | 2023-08-28 | Y23-F106009 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 17:42 | AUH_E2569C_10094_001001001 | 24.380092 | 54.63044 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1306 |  |  | AUH2429 |  | AUH2429 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-29 | AUH | 10G | AUH-2142-PREAGG-SR7-1 | Port 5/1/1 | [10 empty] | 2023-08-28 | Y23-F106014 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 17:26 | AUH_E2770D_10001_001001001 | 24.47571 | 54.85195 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1305 |  |  | AUH1048 |  | AUH1048 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-24 | AUH | 1G | AUH-1048-PREAGG-SR7-1 | Port 4/2/5 | [10 empty] | 2023-08-18 | Y23-F105186 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 17:18 | AUH_E2270H_11224_001001001 | 24.46204 | 54.33725 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1304 |  |  | AUH3500 |  | AUH3500 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-24 | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/22 | [10 empty] | 2023-08-22 | Y23-F105453 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 17:11 | AUH_E2469O_10180_001001001 | 24.354013 | 54.577748 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1303 |  |  | AUH3498 |  | AUH3498 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/21 | [10 empty] | 2023-08-22 | Y23-F105451 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 17:02 | AUH_E2469O_10182_001001001 | 24.340754 | 54.584987 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1302 |  |  | AUH2431 |  | AUH2431 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-09-01 | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 3/2/14 | [10 empty] | 2023-08-15 | Y23-F104842 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 16:50 | AUH_E2871L_10001_001001001 | 24.52824 | 54.90562 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1301 |  |  | IAD5066 |  | IAD5066 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia |  | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/47 | [10 empty] | 2023-08-18 | Y23-F105181 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-09-08 16:35 | AUH_E2370S_10282_001007001 | 24.416117 | 54.453591 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1300 |  |  | IAJ5869 |  | IAJ5869 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | AJM | 1G | AJM-6001-SCSG-SR7B-1 | esat-2/1/51 | AJM-6001-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-09-12 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-09-08 14:57 |  | 55.4598 | 25.39200 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1299 |  |  | IAD5521 |  | IAD5521 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-16 | AUH |  | AUH-2410-SCSG-IXR-R6D-1 | 1/5/c15 | AUH-2410-SCSG-IXR-R6D-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-08 14:06 |  | 24.455852 | 54.615459 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1298 |  |  | DXN0582 |  | DXN0582 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-09-12 | DXB | 10G | DXB-DUBAIOTECH-SCSG-NCS57C3-1 | Te0/0/2/1 | DXN-0582-CSG-N540-LD-1 | FOC2613PNED | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-12 | Y23-F107309 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-09-08 13:24 | DXB_E3177E_10681_001016001 | 25.11363 | 55.24832 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1297 |  |  | IDX5351 |  | IDX5351 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-10-05 | DXB | 10G | DXB-6004-AGGR-SR12e-1 | 2/1/22 | IDX-5351-CSG-IXR-E-1 | NK223433512 | [9 empty] | Y23-F108739 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-07 11:49 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1296 |  |  | IDX5525 |  | IDX5525 |  | Migration |  | Passive Completed | HOI-MEA | 2023-09-18 | DXB | 1G | DXB-DSO-CSG-IXR-E-2 | 1/1/13 | DXB-DSO-CSG-IXR-E-2 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-07 11:47 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1295 |  |  | DUB0316 |  | DUB0316 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-09 | DXB |  | DXB-DSO-CSG-IXR-E-2 | 1/1/14 | DXB-DSO-CSG-IXR-E-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-07 10:55 |  | 25.11683 | 55.36957 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1294 |  |  | DUB0776 |  | DUB0776 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-12 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-1/1/30 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-07 10:44 |  | 25.050017 | 55.19764 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1292 |  |  | IAJ5873 |  | IAJ5873 | Nokia IXR-E | Rollout |  | RFSed | HOI-MEA | 2023-10-06 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-2/1/50 | IAJ-5873-CSG-IXR-E-1 | NK22393A777 | [9 empty] | Y23-F108847 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-09-06 16:07 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1291 |  |  | AAN3398 |  | AAN3398 | Passive | 5G+SRAN Migration | Passive patching | Passive Completed | XAD | 2023-09-07 | AUH |  | AAN-5001-CSG-SAR-8-1 | Port 1/2/6 5G Link | AAN-5001-CSG-SAR-8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-09-05 13:46 |  | 24.48429 | 55.7603 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1290 |  |  | DUB0456 |  | DUB0456 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 10G | DXB-2322-CSG-IXR-E-1 | 1/1/11 | DXB-2322-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-09-04 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-09-01 16:22 |  | 24.985511 | 55.14033 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1289 |  |  | AUH3598 |  | AUH3598 | Passive | 5G | Passive patching | Passive Completed | SHAHID |  | AUH | 10G | AUH-2919-CSG-SAR-8-1 | Port 1/2/6 | AUH-2919-CSG-SAR-8-1 |  |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-08-31 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-08-30 10:29 |  | 24.066057 | 51.758543 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1288 |  |  | AUH3659 |  | AUH3659 | Passive | 5G | Passive patching | Passive Completed | SHAHID |  | AUH |  | AUH-2836-PREAGG-SR7-1 | Port 5/1/3 | AUH-2836-PREAGG-SR7-1 |  |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-08-31 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-08-30 10:27 |  | 23.695623 | 53.70843 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1287 |  |  | SHJ2352 |  | SHJ2352 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-07-27 | SHJ | 10G | SHJ-2020-PREAGG-SR7-1 | Port 4/1/3 | [10 empty] | 2023-07-27 | Y23-F103554 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 18:16 | SHJ_E3379B_11396_001002001 | 25.30468 | 55.3944 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1286 |  |  | AUH3887 |  | AUH3887 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/5 | [10 empty] | 2023-07-26 | Y23-F103664 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 18:09 | AUH_E1554E_10002_001001001 | 23.0081546 | 53.7226176 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1285 |  |  | AUH2668 |  | AUH2668 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-07-27 | AUH | 10G | AUH-2122-SCSG-SR7B-1 | esat-1/1/34 | [10 empty] | 2023-06-21 | Y23-F103391 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 18:02 | AUH_E2469K_11066_001001001 | 24.34168 | 54.50059 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1284 |  |  | DXB2165 |  | DXB2165 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-09 | DXB | Others | DXB-2770-SCSG-IXR-R6D-2 | 1/3/c7/1 | [10 empty] | 2023-07-25 | Y23-F103381 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 17:56 | DXB_E3177M_10656_001001001 | 25.0865 | 55.20842 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1283 |  |  | SiteCPDC |  | SiteCPDC | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-09 | DXB | 10G | DXB-6020-AGGR-SR12e-2 | Port 7/1/3 | [10 empty] | 2023-07-25 | Y23-F103330 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 17:44 | DXB_E3177F_10032_001005003 | 25.09578 | 55.16696 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1282 |  |  | DXB6020 |  | DXB6020 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-09 | DXB | 10G | DXB-6020-AGGR-SR12e-1 | Port 7/1/3 | [10 empty] | 2023-07-25 | Y23-F103331 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 17:33 | DXB_E3177B_10710_001002003 | 25.111701 | 55.203026 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1281 |  |  | AUH3454 |  | AUH3454 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 3/2/8 | [10 empty] | 2023-07-27 | [5 empty] | TRUE | 2023 | Omer Ikram | 2023-08-29 16:57 |  | 24.5062 | 54.799 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1280 |  |  | AAN2315 |  | AAN2315 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 10G | AAN-2019-SCSG-IXR-R6-1 | Port 1/4/4 | [10 empty] | 2023-07-11 | Y23-F102721 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 16:46 | AAN_E3266B_10001_001001001 | 24.1318 | 55.3094 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1279 |  |  | AUHMCR2 |  | AUHMCR2 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 10G | AUH-ADAC-SCSG-SR7B-2 | esat-1/1/11 | [10 empty] | 2023-07-04 | Y23-F102082 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 15:52 |  | 24.450617 | 54.641366 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1278 |  |  | AUHMCR1 |  | AUHMCR1 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 10G | AUH-ADAC-SCSG-SR7B-1 | esat-1/1/11 | [10 empty] | 2023-07-04 | Y23-F102080 |  |  |  |  | TRUE | 2023 | Omer Ikram | 2023-08-29 15:48 | AUH_E2570I_10082_001001002 | 24.450617 | 54.641366 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1277 |  |  | AUH3567 |  | AUH3567 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 10G | AUH-2055-SCSG-SR7B-1 | esat-1/1/10 | [10 empty] | 2023-04-26 | Y23-F79037 |  |  |  |  | FALSE | 2023 | Omer Ikram | 2023-08-29 15:24 |  | 24.490624 | 54.374444 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1276 |  |  | AUH2513 |  | AUH2513 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 3/2/6 | [10 empty] | 2023-07-27 | Y23-F103505 |  |  |  |  | FALSE | 2023 | Omer Ikram | 2023-08-29 15:04 | AUH_E2771E_10001_001001001 | 24.562725 | 54.867507 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1275 |  |  | AUH3124 |  | AUH3124 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-08-08 | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 3/2/16 | [10 empty] | 2023-08-02 | Y23-F103987 |  | Nokia |  |  | FALSE | 2023 | Omer Ikram | 2023-08-29 14:54 | AUH_E2771A_10001_001001001 | 24.56365 | 54.78902 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1274 |  |  | SHJ0292 |  | SHJ0292 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-02-08 | SHJ | 10G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/6 | SCSG | [9 empty] | 2023-02-07 | Y23-F74458 |  | Nokia |  |  | FALSE | 2023 | Omer Ikram | 2023-08-29 14:41 | SHJ_E3380U_10156_001030001 | 25.31470 | 55.37500 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1273 |  |  | SHJ2344 |  | SHJ2344 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-07-27 | SHJ | 10G | SHJ-2053-AGGR-SR7B-1 | esat-1/1/48 | [10 empty] | 2023-07-26 | Y23-F103491 |  |  |  |  | FALSE | 2023 | Omer Ikram | 2023-08-29 14:18 | SHJ_E3479I_10001_001001001 | 25.2817 | 55.5223 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1272 |  |  | SHJ2246 |  | SHJ2246 | Nokia IXR-E | Rollout | New CSG | RFSed | Nokia | 2023-07-27 | SHJ | 10G | SHJ-2053-AGGR-SR7B-1 | esat-1/1/47 | [10 empty] | 2023-07-27 | Y23-F103515 |  |  |  |  | FALSE | 2023 | Omer Ikram | 2023-08-29 14:10 | SHJ_E3479D_10002_001001001 | 25.291790 | 55.529380 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1271 |  |  | DXB2931 |  | DXB2931 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | SHAHID | 2023-09-07 | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-3/1/11 | DXB-2931-CSG-IXR-E-1 | NK224931304 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-09-05 | Y23-F106769 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-08-28 16:34 | DXB_E3279L_11260_001001001 | 25.26 | 55.3001 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1270 |  |  | DXN0623 |  | DXN0623 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-BB-SCSG-NCS57C3-2 | TF0/0/0/50 | DXB-BB-SCSG-NCS57C3-2 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-09-12 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-08-28 16:25 |  | 25.188898 | 55.281931 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1269 |  |  | DXN0112 |  | DXN0112 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-08-25 | DXB |  | DXB-BB-SCSG-NCS57C3-2 | Gi0/0/0/0 | DXB-BB-SCSG-NCS57C3-2 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-08-28 12:40 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1268 |  |  | IAD5599 |  | IAD5599 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-09-11 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/33 | IAD-5599-CSG-N540-LD-1 | FOC2631N0BK |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-09-08 | Y23-F107024 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-28 11:22 | AUH_E2270C_10670_001001001 | 24.47058 | 54.34008 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1267 |  |  | DXN0151 |  | DXN0151 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-31 | DXB |  | DXB-BB-SCSG-NCS57C3-2 | Gi0/0/0/46 | DXB-BB-SCSG-NCS57C3-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-28 11:14 |  | 25.18053 | 55.27864 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1266 |  |  | UAQ1358 |  | UAQ1358 | Cisco NCS540 | BAU + 5G | New CSG | RFSed | XAD | 2023-09-06 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/40 | UAQ-1358-CSG-N540-LD-1 | FOC2624KNPS | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-01 | Y23-F106433 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-25 11:14 | UAQ_E3581A_10003_001001001 | 25.4864349 | 55.5685976 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1265 |  |  | IAD5945 |  | IAD5945 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-09-07 | AUH | 1G | AUH-2713-PREAGG-SRa8-1 | 1/2/29 | IAD-5945-CSG-N540-LD-1 | FOC2624KMST | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-06 | Y23-F106857 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-24 16:59 | AUH_E2367J_10001_001001003 | 24.18899 | 54.46595 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1264 |  |  | DXB3944 |  | DXB3944 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-09-01 | DXB | 10G | DXB-MIRDIFPOP-SCSG-NCS57C3-2 | TF0/0/0/6 | DXB-3944-CSG-N540-LD-1 | FOC2624KMQ6 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-28 | Y23-F105979 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-23 16:58 | DXB_E3378I_10300_001001001 | 25.194304 | 55.432720 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1263 |  |  | DUB0753 |  | DUB0753 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-29 | DXB |  | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | PORT Gi0/0/0/0 | DXB-DUBAIOTECH-SCSG-NCS57C3-2 | [6 empty] | port changed | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-23 11:19 |  | 25.077535 | 55.240532 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1262 |  |  | AAN0004 |  | AAN0004 | Nokia IXR-E | 5G | New CSG | RFSed | XAD |  | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/52 | AAN-0004-CSG-IXR-E-1 | NK231233762 | [5 empty] | EPOC changed. link shifting from 1G to 10GE completed. | Rogelio Pangilinan;#1712 |  |  | Y23-F106214 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-22 12:39 | AAN_E3767A_10011_001003091 | 24.22253 | 55.78222 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1261 |  |  | AUG4431 |  | AUG4431 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-09-06 | AUH |  | AUH-2406-CSG-ASR920-LD-1 | GigabitEthernet0/0/11 | AUH-2406-CSG-ASR920-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-21 16:24 |  | 24.20084 | 54.68417 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1260 |  |  | AUH1338 |  | AUH1338 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-16 | AUH | Others | AUH-0971-CSG-ASR920-LD-1 | Port 0/0/15-5G, Port 0/0/11 3G LTE | AUH-0971-CSG-ASR920-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-21 16:17 |  | 24.5222940° | 54.670598° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1259 |  |  | AUH1332 |  | AUH1332 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-16 | AUH |  | AUH-0971-CSG-ASR920-LD-1 | Port 0/0/14, Port /0/0/8 | AUH-0971-CSG-ASR920-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-21 16:15 |  | 24.524360° | 54.671444° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1258 |  |  | ISH5196 |  | ISH5196 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-13 | SHJ |  | SHJ-2589-CSG-SAR-8-1 | Port 1/1/2 | SHJ-2589-CSG-SAR-8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-21 14:07 |  | 25.306013 | 55.376235 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1257 |  |  | DUB0275 |  | DUB0275 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-08-25 | DXB |  | DUB-0238-CSG-N540-LD-1 | Gi0/0/0/7 | DUB-0238-CSG-N540-LD-1 | [12 empty] | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-08-21 13:47 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1256 |  |  | DUB0239 |  | DUB0239 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2024-01-09 | DXB |  | DUB-0238-CSG-N540-LD-1 | Gi0/0/0/8 | DUB-0238-CSG-N540-LD-1 |  | 5 | [10 empty] | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-08-21 13:47 |  | 25.228448604233947 | 55.290525755728396 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1255 |  |  | SHJ5498E |  | SHJ5498E | Passive | Migration | Passive patching | Access Issues | XAD |  | SHJ |  | SHJ-2038-AGGR-SR7-1 | Port 2/2/19 | SHJ-2038-AGGR-SR7-1 |  | 5 |  |  |  |  | BM refuse to give access. SHJ jail site | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-17 12:51 |  | 25.35802 | 55.45066 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1254 | WO- IIB-CSG-2023-Order # 1254 |  | DXB0788 |  | DXB0788 | Nokia IXR-E | Migration | New CSG | Dewa/Sewa Power not available | XAD |  | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/56 | DXB-0788-CSG-IXR-E-1 |  | 5 |  |  |  |  | Required extra DCDU | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-17 12:30 |  | 25.254 | 55.3356 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1253 |  |  | DXN0994 |  | DXN0994 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-19 | DXB |  | DXB-2295-CSG-IXR-E-1 | 1/1/19 | DXB-2295-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-17 11:46 |  | 25.209988 | 55.345144 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1252 |  |  | DXN0991 |  | DXN0991 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-23 | DXB |  | DXB-2295-CSG-IXR-E-1 | 1/1/18 | DXB-2295-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-17 11:19 |  | 25.209988 | 55.345144 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1251 |  |  | DUB0729 |  | DUB0729 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-11-24 | DXB |  | DXB-DSO-CSG-IXR-E-2 | 1/1/12 | DXB-DSO-CSG-IXR-E-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-16 18:40 |  | 25.117133 | 55.389466 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1250 |  |  | SHJ1484 |  | SHJ1484 | Cisco NCS540 | BAU | New CSG | RFSed | XAD | 2023-08-31 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/22 | SHJ-1484-CSG-NS540-LD-1 | FOC2631N0DQ | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-23 | Y23-F105513 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-16 16:48 | SHJ_E3479A_10031_001001001 | 25.305053 | 55.469053 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1249 |  |  | DUB0408 |  | DUB0408 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-29 | DXB |  | DXB-PALMJ-CSG-IXR-E-1 | 1/1/11 | DXB-PALMJ-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-15 19:23 |  | 25.094449 | 55.149275 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1248 |  |  | AAN3431 |  | AAN3431 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-17 | AUH |  | AAN-2006-PREAGG-SR7-1 | Port 2/2/3 | AAN-2006-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-15 19:18 |  | 24.190977 | 55.698496 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1247 |  |  | AAN3254 |  | AAN3254 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-17 | AUH |  | AAN-2005-PREAGG-SR7-1 | Port 4/1/3 | AAN-2005-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-15 19:00 |  | 24.13463 | 55.69713 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1246 |  |  | AAN2005 |  | AAN2005 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-17 | AUH |  | AAN-2005-PREAGG-SR7-1 | Port 4/1/1 | AAN-2005-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-15 18:57 |  | 24.1709 | 55.711 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1245 |  |  | DXB3040 |  | DXB3040 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-08-29 | DXB | 10G | DXB-VH-SCSG-SR7B-1 | esat-1/1/29 | DXB-3040-CSG-NC540-LD-1 | FOC2633NLZ4 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-18 | Y23-F105150 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-15 13:07 | DXB_E3176D_11048_001001001 | 25.026262 | 55.237113 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1244 |  |  | DXN0435 |  | DXN0435 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-21 | DXB |  | DXB-ZAFRAN-SCSG-IXR-R6D-1 | 1/5/c11 | DXB-ZAFRAN-SCSG-IXR-R6D-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-15 10:50 |  | 25.1942 | 55.26956 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1243 |  |  | DUB0238 |  | DUB0238 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-08-17 | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/11 | DUB-0238-CSG-N540-LD-1 | FOC2624KML6 | [9 empty] | Y23-F104784 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-15 05:35 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1242 |  |  | IFU5623 |  | IFU5623 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-08-30 | FUJ |  | KLB-DC-SCSG-SR7B-1 | esat-1/1/53 | KLB-DC-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-14 18:19 |  | 25.035455 | 56.344165 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1241 |  |  | DXN0678 |  | DXN0678 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-15 | DXB |  | DXB-VILLAPOP-AGGR-SR12e-1 | Port 3/2/8 | DXB-VILLAPOP-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-14 16:20 |  | 25.098166 | 55.378616 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1240 |  |  | RAK2721 |  | RAK2721 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-16 | RAK |  | RAK-2026-SCSG-IXR-R6D-1 | Port 1/6/c20 | RAK-2026-SCSG-IXR-R6D-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-14 11:46 |  | 25.667127 | 55.970750 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1239 |  |  | FUJ3047 |  | FUJ3047 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-16 | FUJ |  | FUJ-2433-SCSG-SR7-1 | 5/1/1 | FUJ-2433-SCSG-SR7-1 | [6 empty] | site has existing 10GE passive patching as per the plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-14 11:42 |  | 24.79614 | 56.12281 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1238 |  |  | RAK3733 |  | RAK3733 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-17 | RAK |  | RAK-2026-SCSG-IXR-R6D-1 | Port 1/5/c9 | RAK-2026-SCSG-IXR-R6D-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-14 11:38 |  | 25.643190 | 55.954160 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1237 |  |  | KFN2625 |  | KFN2625 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-16 | FUJ |  | KFN-2115-SCSG-SR7-1 | Port 5/1/2 | KFN-2115-SCSG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-14 11:35 |  | 25.562900 | 56.20375 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1236 |  |  | AUH3238 |  | AUH3238 |  | 5G Upgrade |  | Passive Completed | HOI-MEA | 2023-10-04 | AUH | 10G | AUH-2999-CSG-SAR-8-1 | Port 1/1/5 | AUH-2999-CSG-SAR-8-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-08-12 10:36 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1235 |  |  | AUH2713 |  | AUH2713 |  | 5G Upgrade |  | Passive Completed | HOI-MEA |  | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | Port 1/3/5 | AUH-2713-PREAGG-SRa8-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-12 10:34 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1234 |  |  | AUH3934 |  | AUH3934 |  | 5G Upgrade |  | Passive Completed | HOI-MEA | 2023-08-31 | AUH | 1G | AUH-2019-CSG-IXR-E-1 | 1/1/15 | AUH-2019-CSG-IXR-E-1 |  | 5 |  |  |  |  | Fiber cable dropped near port for migration. | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-09 16:03 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1233 |  |  | AUH2530 |  | AUH2530 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-09-04 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-1/1/58 | AUH-2530-CSG-N540-LD-1 | FOC2638N26S | [9 empty] | Y23-F106524 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-09 16:02 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1232 |  |  | IAD5458B |  | IAD5458B |  | Migration |  | Passive Completed | HOI-MEA | 2023-08-30 | AUH | 1G | AUH-1222-SCSG-SR7B-1 | esat-1/1/26 | AUH-1222-SCSG-SR7B-1 |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-09 15:59 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1231 |  |  | AUH5458B |  | AUH5458B |  | Migration |  | Passive Completed | HOI-MEA | 2023-08-30 | AUH | 1G | AUH-1222-SCSG-SR7B-1 | esat-1/1/47 | AUH-1222-SCSG-SR7B-1 |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-09 15:58 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1230 |  |  | AUH2891 |  | AUH2891 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-09-21 | AUH | 10G | AUH-5002-AGGR-SR7-1 | Port 1/2/6 | AUH-2891-CSG-IXR-E-1 | NK224931222 | [9 empty] | Y23-F107913 |  | Nokia |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-09 15:56 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1229 |  |  | AUH2826 |  | AUH2826 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-08-30 | AUH | 10G | AUH-1437-SCSG-SR7B-1 | esat-1/1/46 | AUH-2826-CSG-N540-LD-1 | FOC2624KMGN | [9 empty] | Y23-F105127 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-09 15:55 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1228 |  |  | DUB0582 |  | DUB0582 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-08-24 | DXB | 1G | DXB-BV-SCSG-SR7B-1 | esat-1/1/48 | DXB-BV-SCSG-SR7B-1 |  | 5 | [13 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-09 13:14 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1227 |  |  | IDX5383 |  | IDX5383 |  | Migration |  | Passive Completed | HOI-MEA |  | DXB | 10G | DXB-2555 -CSG-N540-LD-1 | Gi0/0/0/8 | DXB-2555 -CSG-N540-LD-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-09 13:13 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1226 |  |  | DXB2555 |  | DXB2555 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-09-06 | DXB | 10G | DXB-DIC4-AGG-ASR9912-1 | Te0/2/0/6 | DXB-2555-CSG-N540-LD-1 | FOC2624KMCW | [9 empty] | Y23-F106244 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-09 13:11 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1225 |  |  | DXB3365 |  | DXB3365 | Nokia IXR-E | 5G Upgrade |  | RFSed | HOI-MEA | 2023-10-16 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-2 | 1/5/c6 | DXB-3365-CSG-IXR-E-1 | NK223134495 | [9 empty] | Y23-F107011 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-08-09 13:10 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1221 |  |  | AUH2442 |  | AUH2442 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-08-17 | AUH | 10G | AUH-1316-PREAGG-SR7-1 | 1/1/2 | AUH-2442-CSG-N540-LD-1 | FOC2624KM9P |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F104921 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-09 12:52 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1220 |  |  | AUH0082 |  | AUH0082 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-14 | AUH |  | AUH-6005-AGGR-SR12e-1 | esat-1/1/26 | AUH-6005-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-08 17:34 |  | 24.51403 | 54.38023 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1219 |  |  | AAN3273 |  | AAN3273 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-08-30 | AUH | 10G | AAN-2007-SCSG-SR7B-1 | esat-1/1/59 | AAN3273-CSG-NC540-LD-1 | FOC2624KMCD | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-24 | Y23-F105647 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-07 12:46 | AAN_E3668T_10005_001001001 | 24.256189 | 55.757117 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1218 |  |  | AAN2454 |  | AAN2454 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 2023-08-31 | AUH | 10G | AAN-2065-PREAGG-SR7-1 | Port 4/1/3 | AAN-2454-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-30 | Y23-F106240 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-07 12:36 |  | 24.22546 | 55.76017 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1217 |  |  | AUH0077 |  | AUH0077 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-10 | AUH |  | AUH-1093-PREAGG-SR7-1 | Port 3/2/4 | AUH-1093-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-07 12:14 |  | 24.429425 | 54.43737 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1216 |  |  | DUB0226 |  | DUB0226 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-07 | DXB |  | DXB-1346-CSG-IXR-E-1 | Port 1/1/11 | DXB-1346-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-07 11:54 |  | 25.296503 | 55.367843 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1215 |  |  | FUJ2159 |  | FUJ2159 | Cisco NCS540 | 5G Upgrade |  | RFSed | HOI-MEA | 2023-09-06 | FUJ | 10G | FUJ-2437-SCSG-SR7-1 | Port 3/1/1 | FUJ-2159-CSG-N540-LD-1 | FOC2624KNQ1 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F105612 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-07 08:15 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1214 |  |  | AUH3269 |  | AUH3269 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-09-13 | AUH | 10G | AUH-6501-AGGR-SR12e-2 | Port 7/1/14 | AUH-3269-CSG-N540-LD-1 | FOC2633NLXZ | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-08 | Y23-F107059 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-05 13:46 | AUH_E2469L_10594_001001001 | 24.342215 | 54.512219 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1213 |  |  | AUH3192 |  | AUH3192 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-11-01 | AUH | 10G | AUH-2205-PREAGG-SR7-1 | Port 3/1/4 | AUH-3192-CSG-NC540-LD-1 | FOC2633NLZK | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-09 | Y23-F107136 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 13:42 | AUH_E2470U_10954_001001001 | 24.3987 | 54.48773 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1212 |  |  | AUH3267 |  | AUH3267 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-09-27 | AUH | 10G | AUH-6501-AGGR-SR12e-1 | 2/1/24 | AUH-3267-CSG-NC540-LD-1 | FOC2633NBXL |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-09-23 | Y23-F108143 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 13:37 | AUH_E2469F_11163_001001001 | 24.366813 | 54.492109 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1211 | WO- IIB-CSG-2023-Order # 1211 |  | IAD5401 |  | IAD5401 | Passive | Migration | Passive patching | Site Not Ready | XAD |  | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-2/1/36 | AUH-6003-AGGR-SR7B-1 |  | 5 |  |  |  |  | site not ready- IAD5401 is 2023 DAS Scope | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 13:34 |  | 24.485358 | 54.352898 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1210 |  |  | IAD5736 |  | IAD5736 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-09-18 | AUH |  | AUH-1437-SCSG-SR7B-1 | esat-1/1/43 | AUH-1437-SCSG-SR7B-1 | [6 empty] | passive complted - XAD team for migration | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 13:30 |  | 24.5027 | 54.6523 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1209 | WO- IIB-CSG-2023-Order # 1209 |  | AAN3607 |  | AAN3607 | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | AUH | 10G | AAN-2305-AGGR-SR7B-1 | esat-1/1/7 | AAN-3607-CSG-NS540-LD-1 | FOC2624KNPP | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-28 | Y23-F105939 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 13:24 | AAN_E3866Q_10001_001001001 | 24.06622 | 55.89289 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1208 |  |  | IAD5774 |  | IAD5774 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-11 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-1/1/44 | AUH-1336-SCSG-SR7B-1 | [6 empty] | migration to be done by XAD | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 13:16 |  | 24.468658 | 54.372762 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1207 | WO- IIB-CSG-2023-Order # 1207 |  | AAN3615 |  | AAN3615 | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | AUH | 10G | AAN-2305-AGGR-SR7B-1 | esat-1/1/8 | AAN-3615-CSG-N540-LD-1 | FOC2624KNPE | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-26 | Y23-F105869 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-05 12:56 | AAN_E3866R_10001_001001001 | 24.08223 | 55.91791 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1206 |  |  | AUH6567 |  | AUH6567 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-08-10 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | esat-1/1/20 | AUH-6567-CSG-N540-LD-1 | FOC2624KMEV |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F104463 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-03 10:14 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1205 |  |  | AUH6564 |  | AUH6564 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-08-10 | AUH | 10G | AUH-1405-PREAGG-SR7-1 | 5/1/5 | AUH-6564-CSG-N540-LD-1 | FOC2624KNR9 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F104464 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-03 10:12 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1204 |  |  | AUH6565 |  | AUH6565 | Cisco NCS540 | SRAN + 5G |  | RFSed | HOI-MEA | 2023-08-10 | AUH |  | AUH-2562-SCSG-SR7B-1 | esat-1/1/55 | AUH-6565-CSG-N540-LD-1 | FOC2624KNPK |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F104462 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-03 10:10 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1203 |  |  | AUH6387 |  | AUH6387 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-12-06 | AUH |  | AUH-2928-CSG-IXR-E-1 | 1/1/12 |  |  |  |  | 1 | 1 | [10 empty] | FALSE | 2023 | Syed Shahzaib | 2023-08-03 10:08 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1202 |  |  | AUH2762 |  | AUH2762 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-08-10 | AUH | 10G | AUH-2937-PREAGG-SR7-1 | 2/2/2 | AUH-2762-CSG-N540-LD-1 | FOC2624KMEM | [9 empty] | Y23-F104461 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-08-03 10:06 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1201 |  |  | DUB0453 |  | DUB0453 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-05 | DXB | 1G | DXB-2324-CSG-IXR-E-1 | 1/1/15 | DXB-2324-CSG-IXR-E-1 |  |  | 0 | 1 | 1 |  | Site re assigned to XAD by Mr. Tasif Maqbool. 8-2-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-08-02 13:31 |  | 25.097778 | 55.386556 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1200 |  |  | AUH3602 |  | AUH3602 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-08-30 | AUH | 10G | AUH-2908-PREAGG-SR7-1 | Port 2/2/2 | AUH-3602-CSG-N540-LD-1 | FOC2624KMRG | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-08-19 | Y23-F105230 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-02 12:39 | AUH_E1366D_10295_001001001 | 24.0854111 | 53.4777389 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1199 |  |  | AUH3447 |  | AUH3447 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-24 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-1/1/48 5G and esat-2/1/18 (3G/LTE - 1G SFP) | AUH-1336-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-02 12:14 |  | 24.4534 | 54.38346 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1198 |  |  | AUH3596 |  | AUH3596 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-08-04 | AUH |  | AUH-2919-CSG-SAR-8-1 | Port 1/2/5 | AUH-2919-CSG-SAR-8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-08-02 11:34 |  | 24.05801 | 51.7513 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1197 |  |  | SHJ0078 |  | SHJ0078 | Passive | Parity | Passive patching | Passive Completed | SHAHID |  | SHJ |  | SHJ-2084-SCSG-SR7B-1 | esat-3/1/8 | SHJ-2084-SCSG-SR7B-1 |  |  | 0 | 1 | 1 | 0 | Kindly be informed that the patching completed till MDF Room as GSM Room still not confirmed.. |  |  | 2023-05-12 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-08-02 10:30 |  | 25.3331 | 55.3745 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1196 |  |  | IAD0986A |  | IAD0986A | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-09-04 | AUH | 1G | AUH-6501-AGGR-SR12e-1 | Port 3/1/17 | IAD-0986A-CSG-IXR-E-1 | NK231134431 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-04 | Y23-F106605 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-08-01 10:02 | AUH_E2367J_10002_001001003 | 24.191309 | 54.470860 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1195 |  |  | DXB1428 |  | DXB1428 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | SHAHID | 2023-12-08 | DXB | 10G | DXB-1583-SCSG-IXR-R6-1 | 1/6/8 | DXB-1428-CSG-IXR-E-1 | NK224931405 |  |  | 4 | 4 | 4 | Site Completed |  |  | 2023-12-07 | Y23-F113103 |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-27 12:52 | DXB_E3076O_10372_001001001 | 24.9937 | 55.1608 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1194 |  |  | DUB0238 |  | DUB0238 | Cisco NCS540 | Rollout | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/11 | DXB-DIFC-ER4-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Site re assigned to XAD by Mr. Tasif Maqbool. 8-2-2023 | [5 empty] | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-27 11:59 |  | 25.227533 | 55.291261 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1193 |  |  | ISH5039 |  | ISH5039 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-10-12 | SHJ |  | SHJ-2580-SCSG-SR7B-1 | esat-2/1/62 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | new passive link | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-26 13:03 |  | 25.314102 | 55.377229 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1192 |  |  | DXN0220 |  | DXN0220 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-22 | DXB |  | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/6 | DXB-BB-SCSG-NCS57C3-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-26 11:36 |  | 25.180892 | 55.252723 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1191 |  |  | DXN0218 |  | DXN0218 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-09-22 | DXB |  | DXB-BB-SCSG-NCS57C3-1 | TF0/0/0/5 | DXB-BB-SCSG-NCS57C3-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-26 11:34 |  | 25.180892 | 55.252723 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1190 | WO- IIB-CSG-2023-Order # 1190 |  | DXB5291F |  | DXB5291F |  | Rollout |  | OSP Issue | HOI-MEA |  | DXB |  | AUH-5005-CSG-SAR-8-1 | 1/3/4 | AUH-5005-CSG-SAR-8-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-07-26 11:14 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1189 |  |  | DXB3051 |  | DXB3051 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-07-28 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | 1/3/c7 | DXB-3051-CSG-N540-LD-1 | FOC2624KMG2 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-26 | Y23-F103494 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-24 16:43 | DXB_E3478R_10367_001001001 | 25.153867 | 55.505525 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1188 |  |  | DXB0038 |  | DXB0038 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | DXB | 1G | DXB-0296A-PREAGG-SR7-1 | 3/2/9 | DXB-0296A-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | cancelled from XAD 9-11-2023. To be served through MW due to high Fiber cost | [5 empty] | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-24 12:03 |  | 25.237903 | 55.386027 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1187 |  |  | DUB0775 |  | DUB0775 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-1828-PREAGG-SR7-1 | 3/2/10 | DXB-1828-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-28 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-24 11:35 |  | 25.268722 | 55.379140 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1186 |  |  | IAJ5866 |  | IAJ5866 |  | SRAN + 5G |  | Passive Completed | HOI-MEA | 2023-08-15 | SHJ | 1G | SHJ-2033-IBS-SAR-8-1 | Port 1/3/5 | SHJ-2033-IBS-SAR-8-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-07-18 15:46 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1185 |  |  | DXB1836 |  | DXB1836 | Cisco NCS540 | 5G Upgrade |  | RFSed | HOI-MEA | 2023-08-04 | DXB | 10G | DXB-MIRDIFPOP-SCSG-NCS57C3-2 | TF0/0/0/5 | DXB-1836-CSG-N540-LD-1 | FOC2631N0DP | [9 empty] | Y23-F103888 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-07-18 15:42 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1184 |  |  | RAK3192 |  | RAK3192 | Nokia IXR-E | Rollout | New CSG | Cancelled/on Hold |  |  | RAK | 1G | RAK-2727-PREAGG-SR7-1 | Port 3/2/10 | RAK-3192-CSG-IXR-E-1 | [6 empty] | site has existing CSG IXR-E | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-18 14:33 |  | 26.034312 | 56.103500 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1183 |  |  | DXB1734 |  | DXB1734 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-07-28 | DXB | 10G | DXB-DFC-SCSG-SR7B-1 | esat-1/1/4 | DXB-1734-CSG-N540-LD-1 | FOC2633NLYL | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-27 | Y23-F103542 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-07-18 13:20 | DXB_E3278E_10231_001001001 | 25.216778 | 55.355481 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1182 |  |  | AAN3417 |  | AAN3417 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-10-02 | AUH | 1G | AAN-2302-SCSG-IXR-R6D-1 | 1/5/c6/1 | AAN-3417-CSG-IXR-E-1 | NK224931200 | [9 empty] | Y23-F107655 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-07-17 11:38 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1181 |  |  | AAN3361 |  | AAN3361 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-08-30 | AUH | 10G | AAN-2302-PREAGG-SR7-1 | Port 5/1/4 | AAN-3361-CSG-N540-LD-1 | FOC2633NBXV | [9 empty] | Y23-F105381 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-07-17 11:36 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1180 |  |  | AUG6088 |  | AUG6088 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-08-31 | AUH | 1G | AUH-2836-PREAGG-SR7-1 | Port 2/1/20 | AUG-6088-CSG-N540-LD-1 | FOC2624KNP7 | [9 empty] | Y23-F106242 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-07-17 11:35 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1179 |  |  | AUH6427 |  | AUH6427 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-09-01 | AUH | 1G | AUH-2836-PREAGG-SR7-1 | Port 3/2/19 | AUH-6427-CSG-N540-LD-1 | FOC2624KNPV | [9 empty] | Y23-F106243 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-07-17 11:32 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1176 |  |  | AUH0080 |  | AUH0080 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-19 | AUH |  | AUH-2713-PREAGG-SRa8-1 | Port 2/2/21 | AUH-2713-PREAGG-SRa8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-15 10:44 |  | 24.15534 | 54.425250 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1175 |  |  | DUB0989 |  | DUB0989 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-20 | DXB |  | DXB-JI-POP-SCSG-IXR-R6-1 | Port 1/5/8 | DXB-JI-POP-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-15 10:27 |  | 25.060628 | 55.141583 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1174 |  |  | DUB0232 |  | DUB0232 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-20 | DXB |  | DXB-JI-POP-SCSG-IXR-R6-1 | Port 1/5/7 | DXB-JI-POP-SCSG-IXR-R6-1 |  | 5 |  |  |  |  | additional fiber termination completed Feb-8-2024 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-15 10:22 |  | 25.060628 | 55.141583 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1173 | WO- IIB-CSG-2023-Order # 1173 |  | IAD5906 |  | IAD5906 | Passive | Migration | Passive patching | Site Not Ready | XAD |  | AUH |  | AUH-6003-AGGR-SR7B-2 | esat-1/1/33 | AUH-6003-AGGR-SR7B-2 |  | 5 |  |  |  |  | IAD5906 not in the DAS plan this year - Hatel Attala | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-13 14:43 |  | 24.469574 | 54.342621 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1172 |  |  | AUH6399 |  | AUH6399 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2024-01-24 | AUH | 10G | AUH-2908-PREAGG-SR7-1 | Port 5/1/1 | AUH-6399-CSG-IXR-E-1 | NK224931363 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2024-01-22 | Y23-F115834 |  | XAD |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-13 14:38 | AUH_E1366I_10305_001001001 | 24.07773 | 53.47435 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1171 |  |  | AUH6398 |  | AUH6398 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-10-24 | AUH | 10G | AUH-2908-PREAGG-SR7-1 | Port 2/2/4 | AUH-6398-CSG-N540-LD-1 | FOC2633NM2L | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-04 | Y23-F108903 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-13 14:33 | AUH_E1366E_10702_001001001 | 24.0913 | 53.5004 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1170 |  |  | AUH3259 |  | AUH3259 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-09-27 | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | Port 1/5/c16 | AUH-3259-CSG-N540-LD-1 | FOC2631N0EA |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-09-23 | Y23-F108179 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-13 14:29 | AUH_E2767G_10001_001001001 | 24.18866 | 54.812009 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1169 |  |  | AUH3260 |  | AUH3260 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-09-22 | AUH | 10G | AUH-2674-SCSG-IXR-R6D-1 | Port 1/5/c5 | AUH-3260-CSG-N540-LD-1 | FOC2626N012 |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-09-21 | Y23-F108004 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-13 14:06 | AUH_E2767I_10001_001001001 | 24.194608 | 54.849606 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1168 |  |  | AUH2063 |  | AUH2063 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-08-09 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/17 | AUH-2063-CSG-N540-LD-1 | FOC2633NLYX | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-24 | Y23-F103280 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-07-13 13:45 | AUH_E2270I_12338_001001001 | 24.45162 | 54.36516 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1167 |  |  | AUH2320 |  | AUH2320 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-08-09 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/16 | AUH-2320-CSG-IXR-E-1 | NK22403B809 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-19 | Y23-F103014 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-07-13 13:38 | AUH_E2270E_12850_001001001 | 24.4687 | 54.3706 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1166 |  |  | DXN0363 |  | DXN0363 | Passive |  |  | Passive Completed | HOI-MEA | 2023-07-16 | DXB |  | DXB-DSO-CSG-IXR-E-1 | 1/1/15 | DXB-DSO-CSG-IXR-E-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-07-13 13:16 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1163 |  |  | AUH0408 |  | AUH0408 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2024-02-02 | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/2 | AUH-0408-CSG-N540-LD-1 | FOC2718N5DF | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2024-01-22 | Y23-F115835 |  | XAD |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-12 23:39 | AUH_E2370S_10419_001001001 | 24.418397 | 54.448117 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1162 |  |  | IAD5415 |  | IAD5415 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-25 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | esat-1/1/11 | IAD-5415-CSG-N540-LD-1 | FOC2624KME8 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-24 | Y23-F103246 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-12 23:36 | AUH_E2271X_10364_001001001 | 24.49071 | 54.3587562 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1161 |  |  | IAD5847 |  | IAD5847 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-24 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | esat-1/1/10 | IAD-5847-CSG-N540-LD-1 | FOC2624KMET |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-24 | Y23-F103230 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-12 23:33 | AUH_E2271Y_11314_001001001 | 24.493988 | 54.377973 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1160 |  |  | IAD5758 |  | IAD5758 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-25 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | esat-1/1/9 | IAD-5758-CSG-N540-LD-1 | FOC2624KMZB |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-22 | Y23-F103162 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-12 23:30 | AUH_E2271Y_11462_001001001 | 24.493946 | 54.375843 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1159 |  |  | IAD5383 |  | IAD5383 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-09-11 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 7/1/28 | IAD-5383-CSG-N540-LD-1 | FOC2624KMC1 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-08-02 |  |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-12 23:26 | AUH_E2371U_10045_001001001 | 24.491126 | 54.385512 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1158 | WO- IIB-CSG-2023-Order # 1158 |  | IAD5839 |  | IAD5839 | Cisco NCS540 | SRAN + 5G | New CSG | Transmission rack not available | SHAHID |  | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 7/1/27 | IAD-5839-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | Site will be RFM and Power Forecast will be Feb 2024 as per mail on 30/11/2023 from Mr Ireneo | [5 empty] | Cisco |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-12 23:23 |  | 24.490377 | 54.360944 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1157 |  |  | IAD5441 |  | IAD5441 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-09-07 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 7/1/26 | IAD-5441-CSG-N540-LD-1 | FOC2624KNQD |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-22 | Y23-F103165 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-12 23:20 | AUH_E2271Y_11347_001020005 | 24.487297 | 54.373086 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1156 |  |  | DUB0689 |  | DUB0689 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-18 | DXB | 1G | DXB-VH-SCSG-SR7B-1 | esat-1/1/49 | DXB-VH-SCSG-SR7B-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-11 10:51 |  | 25.067516 | 55.209901 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1155 |  |  | AUH6123 |  | AUH6123 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | XAD | 2023-08-08 | AUH | 10G | AUH-2118-SCSG-SR7B-1 | esat-1/1/45 | AUH-6123-CSG-IXR-E-1 | NK22403B795 | [5 empty] | integrated | Rogelio Pangilinan;#1712 |  | 2023-08-07 | Y23-F104278 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-11 10:30 | AUH_E2469M_10531_001001001 | 24.344307 | 54.532692 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1154 |  |  | DUB0065 |  | DUB0065 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-12 | DXB |  | DXB-6501-SCSG-NCS57C3-1 | TF0/0/0/5 | DXB-6501-SCSG-NCS57C3-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-10 18:05 |  | 25.070584 | 55.13307 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1153 |  |  | ISH5109 |  | ISH5109 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-07-13 | SHJ |  | SHJ-2058-SCSG-IXR-R6-1 | Port 1/6/8 | SHJ-2058-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-07-10 17:42 |  | 25.353835 | 55.390556 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1152 |  |  | AJM0803 |  | AJM0803 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-1/1/59 | AJM-6001-SCSG-SR7B-1 |  |  |  | 1 | 1 | 1 | site cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-10 10:52 |  | 25.40766 | 55.44497 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1151 |  |  | UAQ3861 |  | UAQ3861 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-08-01 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/39 | UAQ-3861-CSG-N540-LD-1 | FOC2616NXZZ |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-28 | Y23-F103617 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-10 10:42 | UAQ_E3582Q_10013_001001001 | 25.5151 | 55.5828 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1150 |  |  | DUB0410 |  | DUB0410 |  | Rollout |  | Passive Completed | HOI-MEA | 2023-07-24 | DXB |  | DXB-MIRDIFPOP-SCSG-NCS57C3-1 | TF0/0/0/5 | DXB-MIRDIFPOP-SCSG-NCS57C3-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-07-10 10:30 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1148 |  |  | RAK3240 |  | RAK3240 | Cisco NCS540 |  |  | RFSed | HOI-MEA | 2023-08-28 | RAK | 10G | RAK-2026-SCSG-SR7-1 | Port 2/1/9 | RAK-3240-CSG-N540-LD-1 | FOC2624KNPC | [9 empty] | Y23-F105363 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-07-10 10:25 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1147 |  |  | DXN0772 |  | DXN0772 |  |  |  | Passive Completed | HOI-MEA | 2023-07-10 | DXB |  | DXB-2295-SCSG-IXR-R6D-1 | 1/5/c16 | DXB-2295-SCSG-IXR-R6D-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-07-10 10:22 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1146 |  |  | AUH3982 |  | AUH3982 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-07-18 | AUH | 10G | AUH-2674-PREAGG-SR7-1 | Port 3/2/10 | AUH-3982-CSG-IXR-E-1 | NK22403B771 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-18 | Y23-F102889 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-08 17:55 | AUH_E2770S_10002_001001001 | 24.41834 | 54.85376 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1145 |  |  | DXB2809 |  | DXB2809 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-07-20 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-1 | esat-1/1/40 | DXB-2809-CSG-IXR-E-1 | NK22403B807 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-18 | Y23-F102891 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-08 10:51 | DXB_E3277T_10654_001001001 | 25.068409 | 55.353474 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1144 |  |  | DXB3693 |  | DXB3693 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-07-19 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-2 | 1/3/c7 | DXB-3693-CSG-N540-LD-1 | FOC2631N0D6 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-14 | Y23-F102713 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-08 10:48 | DXB_E3479R_10023_001001001 | 25.242086 | 55.511967 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1143 |  |  | AJM2321 |  | AJM2321 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | XAD | 2023-09-22 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat 2/1/49 | AJM-2321-CSG-IXR-E-1 | NK22403B767 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-09-08 | Y23-F107012 |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-08 10:44 | AJM_E3381T_13921_001001001 | 25.420141 | 55.451511 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1142 |  |  | IAD5742 |  | IAD5742 | Cisco NCS540 | BAU | New CSG | RFSed | SHAHID | 2023-08-14 | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 2/1/19 | IAD-5742-CSG-N540-LD-1 | FOC2624KMJB |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-18 | Y23-F102915 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-08 09:25 | AUH_E1562Y_10620_001001001 | 23.657922 | 53.699239 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1138 |  |  | DXB1033 |  | DXB1033 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-20 | DXB | 10G | DXB-DFC-SCSG-SR7B-1 | esat-1/1/3 | DXB-1033-CSG-N540-LD-1 | FOC2624KND0 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-17 | Y23-F102861 |  | Cisco |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-07 09:42 | DXB_E3379U_12324_001001001 | 25.224183 | 55.369266 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1137 |  |  | DUB0277 |  | DUB0277 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-6004-AGGR-SR12e-1 | Port 8/1/10 | DXB-6004-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-05 |  |  | Nokia |  |  | FALSE | 2023 | Munaim Abdul salam | 2023-07-04 15:27 |  | 25.132877 | 55.190144 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1136 |  |  | AUH2716 |  | AUH2716 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-07-13 | AUH | 10G | AUH-2713-PREAGG-SRa8-1 | Port 1/3/4 | AUH-2716-CSG-IXR-E-1 | NK22403B752 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-12 | Y23-F102580 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-04 10:24 | AUH_E1955F_10001_001001001 | 24.20244 | 54.46275 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1134 |  |  | AUH6182 |  | AUH6182 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-07-27 | AUH | 10G | AUH-2929-PREAGG-SRa8-1 | Port 2/1/9 | AUH-6182-CSG-IXR-E-1 | NK22403B788 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-10 | Y23-F102354 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-03 18:32 | AUH_E1955F_10001_001001001 | 23.08757 | 54.04193 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1133 |  |  | AUH2799 |  | AUH2799 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-07-25 | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/20 | AUH-2799-CSG-IXR-E-1 | NK22403B829 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-24 | Y23-F103210 |  | Nokia |  |  | TRUE | 2023 | Munaim Abdul salam | 2023-07-03 18:30 | AUH_E2469O_10179_001001001 | 24.3423608031 | 54.5768342679 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1132 |  |  | IAD5667 |  | IAD5667 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-11 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 2/1/4 | IAD-5667-CSG-N540-LD-1 | FOC2633NBX0 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-08 | Y23-F102333 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-07-03 11:07 | AUH_E2271X_10654_001001002 | 24.490277 | 54.359818 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1130 |  |  | FUJ3709 |  | FUJ3709 | Passive to CSG | Migration | New CSG | RFSed | XAD | 2023-07-25 | FUJ | 10G | FUJ-6001-AGG-ASR9912-1 | TenGigE0/1/0/40 | FUJ-3709-CSG-N540-LD-1 | FOC2624KMDJ |  | 0 | 1 | 1 | 0 | passive changed to CSG | Rogelio Pangilinan;#1712 |  | 2023-07-20 | Y23-F103076 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-23 12:57 | FJR_E4278T_10577_001010001 | 25.15429 | 56.3434 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1129 |  |  | DXB3132 |  | DXB3132 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2023-07-17 | DXB | 10G | DXB-1069-SCSG-SR7B-1 | esat-2/1/5 | DXB-3132-CSG-IXR-E-1 | NK223134571 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-07-06 | Y23-F102117 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-21 11:52 | DXB_E3177L_10276_001001001 | 25.083200° | 55.186400° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1128 |  |  | IDX0952B |  | IDX0952B | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-3155-PREAGG-SR7-1 | Port 2/1/15 | DXB-3155-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-03 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-20 09:23 |  | 25.152385 | 55.290527 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1127 |  |  | IDX0952A |  | IDX0952A | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-3155-PREAGG-SR7-1 | Port 2/1/10 | DXB-3155-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-03 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-20 09:21 |  | 25.152385 | 55.290527 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1126 |  |  | IDX0981B |  | IDX0981B | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-3121-SCSG-SR7B-1 | esat-1/1/12 ,esat-1/1/13 | DXB-3121-SCSG-SR7B-1 |  |  |  | 2 | 2 |  | Site Completed |  |  | 2023-07-12 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-20 09:19 |  | 25.372407 | 55.372407 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1125 |  |  | IDX5593 |  | IDX5593 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-14 | DXB | 10G | DXB-2583-SCSG-SR7B-1 | esat-2/1/14 | IDX-5593-CSG-N540-LD-1 | FOC2638N262 |  |  | 1 | 1 |  | Site Completed |  |  |  | Y23-F102383 |  | Cisco |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-20 09:10 | DXB_E29750_10007_001002001 | 24.897238 | 55.061543 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1124 |  |  | IDX5188 |  | IDX5188 | Passive to CSG | Migration | New CSG | RFSed | SHAHID | 2023-07-04 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/55 | IDX-5188-CSG-N540-LD-1 | FOC2638N28L |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-26 | Y23-F101728 |  | Cisco |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-20 08:30 | DXB_E3279M_11426_001010001 | 25.259713 | 55.318637 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1123 |  |  | DXN0335 |  | DXN0335 | Passive to CSG | Migration | New CSG | RFSed | SHAHID | 2023-07-04 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/58 | DXN-0335-CSG-N540-LD-1 | FOC2633NBXQ |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-26 | Y23-F101723 |  | Cisco |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-20 08:27 | DXB_E3279N_10854_001001001 | 25.258198 | 55.323666 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1122 |  |  | DXB5291J |  | DXB5291J | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | AUH-5005-CSG-SAR-8-1 | 1/3/3 | AUH-5005-CSG-SAR-8-1 | [6 empty] | Site Completed |  |  | 2023-07-17 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-19 15:36 |  | 24.911322 | 54.910733 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1121 |  |  | IDX0938E |  | IDX0938E | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-DGPOP1-CSG-IXR-E-1 | 1/1/8 | DXB-DGPOP1-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-04 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-19 15:12 |  | 25.022009 | 55.130048 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1120 |  |  | AUH3010 |  | AUH3010 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-06-23 | AUH | 10G | AUH-5004-SCSG-SR7B-1 | esat-2/1/29 | AUH-5004-SCSG-SR7B-1 | INL2446A1P2 |  | 0 | 1 | 1 | 1 | Site Completed |  |  | 2023-06-19 | Y23-F101387 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-17 17:08 | AUH_E2772R_10209_001001001 | 24.59693 | 54.81899 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1119 |  |  | UAQ3132 |  | UAQ3132 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | SHAHID | 2023-08-18 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/11, | UAQ-3132-CSG-IXR-E-1 | NK224632180 |  | 0 | 1 | 1 | 1 | Site Completed |  |  | 2023-06-26 | Y23-F101727 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-16 18:24 | UAQ_E3581C_10075_001001001 | 25.4756 | 55.6143 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1118 |  |  | RAK1278 |  | RAK1278 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-07-17 | RAK | 10G | RAK-6001-AGGR-SR7S-2 | esat-1/1/51 | RAK-1278-CSG-N540-LD-1 | FOC2624KMDU | 3 | [7 empty] | 2023-07-07 | Y23-F102269 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-16 10:52 | RKT_E3985O_10004_001001001 | 25.806717 | 56.046554 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1117 |  |  | IAJ5870 |  | IAJ5870 | Passive | BAU | Passive patching | Cancelled/on Hold | SHAHID |  | AJM | 1G | AJM-2450-SCSG-SR7B-1 | esat-1/1/57 | AJM-2450-SCSG-SR7B-1 |  |  | 0 | 1 | 1 | 1 | Once site ready Mr. Deecree will notify , Mail received from Deecree Omas <Deecree.Omas@du.ae> on 04/07/2023 , Same update in Poral | [5 empty] | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-15 13:38 |  | 25.391619 | 55.573781 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1116 |  |  | SHJ3553 |  | SHJ3553 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-06-23 | SHJ | 10G | SHJ-2053-AGGR-SR7B-1 | esat-1/1/14 | SHJ-2053-AGGR-SR7B-1 | OPM260306N0 |  | 0 | 1 | 1 | 1 | Site Completed |  |  | 2023-06-17 | Y23-F101118 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-14 15:32 | SHJ_E3479H_10007_001001001 | 25.2859494 | 55.5200589 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1115 |  |  | UAQ1247 |  | UAQ1247 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-07-04 | UAQ | 10G | UAQ-DC-AGGR-SR7S-1 | esat-2/1/7 | UAQ-DC-AGGR-SR7S-1 | FOC2614N0JN |  | 0 | 1 | 1 | 1 | Site Completed |  |  | 2023-06-24 | Y23-F101622 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-14 15:30 | UAQ_E3582P_10003_001001001 | 25.5224340019324 | 55.5723145164787 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1114 |  |  | IUA5752 |  | IUA5752 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | UAQ | 10G | NE510 (UAQ2012-UAQDC) | UAQ2012_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#B2 OTN RK-1/NE510 C/03/TX14/RX14 | [7 empty] | site has existing cisco NCS540 CSG already | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-06-13 19:27 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1112 |  |  | DXB2349 |  | DXB2349 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-06-22 | DXB | 10G | DXB-BB-AGGR-SR12e-1 | esat-1/1/25 | DXB-2349-CSG-N540-LD-1 | FOC2631N0EJ | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-06-17 | Y23-F101116 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-13 13:06 | DXB_E3278M_10338_001001001 | 25.1778 | 55.3081 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1111 |  |  | DXN0465 |  | DXN0465 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-1866-SCSG-IXR-R6-1 | 1/4/3 | DXB-1866-SCSG-IXR-R6-1 | [6 empty] | Site Completed |  |  | 2023-06-22 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-12 16:04 |  | 25.291432 | 55.403432 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1110 |  |  | AJM0938 |  | AJM0938 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-07 | AJM | 10G | AJM-2459-PREAGG-SR7-1 | esat-2/1/20 | AJM-0938-CSG-N540-LD-1 | FOC2614N0H9 |  | 0 | 1 | 1 |  | Site Completed |  |  | 2023-07-04 | Y23-F102021 |  | Cisco |  |  | TRUE | 2023 | Sami Ullah | 2023-06-12 16:01 | AJM_E3481K_10181_001001001 | 25.436476 | 55.464558 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1109 |  |  | DUB0399 |  | DUB0399 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-BV-SCSG-SR7B-1 | esat-1/1/47 | DXB-BV-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-19 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-12 15:37 |  | 25.2603 | 55.3212 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1108 |  |  | DUB0697 |  | DUB0697 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-BV-SCSG-SR7B-1 | esat-1/1/42 | DXB-BV-SCSG-SR7B-1 |  |  |  | 1 |  |  | Site Completed |  |  | 2023-06-19 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-12 14:03 |  | 25.261309 | 55.319017 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1107 |  |  | FUJ5700D |  | FUJ5700D | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | FUJ | 1G | FUJ-6001-CSG-ASR920-LD-1 | Gi0/0/11 | FUJ-6001-CSG-ASR920-LD-1 |  |  | 0 | 1 | 1 |  | Site Completed |  |  | 2023-06-13 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-12 12:32 |  | 25.125725 | 56.327296 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1106 |  |  | DXB3411 |  | DXB3411 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-06-19 | DXB | 1G | DXB-2302-PREAGG-SR7-1 | 3/2/8 | DXB-2302-PREAGG-SR7-1 | FNS18451XCP |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-15 | Y23-F100979 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-12 11:32 | DXB_E3378U_10015_001001001 | 25.13227 | 55.363344 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1105 |  |  | SHJ1146 |  | SHJ1146 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-06-23 | SHJ | 10G | AJM-2459-SCSG-SR7B-1 | esat-2/1/19 | SHJ-1146-CSG-N540-LD-1 | FOC2633NBZ1 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-06-17 | Y23-F101103 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-12 11:10 | SHJ_E3481E_10002_001001001 | 25.47335 | 55.540311 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1104 |  |  | IAD5513 |  | IAD5513 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | AUH |  | AUH-6005-AGGR-SR12e-2 | 3/2/20 | AUH-6005-AGGR-SR12e-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2022-11-09 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-10 12:05 |  | 24.50322, | 54.376525 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1103 |  |  | DXN0274 |  | DXN0274 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-1117-CSG-IXR-E-1 | 1/1/15 3G 1/1/18 LTE | DXB-1117-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2022-11-07 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-10 12:01 |  | 25.2436 | 55.2805 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1102 |  |  | IDX5213 |  | IDX5213 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-1613-CSG-IXR-E-1 | 1/1/14 3G 1/1/15 LTE | DXB-1613-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2022-07-28 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-10 11:57 |  | 25.2178 | 55.3709 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1101 |  |  | AUH0660 |  | AUH0660 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | AUH |  | AUH-0950-CSG-IXR-E-1 | 1/1/16 | AUH-0950-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2022-12-07 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-10 11:53 |  | 24.8592124 | 54.3844948 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1100 |  |  | DXN0871 |  | DXN0871 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-1613-CSG-IXR-E-1 | 1/1/8 | DXB-1613-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2022-12-28 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-10 11:49 |  | 25.233330 | 55.353994 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1099 |  |  | ISH5024 |  | ISH0024 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-12 | SHJ |  | SHJ-2016-SCSG-SR7B-1 | esat-1/1/24 | SHJ-2016-SCSG-SR7B-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-10 11:45 |  | 25.329529 | 55.391971 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1098 |  |  | DXN0870 |  | DXN0870 | Passive | Rollout | Passive patching | Passive Completed | SHAHID |  | DXB |  | DXB-1156-PREAGG-SR7-1 | PORT:4/1/11 | DXB-1156-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-01-02 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-09 17:37 |  | 25.11121, | 55.1958 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1094 |  |  | AUH2137 |  | AUH2137 | Passive | 5G Upgrade | Passive patching | Passive Completed | SHAHID |  | AUH | 10G | AUH-5002-AGGR-SR7-1 | Port 1/2/5 | AUH-5002-AGGR-SR7-1 |  |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-06-12 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-09 11:39 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1090 |  |  | AUH2223 |  | AUH2223 | Passive | 5G Upgrade | Passive patching | Passive Completed | SHAHID |  | AUH | 10G | AUH-2223-PREAGG-SR7-1 | Port 1/1/4 | [6 empty] | 1 | Site Completed |  |  | 2023-06-12 |  |  | Nokia |  |  | FALSE | 2023 | Sami Ullah | 2023-06-09 11:23 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1088 |  |  | ISH5229 |  | ISH5229 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-07-25 | SHJ |  | SHJ-2049-AGGR-SR7b-1 | 3/1/9 | SHJ-2049-AGGR-SR7b-1 |  |  |  | 1 | 1 |  | port has been change as assigned port is used | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-09 10:47 |  | 25.32168 | 55.483134 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1087 |  |  | DXB1587 |  | DXB1587 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | XAD | 2023-06-22 | DXB | 10G | DXB-6501-AGGR-SR12e-1 | 2/1/32 | DXB-1587-CSG-IXR-E-1 | NK22403B766 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-06-20 | Y23-F101269 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-09 10:33 | DXB_E3077S_10158_001009001 | 25.068167 | 55.130970 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1086 |  |  | ISH5228 |  | ISH5228 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-07-25 | SHJ |  | SHJ-2049-AGGR-SR7b-1 | 3/1/11 | SHJ-2049-AGGR-SR7b-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-09 10:26 |  | 25.32168 | 55.483134 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1085 |  |  | DUB0452 |  | DUB0452 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-12 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/61 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-09 10:08 |  | 55.2162 | 25.06658 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1084 |  |  | SHJ1516 |  | SHJ1516 | Cisco NCS540 | 5G | New CSG | Cancelled/on Hold | SHAHID |  | SHJ | 10G | SHJ-2058-SCSG-IXR-R6-1 | Port 1/6/7 | SHJ-1516-CSG-N540-LD-1 |  |  | 0 | 1 | 1 | 1 | Site on Hold till 2024 , Mial receied form Charles Tome on 14/06/2023 , Mail attached | [5 empty] | Cisco |  |  | FALSE | 2023 | Sami Ullah | 2023-06-09 10:03 |  | 25.364416 | 55.398316 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1083 |  |  | SHJ2636 |  | SHJ2636 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-08-30 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/49 | SHJ-2636-CSG-IXR-E-1 | NK22403B734 |  | 0 | 1 | 1 | 1 |  |  |  |  | Y23-F104427 |  | Nokia |  |  | TRUE | 2023 | Sami Ullah | 2023-06-09 09:59 |  | 25.32526 | 55.65816 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1082 |  |  | AUH2762 |  | AUH2762 | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | AUH | 1G | AUH-2937-PREAGG-SR7-1 | Port 3/2/13 | AUH-2937-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-13 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-08 15:57 |  | 23.368473 | 53.746646 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1081 |  |  | ISH5091 |  | ISH5091 | Passive | BAU | Passive patching | Passive Completed | SHAHID |  | SHJ | 1G | SHJ-2017-AGGR-SR7b-1 | Port 3/1/13 | SHJ-2017-AGGR-SR7b-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-12 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-08 15:52 |  | 25.31665 | 55.38491 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1080 |  |  | AUH0438 |  | AUH0438 | Nokia IXR-E | SRAN + 5G | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-1/1/60 | AUH-0438-CSG-N540-LD-1 |  |  |  | 1 | 1 |  | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-08 13:17 |  | 24.496083 | 54.365741 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1079 |  |  | DXB5630D |  | DXB5630D | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | DXB | 1G | DXB-3230-SCSG-IXR-R6-1 | Port 1/3/2 | DXB-3230-SCSG-IXR-R6-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-14 |  |  | Nokia |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-08 13:12 |  | 25.158130 | 55.22846 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1078 |  |  | DUB0716 |  | DUB0716 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-27 | DXB |  | DXB-DIC4-CSG-IXR-E-1 | Port 1/1/17 | DXB-DIC4-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-08 12:09 |  | 25.110636 | 55.180477 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1077 |  |  | DUB0338 |  | DUB0338 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-10 | DXB |  | DUB-0289-CSG-N540-LD-1 | Gi0/0/0/7 | DUB-0289-CSG-N540-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-08 12:02 |  | 25.171201 | 55.301613 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1076 |  |  | DUB0337 |  | DUB0337 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-10 | DXB |  | DUB-0289-CSG-N540-LD-1 | Gi0/0/0/6 | DUB-0289-CSG-N540-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-08 11:56 |  | 25.171201 | 55.301613 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1075 |  |  | RAK3989 |  | RAK3989 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-08-01 | RAK | 10G | RAK-2000-SCSG-SR7B-1 | esat-2/1/2 | RAK-3989-CSG-N540-LD-1 | FOC2631N0DA |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-06-14 | Y23-F100874 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-08 10:34 | RKT_E3884M_10005_001001001 | 25.714330° | 55.900769° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1074 |  |  | RAK3446 |  | RAK3446 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-07-10 | RAK | 1G | UAQ-2806-PREAGG-SR7-1 | 2/1/7 | RAK-3446-CSG-N540-LD-1 | FOC2614N0GN |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-06-13 | Y23-F100846 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-08 10:28 | RKT_E3883G_10085_001001001 | 25.653938 | 55.882358 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1073 | WO- IIB-CSG-2023-Order # 1073 |  | ISH5232 |  | ISH5232 | Passive | Rollout | Passive patching | Transmission rack not available | XAD |  | SHJ |  | SHJ-2049-AGGR-SR7b-1 | Port 3/1/25 | SHJ-2049-AGGR-SR7b-1 |  | 5 |  | 1 | 1 |  | Site re assigned to XAD by Mr. Tasif Maqbool. 8-2-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-07 09:14 |  | 25.301888 | 55.454693 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1072 | WO- IIB-CSG-2023-Order # 1072 |  | ISH5233 |  | ISH5233 | Passive | BAU | Passive patching | Transmission rack not available | XAD |  | SHJ |  | SHJ-2049-AGGR-SR7b-1 | Port 3/1/9 | SHJ-2049-AGGR-SR7b-1 |  | 5 |  | 1 | 1 |  | Site re assigned to XAD by Mr. Tasif Maqbool. 8-2-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-07 09:01 |  | 25.301888 | 55.454693 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1071 |  |  | DUB0423 |  | DUB0423 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-06-10 | DXB | 1G | DXB-1516-SCSG-SR7B-1 | esat-3/1/90 | DXB-1516-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-10 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-06-07 08:41 |  | 25.228498 | 55.335209 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1070 |  |  | AUG6039 |  | AUG6039 | Nokia IXR-E | 5G+Migration | New CSG | Cancelled/on Hold |  |  | AUH | 1G | AUH-2911-PREAGG-SR7-1 | 4/1/16 | AUG-6039-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:37 |  | 24.02685 | 52.763581 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1069 |  |  | AJM5998D |  | AJM5998D | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-10 | AJM |  | SHJ-2035-SCSG-SR7B-1 | esat-1/1/2 | SHJ-2035-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive link and migration done by XAD | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:34 |  | 25.370307 | 55.477386 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1068 |  |  | ISH5013 |  | ISH5013 | Cisco NCS540 | Parity | New CSG | Cancelled/on Hold |  |  | SHJ | 1G | SHJ-2053-AGGR-SR7b-1 | Port 3/1/27 | ISH-5013-CSG-N540-LD-1 |  |  |  | 1 | 1 |  | Existing cisco NCS540 csg available | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:29 |  | 25.284886 | 55.469762 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1067 |  |  | RAKNR0504 |  | RAKNR0504 | Nokia IXR-E | 5G | New CSG | Cancelled/on Hold |  |  | RAK | 1G | RAK-2026-PREAGG-SR7-1 | Port 2/1/12 | RAK-0504-CSG-IXR-E-1 | [6 empty] | site has existing RAK-0504-CSG-IXR-E-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:24 |  | 25.615454 | 55.942703 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1066 |  |  | ISH5008 |  | ISH5008 | Nokia IXR-E | Rollout | New CSG | Cancelled/on Hold |  |  | SHJ | 10G | SHJ-2017-AGGR-SR7b-1 | esat-1/1/37 | ISH-5008-CSG-IXR-E-1 | [6 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:21 |  | 25.301855 | 55.378455 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1065 |  |  | DXB3599 |  | DXB3599 | Cisco NCS540 | 5G | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-1/1/53 | DXB-3599-CSG-N540-LD-1 | [6 empty] | Site has existing NCS540 CSG | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:17 |  | 25.2086 | 55.347297 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1064 |  |  | DXB2558 |  | DXB2558 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-3165-PREAGG-SR7-1 | 5/2/17 | DXB-2558-CSG-N540-LD-1 |  |  | 1 | 1 | 1 | 1 | existing DXB-2558-CSG-N540-LD-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:10 |  | 25.27318 | 55.34201 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1063 | WO- IIB-CSG-2023-Order # 1063 |  | DXB1307 |  | DXB1307 | Cisco NCS540 | Rollout | New CSG | Handover | XAD |  | DXB | 10G | DXB-1090-SCSG-SR7B-1 | esat-1/1/54 | DXB-1307-CSG-N540-LD-1 | FOC2633NBY3 | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-06 | Y23-F102165 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 20:06 | DXB_E3279L_12003_001001001 | 25.26878 | 55.29561 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1062 |  |  | ISH5007 |  | ISH5007 | Cisco NCS540 | BAU | New CSG | RFSed | XAD | 2023-09-06 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | Esat:2/1/21 | ISH-5007-CSG-N540-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-29 | Y23-F103700 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-06-06 20:00 | SHJ_E3380Y_10017_001001076 | 25.316993 | 55.455385 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1061 |  |  | IAD5497 |  | IAD5497 | To Be Confirmed | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-1/1/56 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:57 |  | 24.354647 | 54.538745 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1060 |  |  | DXB2712 |  | DXB2712 | Cisco ASR920 | 5G+Migration | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-3173-PREAGG-SR7b-1 | esat-1/1/25 | DXB-2712-CSG-ASR920-LD-1 | [6 empty] | Site has existing CSG DXB-2712-CSG-ASR920-LD-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:47 |  | 25.2444 | 55.3063 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1059 |  |  | IDX0234B |  | IDX0234B | To Be Confirmed |  | New CSG | Cancelled/on Hold |  |  | DXB | 1G | DXB-6504-AGGR-SR12e-1 | 3/1/16 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:34 |  | 24.961336 | 55.155304 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1058 |  |  | DXB3651 |  | DXB3651 | To Be Confirmed | 5G+Migration | New CSG | No OSP | SHAHID |  | DXB | 10G | DXB-VillaPOP-AGGR-SR12e-2 | 2/1/3 |  |  | 5 |  | 1 | 2 | 1 | OSP not ready/Updated to Mr Siraj on 18/01/2024 | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:30 |  | 25.0749 | 55.3639 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1057 |  |  | AUH3172 |  | AUH3172 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 1G | AUH-2142-PREAGG-SR7-1 | Port 3/2/17 | AUH-3172-CSG-IXR-E-1 |  |  | 1 | 1 | 1 |  | Site Inside Zayed military city | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:25 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1056 |  |  | AUH3545 |  | AUH3545 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2142-PREAGG-SR7-1 | Port 5/1/4 | AUH-3545-CSG-N540-LD-1 | [6 empty] | Site is with Nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:19 |  | 24.4969 | 54.89785 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1055 |  |  | AUH3581 |  | AUH3581 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-09-21 | AUH | 10G | AUH-2202-SCSG-IXR-R6-1 | 1/6/1 | AUH-3581-CSG-N540-LD-1 | FOC2638N28F |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-07-15 | Y23-F102738 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:15 | AUH_E2569V_10730_001001001 | 24.309931 | 54.623666 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1054 |  |  | DXB2145 |  | DXB2145 | To Be Confirmed | Rollout | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-2583-PREAGG-IXR-R6-1 | 1/6/5 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 19:10 |  | 24.9666 | 55.03548 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1053 |  |  | SHJ0025 |  | SHJ0025 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-20 | SHJ |  | SHJ-2016-SCSG-SR7B-1 | Existing | SHJ-2016-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 15:02 |  | 25.3286 | 55.3924 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1052 |  |  | SHJ0774 |  | SHJ0774 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-23 | SHJ |  | SHJ-2016-PREAGG-SR7-1 | Port 2/1/17 | SHJ-2016-PREAGG-SR7-1 | [6 empty] | Existing Installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:59 |  | 25.328381 | 55.394284 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1051 |  |  | SHJ3556 |  | SHJ3556 | Passive | 5G+Migration | Passive patching | Passive Completed | XAD | 2023-07-24 | SHJ |  | SHJ-2084-SCSG-SR7B-1 | Esat 3/1/10 – 5G and Esat 3/1/21 – 3G LTE | SHJ-2084-SCSG-SR7B-1 | [6 empty] | site has existing installation to new uplink SHJ-2084-SCSG-SR7B-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:54 |  | 25.3629 | 55.3816 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1050 |  |  | AAN3152 |  | AAN3152 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-11-06 | AUH | 10G | AAN-1295-SCSG-SR7B-1 | esat-1/1/30 | AAN-3152-CSG-N540-LD-1 | FOC2616NY20 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-09-05 | Y23-F106693 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:50 | AAN_E3668N_10006_001001001 | 24.26898 | 55.73899 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1049 |  |  | DUB0879 |  | DUB0879 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-27 | DXB |  | DXB-6020-AGGR-SR12e-1 | 3/2/14 | DXB-6020-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:44 |  | 25.113637 | 55.201256 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1048 |  |  | IAD0989D |  | IAD0989D | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-09 | AUH |  | AUH-2639-CSG-IXR-E-1 | 1/1/11 | AUH-2639-CSG-IXR-E-1 | [6 empty] | Passive done by XAD- no BOQ to be claimed - rogelio | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:32 |  | 24.419402 | 54.855519 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1047 |  |  | ISH0496E |  | ISH0496E | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-12 | SHJ |  | SHJ-5500A-CSG-ASR920-LD-1 | Gi0/0/9 | SHJ-5500A-CSG-ASR920-LD-1 | [6 empty] | Site has Existing passive link as per the plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:20 |  | 25.285233 | 55.461398 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1046 |  |  | SHJ0477 |  | SHJ0477 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-20 | SHJ |  | SHJ-2580-PREAGG-SR7-1 | 2/2/16 | SHJ-2580-PREAGG-SR7-1 | [6 empty] | Site has existing installation and operational | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:06 |  | 25.308527 | 55.364913 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1045 |  |  | IRK5507 |  | IRK5507 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-08-11 | RAK |  | RAK-2718-CSG-IXR-E-1 | 1/1/1 | RAK-2718-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 14:01 |  | 25.797961 | 55.954105 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1044 |  |  | IAD5942 |  | IAD0942 | Passive | Rollout | Passive patching | Cancelled/on Hold |  |  | AUH |  | AUH-KHAZNA-AGG-SR12e-2 | 3/1/21 | AUH-KHAZNA-AGG-SR12e-2 | [6 empty] | IAD5942/IAD0942 has existing CSG | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:55 |  | 24.413013 | 54.567582 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1043 |  |  | AUH5818I |  | AUH5818I | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-31 | AUH |  | AUH-5004-SCSG-SR7B-1 | esat 2/1/4 and esat 2/1/5 | AUH-5004-SCSG-SR7B-1 | [6 empty] | existing IIB Passive to AUH-5004-SCSG-SR7B-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:51 |  | 24.657769 | 54.743435 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1042 |  |  | DXN0878 |  | DXN0878 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-2282-PREAGG-SR7-1 | 5/1/19 | DXB-2282-PREAGG-SR7-1 | [6 empty] | existing patching as per the master sheet | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:47 |  | 25.294957 | 55.362134 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1041 |  |  | IAJ5821 |  | IAJ5821 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-23 | AJM |  | SHJ-2540-PREAGG-SR7-1 | 3/2/15 | SHJ-2540-PREAGG-SR7-1 | [6 empty] | existing patching as per the given plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:43 |  | 25.3947 | 55.4334 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1040 |  |  | AJM0939 |  | AJM0939 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-06-13 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-1/1/38 | AJM-0939-CSG-N540-LD-1 | FOC2624KMG8 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-09 | Y23-F100581 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-06 13:40 | AJM_E3381T_10959_001005025 | 25.419437 | 55.45246 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1039 |  |  | AAN0118 |  | AAN0118 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-07-13 | AUH |  | AAN-2049-PREAGG-SR7-1 | 4/1/5 | AAN-2049-PREAGG-SR7-1 | [6 empty] | existing installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:22 |  | 24.209421 | 55.584105 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1038 |  |  | AAN0119 |  | AAN0119 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-07-13 | AUH |  | AAN-2009-PREAGG-SR7-1 | Port 2/1/14 | AAN-2009-PREAGG-SR7-1 | [6 empty] | existing installation to new port 2/1/14 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:19 |  | 24.146618 | 55.690393 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1037 |  |  | ISH5020 |  | ISH5020 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-23 | SHJ |  | SHJ-2058-PREAGG-SR7-1 | 4/1/2 | SHJ-2058-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | existing patching to updated port -4/1/2 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:15 |  | 25.354458 | 55.386903 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1036 |  |  | AAN0121 |  | AAN0121 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-07-13 | AUH |  | AAN-2049-PREAGG-SR7-1 | 4/1/13 | AAN-2049-PREAGG-SR7-1 | [6 empty] | existing installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 13:10 |  | 24.21347 | 55.63713 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1035 |  |  | DXBNR0091 |  | DXB0091 | Nokia IXR-E | SRAN + 5G | New CSG | Cancelled/on Hold |  |  | DXB | 10G |  | Port2/1/4 |  |  | 5 | 1 | 1 | 1 |  | no plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-06 13:02 |  | 25.257805 | 55.298695 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1034 |  |  | DUB0010 |  | DUB0010 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-2282-PREAGG-SR7-1 | Port 5/1/18 (1G-3G LTE) | DXB-2282-PREAGG-SR7-1 | [6 empty] | existing 1G port installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:57 |  | 25.2943 | 55.362005 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1033 |  |  | DXN0762 |  | DXN0762 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-07-03 | DXB |  | DXB-1036-SCSG-IXR-R6-1 | 1/3/10 | DXB-1036-SCSG-IXR-R6-1 | [6 empty] | existing passive link installation as per the plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:50 |  | 25.2405134 | 55.2521968 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1032 |  |  | AAN0133 |  | AAN0133 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-07-13 | AUH |  | AAN-2007-PREAGG-SR7-1 | 2/1/7 | AAN-2007-PREAGG-SR7-1 | [6 empty] | existing installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:45 |  | 24.241982 | 55.739915 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1031 |  |  | DXN0921 |  | DXN0921 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-12 | DXB |  | DXB-2282-PREAGG-SR7-1 | Port 5/1/12 (3G/LTE - 1G SFP) | DXB-2282-PREAGG-SR7-1 | [6 empty] | Site has Existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:40 |  | 25.296538 | 55.385173 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1030 |  |  | DXN0808 |  | DXN0808 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-07-03 | DXB |  | DXB-1096-PREAGG-SR7-1 | 4/1/16 | DXB-1096-PREAGG-SR7-1 | [6 empty] | existing installation for passive link as per the plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:36 |  | 25.288603 | 55.362763 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1029 |  |  | DXN0749 |  | DXN0749 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-1156-PREAGG-SR7-1 | 4/1/2 | DXB-1156-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:30 |  | 25.110975 | 55.196787 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1028 |  |  | DXN0839 |  | DXN0839 | Passive | Parity | Passive patching | Cancelled/on Hold |  |  | DXB |  | BV PREAGG | To be assigned | BV PREAGG | [6 empty] | Dropped site . services are RFSed via GPON | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 12:20 |  | 25.253599 | 55.33569 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1027 |  |  | DXN0397 |  | DXN0397 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-14 | DXB |  | DXB-6020-AGGR-SR12e-2 | 3/1/20 | DXB-6020-AGGR-SR12e-2 | [6 empty] | Site has existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 10:21 |  | 25.097633 | 55.179819 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1026 |  |  | SHJ0724 |  | SHJ0724 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-19 | SHJ |  | SHJ-2589-CSG-SAR-8-1 | 1/4/5 | SHJ-2589-CSG-SAR-8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 10:15 |  | 25.33739 | 55.388224 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1025 |  |  | DUB0298 |  | DUB0298 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-21 | DXB |  | DXB-1023-SCSG-IXR-R6-1 | Port 1/4/2 (3G LTE- 1G SFP) | DXB-1023-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 10:12 |  | 25.217322 | 55.27303 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1024 |  |  | DXN0925 |  | DXN0925 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-JPPOP-CSG-IXR-E-1 | 1/1/15 | DXB-JPPOP-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 09:50 |  | 25.057537 | 55.217001 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1023 |  |  | DXN0906 |  | DXN0906 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-JPPOP-CSG-IXR-E-1 | 1/1/16 | DXB-JPPOP-CSG-IXR-E-1 | [6 empty] | existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-06 09:46 |  | 25.04284 | 55.19189 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1022 |  |  | DXN0347 |  | DXN0347 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-VH-CSG-IXR-E-1 | Port 1/1/21 (3G/LTE - 1G SFP) | DXB-VH-CSG-IXR-E-1 | [6 empty] | existing passive patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 16:28 |  | 25.0405 | 55.20498 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1021 |  |  | IFU5625 |  | IFU5625 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-16 | FUJ |  | FUJ-6001-AGG-ASR9912-1 | 0/1/0/23 | FUJ-6001-AGG-ASR9912-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 16:22 |  | 25.155606 | 56.344986 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1020 |  |  | DXB2020 |  | DXB2020 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-06-14 | DXB | 10G | DXB-3173-SCSG-SR7B-1 | esat-1/1/34 | DXB-2020-CSG-N540-LD-1 | FOC2631NODZ |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-06-12 | Y23-F100745 |  | Cisco |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-05 16:18 | DXB_E3279M_10730_001001001 | 25.257846 | 55.302618° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1019 |  |  | IFU5627 |  | IFU5627 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-16 | FUJ |  | FUJ-6001-AGG-ASR9912-1 | 0/1/0/22 | FUJ-6001-AGG-ASR9912-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 16:17 |  | 25.156243 | 56.345399 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1018 |  |  | DXN0382 |  | DXN0382 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-VH-CSG-IXR-E-1 | 1/1/19 | DXB-VH-CSG-IXR-E-1 | [6 empty] | existing passive patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 16:12 |  | 25.04193 | 55.20544 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1017 |  |  | DXN0344 |  | DXN0344 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-VH-CSG-IXR-E-1 | Port 1/1/20 (3G/LTE - 1G SFP) | DXB-VH-CSG-IXR-E-1 | [6 empty] | existing passive patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 16:00 |  | 25.04124 | 55.20528 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1016 |  |  | DXN0402 |  | DXN0402 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-VH-CSG-IXR-E-1 | Port 1/1/18 (3G/LTE - 1G SFP) | DXB-VH-CSG-IXR-E-1 | [6 empty] | existing passive patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 15:51 |  | 25.04236 | 55.205798 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1015 | WO- IIB-CSG-2023-Order # 1015 |  | DXB2367 |  | DXB2367 | Passive | 5G+Migration | Passive patching | Site Not Ready | XAD |  | DXB |  | DXB-1026-SCSG-IXR-R6-1 | 1/1/6, 1/2/3, 1/2/4 | DXB-1026-SCSG-IXR-R6-1 |  | 5 |  |  |  |  | Site location is under construction. site not found | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 15:41 |  | 25.216096 | 55.259012 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
1014 |  |  | AUH6558 |  | AUH6558 | Passive to CSG | 5G+SRAN Migration | New CSG | RFSed | SHAHID | 2023-06-15 | AUH | 10G | NE542 (AUH2911-Khazna Masda | 6/1/c5/1:615,6/1/c5/1:616 | AUH-6558-CSG-IXR-E-1 | NK224632124 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-06-12 | Y23-F100703 |  | Nokia |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-05 15:07 | AUH_E0566A_10011_001001001 | 24.072365 | 52.633935 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1013 |  |  | AJM0942 |  | AJM0942 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-03 | AJM |  | AJM-2304-CSG-SAR-8-1 | 1/2/3 3G , 1/1/4 LTE | AJM-2304-CSG-SAR-8-1 | [6 empty] | Existing passive link for 3G and LTE | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 14:21 |  | 25.36611 | 55.51072 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1012 |  |  | DXB2062 |  | DXB2062 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-07-06 | DXB |  | DXB-QUDRA-CSG-IXR-E-1 | 1G:1/1/1 ¦ 10G: 1/1/2 | DXB-QUDRA-CSG-IXR-E-1 | [6 empty] | existing installation for passive 3G LTE and 5G | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 14:15 |  | 24.98112 | 55.38218 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1011 |  |  | DXB1691 |  | DXB1691 | Passive | BAU + 5G | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-1153-PRAGG-SR7-1 | 2/1/7 (5G - 10G SFP) 2/1/9 (3G/LTE - 1G SFP) | DXB-1153-PRAGG-SR7-1 | [6 empty] | Existing installation for 3G LTE and 5G link | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 14:08 |  | 25.1842 | 55.4047 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1010 |  |  | IAD5450 |  | IAD5450 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-07-11 | AUH |  | AUH-6005-AGGR-SR12e-2 | 3/2/18 | AUH-6005-AGGR-SR12e-2 | [6 empty] | site has existing passive link as per the given plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 14:03 |  | 24.493441 | 54.365885 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1009 |  |  | IAD5385 |  | IAD5385 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-07-31 | AUH |  | IAD-5124-CSG-SAR-X-1 | 1/3/3 | IAD-5124-CSG-SAR-X-1 | [6 empty] | site is collocated to EPOC. Existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 13:55 |  | 24.401968 | 54.472236 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1008 |  |  | AAN0107 |  | AAN0107 | Passive | Parity | Passive patching | Passive Completed | XAD |  | AUH |  | AAN-2059-PREAGG-SR7-1 | 3/2/15 | AAN-2059-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 13:32 |  | 24.204748 | 55.793459 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1007 |  |  | SHJ0668 |  | SHJ0668 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-23 | SHJ |  | SHJ-2580-SCSG-SR7B-1 | esat-2/1/16 | SHJ-2580-SCSG-SR7B-1 | [6 empty] | existing installation. labelling changed as per the updated active port SHJ-2580-SCSG-SR7B-1 esat-2/1/16 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 13:28 |  | 25.312464 | 55.378311 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1006 |  |  | ISH5079 |  | ISH5079 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-20 | SHJ |  | SHJ-2580-SCSG-SR7B-1 | Esat-2/1/41 (3G/LTE - 1G SFP) | SHJ-2580-SCSG-SR7B-1 | [6 empty] | Site has existing installation and operational. services migrated from preagg to SCSG | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 13:24 |  | 25.319 | 55.3801 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1005 |  |  | SHJ0687 |  | SHJ0687 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-07-05 | SHJ |  | SHJ-2038-AGGR-SR7-2 | 2/2/18 | SHJ-2038-AGGR-SR7-2 | [6 empty] | existing installation for 3G and LTE link as per the plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 13:15 |  | 25.356378 | 55.426311 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1004 |  |  | IAD5678 |  | IAD5678 | Passive | Parity | Passive patching | Passive Completed | XAD |  | AUH |  | AUH-2908-PREAGG-SR7-1 | 2/1/10 | AUH-2908-PREAGG-SR7-1 | [6 empty] | existing installation and port is operational | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 13:11 |  | 24.102771 | 53.479 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1003 |  |  | DUB0402 |  | DUB0402 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-06-07 | DXB |  | DXB-1048-CSG-IXR-E-1 | Port 1/1/14 | DXB-1048-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-07 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-05 13:05 |  | 25.257968 | 55.336526 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1002 |  |  | IAD5729 |  | IAD5729 | Passive | Parity | Passive patching | Access Issues | XAD |  | AUH |  | AUH-1336-PREAGG-SR7-1 | 4/2/10 | AUH-1336-PREAGG-SR7-1 |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 12:59 |  | 24.446227 | 54.389458 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1001 |  |  | AUH3531 |  | AUH3531 | Passive | 5G+Migration | Passive patching | Passive Completed | XAD | 2023-07-25 | AUH |  | AUH-1416-AGGR-SR12E-1 | 2/1/17 | AUH-1416-AGGR-SR12E-1 | [6 empty] | existing installation as per the masterplan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 12:36 |  | 24.3564 | 54.632535 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
1000 |  |  | AUH3431 |  | AUH3431 | Passive | 5G+Migration | Passive patching | Passive Completed | XAD | 2023-07-25 | AUH |  | AUH-1437-SCSG-SR7B-1 | Esat 1/1/20 3G LTE and Esat 1/1/21 5G | AUH-1437-SCSG-SR7B-1 | [6 empty] | existing installation migrated from preagg to SCSG | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 12:28 |  | 24.553 | 54.6842 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
999 |  |  | AUH6533 |  | AUH6533 | Passive | 5G Upgrade | Passive patching | Passive Completed | XAD | 2023-07-04 | AUH |  | AUH-2088-PREAGG-SR7-1 | Port 2/2/4 (5G - 10G XFP) | AUH-2088-PREAGG-SR7-1 | [6 empty] | new 10GE link for 5G upgrade | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 12:19 |  | 24.408947 | 54.44369 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
998 |  |  | DXN0383 |  | DXN0383 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | DXB-1003-PREAGG-SR7B-1 | esat-2/1/5 | DXB-1003-PREAGG-SR7B-1 | [6 empty] | existing passive patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 12:12 |  | 25.067838 | 55.132094 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
997 |  |  | DXN0374 |  | DXN0374 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-12 | DXB |  | DXB-VH-CSG-IXR-E-1 | 1/1/17 | DXB-VH-CSG-IXR-E-1 | [6 empty] | Site has Existing patching and operational | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-05 12:00 |  | 25.060648 | 55.216677 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
996 |  |  | DXN0506 |  | DXN0506 | Passive | Rollout | New CSG | Passive Completed | SHAHID | 2023-03-09 | DXB |  | DXB-3189-CSG-IXR-E-1 | Port:1/1/22 | DXB-3189-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-09 |  |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-06-03 19:02 |  | 24.938949 | 55.111755 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
995 |  |  | DXN0505 |  | DXN0505 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-08 | DXB |  | DXB-3189-CSG-IXR-E-1 | Port:1/1/20 | DXB-3189-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-08 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 18:54 |  | 24.93874 | 55.11381 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
994 |  |  | DXN0504 |  | DXN0504 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-08 | DXB |  | DXB-3189-CSG-IXR-E-1 | Port:1/1/21 | DXB-3189-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-08 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 18:50 |  | 24.938949 | 55.11175 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
993 |  |  | DXN0987 |  | DXN0987 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-14 | DXB |  | DXB-BB-AGGR-SR12e-1 | esat:1/1/58 | DXB-BB-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-14 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 17:13 |  | 25.179942 | 55.304400 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
992 |  |  | DUB0672 |  | DUB0672 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-14 | DXB | 1G | DXB-3122-PREAGG-SR7B-1 | esat 1/1/15 | DXB-3122-PREAGG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-14 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 16:59 |  | 25.262810 | 55.287700 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
991 |  |  | DUB0634 |  | DUB0634 | Passive | Rollout | New CSG | Passive Completed | SHAHID | 2023-02-14 | DXB |  | DXB-1346-CSG-IXR-E-1 | PORT:1/1/12 | DXB-1346-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-14 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 16:40 |  | 25.292177 | 55.371977 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
990 |  |  | DUB0470 |  | DUB0470 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-14 | DXB |  | DXB-ZAFRAN-AGGR-SR12e-1 | PORT:3/1/9 | DXB-ZAFRAN-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-14 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 16:31 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
989 |  |  | DXN0388 |  | DXN0388 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-07 | DXB |  | DXB-6004-AGGR-SR12e-1 | PORT:8/2/3 | DXB-6004-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-07 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 16:21 |  | 25.143691 | 55.192015 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
988 |  |  | DXN0144 |  | DXN0144 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-11 | DXB |  | DXB-1023-SCSG-IXR-R6-1 | Port :1/2/5 | DXB-1023-SCSG-IXR-R6-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-11 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 15:55 |  | 25.224731 | 55.278218 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
987 |  |  | DUB0588 |  | DUB0588 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-10 | DXB |  | DXB-DIFC-TER1-PREAGG-SR7-1 | PORT :2/1/18 | DXB-DIFC-TER1-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-10 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 15:41 |  | 25.201685 | 55.267239 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
986 |  |  | DUB0117 |  | DUB0117 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-10 | DXB |  | DXB-2295-CSG-IXR-E-1 | PORT :1/1/17 | DXB-2295-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-10 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 15:35 |  | 25.202676 | 55.349269 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
985 |  |  | DXB3950 |  | DXB3950 | Passive | 5G | Passive patching | Passive Completed | SHAHID | 2023-02-06 | DXB |  | DXB-3950-CSG-SAR-X-1 | PORT 1/3/7 | DXB-3950-CSG-SAR-X-1 | [5 empty] | 1 | Passive Completed |  |  | 2023-02-06 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 15:01 | NA | 25.247890 | 55.336450 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
984 |  |  | DUB0147 |  | DUB0147 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-02 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat:1/1/57 | DXB-VH-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-02 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-03 14:48 | NA | 25.060515 | 55.198702 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
982 |  |  | DXN0551 |  | DXN0551 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-JPPOP-CSG-IXR-E-1 | 1/1/18 | DXB-JPPOP-CSG-IXR-E-1 | [6 empty] | existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 16:58 |  | 25.058181 | 55.194225 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
981 |  |  | DXB3663 |  | DXB3663 | Passive | BAU + 5G | Passive patching | Passive Completed | XAD | 2023-07-05 | DXB |  | DXB-3129-SCSG-SR7B-1 | esat-1/1/11, 3/1/19, 3/1/13 | DXB-3129-SCSG-SR7B-1 | [6 empty] | existing IIB Patching available (3 Links) | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 16:54 |  | 25.1243 | 55.2166 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
980 |  |  | DXB1845 |  | DXB1845 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | SHAHID | 2023-06-13 | DXB | 10G | DXB-2583-PREAGG-IXR-R6-1 | Port 1/1/3 | DXB-1845-CSG-IXR-E- | L732003436 |  | 1 | 1 | 1 |  | Site Completed |  |  | 2023-06-10 | Y23-F100651 |  | Nokia |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-02 16:30 | DXB_E3076U_10073_001001001 | 24.947500° | 55.074400 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
979 |  |  | AAN3545 |  | AAN3545 | Nokia IXR-E | 5G+SRAN Migration | New CSG | RFSed | SHAHID | 2023-06-16 | AUH | 10G | AAN-6001-AGGR-SR7S-2 | esat-1/1/24 | AAN-3545-CSG-IXR-E-1 | NK224632250 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-13 | Y23-F100834 |  | Nokia |  |  | TRUE | 2023 | Ahmed Khadim | 2023-06-02 16:13 | AAN_E3667E_10442_001001001 | 24.227832 | 55.758009 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
977 |  |  | AJM6001 |  | AJM6001 | Passive |  | Passive patching | Cancelled/on Hold |  |  | AJM |  | SHJ-2540-PREAGG-SR7-1 | Port 5/1/13 | SHJ-2540-PREAGG-SR7-1 | [6 empty] | this site has AJM-6001-SCSG-SR7B-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 15:56 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
976 |  |  | DXB5236I |  | DXB5236I | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-07-31 | DXB |  | DXB-2728-CSG-IXR-E-1 | 1/1/22 | DXB-2728-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 15:30 |  | 25.031223 | 55.217861 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
975 |  |  | IDX5532 |  | IDX5532 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-JPPOP-CSG-IXR-E-1 | 1/1/20 | DXB-JPPOP-CSG-IXR-E-1 | [6 empty] | existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:55 |  | 25.05119 | 55.19385 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
974 |  |  | IDX5646 |  | IDX5646 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-26 | DXB |  | IDX-5644-CSG-IXR-E-1 | Port 1/1/1 | IDX-5644-CSG-IXR-E-1 | [6 empty] | IDX5646 is colocated with IDX5644-CSG-IXR-E-1. existing passive link is done. | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:50 |  | 25.205421 | 55.346604 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
973 |  |  | IDX5680 |  | IDX5680 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-JPPOP-CSG-IXR-E-1 | 1/1/21 | DXB-JPPOP-CSG-IXR-E-1 | [6 empty] | existing installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:42 |  | 25.05119 | 55.19385 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
972 |  |  | AAN2940 |  | AAN2940 | Passive | 5G+Migration | Passive patching | Passive Completed | XAD | 2023-07-13 | AUH |  | AAN-2042-PREAGG-SR7-1 | 2/1/15 | AAN-2042-PREAGG-SR7-1 |  |  |  | 1 | 1 | 1 | existing installation | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:35 |  | 24.218368 | 55.755880 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
971 | WO- IIB-CSG-2023-Order # 971 |  | DXB0739 |  | DXB0739 | Passive | BAU | Passive patching | Site Not Ready | XAD |  | DXB |  | DXB-6020-AGGR-SR12e-1 | 2/1/20 | DXB-6020-AGGR-SR12e-1 |  | 5 |  |  |  |  | site not found. available GSM in same building DXB0638 andDXB0039 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:30 |  | 25.141389 | 55.190834 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
970 | WO- IIB-CSG-2023-Order # 970 |  | KFN3461 |  | KFN3461 | Passive | Migration |  | Site Not Ready | XAD |  | FUJ |  | FUJ-2022-PREAGG-SR7-1 | no free 1or 10G port | FUJ-2022-PREAGG-SR7-1 |  | 5 |  |  |  |  | Card Exp - Rollout Passive Patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:25 |  | 25.3317 | 56.347 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
969 |  |  | AUH0421 |  | AUH0421 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-25 | AUH |  | AUH-1222-SCSG-SR7B-1 | Esat 1/1/41 and Esat 1/1/37 | AUH-1222-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | existing installation migrated from preagg to SCSG | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:16 |  | 24.41995 | 54.44471 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
968 |  |  | RAK0541 |  | RAK0541 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-20 | RAK |  | RAK-0501-CSG-SAR-X-1 | Port 1/2/4 | RAK-0501-CSG-SAR-X-1 |  |  |  | 1 | 1 |  | existing passive installation already as per the plan | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:09 |  | 25.78515 | 55.96585 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
967 |  |  | IDX5361 |  | IDX5361 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-06-21 | DXB |  | IDX-5365-CSG-SAR-X-1 | 1/2/5 | IDX-5365-CSG-SAR-X-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 14:00 |  | 25.18256 | 55.255726 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
966 | WO- IIB-CSG-2023-Order # 966 |  | SHJ0496 |  | SHJ0496 | Passive | BAU | Passive patching | Site Not Ready | XAD |  | SHJ |  | SHJ-2053-AGGR-SR7b-1 | Port 3/1/33 | SHJ-2053-AGGR-SR7b-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 13:56 |  | 25.301007 | 55.540094 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
965 |  |  | DUB0796 |  | DUB0796 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-12 | DXB |  | DXB-2282-PREAGG-SR7-1 | 5/2/20 | DXB-2282-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-02 13:34 |  | 25.290602 | 55.362572 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
964 |  |  | DUB0129 |  | DUB0129 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-06-05 | DXB | 1G | DXB-3173-SCSG-SR7B-1 | port 3/1/35 | DXB-3173-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-05 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-06-01 21:30 |  | 25.239394 | 55.297209 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
963 |  |  | IAD5339 |  | IAD5339 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-21 | AUH |  | AUH-1222-SCSG-SR7B-1 | esat-1/1/57 | AUH-1222-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | 1G Port provided | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-01 16:44 |  | 24.418677 | 54.442809 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
962 |  |  | AUH3454 |  | AUH3454 | To Be Confirmed | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 1G | AUH-2142-PREAGG-SR7-1 | 3/2/15 |  |  |  |  | 1 | 1 |  | site inside Zayed military city | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-06-01 16:38 |  | 24.5062 | 54.799 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
961 |  |  | AJM5998D |  | AJM5999H | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | AJM | 10G | SHJ-2035-SCSG-SR7B-1 | esat-1/1/2 | AJM-5998D-CSG-N540-LD-1 |  |  |  | 1 | 1 |  | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-06-01 16:32 |  | 25.370307 | 55.477386 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
960 |  |  | SHJ0738 |  | SHJ0738 | Passive | Migration | Rollout Passive Patching | Cancelled/on Hold | SHAHID |  | SHJ | 1G | SHJ-0486-CSG-ASR920-LD-1 | GE0/0/1, 0/0/2 |  |  |  |  | 1 | 1 |  | OSP Not Possible, As Per Mr Sibtain Mail Send On 01/06/2023 | [8 empty] | FALSE | 2023 | Ahmed Khadim | 2023-06-01 15:48 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
959 |  |  | SHJ3916C |  | SHJ3916C | Nokia IXR-E | 5G+Migration | New CSG | Cancelled/on Hold |  |  | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-2/1/60 | SHJ-3916-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 | SHJ-3916-CSG-IXR-E-1 has existing CSG | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-31 15:03 |  | 25.3333 | 55.3783 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
958 |  |  | AUH0651 |  | AUH0651 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-09-27 | AUH |  | AUH-2495-CSG-IXR-E-1 | 1/1/13 | AUH-2495-CSG-IXR-E-1 | [6 empty] | Zayed university site. Collocated with AUH2494 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-31 14:56 |  | 24.394095° | 54.583971° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
957 |  |  | DXB0667 |  | DXB0667 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-10 | DXB |  | DXB-0174-CSG-IXR-E-1 | Port 1/1/16 and Port 1/1/17 | DXB-0174-CSG-IXR-E-1 | [6 empty] | Existing IIB installation for DXB0667 is passively connected to DXB-0174-CSG-IXR-E-1 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-31 14:26 |  | 25.0911 | 55.1493 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
956 | WO- IIB-CSG-2023-Order # 956 |  | AAN0011 |  | AAN0011 | Cisco NCS540 | Migration | New CSG | OSP Issue | SHAHID |  | AUH | 1G | AAN-2019-SCSG-IXR-R6-1 | 1/6/6 | AAN-0011-CSG-N540-LD-1 |  | 5 |  |  |  |  | OSP in different building /BM will call us for JV to check the route possibility to do ISP/Mail shared to Mr Shafaat on 02/02/2024 | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-31 10:16 |  | 24.218478 | 55.748557 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
955 |  |  | IDX0183T |  | IDX0183T | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-02 | DXB |  | DXB-3165-PREAGG-SR7-1 | 5/2/18 | DXB-3165-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-31 10:07 |  | 25.2687 | 55.3311 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
954 |  |  | DXB3956 |  | DXB3956 | Passive |  |  | No OSP | XAD |  | DXB | [10 empty] | site located arenco building 3 RT. no OSP in all arenco buildings | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-05-31 10:03 |  | 25.002007 | 55.167830 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
952 |  |  | SHJ0356 |  | SHJ0356 | Passive | Rollout Upgrade | Passive patching | Passive Completed | SHAHID | 2023-06-05 | SHJ | 1G | SHJ-2016-SCSG-SR7B-1 | esat-1/1/54 | SHJ-2016-SCSG-SR7B-1 |  |  | 1 | 1 | 1 |  | Site Completed |  |  | 2023-06-05 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-30 19:34 |  | 25.30543 | 55.38165 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
951 |  |  | DXB1360 |  | DXB1360 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | XAD | 2023-10-23 | DXB | 10G | DXB-PALMJ-AGGR-SR7B-1 | esat-1/1/51 | DXB-1360-CSG-IXR-E-1 | NK224931197 |  |  | 1 | 1 | 1 | Nokia CSG installed and power up,waiting for OSP team to install the rack and OPS team to shift the fiber ) CR ready | Rogelio Pangilinan;#1712 |  | 2023-10-19 | Y23-F109982 |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-30 14:54 | DXB_E3077D_11158_001001001 | 25.10658 | 55.13382 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
950 |  |  | DUB0948 |  | DUB0948 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-19 | DXB |  | DXB-2268-CSG-IXR-E-1 | 1/1/16 | DXB-2268-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-30 10:59 |  | 25.227119 | 55.279873 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
949 |  |  | DXN0309 |  | DXN0309 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-10-03 | DXB |  | DXB-1003-SCSG-SR7B-1 | esat-2/1/10 (3G/LTE - 1G SFP) | DXB-1003-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-30 10:35 |  | 25.090352 | 55.149905 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
948 |  |  | AUH2787 |  | AUH2787 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-29 | AUH | 10G | AUH-2906-CSG-IXR-E-1 | Port 1/1/17 | AUH-2906-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-29 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-29 09:18 |  | 24.042404 | 53.645424 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
947 |  |  | DXN0445 |  | DXN0445 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-05-15 | DXB | 1G | DXB-DFC-SCSG-SR7B-1 | esat-1/1/50 | DXB-DFC-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-15 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-27 13:38 |  | 25.219969 | 55.364559 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
945 |  |  | DXB2687 |  | DXB2687 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-31 | DXB | 10G | DXB-BB-AGGR-SR12e-1 | esat-1/1/30 | DXB-2687-CSG-N540-LD-1 | FOC2616NXVE | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-31 | Y23-F81302 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-26 16:25 | DXB_E3178E_13385_001009001 | 25.034781 | 55.18081 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
944 |  |  | DXB3524 |  | DXB3524 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-06-06 | DXB | 10G | DXB-1583-SCSG-IXR-R6-1 | 1/3/8 | DXB-3524-CSG-N540-LD-1 | FOC2630NSUU | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-29 | Y23-F81149 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-25 13:34 | DXB_E3076G_10643_001001001 | 25.006937 | 55.101041 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
943 |  |  | DUB0440 |  | DUB0440 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-02 | DXB |  | DXB-2268-CSG-IXR-E-1 | 1/1/15 | DXB-2268-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-25 13:22 |  | 25.221583 | 55.272158 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
942 |  |  | AUH0712 |  | AUH0712 | Passive | Migration |  | Access Issues | XAD |  | AUH |  | AUH-1048-PREAGG-SR7-1 | Port 4/2/14 | AUH-1048-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Govt Building provided contact person number not responding Cont # 024932226 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-24 17:30 |  | 24.4543 | 54.3319 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
941 |  |  | SHJ1445 |  | SHJ1445 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-07-26 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-1/1/23 | SHJ-1445-CSG-N540-LD-1 | FOC2633NLYD |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-07-15 | Y23-F102766 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-24 16:20 | SHJ_E3480L_10271_001001001 | 25.346514 | 55.499065 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
940 |  |  | SHJ1482 |  | SHJ1482 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-06-07 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/19 | SHJ-1482-CSG-N540-LD-1 | FOC2624KMKQ |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-05-31 | Y23-F81317 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-24 16:13 | SHJ_E3380Y_10081_001001001 | 25.3087 | 55.4594 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
939 |  |  | DUB0673 |  | DUB0673 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-16 | DXB |  | DXB-1156-SCSG-NCS57C3-1 | Gi0/0/0/13 | DXB-1156-SCSG-NCS57C3-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-24 16:06 |  | 25.107329 | 55.198449 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
938 |  |  | UAQ1355 |  | UAQ1355 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-05-31 | UAQ | 10G | NE508 (UAQ2016-UAQDC) | UAQ2016/MW RACK 2/SH-1 /Front Port#A12 OTN RK-1/NE508 C/03/TX12/RX12 | UAQ-1355-CSG-N540-LD-1 | FOC2616NY23 |  | 0 | 1 | 1 | 1 | Site completed |  |  | 2023-05-29 | Y23-F81182 |  | Cisco |  |  | TRUE | 2023 | Ahmed Khadim | 2023-05-24 13:09 |  | 25.55697I | 55.73287 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
936 |  |  | DUB0267 |  | DUB0267 |  | BAU |  | Passive Completed | HOI-MEA | 2023-07-11 | DXB |  | DXB-DUBAIOTECH-AGGR-SR12e-1 | 3/1/21 | DXB-DUBAIOTECH-AGGR-SR12e-1 |  | 5 | [10 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-05-24 12:42 |  | 25.11254 | 55.24885 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
935 |  |  | AUH3839 |  | AUH3839 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-08-02 | AUH | 10G | AUH-2184-PREAGG-SRa8-1 | Port 2/1/6 | AUH-3839-CSG-N540-LD-1 | FOC2633NM26 |  |  | 1 | 1 |  |  |  |  | 2023-07-31 | Y23-F103815 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-23 22:34 | AUH_E2270G_10204_001001001 | 24.45587 | 54.325362 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
934 |  |  | DUB0795 |  | DUB0795 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-02 | DXB |  | DXB-1346-CSG-IXR-E-1 | Port 1/1/23 | DXB-1346-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-23 18:08 |  | 25.29533 | 55.36522 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
933 |  |  | DUB0786 |  | DUB0786 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-05-31 | DXB | 1G | DXB-VILLAPOP-AGGR-SR12e-1 | Port 3/2/7 | DUB-0786-CSG-N540-LD-1 | FOC2616NXW6 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-30 | Y23-F81220 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-23 17:52 | DXB_E3377F_10475_001001003 | 25.103115 | 55.368995 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
932 |  |  | DUB0339 |  | DUB0339 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-20 | DXB |  | DXB-PALMJ-CSG-IXR-E-2 | Port 1/1/24 (3G/LTE - 1G SFP) | DXB-PALMJ-CSG-IXR-E-2 | [6 empty] | passive completed with 400meters ISP cabling | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-23 17:29 |  | 25.100618 | 55.154949 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
931 |  |  | DXN0736 |  | DXN0736 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-23 | DXB | 1G | DXB-BB-AGGR-SR12e-1 | esat:1/1/10 | DXB-BB-AGGR-SR12e-1 | [6 empty] | Passive Completed |  |  | 2023-05-23 |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-23 17:27 |  | 25.189200, | 55.293800 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
930 | WO- IIB-CSG-2023-Order # 930 |  | ISH5186 |  | ISH5186 | Passive | Rollout | Passive patching | Site Not Ready | XAD |  | SHJ |  | SHJ-2016-SCSG-SR7B-1 | esat-1/1/50 (3G/LTE - 1G SFP) | SHJ-2016-SCSG-SR7B-1 |  | 5 |  |  |  |  | site not ready. patching ready until MDF | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-23 17:03 |  | 25.3369 | 55.38727 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
929 |  |  | DUB0326 |  | DUB0326 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-07 | DXB |  | DXB-BV-SCSG-SR7B-1 | esat-1/1/41 (3G/LTE - 1G SFP) | DXB-BV-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-23 14:45 |  | 25.257543 | 55.328544 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
928 |  |  | DXB3490 |  | DXB3490 | Nokia IXR-E | Rollout |  | RFSed | HOI-MEA | 2023-09-25 | DXB | 10G | DXB-PALMJ-AGGR-SR7B-1 | esat-1/1/25 | DXB-3490-CSG-IXR-E-1 | NK22403B830 | [9 empty] | Y23-F107901 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-05-23 09:44 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
927 |  |  | DUB0580 |  | DUB0580 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-05-27 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/59 | DXB-VH-SCSG-SR7B-1 | [12 empty] | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-05-23 09:41 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
926 |  |  | KFN3966 |  | KFN3966 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 2023-06-07 | FUJ | 10G | FUJ-5003-PREAGG-SRa8-1 | Port 1/1/10 | KFN-3966-CSG-N540-LD-1 | FOC2631N0D9 |  | 0 | 1 | 1 | 1 | Site Completed | Rogelio Pangilinan;#1712 |  | 2023-06-03 | Y23-F100209 |  | Cisco |  |  | TRUE | 2023 | Ahmed Khadim | 2023-05-22 11:55 | SHJ_E4179E_10001_001001001 | 25.308825 | 56.240925 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
925 |  |  | KFN3845 |  | KFN3845 | Nokia IXR-E | 5G+Migration | New CSG | Cancelled/on Hold |  |  | FUJ | 10G | NE522 (FUJ2022-KALBA) | FUJ2022_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#A8 OTN RK-1/NE522 C/03/TX8/RX8 | KFN-3845-CSG-IXR-E-1 |  |  | 0 | 1 | 1 | 1 | site with cisco. (integrated) | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-22 11:51 |  | 25.324707 | 56.350324 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
924 | WO- IIB-CSG-2023-Order # 924 |  | KFN3951 |  | KFN3951 | Cisco NCS540 | 5G+Migration | New CSG | Installed & Power up | XAD |  | FUJ | 10G | FUJ-5003-PREAGG-SRa8-1 | Port 1/1/9 | KFN-3951-CSG-N540-LD-1 |  | 5 | 0 | 1 | 1 | 2 | Link has issue . escalated to Kashif | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-22 11:47 |  | 25.347452 | 56.288273 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
923 |  |  | FUJ2683 |  | FUJ2683 | Nokia IXR-E | 5G Upgrade | New CSG | Cancelled/on Hold |  |  | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/55 | FUJ-2683-CSG-IXR-E-1 |  |  | 2 | 2 | 2 | 2 | Site is with nokia | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-22 11:43 |  | 25.0843 | 56.35728 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
922 | WO- IIB-CSG-2023-Order # 922 |  | KFN3953 |  | KFN3953 | Cisco NCS540 | 5G+Migration | New CSG | Installed & Power up | XAD |  | FUJ | 10G | FUJ-5003-PREAGG-SRa8-1 | Port 1/1/7 | KFN-3593-CSG-N540-LD-1 |  | 5 | 0 | 1 | 1 | 2 | OSP between KFN3951(cross patching) and FUJ5003 has issue | [5 empty] | Cisco |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-22 11:39 |  | 25.34496 | 56.30209 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
921 |  |  | KFN2677 |  | KFN2677 | Nokia IXR-E | 5G Upgrade | New CSG | Cancelled/on Hold |  |  | FUJ | 10G | NE520 (KFN2678-KALBA) | KFN2678/MW RK/SH-1 /Front Port#A13 OTN RK-1/NE520 C/03/TX13/RX13 | KFN-2677-CSG-IXR-E-1 |  |  | 1 | 2 | 2 | 2 | site has existing KFN-2677-CSG-IXR-E-1 already | [5 empty] | Nokia |  |  | FALSE | 2023 | Ahmed Khadim | 2023-05-22 11:35 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
920 |  |  | FUJ0623 |  | FUJ0623 | Nokia IXR-E | BAU | New CSG | RFSed | XAD | 2023-06-08 | FUJ | 1G | FUJ-6001-AGG-ASR9912-2 | GE0/1/0/15 | FUJ-0623-CSG-IXR-E-1 | NK22373A105 |  | 0 | 1 | 1 | 0 |  | Rogelio Pangilinan;#1712 |  | 2023-06-06 | Y23-F100398 |  | Nokia |  |  | TRUE | 2023 | Ahmed Khadim | 2023-05-22 11:25 | FJR_E4278T_10542_001001001 | 25.157225 | 56.349967 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
918 | WO- IIB-CSG-2023-Order # 918 |  | AUH0945 |  | AUH0945 | Passive | Migration | Passive patching | OSP Issue | XAD |  | AUH |  | AUH-DC-AGGR-SR12e-1 | 3/1/22 | AUH-DC-AGGR-SR12e-1 |  | 5 |  | 1 | 1 |  | OSP in different location | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-22 10:38 |  | 24.453793 | 54.392226 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
917 |  |  | DXB2635 |  | DXB2635 | Nokia IXR-E | 5G | New CSG | RFSed | XAD | 2023-05-31 | DXB | 10G | DXB-6004-AGGR-SR12e-1 | 2/1/14 | DXB-2635-CSG-IXR-E-1 | NK22393A437 | [6 empty] | Rogelio Pangilinan;#1712 |  |  | Y23-F81113 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-19 16:19 | DXB_E3178I_12405_001001001 | 25.19015 | 55.238159 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
916 |  |  | DXB3341 |  | DXB3341 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-07-05 | DXB | 1G | DXB-1852-PREAGG-SR7-1 | 5/2/20 | DXB-3341-CSG-N540-LD-1 | FOC2613PNCJ | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-05 | Y23-F102099 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-19 11:47 | DXB_E3478R_10366_001001001 | 25.149877 | 55.514002 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
915 |  |  | DXB3420 |  | DXB3420 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-07-13 | DXB | 1G | DXB-1852-PREAGG-SR7-1 | Port 5/2/16 | DXB-3420-CSG-N540-LD-1 | FOC2630NGYL | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-12 | Y23-F102556 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-19 11:45 | DXB_E3478R_10365_001001001 | 25.146766 | 55.509058 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
914 |  |  | DUB0615 |  | DUB0615 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-29 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/46 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-18 14:49 |  | 25.050166 | 55.207471 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
913 |  |  | DUB0289 |  | DUB0289 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-06-07 | DXB | 1G | DXB-BB-AGGR-SR12e-1 | Port 3/1/11 | DUB-0289-CSG-N540-LD-1 | FOC2626N013 |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  | Y23-F100260 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-18 10:19 | DXB_E3278L_10120_001013002 | 25.171201 | 55.301613 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
911 |  |  | ISH5177 |  | ISH5177 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-19 | SHJ | 1G | SHJ-2016-SCSG-SR7B-1 | esat-1/1/48 | SHJ-2016-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-19 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-17 18:59 |  | 25.317292 | 55.381855 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
909 |  |  | AUH2720 |  | AUH2720 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 2023-05-26 | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-1/1/28 | AUH-2720-CSG-IXR-E-1 | NK22393A589 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-26 | Y23-F80945 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-16 18:40 | AUH_E2469W_10146_001001001 | 24.304122 | 54.536622 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
908 |  |  | AUH0924 |  | AUH0924 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-1097-SCSG-SR7B-1 | esat-1/1/58 | AUH-1097-SCSG-SR7B-1 |  |  | 1 | 1 | 1 |  | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-16 18:38 |  | 24.412605 | 54.49153 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
907 |  |  | AUH3922 |  | AUH3922 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-08-18 | AUH | 10G | AUH-2925-PREAGG-SRa8-1 | Port 1/1/9 | AUH-3922 -CSG-NS540-LD-1 | FOC2633NBXZ | [6 empty] | Rogelio Pangilinan;#1712 |  |  | Y23-F105102 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-16 18:34 | AUH_E2157O_10005_001001001 | 23.25762 | 54.30911 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
906 |  |  | FUJ3568 |  | FUJ3568 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-08-02 | FUJ | 1G | FUJ-2398-SCSG-SRa8-1 | 1/2/27 | FUJ-3568-CSG-N540-LD-1 |  |  |  | 1 | 1 |  |  |  |  | 2023-07-28 | Y23-F103632 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-16 16:59 | RKT_E4079V_10001_001001001 | 25.22675 | 56.09153 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
905 |  |  | DUB0294 |  | DUB0294 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-06-26 | DXB | 10G | DXB-INDC-AGGR-SR12e-2 | 4/1/6 | DXB-DIC4-CSG-IXR-E-1 | NK231133570 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-23 | Y23-F101537 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-16 16:11 | DXB_E3075L_10004_001002001 | 24.903217 | 55.100077 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
904 |  |  | DXB5342D |  | DXB5342D | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-12-20 | DXB |  | DXB-MIRDIFPOP-AGGR-SR12e-1 | esat-1/1/15 | DXB-5342D-CSG-N540-LD-1 |  |  |  | 1 | 1 |  |  |  |  | 2023-12-19 | Y23-F113835 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-16 16:00 | DXB_E3279J_10673_001002001 | 25.276418 | 55.355572 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
903 |  |  | IAD5427 |  | IAD5427 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-15 | AUH | 1G | AUH-6003-AGGR-SR7B-2 | esat-2/1/33 | AUH-6003-AGGR-SR7B-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-15 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-16 10:19 |  | 24.488421 | 54.360596 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
902 |  |  | AUH3580 |  | AUH3580 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-08-23 | AUH | 1G | AUH-2674-PREAGG-SR7-1 | port 2/1/11 | AUH-3580-CSG-N540-LD-1 | FOC2633NBY5 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-20 | Y23-F80569 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-12 20:46 | AUH_E2667Q_10001_001001001 | 24.16127 | 54.71331 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
901 |  |  | DUB0180 |  | DUB0180 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-17 | DXB | 1G | DXB-BB-AGGR-SR12e-1 | port 3/1/7 | DXB-BB-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-17 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-12 20:07 |  | 25.18611 | 55.28601 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
900 |  |  | RAKL0600V |  | RAK5600E | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-05-12 | RAK | 1G | RAK-2779-CSG-N540-LD-1 | Ge 0/0/0/7, Ge 0/0/0/8 | RAK-2779-CSG-N540-LD-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-12 |  |  | Cisco |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-12 20:01 |  | 25.536284° | 56.018127° | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
899 |  |  | DUB0686 |  | DUB0686 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-19 | DXB | 1G | DXB-IC-POP-SCSG-IXR-R6-1 | port 1/5/3 | DXB-IC-POP-SCSG-IXR-R6-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-18 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-12 19:44 |  | 25.147934 | 55.387687 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
898 |  |  | IAJ5867 |  | IAJ5867 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-05-12 | AJM | 1G | AJM-2459-SCSG-SR7B-1 | esat-2/1/18 | AJM-2459-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-12 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-12 19:35 |  | 25.386414 | 55.461882 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
897 |  |  | ISH0497C |  | ISH0497C | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-05-10 | SHJ | 1G | SHJ-0433-CSG-SAR-X-1 | Port 1/3/6 | SHJ-0433-CSG-SAR-X-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-10 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-10 21:29 |  | 25.31101 | 55.373695 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
896 |  |  | DUB0812 |  | DUB0812 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-06-02 | DXB | 10G | DXB-1899-SCSG-SR7B-1 | esat-1/1/32 | DUB-0812-CSG-N540-LD-1 | FOC2616NXQJ | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-26 | Y23-F80983 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-10 17:29 | DXB_E3376L_13116_001001010 | 24.984156 | 55.393084 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
895 |  |  | DUB0559 |  | DUB0559 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-23 | DXB |  | DXB-2279-CSG-SAR-X-1 | 1/2/6 | DXB-2279-CSG-SAR-X-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-10 14:35 |  | 25.308978 | 55.316822 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
894 |  |  | DXB1561 |  | DXB1561 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | XAD | 2023-05-26 | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-2/1/62 | DXB-1561-CSG-IXR-E-1 | NK223436317 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-18 | Y23-F80436 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-10 13:48 | DXB_E3279M_11008_001001001 | 25.26086 | 55.30437 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
893 |  |  | DXT1983 |  | DXT1983 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-05-30 | DXB | 10G | DXB-INDC-AGGR-SR12e-1 | port 2/1/33 | DXT-1983-CSG-IXR-E-1 | NK223433457 |  | 1 | 1 | 1 | 1 | Site Completed |  |  | 2023-05-27 | Y23-F81025 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-09 18:37 | DXB_E3076X_10051_001001001 | 24.9536 | 55.13363 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
892 |  |  | DUB0270 |  | DUB0270 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-18 | DXB |  | DXB-1600-CSG-IXR-E-1 | 1/1/16 (3G - 1SG SFP) | DXB-1600-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-09 14:19 |  | 25.001055 | 55.276111 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
891 |  |  | DUB0926 |  | DUB0926 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-20 | DXB |  | DXB-1346-CSG-IXR-E-1 | Port 1/1/17 (3G/LTE - 1G SFP) | DXB-1346-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-09 11:39 |  | 25.291259 | 55.370237 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
890 |  |  | IDX5834 |  | IDX5834 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-18 | DXB |  | DXB-1635-PREAGG-SR7-1 | port 4/1/20. 3G and LTE Link | DXB-1635-PREAGG-SR7-1 | [6 empty] | existing patching to DXB-1635-PREAGG-SR7-1 port 4/1/20 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-08 16:51 |  | 25.034968 | 55.180823 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
889 |  |  | DXN0520 |  | DXN0520 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-10 | DXB |  | DXB-BB-AGGR-SR12e-1 | Port 3/2/16 (3G/LTE - 1G SFP) | DXB-BB-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-08 11:40 |  | 25.174966 | 55.309566 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
888 |  |  | AAN3291 |  | AAN3291 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-08-23 | AUH | 1G | AAN-2006-PREAGG-SR7-1 | Port 3/2/17 | AAN-3291-CSG-N540-LD-1 | FOC2614N0VZ |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-20 | Y23-F80582 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-06 10:58 | AAN_E3666A_10002_001001001 | 24.1276244 | 55.6897654 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
887 |  |  | DXB2035 |  | DXB2035 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2023-05-17 | DXB | 10G | DXB-DSO-DC-AGGR-SR12-2 | port 10/2/2 | DXB-2035-CSG-N540-LD-1 | FOC2630NTOC |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-16 | Y23-F80271 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-06 10:41 | DXB_E3377B_10041_001001004 | 25.1155 | 55.3893 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
886 |  |  | AUH3718 |  | AUH3718 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-08-22 | AUH | 10G | AUH-2674-PREAGG-SR7-1 | Port 3/2/17 | AUH-3718-CSG-N540-LD-1 | FOC2628N4EE |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-20 | Y23-F80571 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-06 10:12 | AUH_E2667W_10001_001001001 | 24.139822 | 54.744842 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
885 |  |  | SHJ6265 |  | SHJ6265 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-05-08 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/18 | SHJ-6265-CSG-N540-LD-1 | FOC2631N0EB |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-03 | Y23-F79628 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-06 09:51 | SHJ_E3480U_11158_001001001 | 25.095311 | 55.726262 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
884 |  |  | UAQ1375 |  | UAQ1375 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-05-05 | UAQ | 10G | NE510 (UAQ2012-UAQDC) | UAQ2012_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#A8 OTN RK-1/NE510 C/03/TX7/RX7 | UAQ-1375-CSG-N540-LD-1 | FOC2631N0EH |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-02 | Y23-F79501 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-05 14:24 | UAQ_E3482T_10013_001001001 | 25.516 | 55.5426 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
883 |  |  | DXB3596 |  | DXB3596 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-05-17 | DXB | 10G | DXB-3129-SCSG-SR7B-1 | esat-1/1/32 | DXB-3596-CSG-IXR-E-1 | NK22393A561 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-10 | Y23-F79923 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-04 18:13 | DXB_E3177D_11442_001001001 | 25.11176 | 55.233298 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
882 |  |  | IDX5106 |  | IDX5106 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-18 | DXB |  | DXB-BB-AGGR-SR12e-1 | Port 3/2/11 (3G/LTE - 1G SFP) | DXB-BB-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-04 18:11 |  | 25.180892 | 55.252723 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
881 |  |  | DXB0806 |  | DXB0806 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-19 | DXB | 10G | DXB-1023-SCSG-IXR-R6-1 | Port 1/3/1 | DXB-0806-CSG-IXR-E-1 | NK224632249 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-17 | Y23-F80333 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-04 14:18 | DXB_E3279P_12006_001002043 | 25.237733 | 55.272845 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
880 |  |  | IDX5808 |  | IDX5808 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-05-08 | DXB |  | DXB-DSO-CSG-IXR-E-1 | Port 1/1/20 (3G/LTE - 1G SFP)esat-1/1/4( 3G/LTE- 1G SFP) | DXB-DSO-CSG-IXR-E-1 | [6 empty] | additional port requred for migration | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-04 14:13 |  | 25.112003 | 55.384343 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
879 |  |  | IDX5669 |  | IDX5669 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-05-10 | DXB |  | DXB-5008-AGGR-SR2S-1 | esat-1/1/22 (3G/LTE - 1G SFP) esat-1/1/11(EXISTING) | DXB-5008-AGGR-SR2S-1 | [6 empty] | additional port requested for migration. ESAT1/1/11 completed by HOI MEA | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-05-04 14:07 |  | 25.088211 | 55.303062 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
875 |  |  | DXB1497 |  | DXB1497 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-24 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat 1/1/40 | DXB-1497-CSG-N540-LD-1 | FOC2631N0DX | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-19 | Y23-F80483 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-05-02 20:05 | DXB_E3279N_11574_001003001 | 25.25456 | 55.33583 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
873 |  |  | AJM0914 |  | AJM0914 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | SHAHID | 2023-05-02 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-2/1/1 | AJM-0914-CSG-IXR-E-1 | NK22393A498 |  | 1 | 1 | 1 |  | Site Completed |  |  | 2023-05-29 | Y23-F79296 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-02 17:21 | AJM_E3480A_12264_001012011 | 25.3925 | 55.46862 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
872 |  |  | IAJ5862 |  | IAJ5862 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-10 | AJM | 1G | AJM-6001-SCSG-SR7B-1 | esat-2/1/3 | AJM-6001-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-10 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-01 20:59 |  | 25.3898 | 55.4499 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
871 |  |  | IAJ5864 |  | IAJ5864 | Passive | BAU | Passive patching | Cancelled/on Hold | SHAHID |  | AJM |  | AJM-6001-SCSG-SR7B-1 | esat-2/1/2 | AJM-6001-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | OSP Not Possible Until 2024, As Per Mr Decree Mail Send On 1/5/2023 | [5 empty] | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-01 20:54 |  | 25.419148 | 55.448131 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
870 |  |  | SHJ2096 |  | SHJ2096 | Nokia IXR-E | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-05-10 | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | Port 1/1/5 | SHJ-2096-CSG-IXR-E-1 | NK22393A574 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-08 | Y23-F79843 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-01 20:49 | SHJ_E3380K_10023_001001001 | 25.329525 | 55.367376 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
869 |  |  | ISH5005 |  | ISH5005 | Passive | Parity | Passive patching | Passive Completed | XAD | 2023-06-19 | SHJ |  | SHJ-2084-SCSG-SR7B-1 | esat-2/1/34 (3G/LTE - 1G SFP) | SHJ-2084-SCSG-SR7B-1 |  |  |  | 1 | 1 | [7 empty] | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-05-01 20:45 |  | 25.329525 | 55.367376 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
868 |  |  | SHJ0066 |  | SHJ0066 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-05-12 | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-3/1/3 | SHJ-0066-CSG-IXR-E-1 | NK223433678 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-08 | Y23-F79842 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-05-01 20:40 | SHJ_E3380U_10170_001049011 | 25.318909 | 55.375059 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
866 |  |  | SHJ6308 |  | SHJ6308 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-02 | SHJ | 10G | SHJ-3612-SCSG-SRa8-1 | Port 1/3/6 | SHJ-6309-CSG-N540-LD-1 | FOC2637NEWP |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-29 | Y23-F79300 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-29 18:52 | SHJ_E3775D_10001_001001001 | 24.94124 | 55.82978 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
865 |  |  | ISH5165 |  | ISH5165 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-04-29 | SHJ | 1G | SHJ-2084-SCSG-SR7B-1 | esat-3/1/2 | SHJ-2084-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-29 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-29 10:36 |  | 25.328089 | 55.377069 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
864 |  |  | SHJ2992 |  | SHJ2992 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-29 | SHJ | 1G | SHJ-2992-CSG-SAR-X-1 | 1/3/7 | SHJ-2992-CSG-SAR-X-1 | [5 empty] | 1 | Passive Completed |  |  | 2023-04-29 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-29 10:19 |  | 25.3505 | 55.5557 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
863 |  |  | DXB0358 |  | DXB0358 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-26 | DXB | 1G | DXB-3189-CSG-IXR-E-1 | 1/1/17 | DXB-3189-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-26 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-29 10:06 |  | 25.004 | 55.1549 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
862 |  |  | DXB2540 |  | DXB2540 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-26 | DXB | 1G | DXB-1346-CSG-IXR-E-1 | 3G/4G: 1/1/16 5G: 1/1/17 | DXB-1346-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-26 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-29 09:59 |  | 25.29876 | 55.38052 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
861 |  |  | DUB0549 |  | DUB0549 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-18 | DXB | 1G | DXB-1346-CSG-IXR-E-1 | Port 1/1/15 | DXB-1346-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-18 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-29 09:51 |  | 25.372036 | 55.372036 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
860 |  |  | IAJ5816 |  | IAJ5816 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-19 | AJM | 1G | SHJ-2540-SCSG-SR7B-1 | esat-1/1/51 | SHJ-2540-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-19 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-29 09:45 |  | 25.396006 | 55.429187 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
859 |  |  | IRK5520 |  | IRK5520 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-17 | RAK | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/6 | AUH-6005-AGGR-SR12e-2 | [6 empty] | Passive Completed |  |  | 2023-03-17 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-29 09:32 |  | 25.711381 | 55.89555 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
858 |  |  | DXN0438 |  | DXN0438 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-04-07 | DXB | 1G | DXB-BB-AGGR-SR12e-1 | 3/2/8 | DXB-BB-AGGR-SR12e-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-07 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 20:10 |  | 25.186628 | 55.286449 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
857 |  |  | DUB0237 |  | DUB0237 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-04-18 | DXB | 1G | DXB-DMTC-CSG-IXR-E-1 | 1/1/5 | DXB-DMTC-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-18 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 20:02 |  | 25.046116 | 55.233862 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
856 |  |  | DXB3797 |  | DXB3797 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-04-19 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-1 | esat-1/1/49 | DXB-3797-CSG-N540-LD-1 | FOC2633NM2K |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-17 | Y23-F78666 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-28 19:48 | DXB_E3276F_11142_001001001 | 25.004959 | 55.28375 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
855 |  |  | ISH0496C |  | ISH0496C | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-03 | SHJ | 1G | SHJ-2508-PREAGG-SR7-1 | Port 3/2/6 | SHJ-2508-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 19:14 |  | 25.300454 | 55.488671 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
854 |  |  | ISH0496A |  | ISH0496A | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-03 | SHJ | 1G | SHJ-2053-AGGR-SR7b-1 | Port 3/1/37 | SHJ-2053-AGGR-SR7b-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 19:06 |  | 25.300454 | 55.488671 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
853 |  |  | ISH0496B |  | ISH0496B | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-03 | SHJ | 1G | SHJ-2053-AGGR-SR7b-1 | Port 3/1/25 | SHJ-2053-AGGR-SR7b-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 18:54 |  | 25.300454 | 55.488671 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
852 |  |  | ISH5110 |  | ISH5110 | Passive | 5G | Passive patching | Passive Completed | SHAHID | 2023-03-14 | SHJ | 1G | SHJ-2223-CSG-SAR-X-1 | Port 1/2/5 | SHJ-2223-CSG-SAR-X-1 |  |  |  | 1 | 1 | 1 | Passive Completed |  |  | 2023-03-14 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 18:47 |  | 25.3005916 | 55.272566 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
851 |  |  | ISH5093 |  | ISH5093 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-14 | SHJ | 1G | SHJ-2016-SCSG-SR7B-1 | Esat-1/1/1 | SHJ-2016-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-14 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 18:40 |  | 25.306 | 55.3812 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
850 |  |  | ISH5192 |  | ISH5192 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-30 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/60 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-30 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-28 12:06 |  | 25.307785 | 55.357119 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
849 |  |  | IAD5739 |  | IAD5739 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-05-29 | AUH |  | AUH-1372-PREAGG-SR7-1 | Port 3/2/12 (3G/LTE - 1G SFP) | AUH-1372-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-27 13:50 |  | 24.349011 | 54.51292 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
848 |  |  | IAD5940 |  | IAD5940 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-31 | AUH |  | AUH-2018-CSG-SAR-X-1 | Port 1/2/5 (3G/LTE - 1G SFP) | AUH-2018-CSG-SAR-X-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-27 13:47 |  | 24.48612 | 54.35342 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
847 |  |  | FUJ1535 |  | FUJ1535 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-06-08 | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/54 | FUJ-1535-CSG-IXR-E-1 | NK22393A513 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-05-13 | Y23-F80139 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-27 11:07 | SHJ_E4377P_10008_001001001 | 25.077011 | 56.35802 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
846 |  |  | AUH0499 |  | AUH0499 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-08-11 | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/60 | AUH-0499-CSG-N540-LD-1 | FOC2614N0FY | [6 empty] | Rogelio Pangilinan;#1712 |  |  | Y23-F80309 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-27 10:37 | AUH_E2370S_10413_001003001 | 24.420708 | 54.448267 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
844 |  |  | IAD5580 |  | IAD5580 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-13 | AUH |  | AUH-6003-AGGR-SR7B-2 | Port 3/1/37 (3G/LTE - 1G SFP) | AUH-6003-AGGR-SR7B-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-26 17:06 |  | 24.46425 | 54.36459 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
843 |  |  | RAK3526A |  | RAK3526A | Nokia IXR-E |  |  | RFSed | HOI-MEA | 2023-08-24 | RAK | 1G | FUJ-6001-AGG-ASR9122-1 & 2 | Hu0/0/0/3 | RAK-3526A-CSG-IXR-E-1 | NK22373A295 | [9 empty] | Y23-F101179 |  |  |  |  | FALSE | 2023 | Syed Shahzaib | 2023-04-26 14:45 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
842 |  |  | DXB2692 |  | DXB2692 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 2023-09-19 | DXB | 10G | DXB-INDC-AGGR-SR12e-2 | 2/1/36 | DXB-2692-CSG-IXR-E-1 | NK224931407 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-06 | Y23-F106824 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-26 09:57 | DXB_E3075M_10003_001002001 | 24.90732 | 55.11204 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
841 |  |  | SHJ3742 |  | SHJ3742 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-05-11 | SHJ | 10G | AJM-2459-SCSG-SR7B-1 | esat-2/1/17 | SHJ-3742-CSG-N540-LD-1 | FOC2630NXHP |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F79147 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-04-25 11:51 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
840 |  |  | DXN0795 |  | DXN0795 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-02 | DXB |  | DXB-VILLAPOP-AGGR-SR12e-1 | 3/1/13 | DXB-VILLAPOP-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 15:05 |  | 25.085446 | 55.385113 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
839 |  |  | DXB2268 |  | DXB2268 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | RFSed | XAD | 2023-05-12 | DXB | 10G | DXB-1023-SCSG-IXR-R6-1 | 1/4/1 | DXB-2268-CSG-IXR-E-1 | NK22393A865 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-05 | Y23-F79707 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-24 15:03 | DXB_E3279U_15626_001001001 | 25.21734 | 55.27204 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
838 |  |  | DUB0640 |  | DUB0640 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-27 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/58 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 14:52 |  | 25.051152 | 55.205212 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
837 |  |  | DUB0066 |  | DUB0066 | Passive | Rollout |  | Passive Completed | XAD | 2023-06-06 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/57 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 14:47 |  | 25.04832 | 55.20661 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
836 |  |  | DUB0545 |  | DUB0545 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-27 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/56 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 14:44 |  | 25.057255 | 55.197353 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
835 |  |  | DUB0645 |  | DUB0645 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-02 | DXB |  | DXB-JPPOP-AGGR-SR12e-1 | 3/2/15 | DXB-JPPOP-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 14:40 |  | 25.037461 | 55.178728 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
834 |  |  | DUB0915 |  | DUB0915 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-06-01 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/55 | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 14:36 |  | 25.067697 | 55.214958 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
833 |  |  | IAD5633 |  | IAD5633 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-08-11 | AUH |  | AUH-6005-AGGR-SR12e-1 | Esat 1/1/25 | AUH-6005-AGGR-SR12e-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 10:17 |  | 24.499677 | 54.376161 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
832 |  |  | IAD5636 |  | IAD5636 | Passive | Rollout |  | Passive Completed | XAD | 2023-08-11 | AUH |  | AUH-2055-SCSG-SR7B-1 | esat-1/1/4 (3G/LTE - 1G SFP) | AUH-2055-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-24 10:11 |  | 24.480699 | 54.373364 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
831 |  |  | DXN0771 |  | DXN0771 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-05-18 | DXB | 10G | DXB-3121-SCSG-SR7B-1 | esat-1/1/3 | DXN-0771-CSG-IXR-E-1 | NK223436417 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-06 | Y23-F79792 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-19 13:41 | DXB_E3278E_10229_001001002 | 25.203696 | 55.346886 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
830 |  |  | IAD5781 |  | IAD5781 | Cisco NCS540 | BAU | New CSG | RFSed | XAD | 2023-05-22 | AUH | 10G | AUH-DC-AGGR-SR12e-1 | Port 2/1/37 | IAD-5781-CSG-N540-LD-1 | FOC2633NBYM | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-11 | Y23-F80029 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-18 10:13 | AUH_E2370N_10502_001001001 | 24.43187 | 54.464417 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
829 |  |  | DXN0857 |  | DXN0857 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 2023-06-09 | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-2 | esat-2/1/10 | DXN-0857-CSG-N540-LD-1 | NK223433542 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-29 | Y23-F81093 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-15 15:48 | DXB_E3279V_11041_001014033 | 25.219974 | 55.285677 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
828 |  |  | SHJ6309 |  | SHJ6309 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2023-06-06 | SHJ | 10G | SHJ-3612-PREAGG-SRa8-1 | port 2/1/8 | SHJ-6309-CSG-N540-LD-1 | FOC2631NO03 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-29 | Y23-F79298 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-15 15:45 | SHJ_E3775D_10001_001001001 | 24.88858 | 55.80808 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
827 |  |  | AAN3314 |  | AAN3314 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-10 | AUH | 10G | AAN-5002-AGGR-SR12-2 | Port 10/2/3 | AAN-3314-CSG-N540-LD-1 | FOC2614N0H2 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-10 | Y23-F79919 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-15 15:41 | AAN_E3468W_10001_001001001 | 24.229833 | 55.532111 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
826 |  |  | AAN3536 |  | AAN3536 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-11-01 | AUH | 10G | AAN-6001-AGGR-SR7S-2 | esat-1/1/30 | AAN-3536-CSG-N540-LD-1 | FOC2633NLYM | [8 empty] | 2023-07-08 | Y23-F102330 |  |  |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-15 15:37 | AAN_E3571X_10001_001001001 | 24.50608 | 55.63217 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
825 |  |  | AAN3399 |  | AAN3399 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-06-12 | AUH | 10G | AAN-2065-PREAGG-SR7-1 | Port 4/1/1 | AAN-3399-CSG-N540-LD-1 | FOC2626N014 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-29 | Y23-F81161 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-15 15:28 | AAN_E3667E_10442_001001001 | 24.22309 | 55.75041 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
824 |  |  | AAN2817 |  | AAN2817 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-04 | AUH | 10G | AAN-2033-SCSG-SR7B-1 | esat-1/1/47 | AAN-2817-CSG-N540-LD-1 | FOC2614N0FE |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-03 | Y23-F79528 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-15 15:23 | AAN_E3668O_10008_001001001 | 24.27232 | 55.76349 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
823 | WO- IIB-CSG-2023-Order # 823 |  | AUH3921 |  | AUH3921 | Nokia IXR-E | Migration | New CSG | Transmission rack not available | XAD |  | AUH | 10G | AUH-2674-PREAGG-SR7-1 | Port 2/2/2 | AUH-3921-CSG-IXR-E-1 |  | 5 | [13 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-15 15:19 |  | 24.305814 | 54.872204 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
822 |  |  | AUH2281-5G |  | AUH2281 | Passive | 5G | Passive patching | Passive Completed | SHAHID | 2023-06-09 | AUH | 1G | AUH-2720-CSG-SAR-X-1 | Port:1/1/15 , Port:1/1/16 , | AUH-2720-CSG-SAR-X-1 | [5 empty] | 1 | Site Completed on 09/06/2023 |  |  | 2023-06-09 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-15 14:43 |  | 24.32833 | 54.532169 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
821 |  |  | DUB0022 |  | DUB0022 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | XAD | 2023-04-25 | DXB | 10G | DXB-1583-SCSG-IXR-R6-1 | Port 1/6/7 | DUB-0022-CSG-N540-LD-1 | FOC2632NJZL | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-20 | Y23-F78836 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-14 15:03 | DXB_E3076L_10495_001001001 | 24.9852 | 55.1065 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
819 |  |  | DUB0813 |  | DUB0813 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-14 | DXB |  | DXB-3724-AGGR-SR12e-1 | 3/1/20 | DXB-3724-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 15:39 |  | 25.255956 | 55.411908 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
818 |  |  | DXB1293 |  | DXB1293 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | Cancelled/on Hold |  |  | DXB |  | FTTA-eNodeB-DXBL1293-WTTX | To be assigned | [7 empty] | site on hold | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:56 |  | 25.27375 | 55.33143 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
817 |  |  | DXB1094 |  | DXB1094 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | Cancelled/on Hold |  |  | DXB |  | FTTA-eNodeB-DXBL2094-WTTX | To be assigned | [7 empty] | site on hold | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:53 |  | 25.27926 | 55.33474 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
816 |  |  | DXB1118 |  | DXB1118 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | Cancelled/on Hold |  |  | DXB |  | FTTA-eNodeB-DXB1118 | To be assigned | [7 empty] | site on hold | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:50 |  | 25.26735 | 55.3274 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
815 |  |  | SHJ2361 |  | SHJ2361 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | Cancelled/on Hold |  |  | SHJ |  | SHJ-2059-PREAGG-SR7-1 | To be assigned | PREAGG | [6 empty] | site on hold | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:46 |  | 25.38835 | 55.4158 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
814 |  |  | SHJ2218 |  | SHJ2218 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | Cancelled/on Hold |  |  | SHJ |  | SHJ-2059-PREAGG-SR7-1 | To be assigned | PREAGG | [6 empty] | site on hold | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:43 |  | 25.38615 | 55.4127 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
813 |  |  | IDX5199 |  | IDX5199 | Nokia IXR-E | Upgrade from SARX to IXR-E | New CSG | Cancelled/on Hold |  |  | DXB |  | DXB-3183-PREAGG-SR7-1 |  | PREAGG | [6 empty] | case drop 7-19-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:38 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
812 |  |  | IAD5925 |  | IAD5925 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-05-01 | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/38 | IAD-5925-CSG-IXR-E-1 | NK22403B797 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-27 | Y23-F79155 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 13:10 | AUH_E2368I_10002_001001004 | 24.268293 | 54.463131 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
811 |  |  | SHJ1419 |  | SHJ1419 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-08-29 | SHJ | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/51 | SHJ-1419-CSG-N540-LD-1 | FOC2624KMEP |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-08-25 | Y23-F105800 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-13 12:24 | SHJ_E3580E_10001_001001002 | 25.39594 | 55.638333 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
810 |  |  | SHJ0310 |  | SHJ0310 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-17 | SHJ | 10G | SHJ-2058-SCSG-IXR-R6-1 | 1/5/5 | SHJ-0310-CSG-IXR-E-1 | NK224632228 |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-05-12 | Y23-F80049 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-12 10:56 | SHJ_E3380L_10042_001017002 | 25.360226 | 55.394012 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
806 |  |  | AAN2620 |  | AAN2620 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-19 | AUH | 1G | AAN-2302-PREAGG-SR7-1 | 2/2/11 | AAN-2620-CSG-N540-LD-1 | FOC2547N3U8 |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-05-15 | Y23-F80209 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-11 09:46 | AAN_E3666X_10002_001001001 | 24.06343483 | 55.73570207 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
805 |  |  | AAN3144 |  | AAN3144 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-18 | AUH | 1G | AAN-2302-PREAGG-SR7-1 | 2/2/10 | AAN-3144-CSG-N540-LD-1 | FOC2631N0C3 |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-05-18 | Y23-F80405 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-11 09:43 |  | 24.09309 | 55.70149 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
804 |  |  | AAN2877 |  | AAN2877 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-07-25 | AUH | 10G | AAN-2305-AGGR-SR7B-1 | esat-1/1/24 | AAN-2877-CSG-N540-LD-1 | FOC2624KMEE |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-05-16 | Y23-F80286 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-11 09:39 | AAN_E3666C_10003_001001001 | 24.13044 | 55.72324 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
803 | WO- IIB-CSG-2023-Order # 803 |  | AUH6584 |  | AUH6584 | To Be Confirmed | 5G+Migration | New CSG | Transmission rack not available | XAD |  | AUH | 1G | AUH-2962-PREAGG-SR7-1 | 2/1/18 |  |  | 5 |  | 1 | 1 | 1 | required new FCOB for new CSG installation | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-11 09:34 |  | 23.94548 | 52.76682 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
802 |  |  | AUH3229 |  | AUH3229 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-04-28 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | 2/1/37 | AUH-3229-CSG-IXR-E-1 | NK22393A802 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-04-27 | Y23-F79081 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-11 09:30 | AUH_E2469E_10008_001001001 | 24.39384 | 54.5772 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
801 | WO- IIB-CSG-2023-Order # 801 |  | AUH3445 |  | AUH3445 | Nokia IXR-E | Migration | New CSG | Transmission rack not available | XAD |  | AUH | 1G | AUH-2674-PREAGG-SR7-1 | 3/2/18 | PREAGG |  | 5 |  | 1 | 1 |  | no rackspace for new CSG | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-11 09:23 |  | 24.198991 | 54.886883 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
800 |  |  | AUH6397 |  | AUH6397 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-12-01 | AUH | 10G | AUH-2918-PREAGG-SR7-1 | 4/1/4 | AUH-6397-CSG-N540-LD-1 | FOC2631N0BW | [5 empty] | pending OSP segment from EPOC to cross patching | Rogelio Pangilinan;#1712 |  | 2023-11-30 | Y23-F112742 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-11 09:18 | AUH_W0366M_10001_001001001 | 24.00798 | 51.795116 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
797 |  |  | AUH6586 |  | AUH6586 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-30 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/8 | AUH-6586-CSG-N540-LD-1 | FOC2630NJL8 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-20 | Y23-F80574 |  | Cisco |  |  | TRUE | 2023 | Sami Ullah | 2023-04-10 17:02 | AUH_E1656O_10001_001001001 | 23.16888 | 53.80705 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
796 |  |  | AAN3418 |  | AAN3418 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-04-27 | AUH | 1G | AAN-2302-PREAGG-SR7-1 | Port 2/2/13 | AAN-3418-CSG-N540-LD-1 | FOC2628NT0G |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-27 | Y23-F79075 |  | Cisco |  |  | TRUE | 2023 | Sami Ullah | 2023-04-10 17:00 | AAN_E3666L_10006_001001001 | 24.087179 | 55.70469 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
795 |  |  | AAN3362 |  | AAN3362 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-04-27 | AUH | 1G | AAN-2302-PREAGG-SR7-1 | Port 2/2/12 | AAN-3362-CSG-N540-LD-1 | FOC2633NBYQ |  |  | 1 | 1 |  | Site Completed |  |  | 2023-04-27 | Y23-F79074 |  | Cisco |  |  | TRUE | 2023 | Sami Ullah | 2023-04-10 16:56 | AAN_E3666L_10008_001001001 | 24.09142 | 55.70695 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
794 |  |  | IAD5630 |  | IAD5630 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-13 | AUH | 1G | AUH-2134-PREAGG-SR7-1 | Port 3/2/19 | AUH-2134-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-13 | [5 empty] | FALSE | 2023 | Sami Ullah | 2023-04-10 16:52 |  | 24.330538 | 54.618509 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
792 |  |  | ISH5184 |  | ISH5184 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-04-12 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat-1/1/17 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-12 | [5 empty] | FALSE | 2023 | Sami Ullah | 2023-04-10 16:44 |  | 25.31188 | 55.37528 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
791 |  |  | IAD5589 |  | IAD5589 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-13 | AUH | 1G | AUH-1376-CSG-SAR-8-1 | Port 1/3/8 | AUH-1376-CSG-SAR-8-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-13 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-10 16:10 |  | 24.3433 | 54.5309 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
790 |  |  | DUB0848 |  | DUB0848 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-05-12 | DXB | 1G | DXB-6501-AGGR-SR12e-1 | 3/2/11 | DXB-6501-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-04-10 14:41 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
789 |  |  | DUB0328 |  | DUB0328 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-06 | DXB |  | DXB-2111-CSG-SAR-X-1 | 1/2/4 | DXB-2111-CSG-SAR-X-1 | [6 empty] | ISP CABLING AND PASSIVE PATCHING | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 13:36 |  | 25.236055 | 55.439393 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
788 |  |  | DUB0276 |  | DUB0276 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-02 | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/6 | DXB-1516-SCSG-SR7B-1 | [6 empty] | passive link connected to esat-3/1/6 (updated port) | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 13:31 |  | 25.212466 | 55.319088 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
787 |  |  | UAQ2919 |  | UAQ2919 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | XAD | 2023-05-08 | UAQ | 10G | UAQ2012_PREAGG_SR7-1 | UAQ2012_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#B3 OTN RK-1/NE510 C/03/TX15/RX15 | UAQ-2919-CSG-IXR-E-1 | NK223433826 |  | 8 | 2 | 2 | 2 |  | Rogelio Pangilinan;#1712 |  | 2023-05-02 | Y23-F79474 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 13:19 | UAQ_E3582V_10001_001001001 | 25.49506 | 55.58352 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
786 |  |  | KFN3777 |  | KFN3777 | Cisco NCS540 | 5G+Migration | New CSG | Cancelled/on Hold |  |  | FUJ | 10G | NE518 (KFN2611-Kalba) | To be confirmed |  |  |  |  | 1 | 1 | 1 | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 13:08 |  | 25.586550 | 56.356250 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
785 | WO- IIB-CSG-2023-Order # 785 |  | AUH3152 |  | AUH3152 | Passive | SRAN + 5G | Passive patching | Site Not Ready | XAD |  | AUH |  | AUH-0968-CSG-IXR-E-1 | 1/1/12 ¦ 1/1/13 | AUH-0968-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 12:56 |  | 24.41106 | 54.485752 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
783 |  |  | DXB1043 |  | DXB1043 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-06-08 | DXB | 10G | DXB-1516-SCSG-SR7B-1 | esat-3/1/5 | DXB-1043-CSG-IXR-E-1 | NK223433748 |  | 1 | 1 | 1 | 1 | Site completed |  |  | 2023-06-05 | Y23-F100258 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-10 12:44 | DXB_E3279M_10644_001001001 | 25.2547 | 55.3051 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
781 |  |  | DUB0362 |  | DUB0362 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-06 | DXB |  | DXB-1889-CSG-IXR-E-1 | 1/1/12 | DXB-1889-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 12:36 |  | 25.28344 | 55.39838 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
780 | WO- IIB-CSG-2023-Order # 780 |  | AUH3886 |  | AUH3886 | Cisco NCS540 | 5G |  | Transmission rack not available | XAD |  | AUH |  | AUH-KHAZNA-AGG-SR12e-1 |  | AUH-3886-CSG-NCS540-LD-1 |  | 5 |  |  |  | 1 | [6 empty] | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-10 12:26 |  | 24.42486 | 54.6234 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
779 |  |  | AUH3940 |  | AUH3940 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2023-06-22 | AUH | 10G | AUH-2132-SCSG-SR7B-1 | esat-2/1/18 | AUH-3940-CSG-N540-LD-1 | NK224632162 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-06-21 | Y23-F101374 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-10 12:22 | AUH_E2469R_10327_001005005 | 24.334041 | 54.537409 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
777 |  |  | DXB3088 |  | DXB3088 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-09-19 | DXB | 10G | DXB-3155-SCSG-IXR-R6D-1 | 1/5/c13 | DXB-3088-CSG-IXR-E-1 | NK224931277 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-16 | Y23-F107654 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-10 12:09 | DXB_E3278Q_10340_001001001 | 25.15578 | 55.29174 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
776 | WO- IIB-CSG-2023-Order # 776 |  | AUH3151 |  | AUH3151 | Passive | SRAN + 5G | Passive patching | Site Not Ready | XAD |  | AUH |  | AUH-0968-CSG-IXR-E-1 | 1/1/14 ¦ 1/1/15 | AUH-0968-CSG-IXR-E-1 |  | 5 |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 11:53 |  | 24.412641 | 54.486011 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
775 |  |  | DXS6545 |  | DXS6545 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-04-13 | DXB |  | DXB-1516-SCSG-SR7B-1 | esat-3/1/2 | DXB-1516-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-13 |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 11:44 |  | 25.132205 | 55.2330 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
774 |  |  | DXS6115 |  | DXS6115 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-13 | DXB |  | DXB-3159-SCSG-SR7B-1 | esat-1/1/47 | DXB-3159-SCSG-SR7B-1 | [6 empty] | existing patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-10 11:31 |  | 25.132205 | 55.2330 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
773 |  |  | DUB0704 |  | DUB0704 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-19 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-1/1/59 (3G/LTE - 1G SFP) | DXB-VH-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-07 16:11 |  | 25.031402 | 55.223884 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
772 |  |  | DUB0249 |  | DUB0249 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-26 | DXB |  | DXB-DUBAIOTECH-AGGR-SR12e-1 | Port 8/1/9 (3G/LTE - 1G SFP) | DXB-DUBAIOTECH-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-07 16:02 |  | 25.059 | 55.235737 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
771 |  |  | DXB1274 |  | DXB1274 | Cisco NCS540 | Migration | Passive patching | No OSP | SHAHID |  | DXB | 1G | DXB-1516-SCSG-SR7B-1 | esat-2/1/59 | DXB-1274-CSG-N540-LD-1 | FOC2633NBXP | 5 |  | 1 | 1 |  | OSP CIVIL not ready No ECD shared by Civil team/Installed and Powered IXR-E-1 | [5 empty] | Cisco |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-06 21:06 | DXB_E3279M_10680_001001001 | 25.2579 | 55.3074 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
770 | WO- IIB-CSG-2023-Order # 770 |  | DXB0045 |  | DXB0045 | Cisco NCS540 | Migration | New CSG | Transmission rack not available | XAD |  | DXB | 10G | DXB-PALMJ-AGGR-SR7B-1 | esat-1/1/22 | DXB-0045-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | required rectifier for CSG switch DC Power | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 15:54 |  | 25.09155 | 55.14765 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
769 |  |  | FUJ2128 |  | FUJ2128 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-06-01 | FUJ | 1G | FUJ-2437-SCSG-SR7-1 | Port 3/2/10 | FUJ-2128-CSG-IXR-E-1 | NK22393A497 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-05 | Y23-F79718 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-06 15:51 | RKT_E4076E_10001_001001001 | 25.04012 | 56.15076 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
768 |  |  | FUJ2138 |  | FUJ2138 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-05-18 | FUJ | 1G | FUJ-2437-SCSG-SR7-1 | Port 3/2/11 | FUJ-2138-CSG-IXR-E-1 | NK224632225 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-10 | Y23-F79981 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-06 15:47 | RKT_E4077T_10001_001001001 | 25.0761 | 56.1386 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
767 |  |  | FUJ2960 |  | FUJ2960 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-06-06 | FUJ | 1G | FUJ-2437-SCSG-SR7-1 | Port 3/2/14 | FUJ-2960-CSG-IXR-E-1 | NK224632225 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-05 | Y23-F79647 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-06 15:41 | RKT_E4077Y_10001_001001001 | 25.04849 | 56.144 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
766 |  |  | FUJ3060 |  | FUJ3060 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-11-29 | FUJ | 10G | FUJ-2398-PREAGG-SRa8-1 | esat-1/1/7 | KLB-DC-SCSG-SR7B-1 | NK22403B769 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-05 | Y23-F79719 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-06 15:37 | FJR_E4178Y_10002_001001001 | 25.1464 | 56.2456 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
764 |  |  | RAK3566A |  | RAK3566A | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-11-17 | RAK | 1G | RAK-2026-SCSG-SR7-1 | Port 5/1/19 | RAK-3566-CSG-IXR-E-1 | NK224632186 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-11-16 | Y23-F111824 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-06 15:28 | RKT_E3980B_10006_001001001 | 25.396523 | 55.994321 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
763 |  |  | KFN3097 |  | KFN3097 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-07-10 | FUJ | 1G | NE518 (KFN2611-Kalba) | KFN2611/Huawei ODF RK-1/SH-1 /Front Port#C12 OTN RK-1/NE518 C/10/TX12/RX12 | KFN-3097-CSG-N540-LD-1 | FOC2613PNHX |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-06-19 | Y23-F101165 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-06 15:18 | FJR_E4182I_10001_001001001 | 25.551181 | 56.231441 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
761 |  |  | KFN5750C |  | KFN5750C | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | FUJ |  | NE522 (FUJ2022-KALBA) | FUJ2022_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#A4 OTN RK-1/NE522 C/03/TX11/RX11 | KFN-5750C-CSG-N540-LD-1 |  |  |  | 1 | 1 |  | cancelled from XAD 9-11-2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 14:55 |  | 25.31404 | 56.338629 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
760 |  |  | AUH3238 |  | AUH3238 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-20 | AUH |  | AUH-2999-CSG-SAR-8-1 | Port 1/3/5 (1G-3G LTE) Port 1/3/6(1G-5G) | AUH-2999-CSG-SAR-8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-06 14:48 |  | 24.1519694 | 54.4328806 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
759 |  |  | ISH0496D |  | ISH0496D | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-03 | SHJ | 1G | SHJ-2508-PREAGG-SR7-1 | Port 2/1/20 1G | SHJ-2508-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 14:17 |  | 25.287795 | 55.478333 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
758 |  |  | ISH0497A |  | ISH0497A | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-03 | SHJ | 1G | SHJ-2508-PREAGG-SR7-1 | Port 3/2/9 | SHJ-2508-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 14:10 |  | 25.300454 | 55.488671 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
755 | WO- IIB-CSG-2023-Order # 755 |  | FUJ3278B |  | FUJ3278B | Passive | Migration | Passive patching | Site Not Ready | XAD |  | FUJ |  | FUJ-3278A-CSG-N540-LD-1 | Port 0/0/0/10, 0/0/0/11 | FUJ-3278A-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | Site re assigned to XAD by Mr. Tasif Maqbool. 8-2-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 12:11 |  | 25.271344 | 56.052452 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
754 | WO- IIB-CSG-2023-Order # 754 |  | FUJ3278C |  | FUJ3278C | Passive | Migration | Passive patching | Site Not Ready | XAD |  | FUJ |  | FUJ-3278A-CSG-N540-LD-1 | Port 0/0/0/12, 0/0/0/13 | FUJ-3278A-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | Site re assigned to XAD by Mr. Tasif Maqbool. 8-2-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 12:08 |  | 25.271344 | 56.052452 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
751 | WO- IIB-CSG-2023-Order # 751 |  | AUH3243 |  | AUH3243 | Nokia IXR-E | Migration | New CSG | Handover | XAD |  | AUH | 10G | AUH-2118-SCSG-SR7B-1 | esat-1/1/9 | AUH-3243-CSG-IXR-E-1 | NK224931388 | 5 |  | 1 | 1 |  | plan change from Passive to CSG |  |  | 2023-09-28 | Y23-F108561 |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-06 11:53 | AUH_E2369O_10676_001001001 | 24.3491 | 54.479436 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
750 |  |  | AUH3227 |  | AUH3227 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-05-16 | AUH | 1G | AUH-1415-CSG-SAR-8-1 | Port 1/3/6 (1G) ,PORT:1/2/6(10G) | AUH-1415-CSG-SAR-8-1 |  |  |  | 1 | 1 | 1 | Passive Completed |  |  | 2023-04-07 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 11:49 |  | 24.35394 | 54.63596 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
749 |  |  | AUH0481 |  | AUH0481 | Passive | Migration | Passive patching | No OSP | XAD |  | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 3/2/19 | AUH-6005-AGGR-SR12e-2 |  |  |  | 1 | 1 |  | OSP not available site is inside the tunnel | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 11:45 |  | 24.495098 | ° 54.374017 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
748 |  |  | AUH5812C |  | AUH5812C | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-24 | AUH | 1G | AUH-2938-CSG-SAR-8-1 | 1/3/4 | AUH-2938-CSG-SAR-8-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-24 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 11:42 |  | 23.671914 | 53.699076 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
747 |  |  | IAD5538 |  | IAD5538 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-04-26 | AUH | 1G | AUH-DC-AGGR-SR12e-2 | Port 3/1/17 | AUH-DC-AGGR-SR12e-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-26 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-06 11:37 |  | 24.476739 | 54.381305 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
746 |  |  | IAD0989A |  | IAD0989A | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-06 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-2/1/20 | AUH-1336-SCSG-SR7B-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-06 11:35 |  | 24.439653 | 54.385123 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
745 |  |  | IAD5649 |  | IAD5649 | Passive | Migration | Passive patching | Access Issues | XAD |  | AUH |  | AUH-6005-AGGR-SR12e-1 | 3/1/24 | AUH-6005-AGGR-SR12e-1 |  | 5 |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2023 | Mohammed Faris | 2023-04-06 11:28 |  | 24.4944 | 54.3706 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
744 |  |  | IAD5416 |  | IAD5416 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-05-23 | AUH |  | AUH-2039-PREAGG-SR7-1 | 3/2/11 | AUH-2039-PREAGG-SR7-1 |  |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-06 11:25 |  | 24.477361 | 54.36625 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
742 |  |  | AUH0877 |  | AUH0877 | Passive | Rollout |  | Cancelled/on Hold |  |  | AUH |  | AUH-6003-AGGR-SR7B-2 | 3/1/39 | AUH-6003-AGGR-SR7B-2 |  |  |  | 1 | 1 |  | existing IIB Passive link complted as per plan. site is operational | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-06 11:16 |  | 24.464214 | 54.328585 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
740 |  |  | AUH5818D |  | AUH5818D | Passive | Migration | Passive patching | Survey in progress |  |  | AUH |  | AUH-2142-SCSG-IXR-R6D-1 | Port 1/5/c16 | AUH-2142-SCSG-IXR-R6D-1 |  | 5 |  |  |  |  | Site Dropped From Shahid on 19/01/2024 as site inside Zayed Military City | Sirajuddeen Abdulazeez;#1683 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-06 11:09 |  | 24.546541 | 54.772831 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
739 |  |  | AAN3263 |  | AAN3263 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-03 | AUH | 1G | AAN-2006-PREAGG-SR7-1 | 3/2/13 | AAN-3263-CSG-N540-LD-1 | FOC2624KNPH |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-05-02 | Y23-F79431 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-06 11:02 | AAN_E3667W_10004_001001001 | 24.14256 | 55.719825 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
738 |  |  | DXB3984 |  | DXB3984 | Cisco NCS540 | Migration |  | Cancelled/on Hold |  |  | DXB | 10G | DXB-INDC-AGGR-SR12e-1 | 2/1/40 | DXB-3984-CSG-N540-LD-1 | [6 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-05 17:20 |  | 24.90838 | 54.91937 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
737 |  |  | DXB2259 |  | DXB2259 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-10 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-2 | esat-1/1/58 | DXB-2259-CSG-N540-LD-1 | FOC2614N0F4 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-08 | Y23-F79839 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-05 17:12 | DXB_E3176E_11866_001001001 | 25.02821 | 55.2492 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
736 |  |  | IAD5210 |  | IAD5210 | Passive | Rollout | Passive patching | Cancelled/on Hold | SHAHID |  | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 2/1/38 | [7 empty] | OSP Not Possible in 2023, As per Mr Mohaned Mail Send On 6/4/2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-05 17:02 |  | 24.554342 | 54.456434 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
735 |  |  | IAD5211 |  | IAD5211 | Passive | Rollout | Passive patching | Cancelled/on Hold | SHAHID |  | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 2/1/37 | [7 empty] | OSP Not Possible in 2023, As per Mr Mohaned Mail Send On 6/4/2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-05 16:58 |  | 24.555141 | 54.455642 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
734 |  |  | IAD5207 |  | IAD5207 | Passive | Rollout | Passive patching | Cancelled/on Hold | SHAHID |  | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 2/1/36 | [7 empty] | OSP Not Possible in 2023, As per Mr Mohaned Mail Send On 6/4/2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-05 16:51 |  | 24.555669 | 54.455179 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
733 |  |  | IAD5208 |  | IAD5208 | Passive | Rollout | Passive patching | Cancelled/on Hold | SHAHID |  | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 2/1/35 | [7 empty] | OSP Not Possible in 2023, As per Mr Mohaned Mail Send On 6/4/2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-05 16:06 |  | 24.556064 | 54.456549 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
732 |  |  | SHJ1035 |  | SHJ1035 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-04-14 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/9 | SHJ-1035-CSG-N540-LD-1 | FOC2631NOBU |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-12 | Y23-F78311 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-05 15:58 | SHJ_E3380Y_10060_001001001 | 25.30982 | 55.454144 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
731 |  |  | DXN0886 |  | DXN0886 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-05 | DXB | 1G | DXB-DIC4-CSG-IXR-E-1 | port 1/1/16 | DXB-DIC4-CSG-IXR-E-1 | [6 empty] | Passive Completed |  |  | 2023-04-05 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-04-05 15:51 |  | 25.099393 | 55.140743 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
730 |  |  | IAD5209 |  | IAD5209 | Passive | Migration |  | No OSP | XAD |  | AUH |  | AUH-6005-AGGR-SR12e-2 | 2/1/34 | AUH-6005-AGGR-SR12e-2 | [6 empty] | no OSP . incorrect documents in OSP portal | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:37 |  | 24.555247 | 54.457189 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
729 |  |  | AAN5397C |  | AAN5397C | Passive | Migration |  | Cancelled/on Hold |  |  | AUH |  | AAN-6001-AGGR-SR7S-1 | esat-1/1/35 | AGGR | [6 empty] | site is not MR live | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:33 |  | 24.244268 | 55.725514 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
728 |  |  | AUH5532I |  | AUH5532I | Passive | Migration |  | Cancelled/on Hold |  |  | AUH |  | AUH-2024-CSG-SAR-8-1 | 1/3/4 | CSG | [6 empty] | site is MR blocked | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:30 |  | 24.467137 | 54.334463 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
727 |  |  | AUH0892 |  | AUH0892 | Passive | Migration |  | Cancelled/on Hold |  |  | AUH |  | AUH-2919-CSG-SAR-8-1 | 1/3/5 | CSG | [6 empty] | no MR Live record. no IBS record in portal. coordinates pointing to demolished area | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:27 |  | 24.069826 | 51.762709 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
726 |  |  | AUH5812D |  | AUH5812D | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-08 | AUH |  | AUH-2938-CSG-SAR-8-1 | 1/3/3 | AUH-2938-CSG-SAR-8-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:22 |  | 23.671914 | 53.699076 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
725 |  |  | AAN0064 |  | AAN0064 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-10 | AUH |  | AAN-2059-PREAGG-SR7-1 | 3/2/18 | AAN-2059-PREAGG-SR7-1 | [6 empty] | Existing installation for 3G and LTE | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:19 |  | 24.232454 | 55.773972 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
724 |  |  | AUH5811I |  | AUH5811I | Passive | Migration |  | Cancelled/on Hold |  |  | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-1/1/57 | CSG | [6 empty] | site is MR blocked and building is permanently closed | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:15 |  | 24.446613 | 54.363603 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
723 |  |  | AAN5399G |  | AAN5399G | Passive | Rollout |  | Cancelled/on Hold |  |  | AUH |  | AAN-5399F-CSG-IXR-E-1 (New) | 1/1/8 & 1/1/9 | CSG | [6 empty] | site has existing installation as per the given plan | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:12 |  | 24.216748 | 55.757372 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
722 |  |  | AUH0709 |  | AUH0709 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-12 | AUH |  | AUH-0705-CSG-IXR-e-1 | 1/1/15 | AUH-0705-CSG-IXR-e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:06 |  | 24.429956 | 54.427892 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
721 |  |  | AUH0708 |  | AUH0708 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-12 | AUH |  | AUH-0705-CSG-IXR-e-1 | PORT 1/1/12 | AUH-0705-CSG-IXR-e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 13:01 |  | 24.429259 | 54.428014 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
720 |  |  | AUH0707 |  | AUH0707 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-12 | AUH |  | AUH-0705-CSG-IXR-e-1 | 1/1/14 | AUH-0705-CSG-IXR-e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:57 |  | 24.429529 | 54.428401 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
719 |  |  | AUH0706 |  | AUH0706 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-12 | AUH |  | AUH-0705-CSG-IXR-e-1 | 1/1/13 | AUH-0705-CSG-IXR-e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:54 |  | 24.429262 | 54.428798 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
718 |  |  | AUH0675 |  | AUH0675 | Passive | Migration |  | No OSP | XAD |  | AUH |  | AUH-2883-CSG-IXR-E-1 | 1/1/8 | CSG | [7 empty] | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:50 |  | 24.071861 | 52.676139 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
717 |  |  | AAN3435 |  | AAN3435 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-05-22 | AUH |  | AAN-2006-PREAGG-SR7-1 | Port 2/1/14 (3G/LTE - 1G SFP) | AAN-2006-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:43 |  | 24.15185 | 55.73353 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
716 |  |  | AUH0652 |  | AUH0652 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-09-27 | AUH | 1G | AUH-2493-CSG-IXR-E-1 | Port 1/1/11 | AUH-2493-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:28 |  | 24.393579 | 54.58489 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
715 |  |  | AAN0026 |  | AAN0026 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-06-26 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/33 | AAN-0026-CSG-IXR-E-1 | NK231233534 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-06-23 | Y23-F101525 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-05 12:23 | AAN_E3668X_10031_001002001 | 24.233136 | 55.730737 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
714 | WO- IIB-CSG-2023-Order # 714 |  | AUH0576 |  | AUH0576 | Nokia IXR-E | Migration | New CSG | Osp cores full | SHAHID |  | AUH | 10G | AUH-2929-PREAGG-SRa8-1 | Port 1/3/3 | AUH-0576-CSG-IXR-E-1 |  | 5 |  |  |  |  | OSP Cores not available form AUH2929( Uplink) to AUH2931(Cross patching ) /Escalated to Mr Shafat on 05/02/2024 | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:16 |  | 24.372742 | 54.510481 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
713 |  |  | AUH0437 |  | AUH0437 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-1/1/46 | AGGR | [6 empty] | site is MR blocked already. site not found | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:11 |  | 24.474647 | 54.347186 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
712 |  |  | AUH0471 |  | AUH0471 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-06-21 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | 2/1/30 | AUH-0471-CSG-IXR-E-1 | NK22403B751 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-06-20 | Y23-F101258 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-05 12:07 | AUH_E2271X_10680_001022001 | 24.49019 | 54.360472 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
711 |  |  | AUH0595 |  | AUH0595 | To Be Confirmed | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/33 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 12:03 |  | 24.419926 | 54.435283 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
709 |  |  | AUH2463 |  | AUH2463 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-04-28 | AUH | 1G | AUH-2178-PREAGG-SR7-1 | 2/1/14 | AUH-2463-CSG-IXR-E-1 | NK22393A717 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-27 | Y23-F79087 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 11:49 | AUH_E2775O_10147_001001001 | 24.88840 | 54.86673 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
708 |  |  | AAN3402 |  | AAN3402 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-09 | AUH | 1G | AAN-5002-AGGR-SR12-1 | 8/2/24 | AAN-3402-CSG-N540-LD-1 | FOC2616NY0Z | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-19 | Y23-F78769 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-04-05 11:41 | AAN_E3368M_10002_001001001 | 24.26295 | 55.42241 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
707 |  |  | AAN2435 |  | AAN2435 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-09 | AUH | 1G | AAN-2021-PREAGG-SR7-1 | 3/2/18 | AAN-2435-CSG-IXR-E-1 | NK22393A449 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-05-05 | Y23-F79699 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-05 11:18 | AAN_E3867H_10001_001001001 | 24.19813 | 55.92149 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
706 |  |  | IAD5660 |  | IAD5660 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-28 | AUH |  | AUH-6003-AGGR-SR7B-1 | esat-1/1/45 | AUH-6003-AGGR-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-04-03 15:55 |  | 24.479509 | 54.350904 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
703 |  |  | AUH3586 |  | AUH3586 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-06-20 | AUH | 1G | AUH-2836-PREAGG-SR7-1 | Port 3/2/14 | AUH-3586-CSG-N540-LD-1 | FOC2624KNMV |  |  | 1 | 1 |  |  |  |  | 2023-06-12 | Y23-F100736 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-04-03 10:23 | AUH_E1463U_10002_001001001 | 23.7423889 | 53.5323194 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
702 |  |  | AJM1329 |  | AJM1329 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-04-13 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/50 | AJM-1329-CSG-N540-LD-1 | FOC2614N046 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-10 | Y23-F78212 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-31 13:39 | AJM_E3581U_10292_001001001 | 25.405645 | 55.57336 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
699 |  |  | FUJ6314 |  | FUJ6314 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-05-23 | FUJ | 10G | FUJ-2433-PREAGG-SR7-1 | 3/2/19 | FUJ-6314-CSG-N540-LD-1 | FOC2631N0DM |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-05-04 | Y23-F79629 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-29 14:42 | MSF_E3975V_10003_001001001 | 24.86679 | 55.990192 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
698 |  |  | AUH3852 |  | AUH3852 | Nokia IXR-E | Migration | New CSG | No OSP | SHAHID |  | AUH | 10G | AUH-1437-PREAGG-SR7-1 | 4/1/3 | AUH-3852-CSG-IXR-E-1 |  | 5 |  |  |  |  | NO OSP on Site/OSP request shared to Mr Shaffat on 25/01/2024 | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-29 14:37 |  | 24.49591 | 54.58469 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
697 |  |  | AAN2347 |  | AAN2347 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-09 | AUH | 10G | AAN-5002-AGGR-SR12-1 | 10/2/10 | AAN-2347-CSG-IXR-E-1 | NK22393A537 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-19 | Y23-F78773 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-29 14:33 | AAN_E3167L_10001_001001001 | 24.17855 | 55.20058 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
696 |  |  | AAN2525 |  | AAN2525 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-09 | AUH | 10G | AAN-5002-AGGR-SR12-1 | Port 1/1/6 | AAN-2525-CSG-IXR-E-1 | NK22393A792 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-19 | Y23-F78774 |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-29 14:27 | AAN_E3167R_10001_001001001 | 24.16722 | 55.22345 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
695 |  |  | FUJ2824 |  | FUJ2824 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-11 | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/52 | FUJ-2824-CSG-IXR-E-1 | NK22393A803 |  | 1 | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-04-29 | Y23-F79270 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-29 14:20 | SHJ_E4275F_10001_001001001 | 24.92024 | 56.27356 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
694 |  |  | FUJ2166 |  | FUJ2166 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-05 | FUJ | 10G | KLB-DC-SCSG-SR7B-1 | esat-1/1/51 | FUJ-2166-CSG-IXR-E-1 | NK223433705 |  | 3 | 4 | 4 |  |  | Rogelio Pangilinan;#1712 |  | 2023-04-28 | Y23-F79271 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-29 14:03 | SHJ_E4275A_10001_001001001 | 24.9413 | 56.26707 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
692 |  |  | AUH3702 |  | AUH3702 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-06-07 | AUH | 1G | AUH-2962-PREAGG-SR7-1 | Port 2/1/20 | AUH-3702-CSG-N540-LD-1 | FOC2633NLWR |  |  | 1 | 1 |  | AUH3702 > Gayathi > AUH3148 > AUH2962 OSP done on 22-05-2023 |  |  |  | Y23-F100137 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-28 11:50 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
691 |  |  | AAN3381 |  | AAN3381 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-04-28 | AUH | 10G | AAN-2301-AGGR-SR7B-1 | esat-1/1/37 | AAN-3381-CSG-N540-LD-1 | FOC2631N0B7 |  |  | 1 | 1 | [5 empty] | Y23-F79085 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-28 11:49 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
690 |  |  | AAN2825 |  | AAN2825 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-04-28 | AUH | 10G | AAN-2301-AGGR-SR7B-1 | esat-1/1/36 | AAN-2825-CSG-N540-LD-1 | FOC2624KMA1 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F79086 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-28 11:46 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
689 |  |  | DXB2465 |  | DXB2465 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-04-12 | DXB | 10G | DXB-VH-SCSG-SR7B-1 | esat-2/1/54 | DXB-2465-CSG-N540-LD-1 | FOC2631N0E7 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-03-31 | Y23-F77620 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-27 14:56 | DXB_E3176D_10870_001001001 | 25.027947 | 55.230519 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
688 |  |  | IAD5084 |  | IAD5084 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-07-05 | AUH |  | AUH-2845-CSG-IXR-E-1 | Port 1/1/20 (3G/LTE - 1G SFP) Port 1/1/21( 5G-10G SFP) | AUH-2845-CSG-IXR-E-1 | [6 empty] | only 3G LTE link is completed. 5G link once additional OSP is done | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-25 10:31 |  | 24.324238 | 54.613413 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
687 |  |  | IAD5083 |  | IAD5083 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-07-04 | AUH |  | AUH-2845-CSG-IXR-E-1 | Port 1/1/18 (3G/LTE - 1G SFP) Port 1/1/19( 5G-10G SFP) | AUH-2845-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-25 10:29 |  | 24.324238 | 54.613413 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
686 |  |  | DUB0517 |  | DUB0517 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-04-06 | DXB | 1G | DXB-6020-PREAGG-SR7-1 | 2/1/12 | DXB-6020-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-22 11:40 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
685 |  |  | AAN5397E |  | AAN5397E | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-04-11 | AUH | 1G | AAN-1295-SCSG-SR7B-1 | esat-1/1/28 & esat-1/1/29 | AAN-1295-SCSG-SR7B-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-21 13:00 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
684 |  |  | DUB0942 |  | DUB0942 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-04-14 | DXB |  | DXB-3155-PREAGG-SR7-1 | 2/1/17 | DXB-3155-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:40 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
683 |  |  | DXB5155C |  | DXB5155C | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-04-07 | DXB | 1G | DXB-3155-PREAGG-SR7-1 | 2/1/18 | DXB-3155-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:39 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
682 |  |  | IDX5669 |  | IDX5669 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-04-14 | DXB | 1G | DXB-5008-AGGR-SR2S-1 | esat-1/1/11 | DXB-5008-AGGR-SR2S-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:37 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
681 |  |  | DXB0791 |  | DXB0791 | Passive | Migration |  | Access Issues | HOI-MEA |  | DXB | 1G | DXB-1613-CSG-IXR-E-1 | 1/1/9 | DXB-1613-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:36 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
680 |  |  | DXB0895 |  | DXB0895 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-05-04 | DXB | 1G | DXB-3173-PREAGG-SR7B-1 | esat-2/1/2 | DXB-3173-PREAGG-SR7B-1 |  |  |  | 1 | 1 | [10 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:35 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
678 |  |  | AAN3296 |  | AAN3296 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-04-04 | AUH | 1G | AAN-2046-CSG-SAR-8-1 | 1/2/6 & 1/3/4 | AAN-2046-CSG-SAR-8-1 |  |  |  | 1 | 1 | [10 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:32 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
676 |  |  | AUH6061 |  | AUH6061 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-08-30 | AUH | 1G | AUH-KHAZNA-AGG-SR12e-1 & 2 |  | AUH-6061-CSG-N540-LD-1 | FOC2613PNF9 |  |  | 1 | 1 | [5 empty] | Y23-F103276 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-20 17:28 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
675 |  |  | DUB0302 |  | DUB0302 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-03-30 | DXB | 1G | DXB-1346-CSG-IXR-E-1 | 1/1/14 | DXB-1346-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:25 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
674 |  |  | DUB0669 |  | DUB0669 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-03-30 | DXB | 1G | DXB-3234-CSG-SAR-8-1 | 1/3/4 | DXB-3234-CSG-SAR-8-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:24 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
673 |  |  | DUB0710 |  | DUB0710 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-05-12 | DXB | 1G | DXB-PALMJ-AGGR-SR7b-1 | esat-1/1/34 | DXB-PALMJ-AGGR-SR7b-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 17:22 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
672 |  |  | DUB0274 |  | DUB0274 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-04-15 | DXB | 1G | DXB-ZAFRAN-AGG-SR12e-1 | 3/2/4 | DXB-ZAFRAN-AGG-SR12e-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 16:55 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
671 |  |  | DUB0218 |  | DUB0218 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-04-15 | DXB | 1G | DXB-ZAFRAN-AGG-SR12e-1 | 3/1/24 | DXB-ZAFRAN-AGG-SR12e-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 16:54 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
670 |  |  | DXN0924 |  | DXN0924 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-05-09 | DXB | 1G | DXB-3155-PREAGG-SR7-1 | 2/1/8 | DXB-3155-PREAGG-SR7-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 16:52 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
669 |  |  | AUH0753 |  | AUH0753 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-05-12 | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-1/1/21 | AUH-6003-AGGR-SR7B-2 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 16:50 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
667 |  |  | AUH6621 |  | AUH6621 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-03-28 | AUH | 10G | AUH-6005-AGGR-SR12e-1 | Port 2/1/35 | AUH-6005-AGGR-SR12e-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 16:47 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
666 |  |  | AUH2281 |  | AUH2281 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-03-28 | AUH | 1G | AUH-2720-CSG-SAR-X-1 | Port 1/2/6 | AUH-2720-CSG-SAR-X-1 |  |  |  | 1 | 1 | 1 | [9 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-20 16:45 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
665 |  |  | ISH5213 |  | ISH5213 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-18 | SHJ |  | SHJ-2049-AGGR-SR7b-1 | Port 3/1/20 (3G/LTE - 1G SFP) | SHJ-2049-AGGR-SR7b-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-20 10:35 |  | 25.299175 | 55.456736 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
664 |  |  | IAD5775 |  | IAD5775 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-29 | AUH |  | AUH-1336-SCSG-SR7B-1 | esat-2/1/11 (3G/LTE - 1G SFP) | AUH-1336-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-20 09:47 |  | 24.478288 | 54.370011 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
663 |  |  | DXB3564 |  | DXB3564 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-04-06 | DXB | 10G | DXB-DGPOP1-AGGR-SR12e-1 | 2/1/11 | DXB-3564-CSG-N540-LD-1 | FOC2628NU8M |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F77895 |  | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-03-18 12:15 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
662 |  |  | RAK3998 |  | RAK3998 | Cisco NCS540 | Migration | New CSG | RFSed | HOI-MEA | 2023-04-27 | RAK | 10G | NE506 (RAK2028-UAQDC) OTN | RAK2028_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#A13 OTN RK-1/NE506 C/03/TX13/RX13 | RAK-3998-CSG-N540-LD-1 | FOC2633NBXU |  |  | 1 | 1 | 1 |  |  |  | 2023-04-13 | Y23-F78388 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-18 12:13 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
661 |  |  | DXB0513 |  | DXB0513 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-04-28 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/9 | DXB-0513-CSG-IXR-E-1 | NK22393A793 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F79113 |  | Nokia |  |  | FALSE | 2023 | Syed Shahzaib | 2023-03-18 12:08 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
660 |  |  | DXB2774 |  | DXB2774 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-08-02 | DXB | 10G | DXB-5008-AGGR-SR2S-1 | esat-1/1/12 | DXB-2774-CSG-IXR-E-1 | NK22403B744 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F79367 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-18 12:04 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
659 |  |  | DXB1933 |  | DXB1933 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-05-05 | DXB | 10G | DXB-5008-AGGR-SR2S-1 | esat-1/1/14 | DXB-1933-CSG-N540-LD-1 | FOC2633NBX7 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F79164 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-18 12:03 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
658 |  |  | AAN3324 |  | AAN3324 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-04-13 | AUH | 10G | AAN-5002-AGGR-SR12-2 | Port 10/2/8 | AAN-3324-CSG-N540-LD-1 | FOC2631N0ED |  |  | 1 | 1 | 1 |  |  |  | 2023-04-13 | Y23-F78389 |  | Cisco |  |  | FALSE | 2023 | Syed Shahzaib | 2023-03-18 12:01 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
657 |  |  | AUH6457 |  | AUH6457 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-07-24 | AUH | 10G | NE 542 (AUH2911) OTN | AUH2911/HUAWEI ODF RACK-1/SH-1 /Front Port#A12 OTN RK1/NE542 C/03/TX12/RX12 | AUH-6457-CSG-N540-LD-1 | FOC2613PND3 |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F103008 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-18 11:58 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
656 |  |  | AUH6465 |  | AUH6465 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-08-10 | AUH | 10G | NE 542 (AUH2911) OTN | AUH2911/HUAWEI ODF RACK-1/SH-1 /Front Port#A11 OTN RK1/NE542 C/03/TX11/RX11 | AUH-6465-CSG-N540-LD-1 | FOC2624KNTY |  |  | 1 | 1 | [5 empty] | Y23-F103013 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-18 11:49 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
655 |  |  | AAN3579 |  | AAN3579 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-04-24 | AUH | 1G | AAN-2005-PREAGG-SR7-1 | Port 3/2/13 | AAN-3579-CSG-N540-LD-1 | FOC2633NBYF |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F77663 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-18 11:40 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
654 |  |  | ISH5211 |  | ISH5211 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-03-17 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/63 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-17 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-17 18:26 |  | 25.310547 | 55.377408 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
653 |  |  | DXB0601 |  | DXB0601 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-DIFC-TER-2-PREAGG-SR7-1 | Port 1/1/3 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Rogelio Pangilinan | 2023-03-17 11:56 |  | 25.12129 | 55.200600 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
652 | WO- IIB-CSG-2023-Order # 652 |  | SHJ0466 |  | SHJ0466 | Passive | Migration | Passive patching | Site Not Ready | XAD |  | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat-1/1/14 | SHJ-2580-SCSG-SR7B-1 |  | 5 |  | 1 | 1 |  | GSM Room not ready | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 16:16 |  | 25.306778 | 55.370713 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
651 |  |  | ISH5126 |  | ISH5126 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-05-05 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/64 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-05 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 16:12 |  | 25.31358 | 55.361317 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
650 |  |  | SHJ5191C |  | SHJ5191C | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-03-27 | SHJ | 1G | SHJ-2508-PREAGG-SR7-1 | Port 2/1/13 | SHJ-2508-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-27 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 16:07 |  | 25.246379 | 55.541117 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
649 |  |  | IDX5806 |  | IDX5806 | Passive | Migration | New CSG | Passive Completed | XAD | 2023-06-15 | DXB |  | DXB-DSO-CSG-IXR-E-1 | Port 1/1/16 (3G - 1G SFP) and Port 1/1/21 (LTE - 1G SFP) | DXB-DSO-CSG-IXR-E-1 | [6 empty] | passive only due to site has no rectifier and extra power load | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-03-16 16:00 |  | 25.10832 | 55.37668 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
648 |  |  | AAN3307 |  | AAN3307 | Cisco NCS540 | Migration | Passive patching | RFSed | SHAHID | 2023-04-03 | AUH | 1G | AAN-2021-PREAGG-SR7-1 | Port 3/2/12 | NewLD-CSG | FOC2631N0DB |  |  | 1 | 1 |  | Site Completed |  |  | 2023-03-29 | Y23-F77635 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-16 15:57 | AAN_E3867F_10003_001001001 | 24.203075 | 55.869564 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
647 |  |  | AUH2858 |  | AUH2858 | Cisco NCS540 | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-2674-PREAGG-SR7-1 | Port 2/2/3 | AUH-2858-CSG-N540-LD-1 |  |  |  | 1 | 1 |  | Nokia Hotswap | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Mohammed Faris | 2023-03-16 15:54 |  | 24.39515 | 54.8401 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
646 |  |  | AUH3398 |  | AUH3398 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-04 | AUH | 10G | AUH-5004-SCSG-SR7B-1 | esat-2/1/39 | AUH-3398-CSG-N540-LD-1 | FOC2633NBYO |  |  | 1 | 1 |  | Site Completed |  |  | 2023-04-01 | Y23-F77721 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-16 15:50 | AUH_E2772F_10001_001001001 | 24.632759° | 54.779306° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
645 |  |  | AUH2189 |  | AUH2189 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-04 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/35 | AUH-2189-CSG-N540-LD-1 | FOC2624KMFJ |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-15 | Y23-F78567 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-16 15:46 | AUH_E2270D_10393_001001001 | 24.47589 | 54.35361 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
644 | WO- IIB-CSG-2023-Order # 644 |  | AUH3750 |  | AUH3750 | Nokia IXR-E | Migration | New CSG | Osp cores full | SHAHID |  | AUH | 10G | NE 542 (AUH2911) | AUH2911/HUAWEI ODF RACK-1/SH-1 /Front Port#B2 OTN RK1/NE542 C/03/TX14/RX14 | AUH-3750-CSG-IXR-E-1 |  | 5 |  | 1 | 1 |  | OSP Cores required from AUH2912-AUH2911/Mail shared to Mr Shafaat on 09/02/2024 | Rogelio Pangilinan;#1712 |  |  |  |  | Shahid Tech | IIB not ready |  | FALSE | 2023 | Mohammed Faris | 2023-03-16 15:39 |  | 24.0743 | 52.6502 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
643 |  |  | AUH6573 |  | AUH6573 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-07-03 | AUH | 10G | NE 542 (AUH2911) | AUH2911/HUAWEI ODF RACK-1/SH-1 /Front Port#B1 OTN RK-1/NE542 C/03/TX13/RX13 | AUH-6573-CSG-N540-LD-1 | INL2446A1N4 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-24 | Y23-F101563 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-16 15:35 | AUH_E0666L_10003_001001001 | 24.0336 | 52.74772 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
642 |  |  | AUH2616 |  | AUH2616 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-05-01 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/8 | AUH-6003-AGGR-SR7B-1 | FOC2629NZPA |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-28 | Y23-F79231 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-16 15:30 | AUH_E2270D_12919_001001001 | 24.464463 | 54.36172 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
641 |  |  | AUH0897 |  | AUH0897 | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | AUH | 1G | AUH-2862-CSG-SAR-X-1 | Port 1/2/5 | AUH-2862-CSG-SAR-X-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-07 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 15:24 |  | 23.658548 | 53.680119 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
638 |  |  | AUH2192 |  | AUH2192 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-05-01 | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/30 | AUH-2192-CSG-N540-LD-1 | FOC2624KMZJ |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-04-29 | Y23-F79286 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-16 15:06 | AUH_E2270D_11488_001001001 | 24.47842 | 54.35726 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
637 |  |  | IAD5394 |  | IAD5394 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-11 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/6 | AUH-6005-AGGR-SR12e-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-11 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 15:01 |  | 24.492987 | 54.382047 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
636 |  |  | AJM0941 |  | AJM0941 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-01-20 | AJM | 1G | AJM-0940-CSG-N540-LD-1 | PORT-0/0/14 ,0/0/6 , 0/0/7 | AJM-0940-CSG-N540-LD-1 |  |  |  | 1 | 1 | 1 | Passive Completed |  |  | 2023-01-20 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 10:51 |  | 25.3924 | 55.43892 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
635 |  |  | SHJ2005 |  | SHJ2005 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-02-03 | SHJ | 1G | SHJ-2005-CSG-SAR-X-1 | PORT 1/3/7 | SHJ-2005-CSG-SAR-X-1 | [6 empty] | Passive Completed |  |  | 2023-02-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 10:44 |  | 25.3242664, | 55.3783203 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
634 |  |  | IAJ5861 |  | IAJ5861 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-01-27 | AJM | 1G | AJM-6001-SCSG-SR7B-1 | esat 1/1/1 | AJM-6001-SCSG-SR7B-1 | [6 empty] | Passive Completed |  |  | 2023-01-27 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 10:39 |  | 25.3789779, | 55.4579337 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
633 |  |  | SHJ0797 |  | SHJ0797 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-01-17 | SHJ | 1G | SHJ-2016-SCSG-SR7B-1 | esat:2/1/6 | SHJ-2016-SCSG-SR7B-1 |  |  |  | 1 |  |  | Passive Completed |  |  | 2023-01-17 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 10:32 |  | 25.317474 | 55.383575 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
632 |  |  | ISH5074 |  | ISH5074 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-01-27 | SHJ | 1G | SHJ-2058-SCSG-IXR-R6-1 | PORT:1/6/5 | SHJ-2058-SCSG-IXR-R6-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-01-27 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 10:24 |  | 25.3564 | 55.3884 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
631 |  |  | SHJ0785 |  | SHJ0785 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-01-18 | SHJ | 1G | SHJ-2022-AGGR-SR7B-1 | PORT:3/1/37 | SHJ-2022-AGGR-SR7B-1 |  |  |  | 1 |  |  | Passive Completed |  |  | 2023-01-18 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-16 10:16 |  | 25.344488 | 55.401318 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
630 |  |  | SHJ0250 |  | SHJ0250 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-01-27 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat 2/1/59 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-01-27 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-15 17:53 |  | 25.312661 | 55.374148 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
629 |  |  | AJM0954-5G |  | AJM0954-5G | Passive | 5G | Passive patching | Passive Completed | SHAHID | 2023-01-04 | AJM | 1G | AJM-0954-CSG-IXR-E-1 | PORT:1/1/10 | AJM-0954-CSG-IXR-E-1 | [5 empty] | 1 | Passive Completed |  |  | 2023-01-04 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-15 17:37 | AJM_E3480H_10539_001001001 | 25.364081 | 55.511560 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
626 |  |  | AAN0140 |  | AAN0140 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-14 | AUH |  | AAN-6001-AGGR-SR7S-1 | esat-1/1/57 (3G/LTE - 1G SFP) | AAN-6001-AGGR-SR7S-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-15 15:24 |  | 24.2457 | 55.7158 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
624 |  |  | AUH0499 |  | AUH0499 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-31 | AUH |  | AUH-1222-SCSG-SR7B-1 | esat-1/1/60 (3G/LTE - 1G SFP) | AUH-1222-SCSG-SR7B-1 | [6 empty] | passive to CSG | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-15 14:53 |  | 24.420708 | 54.448267 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
623 |  |  | IAD5921 |  | IAD5921 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-17 | AUH |  | AUH-2358-CSG-IXR-E-1 | Port 1/1/11 (3G - 1G SFP) | AUH-2358-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-15 14:48 |  | 24.4016586 | 54.5019177 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
622 |  |  | AUH0678 |  | AUH0678 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-19 | AUH |  | IAD-5143-CSG-IXR-E-1 | Port 1/1/6 (3G - 1G SFP) | IAD-5143-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-15 14:31 |  | 24.45181 | 54.39223 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
621 |  |  | AUH3354 |  | AUH3354 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-03-22 | AUH | 1G | AUH-1416-AGGR-SR12E-1 | esat-1/1/40 | AUH-3354-CSG-N540-LD-1 | FOC2616NXE1 |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-03-22 | Y23-F77018 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-15 13:26 | AUH_E2569G_10034_001001001 | 24.37306 | 54.616 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
620 |  |  | AUH3997 |  | AUH3997 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-03-22 | AUH | 1G | AUH-1416-AGGR-SR12E-1 | esat-1/1/39 | AUH-3997-CSG-N540-LD-1 | FOC2631N0AF |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-03-22 | Y23-F77000 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-15 13:22 |  | 24.3812 | 54.60859 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
619 |  |  | AUH3998 |  | AUH3998 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-03-22 | AUH | 1G | AUH-1416-AGGR-SR12E-1 | esat-1/1/38 | AUH-3998-CSG-N540-LD-1 | FOC2631N0EC |  |  | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  | 2023-03-22 | Y23-F77015 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-15 13:19 |  | 24.37866 | 54.61962 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
617 |  |  | AUH0752 |  | AUH0752 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-05-12 | AUH |  | AUH-6003-AGGR-SR7B-2 | esat-1/1/22 | AUH-6003-AGGR-SR7B-2 |  |  | 1 | 1 | 1 | [10 empty] | FALSE | 2023 | Syed Shahzaib | 2023-03-14 14:08 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
609 |  |  | DUB0177 |  | DUB0177 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-24 | DXB |  | DXB-3155-PREAGG-SR7-1 | Port 2/1/5 (3G/LTE - 1G SFP) | DXB-3155-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-14 09:43 |  | 25.15395 | 55.29001 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
608 |  |  | DXNNR0388 |  | DXN0388 | Passive | 5G | Passive patching | Passive Completed | XAD | 2023-03-17 | DXB |  | DXB-6004-AGGR-SR12e-1 | Port 2/1/19 ( 5G-10G SFP) | DXB-6004-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-13 14:10 |  | 25.144924 | 55.189144 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
607 |  |  | IAD5753 |  | IAD5753 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-06 | AUH |  | AUH-2358-CSG-IXR-E-1 | Port 1/1/6 (3G/LTE - 1G SFP) | AUH-2358-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-13 14:00 |  | 24.407373 | 54.505876 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
606 |  |  | AJM5998E |  | AJM5998E | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-02 | AJM |  | AJM-2312-CSG-ASR920-LD-1 | Port Gi0/0/11(3G/LTE - 1G SFP) | AJM-2312-CSG-ASR920-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-13 12:31 |  | 25.424817 | 55.501953 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
605 |  |  | AUH0722 |  | AUH0722 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-06 | AUH |  | AUH-2931-CSG-SAR-X-1 | P-1/3/5 3G Link, P-1/3/6 LTE Link | AUH-2931-CSG-SAR-X-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-06 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-09 15:47 |  | 22.8968 | 54.3413 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
604 |  |  | ISH5187 |  | ISH5187 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-06 | SHJ | 1G | SHJ-2084-SCSG-SR7B-1 | esat:2/1/47 | SHJ-2084-SCSG-SR7B-1 | NA | [5 empty] | Passive Completed |  |  | 2023-03-06 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-09 15:43 |  | 25.325048 | 55.377860 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
603 |  |  | SHJ0479 |  | SHJ0479 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-08 | SHJ | 1G | SHJ-2049-AGGR-SR7B-1 | P-3/1/31 | SHJ-2049-AGGR-SR7B-1 | NA | [5 empty] | Passive Completed |  |  | 2023-03-08 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-09 15:39 |  | 25.3067 | 55.4664 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
602 |  |  | DUB0317 |  | DUB0317 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-08 | DXB | 1G | DXB-BV-SCSG-SR7-1 | esat-1/1/28 | DXB-BV-SCSG-SR7-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-08 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-09 15:33 |  | 25.258569 | 55.330349 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
601 |  |  | AUH0955 |  | AUH0955 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-14 | AUH | 1G | AUH-0486-CSG-ASR920-LD-1 | Te-0/0/13 | AUH-0486-CSG-ASR920-LD-1 | NA |  |  |  |  | 1 | Passive Completed |  |  | 2023-02-14 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-09 15:28 |  | 24.465176 | 54.386681 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
600 |  |  | RAK0532 |  | RAK0532 |  | Migration | Passive patching | Passive Completed | NETS | 2023-03-09 | RAK | [13 empty] | 2023-03-09 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-03-09 13:38 |  | 25.66968 | 55.74403 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
599 |  |  | IAD5864 |  | IAD5864 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-15 | AUH | 1G | AUH-2202-SCSG-IXR-R6-1 | Port-1/3/5 | AUH-2202-SCSG-IXR-R6-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-02-15 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-09 12:24 |  | 24.315600 | 54.609400 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
598 |  |  | AAN5397F |  | AAN5397F | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-03-01 | AUH |  | AAN-2049-SCSG-SR7B-1 | esat-1/1/48 | AAN-2049-SCSG-SR7B-1 | NA | [5 empty] | Passive Completed |  |  | 2023-03-01 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-08 20:44 |  | 24.210638 | 55.661928 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
597 |  |  | IBS-FTK-21-3693 |  | IAJ5852 | Passive | BAU | Passive patching | Passive Completed | SHAHID | 2023-03-10 | AJM | Others | AJM-6001-SCSG-SR7B-1 | esat-1/1/3 | AJM-6001-SCSG-SR7B-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-10 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-08 16:57 |  | 25.37978 | 55.45841 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
596 |  |  | DUB0964 |  | DUB0964 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-24 | DXB |  | DXB-ZAFRAN-AGG-SR12e-1 | Port 3/2/3 (3G/LTE - 1G SFP) | DXB-ZAFRAN-AGG-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-08 10:16 |  | 25.20265 | 55.280254 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
595 |  |  | DUB0985 |  | DUB0985 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-24 | DXB |  | DXB-ZAFRAN-AGG-SR12e-1 | Port 3/2/2 (3G/LTE - 1G SFP) | DXB-ZAFRAN-AGG-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-08 10:13 |  | 25.202788 | 55.281299 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
594 |  |  | DUB0984 |  | DUB0984 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-24 | DXB |  | DXB-ZAFRAN-AGG-SR12e-1 | Port 3/2/1 (3G/LTE - 1G SFP) | DXB-ZAFRAN-AGG-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-08 10:10 |  | 25.201935 | 55.281335 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
593 |  |  | DXB1730 |  | DXB1730 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-03-30 | DXB | 10G | DXB-1069-SCSG-SR7B-1 | esat-1/1/8 | DXB-1730-CSG-N540-LD-1 | FOC2631N0B8 | [6 empty] | Rogelio Pangilinan;#1712 |  |  | Y23-F77392 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-07 15:42 |  | 25.08596 | 55.172384 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
592 |  |  | IFU5628 |  | IFU5628 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-30 | FUJ |  | FUJ-6001-CSG-ASR920-LD-1 | 0/0/10 (3G/LTE - 1G SFP) | FUJ-6001-CSG-ASR920-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-07 11:56 |  | 25.163805 | 56.351471 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
591 |  |  | DUB0210 |  | DUB0210 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-08 | DXB |  | DXB-1516-SCSG-SR7B-1 | esat 3/1/3 (3G/LTE - 1G SFP) | DXB-1516-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 15:22 |  | 25.21137 | 55.31426 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
589 |  |  | IAD5466 |  | IAD5466 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-22 | AUH |  | AUH-2018-CSG-SAR-X-1 | Port 1/3/6 (3G/LTE - 1G SFP) | AUH-2018-CSG-SAR-X-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 13:28 |  | 24.489795 | 54.357191 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
588 |  |  | IAD5644 |  | IAD5644 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-28 | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 3/2/13 (3G/LTE - 1G SFP) | AUH-6005-AGGR-SR12e-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 13:25 |  | 24.487892 | 54.366932 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
586 |  |  | IAD5307 |  | IAD5307 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-21 | AUH |  | AUH-1048-PREAGG-SR7-1 | Port 4/2/9 (3G/LTE - 1G SFP) | AUH-1048-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 13:05 |  | 24.455226 | 54.329543 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
584 |  |  | AJM1218 |  | AJM1218 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-04-25 | AJM | 10G | SHJ-2035-SCSG-SR7B-1 | esat-1/1/7 | AJM-1218-CSG-N540-LD-1 | FOC2633NBYR |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F78735 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-03-06 12:53 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
582 |  |  | ISH5209 |  | ISH5209 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-23 | SHJ |  | SHJ-2016-SCSG-SR7B-1 | esat-2/1/2 (3G/LTE - 1G SFP) | SHJ-2016-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 12:43 |  | 25.3401 | 55.39126 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
581 |  |  | ISH5174 |  | ISH5174 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-21 | SHJ |  | SHJ-2084-SCSG-IXR-R6-1 | Port 1/1/3 (3G/LTE - 1G SFP) | SHJ-2084-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 12:37 |  | 25.326345 | 55.371825 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
580 |  |  | SHJ0741 |  | SHJ0741 | Passive | Rollout |  | Passive Completed | XAD | 2022-12-21 | SHJ |  | SHJ-2022-AGGR-SR7b-1 | Port 3/1/4(3G/LTE - 1G SFP) | SHJ-2022-AGGR-SR7b-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 12:28 |  | 25.343092 | 55.399292 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
579 |  |  | ISH5178 |  | ISH5178 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-23 | SHJ |  | SHJ-2016-SCSG-SR7B-1 | esat-2/1/1(3G/LTE - 1G SFP) | SHJ-2016-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 12:17 |  | 25.322048 | 55.387577 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
578 |  |  | IAD5914 |  | IAD5914 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-19 | AUH |  | AUH-2204-SCSG-IXR-R6-1 | Port 1/3/9 (3G/LTE - 1G SFP) | AUH-2204-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 12:12 |  | 24.2794828 | 54.6672744 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
577 |  |  | DXN0802 |  | DXN0802 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-28 | DXB |  | DXB-PALMJ-CSG-IXR-E-2 | Port 1/1/12 (3G/LTE - 1G SFP) | DXB-PALMJ-CSG-IXR-E-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 12:03 |  | 25.107544 | 55.144544 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
576 |  |  | DUB0772 |  | DUB0772 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-15 | DXB |  | DXB-1036-SCSG-IXR-R6-1 | Port 1/3/2 (3G/LTE - 1G SFP) | DXB-1036-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 11:50 |  | 25.2402655 | 55.2510891 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
574 |  |  | AAN0082 |  | AAN0082 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-09 | AUH |  | AAN-6001-AGGR-SR7S-2 | esat-2/1/47 (3G - 1G SFP) | AAN-6001-AGGR-SR7S-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 11:20 |  | 24.225904 | 55.74679 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
573 |  |  | DUB0639 |  | DUB0639 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-07 | DXB |  | DXB-1346-CSG-IXR-E-1 | Port 1/1/13 (3G/LTE - 1G SFP) | DXB-1346-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-06 11:08 |  | 25.289877 | 55.365422 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
572 | WO- IIB-CSG-2023-Order # 572 |  | IAJ5857 |  | IAJ5857 | Cisco NCS540 | BAU | New CSG | Transmission rack not available | XAD |  | AJM | 10G | AJM-2459-SCSG-SR7B-1 | esat-2/1/13 | IAJ-5857-CSG-N540-LD-1 |  | 5 |  | 1 | 1 |  | TI not ready | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Mohammed Faris | 2023-03-03 16:20 |  | 25.403401 | 55.505105 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
571 |  |  | DXB0748 |  | DXB0748 | Nokia IXR-E | 5G | New CSG | RFSed | XAD | 2023-03-20 | DXB | 10G | DXB-JBR-BAHAR-PREAGG-IXR-R6 | Port 1/5/1 | DXB-0748-CSG-IXR-E-1 | NK22373A148 | [6 empty] | Rogelio Pangilinan;#1712 |  |  | Y23-F76734 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-03 11:34 |  | 25.075586 | 55.132494 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
570 |  |  | DUB0214 |  | DUB0214 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-31 | DXB |  | DXB-1026-SCSG-IXR-R6-1 | Port 1/4/7 (3G/LTE - 1G SFP) | DXB-1026-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-03 11:12 |  | 25.173156 | 55.229249 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
568 |  |  | IAD5967 |  | IAD5967 | Passive | Rollout |  | Passive Completed | XAD | 2023-02-07 | AUH |  | AUH-6003-AGGR-SR7B-2 | esat-2/1/59 (3G/LTE - 1G SFP) | AUH-6003-AGGR-SR7B-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 18:02 |  | 24.474879 | 54.348128 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
567 |  |  | IAD5648 |  | IAD5648 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-23 | AUH |  | AUH-2562-SCSG-SR7B-1 | esat-1/1/9( 5G-10G SFP) | AUH-2562-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 17:55 |  | 24.384428 | 54.522486 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
566 |  |  | IAD5876 |  | IAD5876 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-14 | AUH |  | AUH-2410-SCSG-IXR-R6-1 | Port 1/4/8 (3G/LTE - 1G SFP) | AUH-2410-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 17:49 |  | 24.441331 | 54.57055 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
564 |  |  | DXS6546 |  | DXS6546 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-08 | DXB |  | DXB-1516-CSG-SAR-X-1 | Port 1/3/5 ( 3G/LTE- 1G SFP) | DXB-1516-CSG-SAR-X-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 17:24 |  | 25.24635 | 55.30977 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
563 |  |  | AUG4351 |  | AUG4351 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-17 | AUH |  | AUH-6501-AGGR-SR12e-1 | Port 7/1/37 ( 5G-10G SFP) | AUH-6501-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 17:18 |  | 24.36673 | 54.51249 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
562 |  |  | AUG4352 |  | AUG4352 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-14 | AUH |  | AUH-2132-PREAGG-SR7-1 | Port 3/2/12 ( 3G/LTE- 1G SFP) | AUH-2132-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 17:05 |  | 24.348324 | 54.54469 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
561 |  |  | AUG4441 |  | AUG4441 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-15 | AUH |  | AUH-2562-PREAGG-SR7-1 | Port 3/2/18 ( 3G/LTE- 1G SFP) | AUH-2562-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 16:58 |  | 24.35131 | 54.52167 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
560 |  |  | AAN3405 |  | AAN3405 | Passive | 5G+SRAN Migration | Passive patching | Passive Completed | XAD | 2023-05-31 | AUH |  | AAN-2049-SCSG-SR7B-1 | esat-1/1/47( 5G-10G SFP) esat 1/1/50 (3G-LTE) | AAN-2049-SCSG-SR7B-1 | [6 empty] | 3G LTE and 5G with XAD | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 16:47 |  | 24.198142 | 545.598289 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
559 |  |  | AUH2494 |  | AUH2494 | Passive | SRAN + 5G | Passive patching | Passive Completed | XAD | 2023-09-27 | AUH |  | AUH-2495-CSG-IXR-E-1 | 1/1/11 5G and 1/1/12 3G LTE | AUH-2495-CSG-IXR-E-1 | [6 empty] | SRAN and 5G Passive patching | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 16:44 |  | 24.394716 | 54.583471 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
558 |  |  | AUH2493 |  | AUH2493 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-09-08 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | 2/1/16 | AUH-2493-CSG-IXR-E-1 | NK224931376 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-07 | Y23-F106990 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-02 16:43 | AUH_E2470Y_10242_001006003 | 24.393226 | 54.583873 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
557 |  |  | AUH0621 |  | AUH0621 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-22 | AUH |  | AUH-0619-PREAGG-SR7-1 | Port 2/1/4 ( 3G/LTE- 1G SFP) | AUH-0619-PREAGG-SR7-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 16:26 |  | 24.470307 | 54.606019 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
556 |  |  | AUH2495 |  | AUH2495 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-09-08 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | 2/1/20 | AUH-2495-CSG-IXR-E-1 | NK224931420 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-09-07 | Y23-F106972 |  | Nokia |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-02 15:38 | AUH_E2470Y_10242_001006005 | 24.39414 | 54.58188 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
553 |  |  | IAD5823 |  | IAD5823 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-11 | AUH |  | AUH-2036-SCSG-IXR-R6-1 | Port 1/4/8 ( 5G-10G SFP) | AUH-2036-SCSG-IXR-R6-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 15:25 |  | 24.482094 | 54.621173 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
552 |  |  | IADNR5578 |  | IAD5578 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-16 | AUH |  | AUH-6005-AGGR-SR12e-1 | Port 2/1/39( 5G-10G SFP) | AUH-6005-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 15:15 |  | 24.495029 | 54.366391 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
551 |  |  | IDX5808 |  | IDX5808 | Passive | Rollout | Passive patching | Cancelled/on Hold |  | 2023-03-31 | DXB |  | DXB-DSO-DC-AGGR-SR12-1 | esat-1/1/4( 3G/LTE- 1G SFP) | DXB-DSO-DC-AGGR-SR12-1 | [6 empty] | cancelled duplicate entry | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 15:06 |  | 24.112003 | 55.384343 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
550 |  |  | ISH5190 |  | ISH5190 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-04 | SHJ |  | SHJ-2016-SCSG-SR7B-1 | esat-1/1/47( 3G/LTE- 1G SFP) | SHJ-2016-SCSG-SR7B-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 15:03 |  | 25.339555 | 55.390271 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
549 |  |  | DUB0525 |  | DUB0525 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-16 | DXB |  | DXB-DSO-CSG-IXR-E-1 | Port 1/1/12 ( 3G/LTE- 1G SFP) | DXB-DSO-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 12:20 |  | 25.116946 | 55.392394 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
548 |  |  | DUB0906 |  | DUB0906 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-03 | DXB |  | DXB-SiteC-Abdullah-AGG-ASR9912-1 | Port 1/0/36 ( 3G/LTE- 1G SFP) | DXB-SiteC-Abdullah-AGG-ASR9912-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 11:57 |  | 25.098554 | 55.172394 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
547 |  |  | IDX5692 |  | IDX5692 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-04-07 | DXB | 1G | DXB-VILLAPOP-AGGR-SR12e-1 | Port 3/1/24 ( 3G/LTE- 1G SFP) | IDX-5692-CSG-N540-LD-1 | FOC2631N0DY | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-04-01 | Y23-F77709 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-03-02 11:37 | DXB_E3377A_10173_001006002 | 25.118648 | 55.378168 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
546 |  |  | DUB0045 |  | DUB0045 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-02-22 | DXB |  | DXB-6501-AGGR-SR12e-1 | Port 3/1/8 ( 3G/LTE- 1G SFP) | DXB-6501-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 11:23 |  | 25.070183 | 55.127214 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
544 |  |  | AAN0102 |  | AAN0102 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-07 | AUH |  | AAN-6001-AGGR-SR7S-1 | esat-2/1/14 ( 3G/LTE- 1G SFP) | AAN-6001-AGGR-SR7S-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 10:58 |  | 24.237782 | 55.733352 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
543 |  |  | DUB0162 |  | DUB0162 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-23 | DXB |  | DXB-DIC4-CSG-IXR-E-1 | Port 1/1/12 ( 3G/LTE- 1G SFP) | DXB-DIC4-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 10:47 |  | 25.09841 | 55.14111 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
542 |  |  | DUB0138 |  | DUB0138 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-03-23 | DXB |  | DXB-DIC4-CSG-IXR-E-1 | Port 1/1/15 (3G/LTE - 1G SFP) | DXB-DIC4-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-03-02 10:24 |  | 25.09841 | 55.14111 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
541 |  |  | AAN0084 |  | AAN0084 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-03-10 | AUH | 10G | AAN-5002-AGGR-SR12-1 | PORT 10/2/2 | AAN-0084-CSG-N540-LD-1 | FOC2631N0DS |  |  | 1 | 1 |  | Site Completed |  |  | 2023-03-03 | Y23-F75910 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-03-01 22:15 |  | 24.275066 | 55.602697 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
540 |  |  | DXB3906 |  | DXB3906 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-04-13 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/8 | DXB-3906-CSG-N540-LD-1 | FOC2631N0EM | [9 empty] | Y23-F78222 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-02-28 11:37 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
539 |  |  | DXB3593 |  | DXB3593 | Nokia IXR-E | 5G Upgrade |  | Passive Completed | HOI-MEA |  | DXB | 10G | DXB-IC-POP-SCSG-IXR-R6-1 | 1/5/5 | [7 empty] | ISP cabling rectification Only | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-28 11:36 |  | 25.18272 | 55.37624 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
537 |  |  | DXB2043 |  | DXB2043 | Nokia IXR-E | BAU + 5G |  | RFSed | HOI-MEA | 2023-05-22 | DXB | 10G | DXB-VILLAPOP-AGGR-SR12e-1 | 2/1/29 | DXB-2043-CSG-IXR-E-1 | NK224632207 | [8 empty] | 2023-05-19 | Y23-80486 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-02-28 11:28 |  | 25.09059 | 55.40502 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
536 |  |  | DXB1993 |  | DXB1993 | Cisco NCS540 | 5G+Migration |  | RFSed | HOI-MEA | 2023-04-04 | DXB | 1G | DXB-1852-PREAGG-SR7-1 | 5/1/19 | DXB-1993-CSG-N540-LD-1 | FOC2631N0DW | [9 empty] | Y23-F76873 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-02-28 11:24 |  | 25.18041 | 55.5126 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
535 |  |  | DXB3918 |  | DXB3918 | Passive | Migration | Passive patching | Passive Completed | HOI-MEA | 2023-10-09 | DXB | 1G | DXB-1866-SCSG-IXR-R6-1 | 1/6/2 | DXB-1866-SCSG-IXR-R6-1 |  |  |  | 1 | 1 |  | CSG Dismantled - Passive Link Completed | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-28 11:22 |  | 25.27816 | 55.38609 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
534 |  |  | DXN0055 |  | DXN0055 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-15 | DXB | 1G | DXB-ZAFRAN-AGGR-SR12-1 | PORT:3/1/17 | DXB-ZAFRAN-AGGR-SR12-1 | [6 empty] | Passive Completed |  |  | 2023-02-15 |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-02-23 18:11 |  | 25.195833 | 55.269166 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
533 |  |  | AUH0940 |  | AUH0940 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-04-13 | AUH | 1G | AUH-DC-AGGR-SR12e-1 | Port 3/1/16 | AUH-DC-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-23 13:27 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
532 |  |  | AUH0468 |  | AUH0468 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-03-01 | AUH | 1G | AUH-6005-AGGR-SR12e-1 | Port 3/2/6 | AUH-6005-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-23 13:25 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
531 |  |  | DUB0583 |  | DUB0583 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-03-15 | DXB | 1G | DXB-DSO-CSG-IXR-E-1 | 1/1/14 | DXB-DSO-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-23 13:23 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
529 |  |  | IAD5683 |  | IAD5683 | Passive | SRAN + 5G |  | Passive Completed | HOI-MEA | 2023-02-27 | AUH | 1G | AUH-6005-AGGR-SR12e-1 | Port 3/1/7 | AUH-6005-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-23 13:18 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
528 |  |  | IAD5563 |  | IAD5563 | Passive | SRAN + 5G |  | Passive Completed | HOI-MEA | 2023-02-22 | AUH | 1G | AUH-1336-SCSG-SR7B-1 | esat-2/1/10 | AUH-1336-SCSG-SR7B-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-21 17:10 |  | 24.45952 | 54.38032 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
527 |  |  | DXB2788 |  | DXB2788 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | SHAHID | 2023-07-20 | DXB | 10G | DXB-6504-AGGR-SR12e-2 | Port 2/1/30 | DXB-2788-CSG-IXR-E-1 | NK213632331 |  | 2 | 1 | 1 |  | Site Completed |  |  | 2023-04-29 | Y23-F79301 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-21 11:42 | DXB_E3177V_11057_001001001 | 25.0412 | 55.1937 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
526 |  |  | DXB2275 |  | DXB2275 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-05-11 | DXB | 1G | DXB-3145-PREAGG-SR7-1 | Port-5/1/4 | DXB-2275-CSG-IXR-E-1 | NK22403B824 |  | 1 | 1 | 1 | 1 | Site Completed |  |  | 2023-05-06 | Y23-F79759 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-21 11:40 | DXB_E3279R_11481_001001001 | 25.23659 | 55.31397 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
525 |  |  | DXB1642 |  | DXB1642 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-05-30 | DXB | 10G | DXB-6504-AGGR-SR12e-2 | Port-2/1/29 | DXB-1642-CSG-IXR-E-1 | NK22393A629 |  | 4 | 2 | 2 |  | Site completed |  |  | 2023-05-06 | Y23-F79753 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-21 11:37 | DXB_E3577P_10070_001001001 | 25.07197 | 55.56556 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
524 |  |  | DUB0273 |  | DUB0273 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-11-03 | DXB |  | DUB-0812-CSG-N540-LD-1 | Te0/0/0/5 (3G/LTE - 1G SFP) | DUB-0812-CSG-N540-LD-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Cisco |  |  | FALSE | 2023 | Mohammed Faris | 2023-02-21 11:32 |  | 24.984402 | 55.39385 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
523 |  |  | DXN0249 |  | DXN0249 | Cisco NCS540 | BAU |  | Cancelled/on Hold |  |  | DXB | 10G | DXB-1074-SCSG-IXR-R6-1 | 1/3/7 | DXN-0249-CSG-N540-LD-1 | [6 empty] | cancelled from XAD 9-11-2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-02-21 11:29 |  | 24.923996 | 55.027481 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
520 |  |  | AUH2531 |  | AUH2531 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-04-27 | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 3/2/16 | AUH-2531-CSG-N540-LD-1 | FOC2631N0E0 | [5 empty] | RFsed | Aris Dumma;#1292 |  | 2023-04-14 | Y23-F78469 |  | Cisco |  |  | FALSE | 2023 | Nouman Shah | 2023-02-21 10:35 | AUH_E1363Y_10003_001001001 | 23.75161 | 53.51645 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
519 |  |  | AUH2310 |  | AUH2310 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-06-01 | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-1/1/27 | AUH-2310-CSG-IXR-E-1 | NK22393A779 | [6 empty] | Aris Dumma;#1292 |  | 2023-05-30 | Y23-F81312 |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-02-21 10:29 | AUH_E2270D_11812_001001001 | 24.474563 | 54.351835 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
518 |  |  | DXB2299 |  | DXB2299 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-03-14 | DXB | 10G | DXB-6002-AGGR-SR7-2 | Port 3/2/2 | DXB-2299-CSG-N540-LD-1 | FOC2628NTW4 | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F75814 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-02-21 10:02 |  | 25.1693 | 55.378 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
517 |  |  | DUB0722 |  | DUB0722 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-02-20 | DXB |  | DXB-2415-CSG-SAR-X-1 | 1/2/4 | DXB-2415-CSG-SAR-X-1 | NA | [5 empty] | Passive Completed |  |  | 2023-02-20 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-02-17 17:53 |  | 24.874390 | 55.041934 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
516 |  |  | DUB0529 |  | DUB0529 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2023-05-29 | DXB | 1G | DXB-6020-PREAGG-SR7-1 | 2/1/7 | DUB-0529-CSG-IXR-E-1 | NK224632225 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-05-25 | Y23-F80915 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-17 17:37 | DXB_E3177F_10141_001003004 | 25.099001 | 55.172777 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
515 |  |  | FUJ2490 |  | FUJ2490 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-08-17 | FUJ | 1G | FUJ-2433-PREAGG-SR7-1 | Port 3/2/12 | FUJ-2490-CSG-IXR-E-1 | NK22393A446 |  | 1 |  |  |  | site with 2G | Aris Dumma;#1292 |  | 2023-05-12 | Y23-F80067 |  | Nokia |  |  | TRUE | 2023 | Nouman Shah | 2023-02-17 17:34 | MSF_E3975V_10002_001001001 | 24.87762 | 55.98724 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
514 |  |  | DUB0576 |  | DUB0576 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-03 | DXB |  | DXB-VH-SCSG-SR7B-1 | esat-2/1/28 | DXB-VH-SCSG-SR7B-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-03 | [5 empty] | FALSE | 2023 | Mohammed Faris | 2023-02-17 17:33 |  | 25.058264 | 55.199386 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
512 |  |  | DXBNR0370 |  | DXBNR0370 | Nokia IXR-E | 5G+Migration | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-0296A-PREAGG-SR7-1 | Port 2/1/5 | DXB-0370-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Mohammed Faris | 2023-02-17 16:25 |  | 25.2379 | 55.38603 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
511 |  |  | SHJ2244 |  | SHJ2244 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-05-17 | SHJ | 10G | SHJ-2094-SCSG-SR7B-1 | esat-2/1/1 | SHJ-2244-CSG-IXR-E-1 | NK224632151 |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-05-13 | Y23-F80158 |  |  |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-17 11:11 | SHJ_E3380Q_10015_001001001 | 25.342120 | 55.385990 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
510 |  |  | SHJ1451 |  | SHJ1451 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-03-28 | SHJ | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/48 | SHJ-1451-CSG-N540-LD-1 | FOC2629NZPA |  |  | 1 | 1 |  | Site Completed |  |  | 2023-03-25 | Y23-F77230 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-17 11:04 | SHJ_E3480O_10295_001001001 | ‎25.362462 ‎ | ‎55.551360 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
509 |  |  | DUB0285 |  | DUB0285 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-02-20 | DXB |  | DXB-3161-PREAGG-SR7-1 | 2/1/13 | DXB-3161-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-15 13:11 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
508 |  |  | DUB0432 |  | DUB0432 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-02-20 | DXB | 1G | DXB-VILLAPOP-AGGR-SR12e-1 | 3/2/6 | DXB-VILLAPOP-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-15 13:09 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
507 |  |  | DUB0083 |  | DUB0083 | Passive | Rollout |  | Passive Completed | HOI-MEA | 2023-02-14 | DXB | 1G | DXB-BB-AGGR-SR12e-1 | 3/2/7 | DXB-BB-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-15 13:07 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
506 |  |  | DUB0937 |  | DUB0937 | Passive | BAU |  | Passive Completed | HOI-MEA | 2023-02-16 | DXB | 1G | DXB-6020-AGGR-SR12e-1 | 3/1/24 | DXB-6020-AGGR-SR12e-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-15 13:00 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
505 |  |  | AUH3439 |  | AUH3439 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-02-24 | AUH | 10G | AUH-2118-SCSG-SR7B-1 | esat-1/1/28 | AUH-3439-CSG-N540-LD-1 | FOC2602N9T5 | [6 empty] | Aris Dumma;#1292;#Nouman Shah;#1288 |  |  | Y23-F75325 |  | Cisco |  |  | FALSE | 2023 | Nouman Shah | 2023-02-14 20:20 | AUH_E2369N_10425_001001001 | 24.34036345 | 54.46638683 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
504 |  |  | AUH2570 |  | AUH2570 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-10-09 | AUH |  | AUH-0463-CSG-IXR-E-1 | Port 1/1/10 | AUH-0463-CSG-IXR-E-1 |  |  | 1 | 1 | 1 | 1 |  | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-02-14 20:16 |  | 24.40712 | 54.4907 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
503 |  |  | DXN0330 |  | DXN0330 | Passive | Rollout | Passive patching | Passive Completed | NETS | 2023-02-14 | DXB | 1G | [12 empty] | 2023-02-14 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-02-14 16:52 |  | 25.15523 | 55.51093 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
502 | WO- IIB-CSG-2023-Order # 502 |  | AUH0603 |  | AUH0603 | Passive | Migration |  | PTW in progress | HOI-MEA |  | AUH | 1G | AUH-2358-CSG-IXR-E-1 | 1/1/25 | AUH-2358-CSG-IXR-E-1 |  | 5 | 1 | 1 | 1 |  | Building Management Not allowing DU to work anymore. As previous contractors did messy cabling. | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-14 15:43 |  |  |  | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
501 |  |  | AUH2678 |  | AUH2678 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/48 | SCSG |  |  |  | 1 | 1 |  | cancelled from XAD 9-11-2023 | Aris Dumma;#1292 | [7 empty] | FALSE | 2023 | Nouman Shah | 2023-02-14 11:30 |  | 24.401172 | 54.475511 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
499 |  |  | AUH3355 |  | AUH3355 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-04-12 | AUH | 1G | AUH-1416-AGGR-SR12E-1 | esat-1/1/42 | AUH-3355-CSG-N540-LD-1 | FOC2631N0D5 | [6 empty] | Aris Dumma;#1292 |  | 2023-04-11 | Y23-F78259 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-02-13 10:27 | AUH_E2569B_10029_001001001 | 24.38655467 | 54.6167907 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
498 | WO- IIB-CSG-2023-Order # 498 |  | IAD5628 |  | IAD5628 | Cisco NCS540 | Parity | New CSG | Transmission rack not available | XAD |  | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 7/1/22 | AGGR |  | 5 |  |  |  |  | rack is full. required new rack | Aris Dumma;#1292 | [7 empty] | FALSE | 2023 | Nouman Shah | 2023-02-13 10:15 |  | 24.495996 | 54.378893 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
497 |  |  | SHJ3422 |  | SHJ3422 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2023-02-21 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/18 | SHJ-3422-CSG-N540-LD-1 | FOC2624KMLJ |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-02-18 | Y23-F75135 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-11 16:40 | SHJ_E3580K_10003_001001001 | 25.357490 | 55.564110 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
496 |  |  | IAJ5818 |  | IAJ5818 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-02-15 | AJM | 10G | AJM-2459-SCSG-SR7B-1 | esat-2/1/14 | IAJ-5818-CSG-N540-LD-1 | FOC2624KMBE |  |  | 1 | 1 |  | Site Completed |  |  | 2023-02-13 | Y23-F74808 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-11 16:27 | AJM_E3481Q_10289_001001004 | 25.432400 | 55.486900 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
494 |  |  | DXB5263H |  | DXB5263H | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-05-03 | DXB | 1G | DXB-1096-PREAGG-SR7-1 | Port 4/2/3 | DXB-1096-PREAGG-SR7-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-06-10 |  |  | Nokia |  |  | FALSE | 2023 | Mohammed Faris | 2023-02-09 11:33 |  | 25.283440 | 55.364010 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
493 |  |  | AUH0055 |  | AUH0055 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | XAD | 2023-05-09 | AUH | 10G | AUH-6501-AGGR-SR12e-1 | Port 2/1/39 | AUH-0055-CSG-N540-LD-1 | FOC2631N0EK | [6 empty] | Aris Dumma;#1292 |  | 2023-05-04 | Y23-F79622 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-02-09 10:00 | AUH_E2369T_10107_001001001 | 24.32966 | 54.476093 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
492 |  |  | AUH0572 |  | AUH0572 | Passive | BAU + 5G | Passive patching | Passive Completed | SHAHID |  | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/48 | AUH-1222-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed | Aris Dumma;#1292 |  | 2023-07-25 |  |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-02-09 09:55 |  | 24.41976 | 54.44853 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
491 |  |  | SHJ0264 |  | SHJ0264 | Passive | 5G |  | Passive Completed | HOI-MEA | 2022-05-19 | SHJ |  | SHJ-2016-PREAGG-SR7-1 | 4/1/5 | SHJ-2016-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:28 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
490 |  |  | ISH5125 |  | ISH5125 | Passive | 5G |  | Passive Completed | HOI-MEA | 2022-05-19 | SHJ |  | SHJ-2084-SCSG-SR7B-1 | esat-2/1/54 | SHJ-2084-SCSG-SR7B-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:27 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
489 |  |  | DXN0118 |  | DXN0118 | Passive | 5G |  | Passive Completed | HOI-MEA | 2022-05-19 | DXB |  | DXB-2282-PREAGG-SR7-1 |  | DXB-2282-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:26 |  | 25.284424 | 55.353293 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
488 |  |  | DXN0428 |  | DXN0428 | Passive | 5G |  | Passive Completed | HOI-MEA | 2022-05-19 | DXB |  | DXB-3173-PREAGG-SR7b-1 | esat-1/1/36 | DXB-3173-PREAGG-SR7B-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:24 |  | 25.24539 | 55.302517 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
487 |  |  | IAD5369 |  | IAD5369 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/15 | IAD-5241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:22 |  | 24.45583 | 54.614595 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
486 |  |  | IAD5371 |  | IAD5371 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/14 | IAD-6241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:20 |  | 24.45583 | 54.614595 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
485 |  |  | IAD5372 |  | IAD5372 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/13 | IAD-5241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:19 |  | 24.45583 | 54.614595 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
484 |  |  | IAD5243 |  | IAD5243 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/12 | IAD-5241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:17 |  | 24.45583 | 54.614595 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
483 |  |  | IAD5246 |  | IAD5246 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/11 | IAD-5241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:15 |  | 24.45583 | 54.614595 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
482 |  |  | IAD5245 |  | IAD5245 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/10 | IAD-5241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:13 |  | 24.45583 | 54.614595 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
481 |  |  | IAD5241 |  | IAD5241 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-05-19 | AUH |  | IAD-5241-CSG-IXR-E-1 | 1/1/9 | IAD-5241-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:11 |  | 24.45601 | 54.61371 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
480 |  |  | UAQ3619 |  | UAQ3619 | Passive | 5G+Migration |  | Passive Completed | HOI-MEA | 2022-04-27 | UAQ |  | UAQ-2012-PREAGG-SR7-1 | 4/1/14, 4/1/15 & 4/1/16 | UAQ-2012-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:10 |  | 25.502004 | 55.560167 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
479 |  |  | AUH3256 |  | AUH3256 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-28 | AUH |  | AUH-2640-CSG-IXR-E-1 | 1/1/8 | AUH-2640-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:08 |  | 24.4118346933 | 54.9481985719 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
478 |  |  | AUH3627 |  | AUH3627 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-26 | AUH |  | AUH-khazna-AGGR-SR12E-2 | 5/1/15 | AUH-khazna-AGGR-SR12E-2 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:05 |  | 24.417973 | 54.606436 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
477 |  |  | AUH3538 |  | AUH3538 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-27 | AUH |  | AUH-khazna-AGGR-SR12E-2 | 5/1/14 | AUH-khazna-AGGR-SR12E-2 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:03 |  | 24.40981 | 54.60981 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
476 |  |  | AUH2783 |  | AUH2783 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-28 | AUH |  | AUH-2639-CSG-IXR-E-1 | 1/1/8 | AUH-2639-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:02 |  | 24.41091 | 54.87276 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
475 |  |  | AUH2605 |  | AUH2605 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-28 | AUH |  | AUH-2606-CSG-IXR-E-1 | 1/1/8 | AUH-2606-CSG-IXR-E-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 11:00 |  | 24.4369 | 54.9048 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
474 |  |  | AUH2325 |  | AUH2325 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-27 | AUH |  | AUH-1093-PREAGG-SR7-1 | 3/2/10 | AUH-1093-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 10:58 |  | 24.435107 | 54.43841 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
473 |  |  | AAN0086 |  | AAN0086 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-06-08 | AUH |  | AAN-2043-PREAGG-SR7-1 | 2/1/10 & 2/1/11 | AAN-2043-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 10:55 |  | 24.23298 | 55.72456 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
472 |  |  | AAN2456 |  | AAN2456 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-26 | AUH |  | AAN-6001-AGGR-SR12-2 | 2/2/17 | AAN-6001-AGGR-SR12-2 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 10:51 |  | 24.224025 | 55.766073 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
471 |  |  | AAN2855 |  | AAN2855 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-04-28 | AUH |  | AAN-2055-CSG-SAR-8-1 | 1/2/2 | AAN-2055-CSG-SAR-8-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 10:44 |  | 24.590901 | 55.746338 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
470 |  |  | AAG6032 |  | AAG6032 | Passive | Migration |  | Passive Completed | HOI-MEA | 2022-06-08 | AUH | 1G | AAN-2043-PREAGG-SR7-1 | 3/1/2 | AAN-2043-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 10:42 |  | 24.24575 | 55.71282 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
469 |  |  | AAN3105 |  | AAN3105 | Passive | 5G+Migration |  | Passive Completed | HOI-MEA | 2022-04-26 | AUH | 1G | AAN-2043-PREAGG-SR7-1 | 3/2/6 | AAN-2043-PREAGG-SR7-1 | [15 empty] | FALSE | 2023 | Syed Shahzaib | 2023-02-07 10:38 |  | 24.248355 | 55.718457 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
467 |  |  | DXB2497 |  | DXB2497 | To Be Confirmed | Rollout | New CSG | Cancelled/on Hold |  |  | DXB | 10G | DXB-3160-PREAGG-SR7-1 | Port 1/1/2 | TBA | [6 empty] | cancelled from XAD 9-11-2023 | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-02-05 20:17 |  | 25.262370 | 55.372630 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
465 |  |  | AAN3221 |  | AAN3221 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-02-20 | AUH | 1G | AAN-2302-PREAGG-SR7-1 | Port 2/1/6 | AAN-3221-CSG-N540-LD-1 | FOC2624KMG7 |  |  | 1 | 1 | 1 | Site is RFSed | Aris Dumma;#1292 |  |  | Y23-F75091 |  | Cisco |  |  | FALSE | 2023 | Nouman Shah | 2023-02-05 20:07 |  | 24.09008 | 55.695424 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
464 |  |  | AUH3130 |  | AUH3130 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | XAD | 2023-02-13 | AUH | 10G | AUH-2205-PREAGG-SR7-1 | Port 3/1/3 | AUH-3130-CSG-N540-LD-1 | FOC2633NBY7 |  |  | 1 | 1 | 1 |  | Aris Dumma;#1292;#Nouman Shah;#1288 |  |  | Y23-F7426 |  | Cisco |  |  | FALSE | 2023 | Nouman Shah | 2023-02-05 20:02 | AUH_E2470U_10966_001001001 | 24.3982 | 54.5017 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
463 |  |  | RAK3345 |  | RAK3345 | To Be Confirmed | 5G+Migration | New CSG | Cancelled/on Hold |  |  | RAK | 10G | RAK2028_PREAGG_SR7-1 | Port 1/1/8 | PREAGG | FOC2633NLZ1 |  |  | 1 | 1 | 1 | cancelled from XAD 9-11-2023 | Aris Dumma;#1292 | [7 empty] | FALSE | 2023 | Nouman Shah | 2023-02-05 19:57 |  | 25.7174 | 55.8411 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
462 | WO- IIB-CSG-2023-Order # 462 |  | RAK3344 |  | RAK3344 | Cisco NCS540 | 5G+Migration | New CSG | OSP Issue | XAD |  | RAK | 10G | NE506 (RAK2028-UAQDC) | RAK2028_PREAGG_SR7-1_RACK-1/SH-1 /Front Port#C2 OTN RK-1/NE506 C/10/TX2/RX2‎ | RAK-3344-CSG-N540-LD-1 |  | 5 |  | 1 | 1 | 1 | BM reject OSP installed in the building | Aris Dumma;#1292 |  |  |  |  | XAD |  |  | FALSE | 2023 | Nouman Shah | 2023-02-05 19:52 |  | 25.7147 | 55.8325 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
461 |  |  | DXB0062 |  | DXB0062 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-02-15 | DXB | 10G | DXB-2282-PREAGG-SR7-1 | PORT 4/1/5 | DXB-0062-CSG-IXR-E-1 | NK22393A041 | [5 empty] | Site Completed |  |  | 2023-02-14 | Y23-F74882 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-04 11:01 | DXB_E3279E_10922_001001001 | 25.29055 | 55.35325 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
460 |  |  | DXB0027 |  | DXB0027 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-06-09 | DXB | 10G | DXB-1090-SCSG-SR7B-1 | esat-1/1/26 | DXB-0027-CSG-IXR-E | NK224632177 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-01 | Y23-F100134 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-02-04 10:48 | DXB_E3279H_10599_001004002 | 25.27876 | 55.3038 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
455 |  |  | AUH2721 |  | AUH2721 | Cisco NCS540 | SRAN + 5G | Passive patching | Cancelled/on Hold |  |  | AUH | 10G | AUH-MASDARCITY-PREAGG-SR7-1 | Port 3/1/2 | AUH-2721-CSG-N540-LD-1 | [6 empty] | cancelled from XAD 9-11-2023 | [8 empty] | FALSE | 2023 | Mohammed Faris | 2023-02-04 09:48 |  | 24.433722 | 54.619853° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
441 |  |  | DXB2171 |  | DXB2171 | Cisco NCS540 | 5G |  | RFSed | HOI-MEA | 2023-02-15 | DXB | 10G | DXB-JI-POP-PREAGG-IXR-R6-2 | 1/3/3 | DXB-2171-CSG-N540-LD-1 | FOC2631N0EL | [9 empty] | Y23-F74788 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-31 14:59 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
440 |  |  | ISH5189 |  | ISH5189 | Nokia IXR-E |  |  | RFSed | HOI-MEA | 2023-07-20 | SHJ |  | SHJ-2547-SCSG-SR7B-1 | esat-1/1/6 | ISH-5189-CSG-IXR-E-1 | NK223433529 | [9 empty] | Y23-102987 |  |  |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-31 14:57 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
436 |  |  | ISH5217 |  | ISH5217 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-03-28 | SHJ | 10G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/58 | ISH-5217-CSG-N540-LD-1 | FOC2633NLZ1 |  |  |  | 1 | 1 |  | Aris Dumma;#1292 |  |  | Y23-F77224 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-01-30 11:58 |  | 25.318722 | 55.377425 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
435 |  |  | IDX0939C |  | IDX0939C | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-02-13 | DXB | 1G | DXB-2302-PREAGG-SR7-1 | Port 3/2/15 | IDX-0939C-CSG-N540-LD-1 | FOC2633NM31 | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F74598 |  | Cisco |  |  | FALSE | 2023 | Nouman Shah | 2023-01-30 11:52 |  | 25.12931 | 55.36329 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
434 |  |  | AJM1265 |  | AJM1265 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-03-27 | AJM | 10G | AJM-2459-SCSG-SR7B-1 | esat-2/1/12 | AJM-1265-CSG-N540-LD-1 | FOC2633NBYH |  |  | 1 | 1 | 1 | Site Completed |  |  | 2023-03-21 | Y23-F76992 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-28 12:32 | AJM_E3481O_10169_001001001 | 25.438458 | 55.551203 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
420 |  |  | DXN0105 |  | DXN0105 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-04-13 | DXB |  | DXB-2295-CSG-IXR-E-1 | Port 1/1/15 (3G/LTE - 1G SFP) | DXB-2295-CSG-IXR-E-1 | [6 empty] | Passive completed by shahidtech | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-01-26 16:24 |  | 25.201750 | 55.349901 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
419 |  |  | IDX0963D |  | IDX0963D | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-08 | DXB |  | DXB-DSO-DC-AGGR-SR12-1 | esat-1/1/3 (3G/LTE - 1G SFP) | DXB-DSO-DC-AGGR-SR12-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-01-26 16:19 |  | 25.13348 | 55.386403 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
418 |  |  | DXB5148I |  | DXB5148I | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-01-27 | DXB |  | DXB-DSO-DC-AGGR-SR12-1 | esat-1/1/5 (3G/LTE - 1G SFP) | DXB-DSO-DC-AGGR-SR12-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-01-26 16:16 |  | 25.1235 | 55.4026 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
417 |  |  | DUB0392 |  | DUB0392 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-27 | DXB |  | DXB-DMTC-SCSG-SR7B-1 | esat-1/1/17(3G/LTE - 1G SFP) | DXB-DMTC-SCSG-SR7B-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-01-26 16:09 |  | 25.045747 | 55.233162 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
415 |  |  | DXB3885 |  | DXB3885 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-03-22 | DXB | 10G | DXB-1074-SCSG-IXR-R6-1 | Port 1/6/5 | DXB-3885-CSG-N540-LD-1 | FOC2614N0HD |  |  | 1 | 1 | 1 |  | Aris Dumma;#1292 |  |  | Y23-F76737 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-01-26 12:56 |  | 24.985396 | 55.14014 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
414 |  |  | DXB1046 |  | DXB1046 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-08 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/7 | DXB-1046-CSG-IXR-E-1 | NK22393A428 |  | 3 | 2 | 2 |  |  | Aris Dumma;#1292 |  | 2023-05-03 | Y23-F79536 |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-01-26 12:48 | DXB_E3279H_10201_001001001 | 25.27257 | 55.30949 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
411 | WO- IIB-CSG-2023-Order # 411 |  | DXB5236E |  | DXB5236E | Cisco NCS540 | Migration | New CSG | Handover | XAD |  | DXB | 10G | DXB-2583-SCSG-SR7B-1 | esat-1/1/42 | DXB-5236E-CSG-N540-LD-1 |  | 5 |  |  |  |  | no rectifier available / cannot proceed with passive OSP more than 10km | Rogelio Pangilinan;#1712 |  |  | Y23-F75511 |  | Cisco |  |  | FALSE | 2023 | Nouman Shah | 2023-01-26 11:29 |  | 24.90862 | 55.06954 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
410 |  |  | IBS-FTK-21-3595 |  | IAD5922 | Cisco NCS540 | Rollout | New CSG | RFSed | NETS | 2023-04-28 | AUH | 10G | AUH-5004-SCSG-SR7B-1 | Port 2/2/5 | IAD-5922-CSG-N540-LD-1 | FOC2610P43A |  |  | 1 | 1 | 1 | Site is RFS | Arif Ahmad;#308 |  | 2023-04-27 | Y23-F79083 |  | Cisco |  |  | FALSE | 2023 | Arif Ahmad | 2023-01-25 19:44 | AUH_E2673N_10010_001001004 | 24.708742 | 54.742877 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
409 |  |  | IBS-SS-19-1118 |  | IAD5356 | Passive | BAU | Passive patching | Passive Completed | NETS | 2023-02-01 | AUH | 1G | AUH-2023-CSG-SAR-X-1 | Port 1/2/6 3G LTE and Port 1/3/3 5G link | [7 empty] | both 3G and LTE , 5G link is done IAD5356- AUH-2023-CSG-SAR-X-1- Port 1/2/6 3G LTE Port 1/3/3 5G Link |  |  | 2023-02-01 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-01-25 19:35 |  | 24.468040 | 54.339096 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
408 |  |  | IBS-FTK-18-0298 |  | IDX5222 | Passive | Rollout | Passive patching | Passive Completed | NETS | 2023-02-06 | DXB | 1G | DXB-JI-POP-PREAGG-IXR-R6-2 | Port 1/2/3 | [10 empty] | 2023-02-06 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-01-25 19:32 |  | 25.066550 | 55.148830 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
407 |  |  | IBS-FTK-21-3741 |  | DUB0172 | Passive | Rollout | Passive patching | Passive Completed | NETS | 2023-02-13 | DXB | 1G | DXB-JPPOP-CSG-IXR-E-1 | Port 1/1/12 |  |  |  |  | 1 | 1 | 1 |  |  |  | 2023-02-13 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-01-25 19:29 |  | 25.052510 | 55.201150 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
406 |  |  | IBS-FTK-20-1640 |  | DXN0675 | Passive | Rollout | Passive patching | Passive in Progress | NETS |  | DXB | 1G | DXB-6020-PREAGG-SR7-1 | Port 3/2/4 | [16 empty] | FALSE | 2023 | Arif Ahmad | 2023-01-25 19:27 |  | 25.109022 | 55.203577 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
404 |  |  | DUB0692 |  | DUB0692 | Passive | Rollout | Passive patching | Passive Completed | NETS | 2023-01-25 | DXB | 1G | DXB-VH-SCSG-SR7B-1 | esat-1/1/37 | [10 empty] | 2023-01-25 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-01-25 19:09 |  | 25.065640 | 55.209000 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
398 |  |  | AAN0101 |  | AAN0101 | Cisco NCS540 | SRAN + 5G | New CSG | RFSed | SHAHID | 2023-02-24 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/60 | AAN-0101-CSG-N540-LD-1 | FOC2633NBXR |  |  | 1 | 1 |  | Site Completed |  |  | 2023-02-23 | Y23-F75403 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-25 12:36 | AAN_E3668X_10025_001001001 | 24.237782 | 55.733352 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
397 |  |  | AUH0802 |  | AUH0802 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-02-13 | AUH | 10G | AUH-6005-AGGR-SR12e-1 | Port 7/1/33 | AUH-0802-CSG-IXR-E-1 | NK22393A686 |  | 1 | 1 | 1 |  | Site Completed |  |  | 2023-02-10 | Y23-F74680 |  | Nokia |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-25 12:30 | AUH_E2271Y_11099_001018001 | 24.484902 | 54.375054 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
396 |  |  | AUH2823 |  | AUH2823 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-02-07 | AUH | 1G | AUH-2836-PREAGG-SR7-1 | Port 3/2/18 | AUH-2823-CSG-N540-LD-1 | FOC2624KMDM |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2023-02-06 | Y23-F74450 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-25 12:25 | AUH_E1362N_10001_001001001 | 23.70299 | 53.48473 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
395 |  |  | AUH3268 |  | AUH3268 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-03-24 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | esat-1/1/57 | AUH-3268-CSG-N540-LD-1 | FOC2624KMDV |  |  | 1 | 2 |  | Site Completed |  |  | 2023-02-10 | Y22-F74658 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-25 12:22 | AUH_E2469G_11365_001001001 | 24.35828 | 54.507727 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
393 |  |  | AJM1338 |  | AJM1338 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 2023-03-24 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-1/1/10 | AJM-1338-CSG-N540-LD-1 | FOC2616NXYW |  |  | 1 | 1 |  | Site Completed |  |  | 2023-03-21 | Y23-F76959 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-25 12:15 | AJM_E3381Y_13975_001001001 | 25.408591 | 55.451001 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
374 |  |  | AUH3627 |  | AUH3627 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-02-10 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-2 | Port 7/1/15 | AUH-3627-CSG-N540-LD-1 | FOC2631N0D0 |  |  | 1 | 1 | 1 |  | Aris Dumma;#1292 |  |  | Y23-F74586 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-01-23 17:24 |  | 24.417973 | 54.606436 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
373 |  |  | IAD5369 |  | IAD5369 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-06-07 | AUH | 10G | AUH-2410-SCSG-IXR-R6-1 | Port 1/3/7 | IAD-5369-CSG-IXR-E-1 | NK224632247 | [8 empty] | 2023-06-03 | Y23-F100203 |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-01-23 17:19 | AUH_E2570G_10024_001001002 | 24.45583 | 54.614595 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
347 |  |  | IAD5266 |  | IAD5266 | Passive | Migration | Passive patching | No OSP | XAD |  | AUH |  | AUH-2410-SCSG-IXR-R6-1 | 1/2/6 | AUH-2410-SCSG-IXR-R6-1 | [6 empty] | OSP not possible Mohaned 8-21-2023 | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-01-23 12:44 |  | 24.443577 | 54.590812 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
346 |  |  | AUH5560D |  | AUH5560D | Passive | Migration | Passive patching | Access Issues | XAD |  | AUH |  | N/A |  | N/A |  | 5 | [5 empty] | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-23 12:41 |  | 24.493752 | 54.599716 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
345 |  |  | IAD5778 |  | IAD5778 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-22 | AUH | 1G | AUH-6003-AGGR-SR7B-2 | port-3/1/39 | AUH-6003-AGGR-SR7B-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-22 |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-01-23 12:35 |  | 24.478291 | 54.351832 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
344 |  |  | IAD5254 |  | IAD5254 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-05 | AUH | 1G | AUH-KHAZNA-AGG-SR12e-1 | 7/1/26 | AUH-KHAZNA-AGG-SR12e-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-05 | [5 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-23 12:30 |  | 24.444252 | 54.612118 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
342 |  |  | IAD5579 |  | IAD5579 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-12 | AUH | 1G | AUH-6003-AGGR-SR7B-1 | esat-2/1/3 | AUH-6003-AGGR-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-12 | [5 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-23 12:14 |  | 24.4712997 | 54.3689128 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
340 | WO- IIB-CSG-2023-Order # 340 |  | AUH0674 |  | AUH0674 | Passive | Migration | Passive patching | OSP Issue | XAD |  | AUH |  | AUH-2911-PREAGG-SR7-1 | Port 2/1/11 | AUH-2911-PREAGG-SR7-1 |  | 5 |  |  |  |  | * | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-23 11:55 |  | 24.0896 | 52.64443 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
338 |  |  | AJM5999I |  | AJM5999I | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | AJM | 1G | AJM-6001-SCSG-SR7B-1 | esat-2/1/6 | AJM-6001-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-19 |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 17:39 |  | 25.419057 | 54.466105 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
337 |  |  | AJM5999J |  | AJM5999J | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | AJM | 1G | AJM-6001-SCSG-SR7B-1 | esat-2/1/7 | AJM-6001-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-19 |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 17:29 |  | 25.419057 | 55.453022 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
336 |  |  | AUH0581 |  | AUH0581 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-31 | AUH | 1G | AUH-2358-CSG-IXR-E-1 | Port-1/1/2 | AUH-2358-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-14 |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 17:22 |  | 24.413090 | 54.49166 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
335 |  |  | IAD5700 |  | IAD5700 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-06 | AUH | 1G | AUH-1097-PREAGG-SR7-1 | 4/2/9 | AUH-1097-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-06 | [5 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 10:49 |  | 24.430334 | 54.466105 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
334 |  |  | IAD5651 |  | IAD5651 | Passive | Migration | Passive patching | No OSP | XAD |  | AUH | 1G | AUH-5004-PREAGG-SR7-1 | 4/1/18 | AUH-5004-PREAGG-SR7-1 | [6 empty] | incorrect OSP in portal. NO OSP on site | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 10:41 |  | 24.66521 | 54.77259 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
333 |  |  | IAD5637 |  | IAD5637 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-24 | AUH | 1G | AUH-6003-AGGR-SR7B-2 | esat-1/1/47 | AUH-6003-AGGR-SR7B-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-03-24 | [5 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 10:33 |  | 24.4842905 | 54.3547769 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
332 |  |  | IAD5448 |  | IAD5448 | Passive | Migration | Passive patching | No OSP | XAD |  | AUH |  | AUH-6005-AGGR-SR12e-1 | 3/1/5 | AUH-6005-AGGR-SR12e-1 | [6 empty] | no OSP | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 10:25 |  | 24.46829 | 54.34081 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
331 |  |  | IAD5548 |  | IAD5548 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-12 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | 2/1/27 | AUH-6005-AGGR-SR12e-2 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-05-12 | [5 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-21 10:14 |  | 24.487848 | 54.372616 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
327 |  |  | IBS-MOD-21-2195 |  | IAD5581 | Passive | Migration | Passive patching | Passive Completed | NETS | 2023-01-25 | AUH |  | AUH-6005-AGGR-SR12e-2 | Port 2/1/39 | [10 empty] | 2023-01-25 | [5 empty] | FALSE | 2023 | Arif Ahmad | 2023-01-19 17:19 |  | 24.499570 | 54.389097 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
322 |  |  | SHJ1490 |  | SHJ1490 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-03-31 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/7 | SHJ-1489-CSG-N540-LD-1 | FOC2624KMFH |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F77296 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-19 16:14 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
321 |  |  | SHJ1489 |  | SHJ1489 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-03-29 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/6 | SHJ-1489-CSG-N540-LD-1 | FOC2624KMFH |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F77338 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-19 16:13 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
320 |  |  | SHJ1483 |  | SHJ1483 | Cisco NCS540 | Rollout |  | RFSed | HOI-MEA | 2023-03-29 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/8 | SHJ-1483-CSG-N540-LD-1 | FOC2631N0CZ |  |  | 1 | 1 | 1 |  |  |  |  | Y23-F77332 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-19 16:11 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
309 |  |  | DXB2979 |  | DXB2979 | Passive to CSG | 5G+Migration | New CSG | RFSed | XAD | 2023-09-01 | DXB | 10G | DXB-1852-SCSG-IXR-R6D-1 | port 1/6/c20 | DXB-2979-CSG-IXR-E-1 | NK224931373 | [5 empty] | passive completed by NETS. New CSG request assigned to XAD |  |  | 2023-08-31 | Y23-F106135 | Nokia | Nokia |  |  | TRUE | 2023 | Arif Ahmad | 2023-01-19 10:48 | DXB_E3478D_10178_001001001 | 25.205682 | 55.521104 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
308 |  |  | IBS-SS-21-2128 |  | ISH5153 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-01-31 | SHJ | 1G | SHJ-6002-AGGR-SR7-1 | Port 2/2/22 | ISH-5153-CSG-N540-LD-1 | FOC2624KMLY |  |  | 1 | 1 |  | Site Completed |  |  | 2023-01-26 | Y22-F73762 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-18 16:53 | SHJ_E3379C_12239_001001001 | 25.292842 | 55.414086 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
304 |  |  | DXB3567 |  | DXB3567 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-01-27 | DXB | 10G | DXB-3724-AGGR-SR12e-1 | 7/1/27 | DXB-3567-CSG-N540-LD-1 | FOC2631N0EE | [5 empty] | Site Completed |  |  | 2023-01-26 | Y22-F73755 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-18 15:34 |  | 25.270337 | 55.435415 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
303 |  |  | IBS-FTK-21-3349 |  | IAJ5838 | Cisco NCS540 | Rollout | New CSG | RFSed | NETS | 2023-02-17 | SHJ | 10G | AJM-2459-SCSG-SR7B-1 | esat-2/1/10 | IAJ-5838-CSG-N540-LD-1 | FOC2633NBY9 |  |  | 1 | 1 | 1 |  | ISP Planning;#234;#Arif Ahmad;#308 |  | 2023-02-01 | Y23-F74194 |  | Cisco |  |  | FALSE | 2023 | Arif Ahmad | 2023-01-18 14:56 | AJM_E3480A_12320_001001001 | 25.394202 | 55.472543 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
302 |  |  | AAN0122 |  | AAN0122 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-01-09 | AUH |  | AAN-2019-SCSG-IXR-R6-1 | Port 1/4/2 (3G/LTE - 1G SFP) | AAN-2019-SCSG-IXR-R6-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-01-18 12:11 |  | 24.207522 | 55.727729 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
301 |  |  | IAD5870 |  | IAD5870 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-04-07 | AUH |  | AUH-0670-CSG-IXR-E-1 | Port 1/1/9 | AUH-0670-CSG-IXR-E-1 |  |  |  | 1 | 1 | 1 |  | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2023 | Nouman Shah | 2023-01-18 11:50 |  | 24.496814 | 54.383259 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
300 |  |  | IAD5555 |  | IAD5555 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-15 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | 2/1/26 | AUH-6005-AGGR-SR12e-2 | [7 empty] | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-18 11:20 |  | 24.486361 | 54.373835 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
299 |  |  | IAD5351 |  | IAD5351 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2023-06-22 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | Port 2/1/26 | IAD-5351-CSG-IXR-E-1 | NK22393A633 |  |  | 1 | 1 |  | Site Completed |  |  | 2023-06-02 | Y23-F100227 |  | Nokia |  |  | TRUE | 2023 | Muhammad Shoaib | 2023-01-18 11:14 | AUH_E2570L_10040_001001002 | 24.447799 | 24.489604 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
298 |  |  | AAN3589 |  | AAN3589 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-30 | AUH | 1G | AAN-2021-PREAGG-SR7-1 | Port 2/1/8 | AAN-3589-CSG-N540-LD-1 | FOC2624KMFB |  |  | 1 | 1 |  |  | Aris Dumma;#1292 |  | 2023-01-27 | Y22-F73808 |  | Cisco |  |  | TRUE | 2023 | Nouman Shah | 2023-01-18 11:10 |  | 24.190649 | 55.839687 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
297 |  |  | DXB3683 |  | DXB3683 | Cisco NCS540 | 5G | New CSG | RFSed | SHAHID | 2023-01-26 | DXB | 10G | DXB-1852-PREAGG-SR7-1 | port 5/1/18 | DXB-3683-CSG-N540-LD-1 | FOC2633NBYS | [5 empty] | Site Completed |  |  | 2023-01-25 | Y22-F73643 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-18 10:16 | DXB_E3479S_10142_001001001 | 25.24628 | 55.52972 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
295 |  |  | AUH0723 |  | AUH0723 | Passive | Rollout | Passive patching | Cancelled/on Hold | SHAHID |  | AUH | 1G | AUH-1090-PREAGG-SR7-1 | 4/2/7 | AUH-1090-PREAGG-SR7-1 | [6 empty] | BM Not Approved Access for DU /Mail shared to tasif on 1/4/2023 | [8 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-17 16:26 |  | 24.44632 | 54.43505 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
294 | WO- IIB-CSG-2023-Order # 294 |  | AUH5811F |  | AUH5811F | Passive | Rollout | Passive patching | PTW in progress | XAD |  | AUH | 1G | AUH-2713-PREAGG-SRa8-1 | Port 2/2/19 | AUH-2713-PREAGG-SRa8-1 |  | 5 |  |  |  |  | * | [8 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-17 16:18 |  | 24.285281 | 54.471685 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
293 | WO- IIB-CSG-2023-Order # 293 |  | IAD5174 |  | IAD5174 | Passive | Rollout | Passive patching | OSP Issue | XAD |  | AUH | 1G | AUH-2132-SCSG-SR7B-1 | esat-1/1/55 | AUH-2132-SCSG-SR7B-1 |  | 5 |  |  |  |  | OSP terminated in different building | [8 empty] | FALSE | 2023 | Muhammad Shoaib | 2023-01-17 16:07 |  | 24.39775 | 54.55185 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
292 | WO- IIB-CSG-2023-Order # 292 |  | AJM0932 |  | AJM0932 | Cisco NCS540 | 5G+Migration |  | Dewa/Sewa Power not available | HOI-MEA |  | AJM | 10G | AJM-2450-SCSG-SR7B-1 | esat-2/1/47 |  | FOC2624KNEU | 5 |  | 1 | 1 | 1 | Rectifier Modiles full | [8 empty] | FALSE | 2023 | Syed Shahzaib | 2023-01-16 10:08 |  |  |  | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
291 |  |  | IBS-FTK-21-2042 |  | ISH5130 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-01-18 | SHJ | 10G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/56 | ISH-5130-CSG-N540-LD-1 | FOC2624KMFW |  |  | 1 | 1 |  | Site Completed |  |  | 2023-01-17 | Y22-F73169 |  | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-13 16:43 | SHJ_E3379A_10666_001001001 | 25.305261 | 55.365206 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
290 |  |  | ISH5204 |  | ISH5204 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-01-06 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat: 2/1/57 | SHJ-2580-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-01-06 |  |  | Nokia |  |  | FALSE | 2023 | Muhammad Shoaib | 2023-01-12 19:20 |  | 25.307456 | 55.373533 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
288 |  |  | AAN3129 |  | AAN3129 | Cisco NCS540 | Migration | New CSG | RFSed | NETS | 2023-01-30 | AUH | 1G | AAN-5002-AGGR-SR12-1 | Port 1/1/10 | AAN-3129-CSG-N540-LD-1 | FOC2624KMGC | [8 empty] | 2023-01-23 | Y22-F73539 | Cisco SFP-10/25G LR | Cisco |  |  | FALSE | 2023 | Arif Ahmad | 2023-01-12 14:07 |  | 24.242725 | 55.332942 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
287 |  |  | AUH3407 |  | AUH3407 | Cisco NCS540 | Migration | New CSG | RFSed | NETS | 2023-01-30 | AUH | 10G | AUH-5004-SCSG-SR7B-1 | esat-2/1/36 | AUH-3407-CSG-N540-LD-1 | FOC2624KNP2 | [8 empty] | 2023-01-23 | Y22-F73543 | Cisco SFP-10/25G LR | Cisco |  |  | TRUE | 2023 | Arif Ahmad | 2023-01-12 14:07 |  | 24.618253 | 54.8357044 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
286 |  |  | AUH3786 |  | AUH3786 | Cisco NCS540 | Migration | New CSG | RFSed | NETS | 2023-01-30 | AUH | 10G | AUH-2929-PREAGG-SRa8-1 | Port 1/1/10 | AUH-3786-CSG-N540-LD-1 | FOC2624K9P9 | [8 empty] | 2023-01-23 | Y22-F73541 | Cisco SFP-10/25G LR | Cisco |  |  | TRUE | 2023 | Arif Ahmad | 2023-01-12 14:06 |  | 23.012720 | 54.17865 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
285 |  |  | AUH6357 |  | AUH6357 | Cisco NCS540 | Migration | New CSG | RFSed | NETS | 2023-01-30 | AUH | 10G | AUH-2836-PREAGG-SR7-1 | Port 3/2/17 | AUH-6357-CSG-N540-LD-1 | FOC2624KMFZ | [8 empty] | 2023-01-23 | Y22-F73546 | Cisco SFP-10/25G LR | Cisco |  |  | TRUE | 2023 | Arif Ahmad | 2023-01-12 14:06 |  | 24.497011 | 54.934841 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
284 |  |  | DXB3093 |  | DXB3093 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-01-20 | DXB | 10G | DXB-FCPOP-SCSG-SR7B-1 | esat-1/1/59 | DXB-3093-CSG-N540-LD-1 | FOC2624KNQJ | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-20 | Y22-F73309 | Cisco SFP-25G ER | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-12 10:19 | DXB_E3276G_13684_001001001 | 25.000007 | 55.289880 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
283 |  |  | AAN3383 |  | AAN3383 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-23 | AUH | 10G | AAN-2302-PREAGG-SR7-1 | Port 1/1/2 | AAN-3383-CSG-N540-LD-1 | FOC2633NMF2I | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-23 | Y22-F73478 | Cisco SFP-25G ER | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-11 13:49 | AAN_E3666N_10002_001001001 | 24.086996 | 55.73134 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
282 |  |  | IAD5509 |  | IAD5509 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-23 | AUH | 10G | AUH-6003-AGGR-SR7B-2 | esat-2/1/31 | IAD-5509-CSG-N540-LD-1 | FOC2624KMED |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2023-01-20 | Y22-F73393 | Cisco SFP-25G ER | Cisco |  |  | TRUE | 2023 | Mohammed Faris | 2023-01-11 13:44 | AUH_E2270D_10751_001001001 | 24.4803 | 54.354736 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
279 |  |  | AUH6387 |  | AUH6387 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-11-14 | AUH |  | AUH-2928-CSG IXR-E-1 | Port 1/1/12 (5G Link) | AUH-2928-CSG IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  | Cisco SFP-25G ER | Nokia |  |  | FALSE | 2023 | Aris Dumma | 2023-01-11 13:21 |  | 23.06986 | 54.093835 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
278 |  |  | AAN3556 |  | AAN3556 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-02-22 | AUH | 10G | AAN-6001-AGGR-SR12-1 | 10/2/9 | AAN-3556-CSG-N540-LD-1 | FOC2638N26T |  |  | 1 | 1 | [5 empty] | Y23-F75093 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-11 13:17 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
277 |  |  | AAN3593 |  | AAN3593 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-03-14 | AUH | 10G | AAN-2059-PREAGG-SR7-1 | Port 5/1/5 | AAN-3593-CSG-N540-LD-1 | FOC2624KNP0 |  |  | 1 | 1 | [5 empty] | Y23-F75120 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-11 13:15 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
276 |  |  | AUH3763 |  | AUH3763 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-04-13 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/17 | AUH-3763-CSG-N540-LD-1 | FOC2631N0E9 |  |  | 1 | 1 | [5 empty] | Y23-F76089 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-11 13:10 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
275 |  |  | AAN2627 |  | AAN2627 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-02-28 | AUH | 1G | AAN-2302-PREAGG-SR7-1 | Port 3/2/18 | AAN-2627-CSG-N540-LD-1 | FOC2624KMBC |  |  | 1 | 1 | [5 empty] | Y23-F74939 |  | Cisco |  |  | TRUE | 2023 | Syed Shahzaib | 2023-01-11 13:08 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
274 |  |  | AUH6391 |  | AUH6391 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-02-06 | AUH | 1G | AUH-2908-PREAGG-SR7-1 | Port 3/2/20 | AUH-6391-CSG-N540-LD-1 | FOC2633NM4A | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F74293 | Cisco SFP-25G ER | Cisco |  |  | FALSE | 2023 | Aris Dumma | 2023-01-11 12:54 |  | 24.10876 | 53.36888 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
273 |  |  | AUH2567 |  | AUH2567 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-04-12 | AUH |  | AUH-2039-PREAGG-SR7-1 | Port 3/2/9 3G LTE and 1/1/3 5G Link | AUH-2039-PREAGG-SR7-1 | [6 empty] | site plan changed from CSG to Passive. additional port required for 5G link | Aris Dumma;#1292 |  |  |  | Cisco SFP-25G ER | Nokia |  |  | FALSE | 2023 | Aris Dumma | 2023-01-11 12:36 |  | 24.48191 | 54.36503 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
272 |  |  | IAD5658 |  | IAD5658 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-01-31 | AUH |  | AUH-6003-AGGR-SR7B-2 | esat-2/1/32 | AUH-6003-AGGR-SR7B-2 | [7 empty] | Aris Dumma;#1292 |  |  |  | Cisco SFP-25G ER | Nokia |  |  | FALSE | 2023 | Aris Dumma | 2023-01-11 12:24 |  | 24.48119 | 54.351893 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
271 |  |  | DUB0587 |  | DUB0587 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2023-01-11 | DXB |  | DXB-DIC4-CSG-IXR-E-1 | Port 1/1/14 (3G/LTE - 1G SFP) | DXB-DIC4-CSG-IXR-E-1 | [7 empty] | Aris Dumma;#1292 |  |  |  | Cisco SFP-25G ER | Nokia |  |  | FALSE | 2023 | Aris Dumma | 2023-01-11 11:36 |  | 25.100353 | 55.167913 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
270 |  |  | IDX5873 |  | IDX5873 | Cisco NCS540 | 5G | New CSG | RFSed | XAD | 2023-01-26 | DXB | 10G | DXB-5008-AGGR-SR7-2 | 5/1/3 | IDX-5873-CSG-N540-LD-1 | FOC2628N4C1 | [6 empty] | Aris Dumma;#1292;#Rogelio Pangilinan;#1712 |  |  | Y22-F73595 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-01-06 16:18 |  | 25.06512 | 55.304000 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
268 |  |  | DXB0186 |  | DXB0186 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-02-24 | DXB | 10G | DXB-PALMJ-AGGR-SR7B-2 | Port 1/1/53 | DXB-0186-CSG-N540-LD-1 | FOC2626N010 | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F74879 |  | Cisco |  |  | FALSE | 2023 | Rogelio Pangilinan | 2023-01-06 11:54 |  | 25.134485 | 55.150425 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
267 |  |  | DUB0563 |  | DUB0563 | Cisco NCS540 | Rollout | New CSG | RFSed | XAD | 2023-01-17 | DXB | 10G | DXB-DUBAIOTECH-AGGR-SR12e-1 | 3/2/9 | DUB-0563-CSG-N540-LD-1 | FOC2624KMLM | [6 empty] | Aris Dumma;#1292 |  | 2023-01-13 | Y22-F73039 |  | Cisco |  |  | TRUE | 2023 | Rogelio Pangilinan | 2023-01-05 10:44 | DXB_E3177E_10674_001022001 | 25.12352 | 55.2603 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
264 |  |  | AUH6606 |  | AUH6606 | Cisco NCS540 | Rollout | New CSG | RFSed | SHAHID | 2023-01-12 | AUH | 10G | AUH-2149-SCSG-SR7B-1 | esat 1/1/51 | AUH-6066-CSG-N540-LD-1 | F0C2633NLYS |  |  | 1 | 1 | 1 | Site Completed | Mohammed Faris;#1773 |  | 2023-01-10 | Y22-F72863 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-30 10:54 | AUH_E2672H_10943_001001001 | 24.638684 | 54.730647 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
263 |  |  | AAN3621 |  | AAN3621 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2022-12-30 | AUH | 1G | AAN-2009-PREAGG-SR7-1 | Port 3/2/3 | AAN-3621-CSG-IXR-E-1 | NK220937109 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-29 | Y22-F72221 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-30 09:21 | AAN_E3667P_10005_001001001 | 24.165147 | 55.674005 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
262 |  |  | IBS-FTK-21-3204 |  | ISH5188 | Cisco NCS540 | Rollout | New CSG | RFSed | NETS | 2023-01-30 | SHJ | 10G | SHJ-5001-SCSG-SR7B-1 | esat-1/1/56 | ISH-5188-CSG-N540-LD-1 | [6 empty] | Power issue breaker not stable | ISP Planning;#234 |  | 2023-01-23 | Y22-F73544 |  | Cisco |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-29 21:01 | SHJ_E3879F_10007_001001001 | 25.280501 | 55.876864 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
261 |  |  | IBS-FTK-20-1830 |  | ISH5078 | Nokia IXR-E | Rollout | New CSG | RFSed | NETS | 2023-01-19 | SHJ | 10G | SHJ-2580-SCSG-SR7B-1 | esat-1/1/48 | ISH-5078-CSG-IXR-E-1 | FOC2624KMVV | [6 empty] | ISP Planning;#234;#Arif Ahmad;#308 |  | 2023-01-18 | Y22-F73251 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-29 20:57 | SHJ_E3380U_10270_001001001 | 25.309500 | 55.372158 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
257 |  |  | DXB0121 |  | DXB0121 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-02-08 | DXB | 1G | DXB-1516-SCSG-SR7B-1 | esat-1/1/33 | DXB-0121-CSC-IXR-E-7 |  |  |  | 1 | 1 | 1 |  |  |  | 2023-02-06 | Y23-F74432 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-27 12:39 | DXB_E3279S_10047_001002001 | Lat: 25.24280° N | Lon: 55.34065° E | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
256 |  |  | DXT4387 |  | DXT4387 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-04 | DXB | 10G | DXB-1522-SCSG-SR7B-1 | esat-1/1/35 | DXT-4387-CSC-IXR-E-7 | NK223436014 | [8 empty] | 2022-12-28 | Y22-F72109 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-27 12:35 | DXB_E3175H_10001_001001001 | Lat: 24.91092° N | Lon: 55.21788° E | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
255 |  |  | DXB0034 |  | DXB0034 | Nokia IXR-E | BAU | New CSG | RFSed | NETS | 2023-02-06 | DXB | 1G | DXB-1090-SCSG-SR7B-1 | esat-1/1/43 | DXB-0034-CSC-IXR-E-7 | NK22373A347 | [8 empty] | 2023-02-03 | Y23-F74283 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-27 10:10 | DXB_E3279H_10599_001004003 | Lat: 25.27877° N | Lon: 55.30379° E | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
254 |  |  | DXB0007 |  | DXB0007 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-23 | DXB | 1G | DXB-3122-PREAGG-SR7B-1 | Port 3/1/37 | DXB-0007-CR-IXR-E-1 | NK22393A837 | [8 empty] | 2023-01-05 | Y22-F72636 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-27 10:07 | DXB_E2976T_11141_001001002 | Lat: 25.25706° N | Lon: 55.29577° E | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
253 |  |  | IDX0630 |  | IDX0630 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | NETS | 2023-01-26 | DXB | 10G | DXB-6020-AGGR-SR12e-1 | Port 7/1/23 | IDX-0630-CSG-N540-LD-1 | FOC2631N00F |  |  | 1 | 1 | 1 |  | ISP Planning;#234 |  | 2023-01-23 | Y22-F73545 |  | Cisco |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-27 10:03 | DXB_E3178V_11662_001001005 | 25.135856 | 55.187435 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
252 |  |  | DUB0104 |  | DUB0104 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-02-08 | DXB | 10G | DXB-1866-SCSG-IXR-R6-2 | 1/4/9 | DUB-0104-CSG-IXR-E-1 | NK22393A687 |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2023-02-02 | Y22-F74447 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-23 18:19 | DXB_E3379H_11111_001001001 | 25.282700 | 55.401650 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
251 |  |  | IDX5499 |  | IDX5499 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-13 | DXB |  | DXB-1613-CSG-IXR-E-1 | Port 1/1/7 (3G - 1G SFP) Port 1/1/19 (LTE - 1G SFP) | DXB-1613-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-23 10:26 |  | 25.216472 | 55.371882 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
250 |  |  | IDX0981D |  | IDX0981D | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-07-13 | DXB |  | DXB-2583-SCSG-SR7B-1 | esat-2/1/4 (3G - 1G SFP) esat-2/1/6 (LTE - 1G SFP) | DXB-2583-SCSG-SR7B-1 | [6 empty] | 2 ports passive migration | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-23 10:22 |  | 24.975008 | 55.087975 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
249 |  |  | DXN0355 |  | DXN0355 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-02-08 | DXB | 1G | DXB-3165-PREAGG-SR7-1 | Port 5/1/16 | DXN-0355-CSG-N540-LD-1 | FOC2624KMG0 | [5 empty] | RFSED | Aris Dumma;#1292 |  |  | Y23-F74118 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-23 10:15 |  | 25.271231 | 55.328312 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
248 |  |  | DXB3942 |  | DXB3942 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-02-03 | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/24 | DXB-3942-CSG-IXR-E-1 | FOC2624KNQZ |  |  | 1 | 1 | 1 |  | Aris Dumma;#1292 |  |  | Y23-F74212 |  | Nokia |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-23 10:10 |  | 25.20636 | 55.27096 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
247 |  |  | DXB1315 |  | DXB1315 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-02-21 | DXB | 1G | DXB-6002-AGGR-SR7-2 | Port 2/2/10 | DXB-1315-CSG-N540-LD-1 | FOC2624KNQS | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F74249 |  | Cisco |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-23 10:05 |  | 25.1355 | 55.3362 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
246 |  |  | DXB0369 |  | DXB0369 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | DXB | 1G | DXB-DSO-DC-AGGR-SR12-1 | esat-1/1/2 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2022 | Rogelio Pangilinan | 2022-12-23 10:02 |  | 25.124166 | 55.402586 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
245 |  |  | DXN0439 |  | DXN0439 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-31 | DXB | 10G | DXB-IC-POP-SCSG-IXR-R6-1 | port 1/5/8 | DXN-0439-CSG-N540-LD-1 | NK2239686 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-26 | Y22-F73764 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-23 08:37 | DXB_E3378L_10677_001005001 | 25.171194 | 55.396846 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
243 |  |  | DXN0985 |  | DXN0985 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-01-11 | DXB | 1G | DXB-3161-PREAGG-SR7-1 | csg-ixr-e-1 | DXN-0985-CSG-IXR-E-1 | NK22393A583 |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2023-01-09 | Y22-F72796 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-23 08:27 | DXB_E3279X_10703_001001001 | 25.221374 | 55.322578 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
242 |  |  | DXN0245 |  | DXN0245 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-01-17 | DXB | 1G | DXB-3145-PREAGG-SR7-1 | 2/2/5 | DXN0245-CSG-IXR-E-1 | NK22373A059 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-06 | Y22-F72696 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-23 06:57 | DXB_E3279R_10942_001007003 | 25.243570 | 55.313925 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
241 |  |  | DXB0658 |  | DXB0658 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-01-05 | DXB | 1G | DXB-1023-SCSG-IXR-R6-1 | 1/4/4 | DXB-0658-CSG-IXR-E-1 | NK22393A668 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-29 | Y22-F72151 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-22 22:59 | DXB_E3278A_11577_001001001 | 25.21185 | 55.2739 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
240 |  |  | IDX5291 |  | IDX5291 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-07-14 | DXB | 1G | DXB-1516-SCSG-SR7B-1 | esat-1/1/34 | IDX-5291-CSG-N540-LD-1 | FOC2630NXHQ | [6 empty] | Aris Dumma;#1292 |  | 2023-07-12 | Y23-F102541 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-22 18:18 | DXB_E3279M_11437_001001001 | 25.262412 | 55.305938 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
238 |  |  | DUB0077 |  | DUB0077 | Passive | Rollout | Passive patching | Passive Completed | XAD | 2022-12-22 | DXB |  | DXB-3161-PREAGG-SR7-1 | Port 3/2/14 | DXB-3161-PREAGG-SR7-1 | [6 empty] | passive completed 12/22/2022 | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-20 13:09 |  | 25.22139 | 55.324591 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
237 |  |  | AUH2974 |  | AUH2974 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-17 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/20 | AUH-2974-CSG-N540-LD-1 | FOC2624KMG6 | [5 empty] | RFSed | Aris Dumma;#1292 |  |  | Y22-F73179 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-20 12:29 |  | 23.0432111 | 53.7608 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
236 |  |  | AUH6350 |  | AUH6350 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-10 | AUH | 1G | AUH-2908-PREAGG-SR7-1 | Port 3/2/19 | AUH-6350-CSG-N540-LD-1 | FOC2638N26Y | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F72822 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-20 12:25 |  | 24.06431 | 53.4619 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
235 |  |  | AUH3272 |  | AUH3272 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-10 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | esat-1/1/60 | AUH-3272-CSG-N540-LD-1 | FOC2638N276 | [5 empty] | Y22-F72694 | Aris Dumma;#1292 |  | 2023-01-06 | Y22-F72694 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-20 12:22 |  | 24.379477 | 54.48777 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
233 |  |  | RAK0540 |  | RAK0540 | Cisco NCS540 | Migration | New CSG | RFSed | NETS | 2023-02-17 | RAK | 1G | RAK-2000-PREAGG-SR7-1 | Port 4/1/23 | RAK-0540-CSG-N540-LD-1 | FOC2613PNJ9 |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2023-02-16 | Y23-F75005 |  | Cisco |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-20 09:50 | RKT_E3884H_10010_001002001 | 25.738939 | 55.895176 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
231 |  |  | DXS6074 |  | DXS6074 | Passive | Migration | Passive patching | Passive Completed | NETS | 2023-01-10 | DXB | 1G | DXS-6074-SCSG-SR7B-1 | PORT : esat1/1/48 | [10 empty] | 2023-01-10 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-20 09:49 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
230 |  |  | IBS-SS-19-371 |  | IAD5288 | Passive | Migration | Passive patching | Passive Completed | NETS | 2023-01-25 | AUH | 1G | [9 empty] | ISP and passive Patching COmpleted |  |  | 2023-01-25 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-20 09:49 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
229 |  |  | IBS-MOD-22-3395 |  | IAD5806 | Passive | Migration | Passive patching | Passive Completed | NETS | 2022-12-30 | AUH | 1G | AUH-2039-PREAGG-SR7-1 | Port 3/2/19 | [10 empty] | 2022-12-30 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-20 09:49 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
228 |  |  | IBS-SS-19-1296 |  | IAD5601 | Passive | Migration | Passive patching | Passive Completed | NETS | 2022-12-27 | AUH | 1G | AUH6003-AGGR-SR12e-2 | esat:1/1/48 | [10 empty] | 2022-12-27 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-20 09:49 | AUH_E2270I_12333_001001001 | 24.456376 | 54.359700 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
226 |  |  | FUJ3574 |  | FUJ3574 | Cisco NCS540 | Migration | New CSG | RFSed | NETS |  | FUJ | 1G | FUJ-2398-PREAGG-SRa8-1 | Port 1/2/25 | FUJ-3574-CSG-N540-LD-1 | FOC2638N250 | 5 |  | 1 | 1 | 1 | Manual INtegration not Possible as per CIsco at this moment | Arif Ahmad;#308 | [7 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-19 15:43 | RKT_E3978D_10001_001001001 | 25.218888 | 56.021484 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
221 | WO- IIB-CSG-2022-Order # 221 |  | DXB0141 |  | DXB0141 | Nokia IXR-E | Migration | New CSG | Transmission rack not available | XAD |  | DXB | 10G | DXB-INDC-AGGR-SR12e-1 | Port 3/1/7 | DXB-0141-CSG-IXR-E-1 |  | 5 |  |  |  |  | no rack space for new CSG. no available load in APM30 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-19 15:43 |  | 24.909936 | 55.119446 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
219 |  |  | IDX5228 |  | IDX5228 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-12 | DXB | 10G | DXB-3165-PREAGG-SR7-1 | Port 5/2/21 | IDX-5228-CSG-IXR-E-1 | NK22393A724 | [8 empty] | 2023-01-05 | Y22-F72639 | Nokia - SFP 1G | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-19 15:43 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
218 |  |  | IDX5189 |  | IDX5189 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-04 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/52 | IDX-5189-CSG-IXR-E-1 | NK223436008 | [8 empty] | 2022-12-30 | Y22-F72283 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-19 15:43 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
217 |  |  | AUH2158 |  | AUH2158 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-04 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | Port 1/1/59 | AUH-2158-CSG-IXR-E-1 | NK22373A044 | [8 empty] | 2022-11-30 | Y22-F72260 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-19 15:19 | AUH_E2469G_11346_001001001 | 24.37005 | 54.50853 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
215 |  |  | IAD5424 |  | IAD5424 | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-08-02 | AUH |  | AUH-6005-AGGR-SR12e-2 | esat-1/1/21 (3G/LTE - 1G SFP) | AUH-6005-AGGR-SR12e-2 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 14:03 |  | 24.48542 | 54.375805 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
214 |  |  | DXN0955 |  | DXN0955 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-05-23 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/59 | DXN-0955-CSG-IXR-E-1 | NK22403B823 | [5 empty] | Passive plan change to active CSG.passive completed by XAD. new CSG with XAD | Aris Dumma;#1292 |  | 2023-05-17 | Y23-F80378 |  | Nokia |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-19 14:00 | DXB_E3279M_11397_001001002 | 25.2588 | 55.3219 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
212 |  |  | DXN0087 |  | DXN0087 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-07-10 | DXB | 10G | DXB-INDC-AGGR-SR12e-2 | 4/1/12 | DXN-0087-CSG-IXR-E-1 | NK231134825 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-06 | Y23-F102199 |  | Nokia |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-19 13:40 | DXB_E3075L_10002_001001002 | 24.905842 | 55.105039 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
210 |  |  | IDX5901 |  | IDX5901 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-08-03 | DXB | 10G | DXB-INDC-AGGR-SR12e-2 | 4/1/11 | IDX-5901-CSG-IXR-E-1 | [7 empty] | Rogelio Pangilinan;#1712 |  | 2023-07-11 | Y23-F102494 |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 13:26 | DXB_E3075X_10845_001009001 | 24.867085 | 55.14694 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
209 |  |  | IAD0992E |  | IAD0992E | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-06 | AUH |  | AUH-DC-AGGR-SR12e-1 | esat-1/1/46 (3G/LTE - 1G SFP) | AUH-DC-AGGR-SR12e-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 13:21 |  | 24.47285 | 54.377702 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
208 | WO- IIB-CSG-2022-Order # 208 |  | IDX0958C |  | IDX0958C | Passive | Migration | Passive patching | Site Not Ready | XAD |  | DXB |  | IDX-5320-CSG-IXR-E-1 | Port 3/1/9 (3G/LTE - 1G SFP) | IDX-5320-CSG-IXR-E-1 |  | 5 |  |  |  |  | Waiting for update : Passive not possible, only FPMA available for DC Power | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 13:16 |  | 24.8748 | 55.1329 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
207 |  |  | DXB1922 |  | DXB1922 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-27 | DXB | 1G | DXB-1522-SCSG-SR7B-1 | 02/01/13 | DXB-1922-CSG-IXR-E-1 | NK220936991 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-21 | Y22-F71538 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-19 13:14 |  | 55.116810° | 24.768500° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
206 |  |  | IDX5717 |  | IDX5717 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-06-26 | DXB | 10G | DXB-INDC-AGGR-SR12e-2 | 4/1/10 | IDX-5717-CSG-N540-LD-1 | FOC2631N0DT | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-06-23 | Y23-F101543 |  | Cisco |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 13:07 | DXB_E3075S_10022_001002002 | 24.8745 | 55.1365 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
205 |  |  | DXB0258 |  | DXB0258 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-23 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/50 | DXB0258-CSG-IXR-E-1 | NK22393A815 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-21 | Y22-F71531 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-19 13:04 | DXB_E3279M_11332_001002002 | 55.320058 | 25.260524 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
204 | WO- IIB-CSG-2022-Order # 204 |  | IDX0005T |  | IDX0005T | Passive | Migration | Passive patching | Transmission rack not available | XAD |  | DXB |  | DXB-BV-SCSG-SR7B-1 | esat-1/1/57 | DXB-BV-SCSG-SR7B-1 |  | 5 |  |  |  |  | GSM cant be found | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 13:03 |  | 25.258526 | 55.321406 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
203 |  |  | DXB5237G |  | DXB5237G | Passive | Migration | Passive patching | Passive Completed | XAD | 2023-06-14 | DXB |  | DXB-6020-AGGR-SR12e-1 | Port 3/2/13 | DXB-6020-AGGR-SR12e-1 | [7 empty] | Rogelio Pangilinan;#1712 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 12:47 |  | 25.145941 | 55.224293 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
202 |  |  | DXB0803 |  | DXB0803 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-26 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/51 | DXB-0803-CSG-IXR-E-1 | NK220937032 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-22 | Y22-F71683 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-19 12:47 |  | 25.2562 | 55.3348 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
201 |  |  | DUB0002 |  | DUB0002 | Passive | BAU | Passive patching | Passive Completed | XAD | 2023-01-14 | DXB |  | DXB-2282-PREAGG-SR7-1 | Port 5/1/3 (3G/LTE - 1G SFP) | DXB-2282-PREAGG-SR7-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-19 12:42 |  | 25.29537 | 55.37524 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
199 |  |  | AUH2714 |  | AUH2714 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-01-09 | AUH | 10G | AUH-5002-AGGR-SR7-1 | Port 5/1/10 | AUH-2714-CSG-IXR-E-1 | NK22393A549 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-02 | Y22-F72446 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-19 12:22 | AUH_E2967H_10092_001001001 | 24.18515 | 55.036821 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
198 |  |  | AAN2614 |  | AAN2614 | Cisco NCS540 | 5G |  | RFSed | HOI-MEA | 2023-02-06 | AUH | 10G | AAN-2059-PREAGG-SR7-1 | Port 5/1/3 | AAN-2614-CSG-N540-LD-1 | FOC2638N29T | [9 empty] | Y22-F73907 |  | Cisco |  |  | TRUE | 2022 | Syed Shahzaib | 2022-12-19 10:00 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
197 |  |  | AUH2478 |  | AUH2478 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-02-10 | AUH | 10G | AUH-5002-AGGR-SR7-1 | 5/2/2 | AUH-2478-CSG-IXR-E-1 | NK22373A230 |  | 1 | [7 empty] | Y23-F74339 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-12-19 09:58 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
196 |  |  | AUH2317 |  | AUH2317 | Nokia IXR-E | 5G |  | Cancelled/on Hold | HOI-MEA |  | AUH | 1G | AUH-1336-PREAGG-SR7-1 | 4/2/20 |  | NK22393A793 |  | 1 |  |  |  | CSG Power UP / Removed | [8 empty] | FALSE | 2022 | Syed Shahzaib | 2022-12-19 09:57 |  |  |  | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
195 |  |  | FUJ3261 |  | FUJ3261 | Nokia IXR-E |  |  | RFSed | HOI-MEA | 2023-04-26 | FUJ | 10G | RAK-2853 OTN to FUJ6001 |  | FUJ-3261-CSG-IXR-E-1 | NK223939A834 |  | 1 | 1 | 1 | [5 empty] | Y23-F78676 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-12-19 09:55 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
193 |  |  | DXB0180 |  | DXB0180 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-02-23 | DXB | 10G | DXB-BV-SCSG-SR7B-1 | esat-1/1/54 | DXB-0180-CSG-IXR-E-1 | NK22373A122 |  | 1 | [7 empty] | Y23-F75090 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-12-19 09:45 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
192 |  |  | DXBNR1237 |  | DXB1237 | Passive | 5G | Passive patching | Passive Completed | XAD | 2022-12-22 | DXB |  | DXB-1852-PREAGG-SR7-1 | Port 5/1/5 (5G-10G SFP) | DXB-1852-PREAGG-SR7-1 | [6 empty] | passive completed 12/22/2022 | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-17 09:25 |  | 25.2413 | 55.5218 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
191 |  |  | AUH6326 |  | AUH6326 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-03-06 | AUH | 10G | AUH-2923-PREAGG-SRa8-1 | Port 1/1/6 | AUH-6326-CSG-N540-LD-1 | F0C2638N285 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-24 | Y22-F73598 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-15 15:40 | AUH_E2260E_10001_001001001 | 23.567648 | 54.397493 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
190 |  |  | AUH3409 |  | AUH3409 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-18 | AUH | 10G | AUH-2149-SCSG-SR7B-1 | Port 5/2/6 | NewLD-CSG | F0C263N27K | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-04 | Y22-F72579 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-15 15:20 | AUH_E2672L_10458_001001001 | 24.629029 | 54.714096 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
189 |  |  | IBS-FTK-20-1435 |  | DXN0714 | Passive | BAU | Passive patching | Passive Completed | NETS | 2022-12-26 | DXB | 1G | DXB-ICPOP-SCSG-IXR-R6-1 | 1/4/3 | [10 empty] | 2022-12-26 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-15 13:42 |  | 25.180102 | 55.383202 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
188 |  |  | AUH6388 |  | AUH6388 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-24 | AUH | 10G | AUH-2929-PREAGG-SRa8-1 | Port 2/1/8 | NewLD-CSG | F0C2637NEWP | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-24 | Y22-F73584 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-15 12:27 | AUH_E2154P_10030_001001001 | 22.97779 | 54.23657 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
187 |  |  | IAD5376 |  | IAD5376 | Passive | Migration | Passive patching | Passive Completed | NETS | 2022-12-26 | AUH | 1G | AUH-2076-PREAGG-SR7-1 | Port 3/2/7 | [10 empty] | 2022-12-26 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-14 21:47 |  | 24.466642 | 54.385982 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
186 |  |  | IAD5666 |  | IAD5666 | Passive | Migration | Passive patching | Passive Completed | NETS | 2022-12-26 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/5 | [10 empty] | 2022-12-26 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-14 21:45 |  | 24.466642 | 54.385982 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
185 |  |  | IAD5848 |  | IAD5848 | Passive | Migration | Passive patching | Passive Completed | SHAHID |  | AUH | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/4 | AUH-6005-AGGR-SR12e-2 |  |  |  | 1 | 1 |  | Site Completed |  |  | 2023-07-11 |  |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-14 21:42 |  | 24.497740 | 54.372840 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
184 |  |  | IAD5443 |  | IAD5443 | Passive | Migration | Passive patching | Passive Completed | NETS | 2022-12-26 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/3 | [10 empty] | 2022-12-26 | [5 empty] | FALSE | 2022 | Arif Ahmad | 2022-12-14 21:40 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
183 |  |  | AAN3344 |  | AAN3344 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-03 | AUH | 1G | AAN-2006-PREAGG-SR7-1 | Port 3/2/20 | AAN-3344-CSG-IXR-E-1 | NK220936979 | [6 empty] | Arif Ahmad;#308 |  | 2022-12-28 | Y22-F72124 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-14 21:35 | AAN_E3667R_10005_001001001 | 24.157893 | 55.724489 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
182 |  |  | AUH6474 |  | AUH6474 | Cisco NCS540 | Migration | New CSG | RFSed | NETS | 2023-01-30 | AUH | 1G | AUH-2937-PREAGG-SR7-1 | Port 3/2/14 | AUH-6474-CSG-N540-LD-1 | FOC2624KMVM |  |  | 1 | 1 | 1 |  |  |  | 2023-01-23 | Y22-F73538 |  | Cisco |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-14 21:31 | AUH_E1562X_10148_001001001 | 23.650900 | 53.6757 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
181 |  |  | AUH6576 |  | AUH6576 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2022-12-23 | AUH | 10G | AUH-5004-PREAGG-SR7-1 | Port 5/1/3 | AUH-6576-CSG-IXR-E-1 | NK213632444 | [8 empty] | 2022-12-20 | Y22-F71598 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-12-14 21:28 | AUH_E2673Y_10735_001001001 | 24.669820 | 54.77261 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
180 |  |  | AUH6386 |  | AUH6386 | Passive | Migration |  | Passive Completed | HOI-MEA | 2023-08-22 | AUH | 1G | AUH-2932-CSG-SAR-X-1 | Port 1/3/5 | AUH-2932-CSG-SAR-X-1 | [12 empty] | Nokia |  |  | FALSE | 2022 | Syed Shahzaib | 2022-12-14 12:31 |  |  |  | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
179 |  |  | AAN3333 |  | AAN3333 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-02-09 | AUH | 10G | AAN-5002-AGGR-SR12-1 | Port 1/1/7 | AAN-3333-CSG-N540-LD-1 | FOC2638N24B | [9 empty] | Y23-F74366 |  | Cisco |  |  | TRUE | 2022 | Syed Shahzaib | 2022-12-14 12:30 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
178 |  |  | AUH6481 |  | AUH6481 | Cisco NCS540 | Migration |  | RFSed | HOI-MEA | 2023-02-07 | AUH | 1G | AUH-2713-PREAGG-SRa8-1 | Port 2/2/17 | AUH-6481-CSG-N540-LD-1 | FOC2638N27A |  |  | 1 | 1 | [5 empty] | Y22-73803 |  | Cisco |  |  | TRUE | 2022 | Syed Shahzaib | 2022-12-14 12:28 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
175 |  |  | IAD5792 |  | IAD5792 | Passive | Migration | Passive patching | Passive Completed | XAD | 2022-12-22 | AUH |  | AUH-2410-SCSG-IXR-R6-1 | Port 1/6/7 | AUH-2410-SCSG-IXR-R6-1 | [6 empty] | passive completed | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-12-14 12:19 |  | 24.454989 | 54.614915 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
174 |  |  | AUH2763 |  | AUH2763 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-02-08 | AUH | 10G | AUH-6501-AGGR-SR12e-2 | Port 2/1/20 | AUH-2763-CSG-IXR-E-1 | NK22373A307 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-02-06 | Y23-F74439 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-14 11:40 | AUH_E2369Y_10090_001001001 | 24.319052 | 54.473473 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
173 |  |  | AAN2878 |  | AAN2878 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-16 | AUH | 1G | AAN-2305-PREAGG-SR7-1 | Port 5/2/17 | AAN-2878-CSG-N540-LD-1 | FOC2638N26Q | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F72820 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-14 11:08 |  | 24.124097 | 55.722984 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
172 |  |  | AAN2882 |  | AAN2882 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-16 | AUH | 1G | AAN-2305-PREAGG-SR7-1 | Port 5/2/16 | AAN-2882-CSG-N540-LD-1 | FOC2638N27F | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F72821 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-14 11:04 |  | 24.129413 | 55.733578 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
171 |  |  | AUH6614 |  | AUH6614 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-16 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | AUH6614 | AUH-6614-CSG-N540-LD-1 | FOC2633NM42 | [6 empty] | Aris Dumma;#1292 |  | 2023-01-13 | Y22-F73016 |  | Cisco |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-12-14 11:00 |  | 24.502788 | 54.377267 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
170 |  |  | AUH6557 |  | AUH6557 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-26 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/15 | AUH6557-CSG-N540-LD-1 | FOC2638N27U | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-24 | Y22-F73602 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-14 10:46 | AUH_E1657N_10075_001001001 | 23.24723 | 53.79858 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
169 |  |  | AUH3467 |  | AUH3467 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-20 | AUH | 1G | AUH-2934-PREAGG-SR7-1 | Port 3/2/14 | AUH-3467-CSG-N540-LD-1 | FOC2638N28S |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2023-01-19 | Y22-F73317 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-12-14 10:29 |  | 23.02769 | 53.44127 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
168 |  |  | AUH3465 |  | AUH3465 | Nokia IXR-E | BAU | New CSG | RFSed | NETS | 2022-12-29 | AUH | 1G | AUH-2836-PREAGG-SR7-1 | Port 3/2/15 | AUH-3465-CSG-IXR-E-1 | [7 empty] | Arif Ahmad;#308 |  | 2022-12-28 | Y22-F72138 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-13 13:16 |  | 23.670780 | 53.701550 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
166 |  |  | IAD5306 |  | IAD5306 | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2024-01-08 | AUH |  | AUH-2223-SCSG-IXR-R6D-1 | 1G Port | AUH-2223-SCSG-IXR-R6D-1 |  | 5 |  | 1 | 1 |  | Passive Completed | Rogelio Pangilinan;#1712 |  | 2024-01-08 |  |  | Nokia |  |  | FALSE | 2022 | Muhammad Shoaib | 2022-12-12 18:19 |  | 24.4046 | 54.5968 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
165 |  |  | IAD5564 |  | IAD5564 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2022-12-14 | AUH | 1G | AUH-1336 | esat-1/1/6 | AUH-1336-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed | Muhammad Shoaib;#1360 |  | 2022-12-14 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-12-12 17:47 |  | 24.460292 | 54.38077 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
164 |  |  | DUB0281 |  | DUB0281 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-05-10 | DXB |  | DXB-3189-CSG-IXR-E-1 | Port 1/1/7 | DXB-3189-CSG-IXR-E-1 |  |  |  | 1 | 1 |  | Passive Completed | Tasif Maqbool;#267 |  | 2023-03-10 |  |  | Nokia |  |  | FALSE | 2022 | Muhammad Shoaib | 2022-12-12 16:42 |  | 24.9682 | 55.13706 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
162 |  |  | IAD5492 |  | IAD5492 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-04-03 | AUH | 1G | AUH-2039-PREAGG-SR7-1 | 3/2/18 | AUH-2039-PREAGG-SR7-1 | NA |  |  | 1 | 1 |  | Passive Completed |  |  | 2023-04-03 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-12-12 16:37 |  | 24.48034 | 54.37003 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
161 |  |  | IAD5820 |  | IAD5820 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-07 | AUH | 1G | AUH-1336-SCSG-SR7B-1 | esat-2/1/3 | AUH-1336-SCSG-SR7B-1 | NA | [5 empty] | Passive Completed |  |  | 2023-03-07 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-12-12 16:33 |  | 24.458781 | 54.380831 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
160 |  |  | IDX5843 |  | IDX5843 | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-03-21 | DXB | 1G | DXB-DSO-CSG-IXR-E-1 | Port:1/1/17 - 3G Port:1/1/18 - LTE | DXB-DSO-CSG-IXR-E-1 | [6 empty] | Passive Completed |  |  | 2023-03-21 |  |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-12-12 16:28 |  | 25.124014 | 55.377646 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
158 |  |  | ISH5216 |  | ISH5216 | Cisco NCS540 | Parity | New CSG | RFSed | XAD | 2023-08-11 | SHJ | 10G | SHJ-2016-SCSG-SR7B-1 | esat-1/1/53 | ISH-5216-CSG-N540-LD-1 | FOC2613PNDF |  |  | 1 | 1 |  |  | Rogelio Pangilinan;#1712 |  | 2023-08-09 | Y23-F104420 |  | Cisco |  |  | TRUE | 2022 | Arif Ahmad | 2022-12-08 10:29 | SHJ_E3379A_10388_001001017 | 25.299468 | 55.370364 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
157 |  |  | DXB3835 |  | DXB3835 | Cisco NCS540 | 5G Upgrade | New CSG | RFSed | SHAHID | 2023-01-18 | DXB | 10G | DXB-1852-PREAGG-SR7-1 | Port 5/2/4 | New CSG Integration | FOC2638N27V | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-16 | Y22-F73131 |  | Cisco |  |  | TRUE | 2022 | Mohammed Faris | 2022-11-26 10:52 |  | 25.222193 | 55.530103 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
155 |  |  | DXBNR0317 |  | DXBNR0317 | Nokia IXR-E | 5G Upgrade | New CSG | RFSed | SHAHID | 2022-12-23 | DXB | 10G | DXB-3131-PREAGG-SR7-1 | Port 3/2/3 | DXB-0317-CSG-IXR-E-1 | NK22373A173 |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2022-12-20 | Y22-F71356 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-11-26 10:12 |  | 25.097090 | 55.183810 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
154 |  |  | SHJ1389 |  | SHJ1389 | Nokia IXR-E | Rollout | New CSG | RFSed | SHAHID | 2022-12-16 | SHJ | 10G | SHJ-2049-AGGR-SR7b-1 | esat-2/1/1 | SHJ-1389-CSG-IXR-1 | NK22153B879 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-13 | Y22-F70909 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-11-26 09:38 |  | 25.3019827 | 55.4440878 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
153 |  |  | DXBNR0074 |  | DXBNR0074 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-01-20 | DXB | 10G | DXB-Shatha-MC-AGG-ASR9912-1 | Te0/1/0/22 | DXB-0074-CSG-IXR-E-1 | NK22393A685 | [9 empty] | Y22-F72974 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-25 14:50 |  | 25.09786029 | 55.15640213 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
152 |  |  | DXBNR0502 |  | DXBNR0502 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-01-20 | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/9 | DXB-0502-CSG-IXR-E-1 | NK22393A849 | [9 empty] | Y22-F72521 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-25 14:48 |  | 25.2145797528 | 55.2802015274 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
151 |  |  | DXB0277 |  | DXB0277 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-02-08 | DXB | 10G | DXB-BB-AGGR-SR12e-2 | 7/1/36 | DXB-0277-CSG-IXR-E-1 | NK223034127 | [9 empty] | Y23-F74333 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-25 14:47 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
150 |  |  | DXBNR0616 |  | DXBNR0616 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2023-01-09 | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/8 | DXB-0616-CSG-IXR-E-1 | NK22373A301 | [9 empty] | Y22-F72518 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-25 14:45 |  | 25.214551 | 55.282110 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
139 |  |  | AJM3981 |  | AJM3981 | Nokia IXR-E | 5G | New CSG | RFSed | NETS | 2022-12-30 | AJM | 10G | AJM-2459-SCSG-SR7B-1 | esat-1/1/42 | AJM-3981-CSG-IXR-E-1 | NK214832051 |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2022-12-22 | Y22-F72082 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-11-23 11:44 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
137 |  |  | AJM1255 |  | AJM1255 | Nokia IXR-E | 5G | New CSG | RFSed | NETS | 2023-04-10 | AJM | 10G | AJM-2459-SCSG-SR7B-1 | esat-1/1/42 | AJM-1255-CSG-N540-LD-1 | FOC2624KMBF |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2023-03-27 | Y23-F77360 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-11-23 11:26 | AJM_E3480B_12751_001001001 | 25.3948 | 55.4828 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
136 |  |  | SHJ6253 |  | SHJ6253 | Nokia IXR-E | 5G | New CSG | RFSed | NETS | 2022-12-13 | SHJ | 10G | SHJ-2547-SCSG-SR7B-1 | esat-1/1/1 | SHJ-6253-CSG-IXR-E-1 | NK220937146 |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2022-12-08 | Y22-F70646 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-11-23 11:23 | SHJ_E3578I_10086_001001001 | 25.196440 | 55.633690 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
134 |  |  | DXB1810 |  | DXB1810 | Cisco NCS540 | 5G Upgrade |  | RFSed | HOI-MEA | 2023-01-25 | DXB | 10G | DXB-1583-SCSG-IXR-R6-1 | 1/6/5 | DXB-1810-CSG-N540-LD-1 | F0C2638N25C |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F72439 |  | Cisco |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-23 11:01 |  | 25.0081356729566 | 55.1123352894631 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
131 |  |  | DXB1247 |  | DXB1247 | Cisco NCS540 | 5G |  | RFSed | HOI-MEA | 2023-01-05 | DXB | 10G | DXB-3724-AGGR-SR12e-2 | 2/1/8 | DXB-1247-CSG-N540-LD-1 | F0C2638N29V |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F72287 |  | Cisco |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-23 10:55 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
130 |  |  | IDXNR5740 |  | IDXNR5740 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | SHAHID | 2022-12-20 | DXB | 10G | DXB-6020-AGGR-SR12e-2 | Port 5/2/1 | IDX5740-CSG-IXR-E-1 | NK22373A189 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-19 | Y22-F71279 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-11-22 21:21 | DXB_E3178V_11660_001007001 | 25.13207 | 55.18419 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
129 |  |  | DXB1346 |  | DXB1346 | Nokia IXR-E | Rollout | New CSG | RFSed | XAD | 2023-02-08 | DXB | 10G | DXB-2282-PREAGG-SR7-1 | Port 4/1/5 | DXB-1346-CSG-IXR-E-1 | NK22373A231 | [6 empty] | Aris Dumma;#1292 |  | 2023-01-18 | Y22-F73265 |  | Nokia |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-11-21 14:12 |  | 25.29162 | 55.38136 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
125 |  |  | IBS-5G-22-2849 |  | DXBNR0355 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2023-02-02 | DXB | 10G | DXB-3248-SCSG-IXR-R6-1 | port 1/6/5 | DXB-0355-CSG-IXR-E-1 | NK223433742 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2023-01-31 | Y23-F74047 |  | Nokia |  |  | TRUE | 2022 | Mohammed Faris | 2022-11-18 00:13 | DXB_E3279V_11010_001008009 | 25.228400 | 55.285800 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
121 |  |  | SHJ0467 |  | SHJ0467 | Nokia IXR-E | Parity | New CSG | RFSed | NETS | 2022-12-08 | SHJ | 1G | SHJ-2580-SCSG-SR7B-1 | esat-2/1/50 | SHJ-0467-CSG-IXR-E-1 | NK22373A053 | [6 empty] | Arif Ahmad;#308 |  | 2022-12-08 | Y22-F70559 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-11-16 15:46 | SHJ_E3379A_10250_001042002 | 25.305361 | 55.362781 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
120 |  |  | DXB2322 |  | DXB2322 | Nokia IXR-E | 5G | New CSG | RFSed | NETS | 2022-11-30 | DXB | 10G | DXB-1074-SCSG-IXR-R6-1 | Port 1/6/4 | DXB-2322-CSG-IXR-E-1 | NK22373A299 | [5 empty] | Site Integrated RFS in Progress | Arif Ahmad;#308 |  | 2022-11-24 | Y22-F69777 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-11-16 15:27 | DXB_E3076I_10106_001001001 | 24.985396 | 55.140140 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
119 |  |  | DXBNR0869 |  | DXBNR0869 | Nokia IXR-E | 5G | New CSG | RFSed | XAD | 2023-01-26 | DXB | 10G | DXB-DIFC-ER4-AGGR-SR12e-1 | esat-2/1/2 | DXB-0869-CSG-IXR-E-1 | NK22373A357 | [5 empty] | Y22-F73146 | Aris Dumma;#1292 |  | 2023-01-16 | Y22-F73146 |  | Nokia |  |  | TRUE | 2022 | Rogelio Pangilinan | 2022-11-16 15:21 |  | 25.2085 | 55.2764 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
118 |  |  | DXB0573 |  | DXB0573 | Nokia IXR-E | 5G | New CSG | RFSed | XAD | 2023-02-09 | DXB | 10G | DXB-1003-PREAGG-SR7B-1 | esat-1/1/38 | DXB-0573-CSG-IXR-E-1 | NK223436340 | [5 empty] | for hand over | Aris Dumma;#1292 |  |  | Y22-F73410 |  | Nokia |  |  | FALSE | 2022 | Rogelio Pangilinan | 2022-11-16 15:18 |  | 25.075327 | 55.140019 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
110 |  |  | IAD5875 |  | IAD5875 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2022-12-23 | AUH | 10G | AUH-2036-SCSG-IXR-R6-1 | 1/6/7 | IAD-5875-CSG-IXR-E-1 | NK22373A116 | [9 empty] | Y22-F71524 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-16 11:22 |  | 24.441198 | 54.5715363 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
108 |  |  | DXB3837 |  | DXB3837 | Nokia IXR-E | 5G+Migration |  | RFSed | HOI-MEA | 2022-12-15 | DXB | 1G | DXB-3165-PREAGG-SR7-1 | 5/1/20 | DXB-3837-CSG-IXR-E-1 | NK220937037 |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F70560 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-16 11:19 |  | 25.2818870 | 55.33568 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
105 |  |  | DXB0674 |  | DXB0674 | Cisco NCS540 | 5G |  | RFSed | HOI-MEA | 2023-02-06 | DXB | 10G | DXB-BB-AGGR-SR12e-1 | 2/1/34 | DXB-0674-CSG-N540-LD-1 | FOC2624KNNZ |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F73802 |  | Cisco |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-16 11:16 |  |  |  | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
104 |  |  | DXB0212 |  | DXB0212 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | NETS | 2022-11-25 | DXB | 10G | DXB-BB-AGGR-SR12e-1 | Port 2/1/19 | DXB-0212-CSG-IXRE-1 | NS2203C6484 |  |  | 1 | 1 | 1 |  |  |  | 2022-11-16 | Y22-F69030 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-16 11:15 | DXB_E3178J_11970_001005002 | 25.188839 | 55.262921 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
102 |  |  | IDX0948C |  | IDX0948C | To Be Confirmed |  |  | Cancelled/on Hold | HOI-MEA |  | DXB | [19 empty] | FALSE | 2022 | Syed Shahzaib | 2022-11-16 11:12 | [5 empty] | Item | sites/IMP/Control/Lists/ABC2 TEST333
101 |  |  | IDX0962B |  | IDX0962B | To Be Confirmed |  |  | Cancelled/on Hold | HOI-MEA |  | DXB | [19 empty] | FALSE | 2022 | Syed Shahzaib | 2022-11-16 11:11 | [5 empty] | Item | sites/IMP/Control/Lists/ABC2 TEST333
99 |  |  | IDXNR5010 |  | IDXNR5010 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2022-12-20 | DXB | 10G | DXB-BB-AGGR-SR12e-2 | esat-1/1/37 | IDX-5010-CSG-IXR-E-1 | NK22373A260 |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F71144 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-16 11:08 |  | 25.1874301 | 55.297490312 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
93 |  |  | AUH3014 |  | AUH3014 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2023-01-02 | AUH | 10G | AUH-2149-SCSG-SR7B-1 | Port 5/2/4 | AUH-3014-CSG-N540-LD-1 | FOC2638N277 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-12-27 | Y22-F72025 |  | Cisco |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-14 22:05 | AUH_E2572N_10105_001001001 | 24.629658 | 54.656668 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
92 |  |  | AUH3705 |  | AUH3705 | To Be Confirmed | 5G+Migration | New CSG | No OSP | XAD |  | AUH | 10G | AUH-6003-AGGR-SR7B-1 | esat-2/1/46 | [7 empty] | no OSP | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-14 21:56 |  | 24.470980 | 54.34058 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
89 |  |  | AAN2029 |  | AAN2029 | Nokia IXR-E | 5G+Migration | Card Exp - Rollout Passive Patching | RFSed | SHAHID | 2022-12-30 | AUH | 1G | AAN-2399-PREAGG-SR7-1 | Port 3/2/19 | AAN-2029-CSG-IXR-E-1 | NK22393A636 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-12-29 | Y22-F72207 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-14 21:25 | AAN_E3566F_10001_001001001 | 24.1036 | 55.58852 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
88 |  |  | AUH3733 |  | AUH3733 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | SHAHID | 2023-01-05 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-1/1/45 | AUH-3733-CSG-N540-LD-1 | F0C2638N246 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2023-01-03 | Y22-F72509 |  | Cisco |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-14 21:13 | AUH_E2270I_12330_001001001 | 24.456826° | 54.368216° | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
85 |  |  | AUH6563 |  | AUH6563 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2022-12-12 | AUH | 10G | AUH-2562-SCSG-SR7B-1 | esat-1/1/4 | AUH-6563-CSG-IXR-E-1 | NK22113B640 |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F69094 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-11 14:48 |  | 24.36723 | 54.4992 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
84 |  |  | AUH6156 |  | AUH6156 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2022-11-24 | AUH | 10G | AUH-2149-SCSG-SR7B-1 | esat-1/1/5 | AUH-6156-CSG-IXR-E-1 | NK22113B628 |  |  | 1 | 1 | 1 |  |  |  |  | Y22-F68889 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-11-11 14:36 |  | 24.632869 | 54.701771 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
83 |  |  | AJM0969 |  | AJM0969 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-11-30 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | Port 2/1/44 | AJM0969-CSG-IXR-E-1 | NK223433820 | [5 empty] | Site completed | Muhammad Shoaib;#1360 |  | 2022-11-25 | Y22-F69723 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-08 19:17 | AJM_E3480H_10531_001001002 | 25.367670 | 55.509840 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
82 |  |  | AJM0954 |  | AJM0954 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-09 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | Port esat 2/1/43 | AJM-0954-CSG-IXR-E-1 | NK223236148 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-11-26 | Y22-F69773 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-08 19:08 | AJM_E3480H_10539_001001001 | 25.364081 | 55.511560 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
81 |  |  | AJM0944 |  | AJM0944 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-16 | AJM | 10G | AJM-2450-SCSG-SR7B-1 | Port 2/1/42 | AJM0944-CSG-IXR-E-1 | NS2203C6268 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-12-14 | Y22-F70991 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-08 19:02 | AJM_E3480H_10535_001002001 | 25.365280 | 55.507150 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
80 |  |  | AJM5998A |  | AJM5998A | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2022-12-21 | AJM | 1G | AJM-2450-SCSG-SR7B-1 | Port 4/2/18 | AJM-2450-SCSG-SR7B-1 | [6 empty] | Passive Completed | Muhammad Shoaib;#1360 |  | 2022-12-21 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-08 18:55 |  | 25.385490 | 55.554240 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
79 |  |  | DUB0558 |  | DUB0558 | Nokia IXR-E | BAU | New CSG | RFSed | SHAHID | 2022-11-24 | DXB | 1G | DXB-1516-SCSG-SR7B-1 | 3/1/18 | DUB-0558-CSG-IXR-E-1 | NS2133C3850 |  |  | 1 | 1 |  | Site Completed | Muhammad Shoaib;#1360 |  | 2022-11-11 | Y22-F69009 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-08 15:24 | DXB_E3279R_11434_001001002 | 25.249124 | 55.311353 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
78 |  |  | IBS-FTK-21-3596 |  | DUB0981 | Cisco NCS540 | BAU |  | RFSed | NETS | 2023-06-08 | DXB | 1G | DXB-6504-AGGR-SR12e-1 | Port 3/1/17 | DUB-0981-CSG-N540-LD-1 | FOC2624KMDG |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2023-05-30 |  |  | Cisco |  |  | TRUE | 2022 | Arif Ahmad | 2022-11-08 14:20 | DXB_E3075M_10028_001001004 | 24.893000 | 55.109600 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
77 |  |  | IBS-FTK-20-0018 |  | DXN0748 | Nokia IXR-E | BAU | New CSG | RFSed | NETS | 2022-11-30 | DXB | 10G | DXB-INDC-AGGR-SR12e-1 | Port 3/1/7 | DXN-0748-CSG-IXR-E-1 | NK22373A025 |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2022-11-23 | Y22-F69781 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-11-08 14:13 | DXB_E2975X_10003_001001003 | 24.859696 | 55.049575 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
76 |  |  | DUB0679 |  | DUB0679 | Nokia IXR-E | BAU | New CSG | RFSed | NETS | 2023-05-16 | DXB | 1G | DXB-5008-AGGR-SR2S-1 | esat-1/1/20 | DUB-0679-CSG-IXR-E-1 | NS2203C6192 |  |  | 1 | 1 | 1 |  | Arif Ahmad;#308 |  | 2023-05-12 | Y23-F80050 |  |  |  |  | FALSE | 2022 | Arif Ahmad | 2022-11-08 13:59 | DXB_E3277M_10123_001017001 | 25.087160 | 55.316460 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
75 |  |  | IBS-FTK-21-2045 |  | DUB0076 | Nokia IXR-E | BAU | New CSG | RFSed | NETS | 2022-12-20 | DXB | 10G | DXB-VH-SCSG-SR7B-1 | esat-1/1/40 | DUB-0076-CSSG-IXR-E-1 | NK223739975 | [6 empty] | Arif Ahmad;#308 |  | 2022-12-15 | Y22-F71082 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-11-08 13:56 | DXB_E3177R_11556_001026002 | 25.05732 | 55.22059 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
74 |  |  | IAJ5860 |  | IAJ5860 | Nokia IXR-E | BAU |  | RFSed | HOI-MEA | 2022-11-29 | SHJ | 10G | SHJ-2540-SCSG-SR7B-1 | esat-1/1/34 | IAJ-5860-CSG-IXR-E-1 | NK223739992 |  |  | 1 | 1 | [5 empty] | Y22-F69630 |  | Nokia |  |  | TRUE | 2022 | Mohamed Abussalah | 2022-11-07 12:21 |  | 25.39415 | 55.42738 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
73 |  |  | AUH5403C |  | AUH5403C | Passive | Rollout | Passive patching | Passive Completed | SHAHID | 2023-01-05 | AUH | 1G | AUH-6501-AGGR-SR12e-2 | Port 3/1/15 | AUH-6501-AGGR-SR12e-2 | [6 empty] | Passive Completed | Muhammad Shoaib;#1360 |  | 2023-01-05 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 19:09 |  | 24.341519 | 54.524951 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
72 |  |  | AUH5403B |  | AUH5403B | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2022-12-23 | AUH | 1G | AUH-1372-PREAGG-SR7-1 | 3/2/20 | AUH-1372-PREAGG-SR7-1 | [6 empty] | Passive Completed | Muhammad Shoaib;#1360 |  | 2022-12-23 |  |  | Nokia |  |  | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 18:42 |  | 24.341519 | 54.524951 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
71 |  |  | AUH5403A |  | AUH5403A | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2022-12-23 | AUH | 1G | AUH-1372-PREAGG-SR7-1 | 3/2/19 | AUH-1372-PREAGG-SR7-1 | [6 empty] | Passive Completed |  |  | 2022-12-23 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 18:37 |  | 24.341519 | 54.524951 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
69 |  |  | AUH5458C |  | AUH5458C | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2022-07-27 | AUH | 1G | AUH-2122-SCSG-SR7B-1 | esat-1/1/32 | AUH-2122-SCSG-SR7B-1 | [6 empty] | Passive Completed |  |  | 2022-07-27 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 18:20 |  | 24.343048 | 54.500366 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
68 |  |  | AAN0029 |  | AAN0029 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-11-29 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/45 | AAN0029-CSG-IXR-E-1 | NK223739924 |  |  | 1 | 1 |  | Site Completed | Muhammad Shoaib;#1360 |  | 2022-11-28 | Y22-F69860 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-02 17:59 | AAN_E3668T_10004_001001001 | 24.263396 | 55.766055 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
67 |  |  | AUH0463 |  | AUH0463 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-30 | AUH | 10G | AUH-1097-SCSG-SR7B-1 | esat-1/1/56 | AUH-0463-CSG-IXR-E-1 | NK223739952 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-12-28 | Y22-F72111 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-02 17:53 | AUH_E2470U_10775_001001001 | 24.40666 | 54.49066 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
66 |  |  | AUH5458D |  | AUH5458D | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2022-12-15 | AUH |  | AUH-2036-CSG-SAR-8-1 | Port 1/3/4 | AUH-2036-CSG-SAR-8-1 | [6 empty] | Passive Completed | Muhammad Shoaib;#1360 |  | 2022-12-15 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 17:42 |  | 24.491857 | 54.612532 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
65 |  |  | AAN5398E |  | AAN5398E | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-03-28 | AUH |  | AAN-2265-PREAGG-SR7-1 | Port-3/2/14 | AAN-2265-PREAGG-SR7-1 |  |  |  | 1 | 1 |  | Passive Completed | Muhammad Shoaib;#1360 |  | 2023-03-28 | [5 empty] | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 17:33 |  | 24.1639947 | 55.8079155 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
64 |  |  | IAD0996E |  | IAD0996E | Passive | Migration | Passive patching | Passive Completed | SHAHID | 2023-03-13 | AUH | 1G | AUH-1097-SCSG-SR7B-1 | esat-1/1/54 | AUH-1097-SCSG-SR7B-1 |  |  |  | 1 | 1 |  | Passive Completed | Muhammad Shoaib;#1360 |  | 2023-03-13 |  |  | Nokia |  |  | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 17:11 |  | 24.416851 | 54.49631 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
63 |  |  | IAD5477 |  | IAD5477 | Passive | Migration | Passive patching | No OSP | XAD |  | AUH |  | AUH-1222-SCSG-SR7B-1 | esat-1/1/29 | AUH-1222-SCSG-SR7B-1 |  | 5 |  |  |  |  | incorrect OSP in portal | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2022 | Muhammad Shoaib | 2022-11-02 16:57 |  | 24.43031 | 54.43763 | Passive site |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
62 |  |  | IAD5238 |  | IAD5238 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-11-28 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | port 7/1/18 | IAD5238-CSG-IXR-E-1 | NK22373A086 |  |  | 1 | 1 |  | Site Completed | Mohammed Faris;#1773 |  | 2022-11-16 | Y22-F69198 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-11-02 16:29 | AUH_E2271X_10398_001013005 | 24.48753 | 54.35171 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
61 |  |  | AUH0488 |  | AUH0488 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-03-15 | AUH | 1G | AUH-2170-PREAGG-SR7-1 | Port 2/1/15 | AUH-0488-CSG-IXR-E-1 | NK22373A206 | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F76251 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-11-02 10:54 |  | 24.37196 | 54.68429 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
60 | WO- IIB-CSG-2022-Order # 60 |  | AUH0759 |  | AUH0759 | Nokia IXR-E | Migration | New CSG | Installed & Power up | XAD |  | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 2/1/32 |  |  | 5 |  |  |  |  | passive link in progress CR - 981406 | Aris Dumma;#1292 | [7 empty] | FALSE | 2022 | Aris Dumma | 2022-11-02 10:51 |  | 24.499304 | 54.367282 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
59 |  |  | AUH0460 |  | AUH0460 | Passive to CSG | Migration | New CSG | RFSed | XAD | 2023-09-18 | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-2/1/15 | AUH-0460-CSG-IXR-E-1 | NK231134365 | [5 empty] | passive changed to CSG | Aris Dumma;#1292 |  | 2023-09-15 | Y23F107611 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-11-02 10:46 | AUH_E2270E_12846_001003001 | 24.469391 | 54.3725 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
58 |  |  | AUH0853 |  | AUH0853 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-01-17 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/22 | AUH-0853-CSG-IXR-E-1 | NK22373A238 | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F69263 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-11-02 10:40 |  | 24.489017 | 54.374086 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
57 |  |  | AUH0687/IAD5873 |  | AUH0687/IAD5873 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-1336-SCSG-SR7B-1 | esat-1/1/58 | [7 empty] | cancelled from XAD 9-11-2023 | Aris Dumma;#1292 | [7 empty] | FALSE | 2022 | Aris Dumma | 2022-11-02 10:36 |  | 24.4497 | 54.3939 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
56 |  |  | AUH0825 |  | AUH0825 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-01-16 | AUH | 1G | AUH-6005-AGGR-SR12e-2 | Port 3/2/23 | AUH-0825-CSG-IXR-E-1 | NK223433559 | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F69300 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-11-02 10:32 |  | 24.488771 | 54.373817 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
55 |  |  | IAD5277 |  | IAD5277 | Nokia IXR-E | Migration | New CSG | Cancelled/on Hold |  |  | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | Port 7/1/23 | [7 empty] | cancelled from XAD 9-11-2023 | Rogelio Pangilinan;#1712 | [7 empty] | FALSE | 2022 | Aris Dumma | 2022-11-02 10:27 |  | 24.499115 | 54.404964 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
54 |  |  | AUH5662 |  | AUH0662 | Nokia IXR-E | Migration | New CSG | No OSP | XAD |  | AUH | 10G | AUH-1222-SCSG-SR7B-1 | esat-1/1/27 | AUH-0662-CSG-IXR-E-1 | [7 empty] | Aris Dumma;#1292 |  |  |  |  | Nokia |  |  | FALSE | 2022 | Aris Dumma | 2022-11-02 10:21 |  | 24.415627 | 54.446044 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
53 | WO- IIB-CSG-2022-Order # 53 |  | AUH5673A |  | AUH5673A | Passive | Migration | Passive patching | Transmission rack not available | XAD |  | AUH | 1G | AUH-ADAC-SCSG-SR7B-1 | esat-1/1/12 | AUH-ADAC-SCSG-SR7B-1 |  | 5 |  |  |  |  | no TI rack no rectifier no OSP available | Rogelio Pangilinan;#1712 |  |  |  |  | XAD |  |  | FALSE | 2022 | Aris Dumma | 2022-11-02 10:13 |  | 24.429202 | 54.640822 | Passive site | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
52 |  |  | AAN5397D |  | AAN5397D | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-02-01 | AUH | 10G | AAN-6001-AGGR-SR7S-1 | esat-1/1/31 | AAN-5397D-CSG-IXR-E-1 | NK223235603 | [6 empty] | Aris Dumma;#1292 |  | 2023-01-20 | Y22-F73402 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-11-02 10:06 |  | 24.214694 | 55.757833 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
51 |  |  | DXBNR0754 |  | DXBNR0754 | Nokia IXR-E | 5G |  | RFSed | HOI-MEA | 2022-12-27 | DXB | 10G | DXB-JI-POP-PREAGG-IXR-R6-2 | Port 1/4/1 | DXB-0754-CSG-IXR-E-1 | NS2203C6717 | [9 empty] | Y22-F71366 |  | Nokia |  |  | TRUE | 2022 | Syed Shahzaib | 2022-10-26 12:59 |  | 25.078228 | 55.154029 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
50 |  |  | DXBNR0010B |  | DXBNR0010B | To Be Confirmed | 5G |  | Cancelled/on Hold | HOI-MEA |  | DXB | 10G | DXB-1025-PREAGG-SR7-1 | [8 empty] | Ti Not Found | [8 empty] | FALSE | 2022 | Syed Shahzaib | 2022-10-26 12:56 |  | 25.25413 | 55.30360 |  |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
49 |  |  | IDXNR5008 |  | IDXNR5008 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2022-11-25 | DXB | 10G | DXB-BB-AGGR-SR12e-2 | 7/1/33 | IDX-5008-CSG-IXR-E-1 | NS2124CD841 |  |  | 1 | 1 |  | Site Completed | Muhammad Shoaib;#1360 |  | 2022-11-14 | Y22-F68937 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-26 10:22 | DXB_E3278G_10188_001002002 | 25.188300 | 55.297420 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
47 |  |  | DXBNR0885 |  | DXBNR0885 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2022-12-20 | DXB | 10G | DXB-JI-POP-PREAGG-IXR-R6-2 | 1/4/4 | DXB-0885-CSG-IXR-E-1 | NK22373A348 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-12-16 | Y22-F71132 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-25 19:23 | DXB_E3077S_10425_001005008 | 25.069500 | 55.146200 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
46 |  |  | DXBNR0884 |  | DXBNR0884 | Nokia IXR-E | 5G | New CSG | RFSed | SHAHID | 2022-12-21 | DXB | 10G | DXB-JI-POP-PREAGG-IXR-R6-2 | 1/4/2003 | DXB-0884-CSG-IXR-E-1 | NK223739902 | [5 empty] | Site Completed | Mohammed Faris;#1773 |  | 2022-12-16 | Y22-F71140 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-25 17:12 | DXB_E3077S_10424_001005006 | 25.06931 | 55.146190 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
45 |  |  | DXB0927 |  | DXB0927 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2022-12-12 | DXB | 10G | DXB-BB-AGGR-SR12e-2 | 7/1/34 | DXB-0927-CSG-IXR-E-1 | NK220937167 | [6 empty] | Aris Dumma;#1292 |  | 2022-12-01 | Y22-F68852 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-10-25 13:17 |  | 25.202328 | 25.202328 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
44 |  |  | DXB0338 |  | DXB0338 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2022-12-12 | DXB | 10G | DXB-BB-AGGR-SR12e-2 | 7/1/35 | DXB-0338-CSG-IXR-E-1 | NK220937073 | [6 empty] | Aris Dumma;#1292 |  | 2022-12-01 | Y22-F69016 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-10-25 13:08 |  | 25.188427 | 55.271439 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
43 |  |  | DXN0932 |  | DXN0932 | Nokia IXR-E | Rollout |  | RFSed | HOI-MEA | 2022-11-24 | DXB | 1G | DXB-1516-SCSG-SR7B-1-New IXR | 3/1/22 | DXN-0932-CSG-IXR-E-1 | NS2203C6667 |  | 1 | 1 | 1 | [5 empty] | Y22-F69041 |  | Nokia |  |  | TRUE | 2022 | Mohamed Abussalah | 2022-10-16 16:54 |  | 25.223215 | 55.334033 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
42 |  |  | AJM0925 |  | AJM0925 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-31 | AJM | 10G | AJM-6001-SCSG-SR7B-1 | esat-1/1/35 | AJM-0925-CSG-N540-LD-1 | FOC2633NM2E | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F72936 |  | Cisco |  |  | FALSE | 2022 | Aris Dumma | 2022-10-14 09:58 |  | 25.417246 | 55.43972 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
41 |  |  | AUH6417 |  | AUH6417 | Cisco NCS540 | Migration | New CSG | RFSed | SHAHID | 2023-01-19 | AUH | 1G | AUH-2911-PREAGG-SR7-1 | Port 2/1/11 1G | NEW CSG | FOC2633NM0Y | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2023-01-14 | Y22-F72579 |  | Cisco |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-12 14:45 |  | 24.033151 | 52.798421 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
39 |  |  | RAK3533 |  | RAK3533 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2023-01-24 | RAK | 1G | RAK-2727-PREAGG-SR7-1 | Port 3/2/12 | RAK-3533-CSG-IXR-E-1 | NK220936999 | [9 empty] | Y22-F73394 |  | Nokia |  |  | TRUE | 2022 | Mohamed Abussalah | 2022-10-11 15:03 |  | 26.034784 | 56.130257 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
37 |  |  | AUH2812 |  | AUH2812 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2022-11-25 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-1 | Port 7/1/22 | AUH-2812-CSG-IXR-E-1 | NS2203C6532 |  |  | 1 | 1 | 1 |  |  |  | 2022-11-08 | Y22-F68908 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 19:47 |  | 24.457910 | 54.613600 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
35 |  |  | AUH0433 |  | AUH0433 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-03-16 | AUH | 10G | AUH-2055-SCSG-SR7B-1 | esat-1/1/13 | AUH-0433-CSG-IXR-E-1 | NK22393A573 |  |  | 1 | 1 | 1 |  |  |  | 2023-03-13 | Y23-F76427 |  | Nokia |  |  | FALSE | 2022 | Arif Ahmad | 2022-10-10 19:40 |  | 24.465704 | 54.393706 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
34 |  |  | AUH0582 |  | AUH0582 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-11-25 | AUH | 10G | AUH-KHAZNA-AGG-SR12e-2 | Port 7/1/9 | AUH-0582-CSG-IXR-E-1 | NS2203C7767 |  |  | 1 | 1 |  | Site Completed | Muhammad Shoaib;#1360 |  | 2022-11-12 | Y22-F68560 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-10 19:31 | AUH_E2470Y_10255_001001001 | 24.406021 | 54.568994 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
33 |  |  | AUG6067 |  | AUG6067 | Nokia IXR-E | Rollout | New CSG | RFSed | NETS | 2022-12-16 | AUH | 10G | AUH-2674-PREAGG-SR7-1 | 2/1/14 | AUG-6067-CSG-IXR-E-1 | NK220937085 | [6 empty] | Arif Ahmad;#308 |  | 2022-12-14 | Y22-F71078 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 19:29 | AUH_E2768Y_10001_001001001 | 24.233317° | 54.881736° | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
32 |  |  | AUH0819 |  | AUH0819 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2022-12-19 | AUH | 10G | AUH-6005-AGGR-SR12e-2 | Port 2/1/21 10G | AUH-0819-CSG-IXR-E-1 | NK22373A263 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2022-11-14 | Y22-F69183 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-10 19:26 | AUH_E2271X_10053_001001001 | 24.49437 | 54.36338 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
31 |  |  | SHR2646 |  | SHR2646 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | NETS | 2022-07-15 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/9 | SHR-2646-CSG-IXR-E-1 | NS2203C4677 |  |  | 1 | 1 | 1 |  |  |  | 2022-07-11 | Y22-F59996 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 19:24 | SHJ_E3579C_10006_001001001 | 25.3054 | 55.61781 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
30 |  |  | FUJ0638 |  | FUJ0638 | Nokia IXR-E | Migration | New CSG | RFSed | SHAHID | 2023-01-23 | FUJ | 1G | FUJ-2433-PREAGG-SR7-1 | Port 2/1/17 | New CSG | NK22393A550 | [5 empty] | Site Completed | Muhammad Shoaib;#1360 |  | 2023-01-19 | Y22-F73340 |  | Nokia |  |  | TRUE | 2022 | Muhammad Shoaib | 2022-10-10 19:22 | MSF_E4074K_10003_001001001 | 24.82097 | 56.07407 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
29 |  |  | SHJ3003 |  | SHJ3003 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | NETS | 2022-07-15 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/9 | SHR-2646-CSG-IXR-E-1 | NK214832064 |  |  | 1 | 1 | 1 |  |  |  | 2022-07-11 | Y22-F59992 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 19:12 | SHJ_E3579B_10007_001001001 | 25.29797 | 55.58571 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
28 |  |  | SHJ2365 |  | SHJ2365 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | NETS | 2022-08-30 | SHJ | 10G | SHJ-2054-SCSG-SR7B-1 | esat-1/1/59 | SHJ-2365-CSG-IXR-E-1 | NK214832012 | [8 empty] | 2022-08-27 | Y22-F63543 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 18:55 | SHJ_E3579G_10001_001001001 | 25.2808508007 | 55.5824970741 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
27 |  |  | SHJ3381 |  | SHJ3381 | Cisco NCS540 | 5G+Migration | New CSG | RFSed | NETS | 2023-03-17 | SHJ | 10G | SHJ-5003-SCSG-SR7B-1 | esat-1/1/8 | SHJ-3381-CSG-N540-LD-1 | FOC2628P2P9 |  |  | 1 | 1 | 1 |  |  |  | 2023-03-13 | Y23-F76443 |  | Cisco |  |  | FALSE | 2022 | Arif Ahmad | 2022-10-10 18:43 |  | 25.361300 | 55.565800 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
26 |  |  | DXB3566 |  | DXB3566 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | NETS | 2022-06-29 | DXB | 10G | DXB-DFC-PREAGG-SR7-1 | Port 5/1/5 | DXB-3566-CSG-IXR-E-1 | NK213632308 | [8 empty] | 2022-06-13 | Y22-F58596 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 18:31 | DXB_E3279Y_10486_001006002 | 25.22047 | 55.35136 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
25 |  |  | AUH3120 |  | AUH3120 | Nokia IXR-E | 5G+Migration | New CSG | RFSed | NETS | 2022-10-11 | AUH | 10G | AUH-1416-AGGR-SR12E-1 | Port 2/1/18 | AUH-3120-CSG-IXR-E-1 | NS2147CA623 | [8 empty] | 2022-07-04 | Y22-F59623 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-10 18:02 | AUH_E2569Q_10002_001002001 | 24.324622 | 54.612842 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
24 |  |  | AAG6065 |  | AAG6065 | Nokia IXR-E | Migration | New CSG | RFSed | NETS | 2023-01-02 | AUH | 1G | AAN-5002-AGGR-SR12-2 | 8/2/24 | AAG-6065-CSG-IXR-E-1 | NK220937171 | [6 empty] | Arif Ahmad;#308 |  | 2022-12-30 | Y22-F72280 |  | Nokia |  |  | TRUE | 2022 | Arif Ahmad | 2022-10-07 14:58 | AAN_E3568G_10001_001001002 | 24.280860 | 55.603960 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
21 |  |  | AUH0724 |  | AUH0724 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-12-06 | AUH | 10G | AUH-1090-SCSG-SR7B-1 | esat-1/1/46 | AUH-0724-CSG-IXR-E-1 | NS2147CA631 | [6 empty] | Rogelio Pangilinan;#1712 |  | 2023-10-02 | Y23-F108770 |  |  |  |  | FALSE | 2022 | Arif Ahmad | 2022-10-06 18:12 | AUH_E2370H_10004_001005023 | 24.4459 | 54.43918 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
20 | WO- IIB-CSG-2022-Order # 20 |  | AUH0918 |  | AUH0918 | Nokia IXR-E | 5G+Migration | New CSG | PTW in progress | SHAHID |  | AUH | 10G | AUH-1416-AGGR-SR12-1 | esat-1/1/9 | AUH-0918-CSG-IXR-E-1 |  | 5 |  |  |  |  | Discussion ongoing to get BM Engg team appoinment for survey | [5 empty] | Shahid Tech | IIB not ready |  | FALSE | 2022 | Arif Ahmad | 2022-10-06 18:05 |  | 24.432486 | 54.618452 | ZTP | 5 | Item | sites/IMP/Control/Lists/ABC2 TEST333
19 |  |  | SHJ0354 |  | SHJ0354 | Nokia IXR-E | Migration |  | RFSed | HOI-MEA | 2022-11-24 | SHJ | 1G | SHJ-2022-AGGR-SR7b-1 | Port 3/1/27 | SHJ-0354-CSG-IXR-E-1 | NS2202CA327 |  | 1 | 1 | 1 | [5 empty] | Y22-F69041 |  | Nokia |  |  | TRUE | 2022 | Mohamed Abussalah | 2022-10-06 17:09 |  | 25.344724 | 55.392251 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
18 |  |  | SHJ0207 |  | SHJ0207 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-02-28 | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-2/1/61 | SHJ-0207-CSG-IXR-E-1 | NK224031035 | [5 empty] | changed the switch from cisco to nokia | Aris Dumma;#1292 |  |  | Y23-F74308 |  | Nokia |  |  |  | 2022 | Aris Dumma | 2022-10-05 17:51 |  | 25.335275 | 55.375559 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
17 |  |  | SHJ0205 |  | SHJ0205 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2023-03-03 | SHJ | 10G | SHJ-2084-SCSG-SR7B-1 | esat-2/1/62 | SHJ-0205-CSG-IXR-E-1 | NK224030879 | [6 empty] | Aris Dumma;#1292 |  |  | Y23-F74410 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-10-05 17:46 |  | 25.34511 | 55.375728 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
16 |  |  | ISH5202 |  | ISH5202 | Nokia IXR-E | Migration | New CSG | RFSed | XAD | 2022-12-08 | SHJ | 10G | SHJ-2084-SCSG-IXR-R6-1 | Port 1/4/9 | ISH-5202-CSG-IXR-E-1 | NK22373A246 | [6 empty] | Aris Dumma;#1292 |  |  | Y22-F69766 |  | Nokia |  |  | TRUE | 2022 | Aris Dumma | 2022-10-05 17:30 |  | 25.325196 | 55.374879 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
15 |  |  | ISH5173 |  | ISH5173 | Cisco NCS540 | Rollout | New CSG | Cancelled/on Hold |  |  | SHJ | 1G | SHJ-2016-PREAGG-SR7-1 | Port 4/1/11 | [7 empty] | cancelled from XAD 9-11-2023 | Aris Dumma;#1292 | [8 empty] | 2022 | Aris Dumma | 2022-10-05 17:23 |  | 25.302106 | 55.380178 | Manual |  | Item | sites/IMP/Control/Lists/ABC2 TEST333
14 |  |  | ISH5127 |  | ISH5127 | Cisco NCS540 | Migration | New CSG | RFSed | XAD | 2023-01-26 | SHJ | 10G | SHJ-5001-SCSG-SR7B-1 | esat-1/1/12 | ISH-5127-CSG-N540-LD-1 | FOC2633NM3A | [6 empty] | Aris Dumma;#1292 |  | 2023-01-24 | Y22-F73588 |  | Cisco |  |  | TRUE | 2022 | Aris Dumma | 2022-10-05 17:16 |  | 25.281 | 55.87354 | ZTP |  | Item | sites/IMP/Control/Lists/ABC2 TEST333