## summary
Category | Qty | Estimated OSP Budget Requirements
AUH Y2024 Fiber scope | 622 | 23.75M AED
MW | 1076
other region | 4
Total | 1702

## consdolidated (2)
[11 empty] | Total Required Budget | 23933100.876
IBS Ref. Code | Sitecode | Area | Lat | Long | Site Type | Scope | Status | Timeline | EPOC | Cost | Depandancy | Cost of Confirmed Fibe Sites | Transport Feedback |  | MW/CSG Plan statuw
| AAG6105 | AUH | 24.301 | 55.1264 | Existing | OD | Possible | #N/A | 0 | 1168587.036 |  |  | stay in MW
| AAN2200 | AUH | 23.631 | 55.561 | Existing | OD | Possible | #N/A | 0 | 465948.03 | Depend to Connect AAN2269 |  | stay in MW
| AAN2263 | AUH | 24.1044 | 55.7408 | Existing | OD | Possible | #N/A | 0 | 412056.04 |  |  | stay in MW
| AAN2268 | AUH | 23.7534 | 55.526 | Existing | OD | Possible | #N/A | 0 | 1041620.78 | Depend to Connect AAN3258 |  | stay in MW
| AAN2269 | AUH | 23.6385 | 55.566 | Existing | OD | Possible | #N/A | 0 | 1227183.055 | Depend to Connect AAN2421 |  | stay in MW
| AAN2270 | AUH | 23.5403 | 55.4962 | Existing | OD | Possible | #N/A | 0 | 1123293.78 | Depend to Connect AAN2423 |  | stay in MW
| AAN2271 | AUH | 23.399 | 55.4231 | Existing | OD | Possible | #N/A | 0 | 381278.82 | Depend to Connect AAN2424 |  | stay in MW
| AAN2272 | AUH | 23.3157 | 55.3571 | Existing | OD | Possible | #N/A | 0 | 1410819.31 | Depend to Connect AAN2425 |  | stay in MW
| AAN2273 | AUH | 23.4725 | 55.2967 | Existing | OD | Possible | #N/A | 0 | 1490477.395 | Depend to Connect AAN2383 |  | stay in MW
| AAN2312 | AUH | 24.1454 | 55.5525 | Existing | OD | Possible | #N/A | 0 | 232515.625 | Depend to Connect AAN3276 |  | stay in MW
| AAN2314 | AUH | 24.1776 | 55.4679 | Existing | OD | Possible | #N/A | 0 | 581935.88 |  |  | stay in MW
| AAN2326 | AUH | 24.1206 | 55.4058 | Existing | OD | Possible | #N/A | 0 | 710997.505 | Depend to Connect AAN2588 |  | stay in MW
| AAN2383 | AUH | 23.4285 | 55.4105 | Existing | OD | Possible | #N/A | 0 | 1027449.905 | Depend to Connect AAN3287 |  | stay in MW
| AAN2393 | AUH | 24.0934 | 55.101 | Existing | OD | Possible | #N/A | 0 | 756039.555 |  |  | stay in MW
| AAN2394 | AUH | 24.0304 | 55.1079 | Existing | OD | Possible | #N/A | 0 | 1077294.815 | Depend to Connect AAN2393 |  | stay in MW
| AAN2396 | AUH | 23.9825 | 55.1826 | Existing | OD | Possible | #N/A | 0 | 490163.465 | Depend to Connect AAN3323 |  | stay in MW
| AAN2398 | AUH | 24.0061 | 55.4082 | Existing | OD | Site survey required | #N/A | 0 |  |  |  | stay in MW
| AAN2408 | AUH | 23.8806 | 55.4038 | Existing | OD | Possible | #N/A | 0 | 974941.48 |  |  | stay in MW
| AAN2421 | AUH | 23.7064 | 55.5682 | Existing | OD | Possible | #N/A | 0 | 1377790.505 | Depend to Connect AAN2268 |  | stay in MW
| AAN2422 | AUH | 23.6429 | 55.5335 | Existing | OD | Possible | #N/A | 0 | 328536.255 | Depend to Connect AAN3396 |  | stay in MW
| AAN2423 | AUH | 23.5887 | 55.5346 | Existing | OD | Possible | #N/A | 0 | 854510.375 | Depend to Connect AAN2200 |  | stay in MW
| AAN2424 | AUH | 23.4184 | 55.4229 | Existing | OD | Possible | #N/A | 0 | 411812.24 | Depend to Connect AAN2424 |  | stay in MW
| AAN2425 | AUH | 23.3991 | 55.4009 | Existing | OD | Possible | #N/A | 0 | 381654.18 | Depend to Connect AAN3231 |  | stay in MW
| AAN2426 | AUH | 23.4875 | 55.4572 | Existing | OD | Possible | #N/A | 0 | 1136245.655 | Depend to Connect AAN2270 |  | stay in MW
| AAN2427 | AUH | 23.6323 | 55.5543 | Existing | OD | Possible | #N/A | 0 | 208440.375 | Depend to Connect AAN2200 |  | stay in MW
| AAN2429 | AUH | 24.0325 | 55.6523 | Existing | OD | Possible | #N/A | 0 | 632676.755 | Depend to Connect AAN3113 |  | stay in MW
| AAN2436 | AUH | 24.2127 | 55.9538 | Existing | OD | Possible | #N/A | 0 | 611344.255 |  |  | stay in MW
| AAN2472 | AUH | 24.1399 | 55.4788 | Existing | OD | Possible | #N/A | 0 | 808895.395 | Depend to Connect AAN3280 |  | stay in MW
| AAN2486 | AUH | 24.4368 | 55.1946 | Existing | OD | Possible | #N/A | 0 | 999138.63 |  |  | stay in MW
| AAN2490 | AUH | 24.5756 | 55.3429 | Existing | OD | Possible | #N/A | 0 | 1418931.755 |  |  | stay in MW
| AAN2504 | AUH | 23.584 | 55.4508 | Existing | OD | Possible | #N/A | 0 | 1101991.755 | Depend to Connect AAN2270 |  | stay in MW
| AAN2511 | AUH | 23.9867 | 55.2575 | Existing | OD | Possible | #N/A | 0 | 1585477.63 | Depend to Connect AAN3318 |  | stay in MW
| AAN2513 | AUH | 24.5961 | 55.3952 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN2530 | AUH | 24.0895 | 55.9822 | Existing | OD | Possible | #N/A | 0 | 696735.205 |  |  | stay in MW
| AAN2849 | AUH | 23.4138 | 55.4064 | Existing | OD | Possible | #N/A | 0 | 265715.09 | Depend to Connect AAN2383 |  | stay in MW
| AAN2871 | AUH | 24.1773 | 55.738 | Existing | OD | Possible | #N/A | 0 | 316791.19 |  |  | stay in MW
| AAN2873 | AUH | 24.6086 | 55.4612 | Existing | OD | Possible | #N/A | 0 | 732147.155 | Depend to Connect AAN3134 |  | stay in MW
| AAN2896 | AUH | 23.3976 | 55.412 | Existing | OD | Possible | #N/A | 0 | 205831.715 | Depend to Connect AAN2425 |  | stay in MW
| AAN2912 | AUH | 23.6423 | 55.554 | Existing | OD | Possible | #N/A | 0 | 399622.24 | Depend to Connect AAN3230 |  | stay in MW
| AAN2914 | AUH | 24.0819 | 56.0133 | Existing | OD | Possible | #N/A | 0 | 612807.055 | Depend to Connect AAN2530 |  | stay in MW
| AAN2944 | AUH | 24.5466 | 55.2078 | Existing | OD | Possible | #N/A | 0 | 958765.9296 |  |  | stay in MW
| AAN3109 | AUH | 24.1073 | 55.748 | Existing | OD | Possible | #N/A | 0 | 219429.66 | Depend to Connect AAN2263 |  | stay in MW
| AAN3113 | AUH | 24.0472 | 55.692 | Existing | OD | Possible | #N/A | 0 | 662054.655 |  |  | stay in MW
| AAN3115 | AUH | 23.6492 | 55.4803 | Existing | OD | Possible | #N/A | 0 | 780340.32 | Depend to Connect AAN2422 |  | stay in MW
| AAN3116 | AUH | 23.5031 | 55.4143 | Existing | OD | Possible | #N/A | 0 | 894213.205 | Depend to Connect AAN2426 |  | stay in MW
| AAN3134 | AUH | 24.5946 | 55.4099 | Existing | OD | Possible | #N/A | 0 | 1143328.045 | Depend to Connect AAN2490 |  | stay in MW
| AAN3154 | AUH | 23.4124 | 55.4235 | Existing | OD | Possible | #N/A | 0 | 184688.16 | Depend to Connect AAN2424 |  | stay in MW
| AAN3213 | AUH | 24.1543 | 55.644 | Existing | OD | Possible | #N/A | 0 | 172034.4509 |  |  | stay in MW
| AAN3223 | AUH | 24.1195 | 55.9681 | Existing | OD | Possible | #N/A | 0 | 446797.54 | Depend to Connect AAN2530 |  | stay in MW
| AAN3230 | AUH | 23.6353 | 55.5489 | Existing | OD | Possible | #N/A | 0 | 210658.955 | Depend to Connect AAN2427 |  | stay in MW
| AAN3231 | AUH | 23.416 | 55.4151 | Existing | OD | Possible | #N/A | 0 | 334765.345 | Depend to Connect AAN2849 |  | stay in MW
| AAN3257 | AUH | 24.4142 | 55.097 | Existing | OD | Possible | #N/A | 0 | 1247278.27 |  |  | stay in MW
| AAN3276 | AUH | 24.1421 | 55.5427 | Existing | OD | Possible | #N/A | 0 | 882015.8384 |  |  | stay in MW
| AAN3279 | AUH | 24.0981 | 55.3651 | Existing | OD | Possible | #N/A | 0 | 789623.005 | Depend to Connect AAN2326 |  | stay in MW
| AAN3280 | AUH | 24.1416 | 55.4198 | Existing | OD | Possible | #N/A | 0 | 425050.58 | Depend to Connect AAN2326 |  | stay in MW
| AAN3283 | AUH | 24.6272 | 55.402 | Existing | OD | Possible | #N/A | 0 | 1278106.78 |  |  | stay in MW
| AAN3284 | AUH | 23.8182 | 55.4609 | Existing | OD | Possible | #N/A | 0 | 799454.24 | Depend to Connect AAN3258 |  | stay in MW
| AAN3286 | AUH | 23.9699 | 55.5181 | Existing | OD | Possible | #N/A | 0 | 722212.305 |  |  | stay in MW
| AAN3287 | AUH | 23.4576 | 55.4414 | Existing | OD | Possible | #N/A | 0 | 564626.08 | Depend to Connect AAN2426 |  | stay in MW
| AAN3289 | AUH | 24.5254 | 55.1481 | Existing | OD | Possible | #N/A | 0 | 1341159.555 | Depend to Connect AAN2944 |  | stay in MW
| AAN3297 | AUH | 24.4059 | 55.1992 | Existing | OD | Possible | #N/A | 0 | 598727.605 | Depend to Connect AAN2486 |  | stay in MW
| AAN3298 | AUH | 24.4019 | 55.1852 | Existing | OD | Possible | #N/A | 0 | 206593.59 | Depend to Connect AAN3297 |  | stay in MW
| AAN3318 | AUH | 23.997 | 55.3738 | Existing | OD | Possible | #N/A | 0 | 1170037.3366 | Depend to Connect AAN2398 |  | stay in MW
| AAN3323 | AUH | 23.9908 | 55.2132 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN3326 | AUH | 24.4101 | 55.7332 | Existing | OD | Possible | #N/A | 0 | 552070.38 |  |  | stay in MW
| AAN3330 | AUH | 24.0928 | 55.5482 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN3339 | AUH | 23.9051 | 55.411 | Existing | OD | Possible | #N/A | 0 | 356682.965 | Depend to Connect AAN2408 |  | stay in MW
| AAN3340 | AUH | 24.5608 | 55.3452 | Existing | OD | Possible | #N/A | 0 | 1272325.155 | Depend to Connect AAN2490 |  | stay in MW
| AAN3346 | AUH | 24.2121 | 55.7633 | Existing | OD | Possible | #N/A | 0 | 346486.03 |  |  | stay in MW
| AAN3351 | AUH | 24.3615 | 55.6997 | Existing | OD | Possible | #N/A | 0 | 592784.98 |  |  | stay in MW
| AAN3357 | AUH | 24.446 | 55.4571 | Existing | OD | Site survey required | #N/A | 0 | 1441423.8 | tentative cost |  | stay in MW
| AAN3366 | AUH | 24.3378 | 55.6578 | Existing | OD | Possible | #N/A | 0 | 918105.605 |  |  | stay in MW
| AAN3372 | AUH | 24.3346 | 55.3227 | Existing | OD | Possible | #N/A | 0 | 1100598.53 |  |  | stay in MW
| AAN3396 | AUH | 23.6299 | 55.5378 | Existing | OD | Possible | #N/A | 0 | 298609.805 | Depend to Connect AAN3230 |  | stay in MW
| AAN3419 | AUH | 24.1062 | 55.984 | Existing | OD | Possible | #N/A | 0 | 364935.595 | Depend to Connect AAN2914 |  | stay in MW
| AAN3420 | AUH | 24.1217 | 55.6032 | Existing | OD | Possible | #N/A | 0 | 640852.68 |  |  | stay in MW
| AAN3422 | AUH | 24.1365 | 55.1617 | Existing | OD | Possible | #N/A | 0 | 544732 |  |  | stay in MW
| AAN3438 | AUH | 24.1027 | 55.0523 | Existing | OD | Possible | #N/A | 0 | 619091 | Depend to Connect AAN2393 |  | stay in MW
| AAN3498 | AUH | 24.3917 | 55.5146 | Existing | OD | Possible | #N/A | 0 | 2067656.0976 |  |  | stay in MW
| AAN3520 | AUH | 24.0662 | 55.5048 | Existing | OD | Possible | #N/A | 0 | 719329.37 |  |  | stay in MW
| AAN3531 | AUH | 23.9614 | 55.0329 | Existing | OD | Possible | #N/A | 0 | 1893070.43 | Depend to Connect AAN2394,AAN2393 |  | stay in MW
| AAN3534 | AUH | 24.6708 | 55.8315 | Existing | OD | Possible | #N/A | 0 | 1206097.1304 |  |  | stay in MW
| AAN3535 | AUH | 24.0644 | 55.1755 | Existing | OD | Possible | #N/A | 0 | 1280666.68 | Depend to Connect AAN2394 |  | stay in MW
| AAN3537 | AUH | 24.4801 | 55.2305 | Existing | OD | Possible | #N/A | 0 | 514799.455 |  |  | stay in MW
| AAN3542 | AUH | 24.2277 | 55.2998 | Existing | OD | Possible | #N/A | 0 | 664472.0049 |  |  | stay in MW
| AAN3552 | AUH | 24.7168 | 55.6544 | Existing | OD | Possible | #N/A | 0 | 620255.145 |  |  | stay in MW
| AAN3554 | AUH | 24.3377 | 55.714 | Existing | OD | Possible | #N/A | 0 | 589188.93 |  |  | stay in MW
| AAN3555 | AUH | 24.7457 | 55.7613 | Existing | OD | Site survey required | #N/A | 0 | 622711.43 |  |  | stay in MW
| AAN3559 | AUH | 24.5241 | 55.327 | Existing | OD | Possible | #N/A | 0 | 667204.93 |  |  | stay in MW
| AAN3562 | AUH | 24.3851 | 55.0809 | Existing | OD | Possible | #N/A | 0 | 1463336.8476 |  |  | stay in MW
| AAN3566 | AUH | 24.6346 | 55.6148 | Existing | OD | Possible | #N/A | 0 | 687470.805 | Depend to Connect AAN3566 |  | stay in MW
| AAN3567 | AUH | 24.6413 | 55.6643 | Existing | OD | Possible | #N/A | 0 | 563004.81 |  |  | stay in MW
| AAN3568 | AUH | 24.2853 | 55.4098 | Existing | OD | Possible | #N/A | 0 | 375683.61 |  |  | stay in MW
| AAN3570 | AUH | 24.4108 | 55.1278 | Existing | OD | Possible | #N/A | 0 | 542525.61 | Depend to Connect AAN3257 |  | stay in MW
| AAN3573 | AUH | 24.6228 | 55.7378 | Existing | OD | Possible | #N/A | 0 | 434684.1852 |  |  | stay in MW
| AAN3582 | AUH | 24.2251 | 55.7293 | Existing | OD | Possible | #N/A | 0 | 195232.05 |  |  | stay in MW
| AAN3586 | AUH | 24.7727 | 55.7802 | Existing | OD | Possible | #N/A | 0 | 646216.28 | Depend to Connect AAN3555 |  | stay in MW
| AAN3608 | AUH | 24.0342 | 55.8694 | Existing | OD | Possible | #N/A | 0 | 341131.055 |  |  | stay in MW
| AAN3609 | AUH | 24.0458 | 55.8918 | Existing | OD | Possible | #N/A | 0 | 326442.105 | Depend to Connect AAN3608 |  | stay in MW
| AAN3612 | AUH | 24.3883 | 55.7604 | Existing | OD | Possible | #N/A | 0 | 520232.63 |  |  | stay in MW
| AAN3617 | AUH | 24.0589 | 55.8523 | Existing | OD | Possible | #N/A | 0 | 283502.83 |  |  | stay in MW
| AAN3636 | AUH | 24.4368 | 55.8025 | Existing | OD | Possible | #N/A | 0 | 540903.9444 |  |  | stay in MW
| AAN3642 | AUH | 24.1239 | 55.9381 | Existing | OD | Possible | #N/A | 0 | 677611.3812 |  |  | stay in MW
| AAN3650 | AUH | 24.196181 | 55.6426 | Existing | OD | Possible | #N/A | 0 | 110603.7708 |  |  | stay in MW
| AAN3654 | AUH | 24.7794 | 55.7911 | Existing | OD | Possible | #N/A | 0 | 234155.18 | Depend to Connect AAN3586 |  | stay in MW
| AAN3939 | AUH | 24.3047 | 55.7832 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AAN3942 | AUH | 24.303 | 55.782 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AAN2813 | AUH | 24.0666 | 55.7775 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN2814 | AUH | 24.0599 | 55.7781 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN2922 | AUH | 24.3032 | 55.7873 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AAN2311 | AUH | 24.1534 | 55.5832 | Existing | OD | Possible | #N/A | 0 | 627587.43 | Depend to Connect AAN2312 |  | stay in MW
| AAN2560 | AUH | 24.1689 | 55.6333 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN2804 | AUH | 24.0944 | 55.761 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN2810 | AUH | 24.0828 | 55.7691 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN3282 | AUH | 24.483 | 55.6989 | Existing | OD | Possible | #N/A | 0 | 975813.065 |  |  | stay in MW
| AAN2542 | AUH | 24.7837 | 55.813 | Existing | OD | Possible | #N/A | 0 | 586409.61 | Depend to Connect AAN3654 |  | stay in MW
| AAN2514 | AUH | 22.7068 | 55.2122 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN3640 | AUH | 23.8772 | 55.3972 | Existing | OD | Possible | #N/A | 0 | 117316.56 | covering AAN2408 |  | stay in MW
| AUG4264 | AUH | 24.4824 | 54.6114 | Existing | OD | Possible | #N/A | 0 | 212603.26 |  |  | stay in MW
| AUG4279 | AUH | 24.4841 | 54.4059 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG4357 | AUH | 24.289 | 54.6333 | Existing | OD | Possible | #N/A | 0 | 537277.815 |  |  | stay in MW
| AUG4375 | AUH | 24.2939 | 54.6255 | Existing | OD | Possible | #N/A | 0 | 381654.18 | Depend to Connect AUG4357 |  | stay in MW
| AUG4408 | AUH | 24.541 | 54.4413 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG4418 | AUH | 24.3923 | 54.5006 | Existing | OD | Possible | #N/A | 0 | 242779.605 |  |  | stay in MW
| AUG6011 | AUH | 24.5095 | 54.454 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6012 | AUH | 24.5094 | 54.4515 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6015 | AUH | 24.5076 | 54.391 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6020 | AUH | 23.9612 | 52.2406 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6034 | AUH | 24.4595 | 54.6692 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6051 | AUH | 24.5603 | 54.6382 | Existing | OD | Possible | #N/A | 0 | 259479.905 |  |  | stay in MW
| AUG6052 | AUH | 24.4046 | 54.5124 | Existing | OD | Possible | #N/A | 0 | 430657.98 |  |  | stay in MW
| AUG6056 | AUH | 24.5224 | 54.3721 | Existing | OD | Possible | #N/A | 0 | 257880.83 | Depend to Connect AUH2555 |  | stay in MW
| AUG6081 | AUH | 24.5118 | 54.4532 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6082 | AUH | 24.4982 | 54.9338 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6083 | AUH | 24.3213 | 54.5962 | Existing | OD | Possible | 7-8 month | AUH6501 | 264217.1 |  | 264217.1 | Y2024 fiber scope |  | 264217.1 | 7-8 month
| AUG6093 | AUH | 24.0532 | 52.4475 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6098 | AUH | 24.6436 | 55.119 | Existing | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUG6104 | AUH | 23.9753 | 52.2658 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6105 | AUH | 23.9707 | 52.2515 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6114 | AUH | 24.3277 | 54.6104 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUG6155 | AUH | 24.5027 | 54.3804 | Existing | OD | Possible | 7-8 month | AUH6005 | 75035 |  | 75035 | Y2024 fiber scope
| AUG6244 | AUH | 24.4218 | 54.6801 | Existing | OD | Possible | 7-8 month | AUH2426 | Taawun |  | Taawun | Y2024 fiber scope
| AUG6245 | AUH | 22.8944 | 54.364 | Existing | OD | Possible | #N/A | 0 | 372531.276 |  |  | stay in MW
| AUH2128 | AUH | 24.5031 | 54.488 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2155 | AUH | 24.4119 | 54.4681 | Existing | OD | Possible | #N/A | 0 | 208896.35 |  |  | stay in MW
| AUH2010 | AUH | 24.4764 | 54.698 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2005 | AUH | 24.5013 | 54.371 | Existing | OD | Possible | #N/A | 0 | 226358.87 |  |  | stay in MW
| AUH2100 | AUH | 24.4249 | 54.4156 | Existing | OD | Possible | #N/A | 0 | 152906.99 |  |  | stay in MW
| AUH2095 | AUH | 24.4117 | 54.4579 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH2106 | AUH | 24.4064 | 54.518 | Existing | OD | Possible | #N/A | 0 | 411793.955 |  |  | stay in MW
| AUH2110 | AUH | 24.4228 | 54.5343 | Existing | OD | Possible | #N/A | 0 | 476400.955 |  |  | stay in MW
| AUH2113 | AUH | 24.4326 | 54.58 | Existing | OD | Possible | #N/A | 0 | 144010.13 |  |  | stay in MW
| AUH2171 | AUH | 24.4241 | 54.5772 | Existing | OD | Possible | #N/A | 0 | 201065.425 |  |  | stay in MW
| AUH2243 | AUH | 24.3708 | 54.6301 | Existing | OD | Possible | #N/A | 0 | 155761.29 |  |  | stay in MW
| AUH2168 | AUH | 24.2234 | 54.5443 | Existing | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH2167 | AUH | 24.0906 | 54.8973 | Existing | OD | Possible | #N/A | 0 | 813466.645 |  |  | stay in MW
| AUH2169 | AUH | 24.5979 | 54.9834 | Existing | OD | Possible | #N/A | 0 | 1236760.83 |  |  | stay in MW
| AUH2175 | AUH | 24.8157 | 54.8711 | Existing | OD | Not possible | 7-8 month | KIZAD DC | 201498.2 |  | 201498.2 | Y2024 fiber scope |  | 201498.2 | 7-8 month
| AUH2191 | AUH | 24.3662 | 52.5945 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2196 | AUH | 24.3188 | 52.5987 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2197 | AUH | 24.4981 | 54.3693 | Existing | OD | Possible | #N/A | 0 | 376616.03 |  |  | stay in MW
| AUH2190 | AUH | 24.2892 | 52.5616 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2201 | AUH | 24.4201 | 54.5653 | Existing | OD | Possible | #N/A | 0 | 128086.333 |  |  | stay in MW
| AUH2216 | AUH | 24.3298 | 54.5462 | Existing | OD | Possible | #N/A | 0 | 299755.665 | Depend to Connect AUH2216 |  | stay in MW
| AUH2232 | AUH | 24.4903 | 54.3725 | Existing | OD | Possible | #N/A | 0 | 171040.19 |  |  | stay in MW
| AUH2239 | AUH | 24.4181 | 54.5024 | Existing | OD | Possible | #N/A | 0 | 344279.64 |  |  | stay in MW
| AUH2240 | AUH | 24.4966 | 54.3698 | Existing | OD | Possible | #N/A | 0 | 220813.34 | Depend to Connect AUH2197 |  | stay in MW
| AUH2273 | AUH | 24.3105 | 54.5191 | Existing | OD | Possible | #N/A | 0 | 359773.13 |  |  | stay in MW
| AUH2317 | AUH | 24.4614 | 54.367 | Existing | OD | Possible | #N/A | 0 | 437890.1 |  |  | stay in MW
| AUH2354 | AUH | 24.4393 | 54.5199 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2357 | AUH | 24.4216 | 54.5079 | Existing | OD | Possible | #N/A | 0 | 152981.32 |  |  | stay in MW
| AUH2356 | AUH | 24.7475 | 54.6576 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2370 | AUH | 24.3586 | 54.5358 | Existing | OD | Possible | #N/A | 0 | 220612.09 | Depend to Connect AUH3685 |  | stay in MW
| AUH2379 | AUH | 24.3274 | 54.5571 | Existing | OD | Possible | #N/A | 0 | 231302.72 |  |  | stay in MW
| AUH2380 | AUH | 24.3377 | 54.5524 | Existing | OD | Possible | #N/A | 0 | 266702.48 |  |  | stay in MW
| AUH2384 | AUH | 24.3339 | 54.5559 | Existing | OD | Possible | #N/A | 0 | 206678.92 | Depend to Connect AUH2380 |  | stay in MW
| AUH2441 | AUH | 24.4341 | 54.5988 | Existing | OD | Possible | #N/A | 0 | 298908.46 |  |  | stay in MW
| AUH2445 | AUH | 24.4146 | 54.6033 | Existing | OD | Possible | #N/A | 0 | 125566.66 |  |  | stay in MW
| AUH2451 | AUH | 24.4268 | 54.552 | Existing | OD | Possible | #N/A | 0 | 160295.97 |  |  | stay in MW
| AUH2462 | AUH | 24.8431 | 54.7776 | Existing | OD | Site survey required | #N/A | 0 | 619916.355 | tentative cost-Depend to Connect AUH2819 |  | stay in MW
| AUH2470 | AUH | 24.3551 | 54.5526 | Existing | OD | Possible | #N/A | 0 | 413707.785 | Depend to Connect AUH2646 |  | stay in MW
| AUH2477 | AUH | 24.273 | 55.0048 | Existing | OD | Possible | #N/A | 0 | 1366789.03 |  |  | stay in MW
| AUH2485 | AUH | 24.5756 | 55.1724 | Existing | OD | Possible | #N/A | 0 | 997276.8931 | Depend to Connect AUH2774 |  | stay in MW
| AUH2491 | AUH | 24.4681 | 54.4039 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2514 | AUH | 24.7285 | 54.6411 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2526 | AUH | 24.2449 | 54.3415 | Existing | OD | Possible | #N/A | 0 | 649903.755 | Depend to Connect AUH2772 |  | stay in MW
| AUH2766 | AUH | 24.895 | 53.0657 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2501 | AUH | 24.2127 | 52.0091 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH2553 | AUH | 24.4128 | 54.5682 | Existing | OD | Possible | #N/A | 0 | 130570.655 |  |  | stay in MW
| AUH2555 | AUH | 24.5185 | 54.3735 | Existing | OD | Possible | #N/A | 0 | 538471.992 |  |  | stay in MW
| AUH2565 | AUH | 24.3916 | 54.648 | Existing | OD | Possible | #N/A | 0 | 423618.255 |  |  | stay in MW
| AUH2610 | AUH | 24.261 | 54.5469 | Existing | OD | Not possible | 4-5 month | AUH3119 | 28401.5 |  | 28401.5 | Y2024 fiber scope |  | 28401.5 | 4-5 month
| AUH2612 | AUH | 24.4961 | 54.4086 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2621 | AUH | 24.1012 | 54.974 | Existing | OD | Possible | #N/A | 0 | 1977388.66 | Depend to Connect AUH2622 |  | stay in MW
| AUH2622 | AUH | 24.1187 | 54.8327 | Existing | OD | Possible | #N/A | 0 | 872493.155 | Depend to Connect AUH2847 |  | stay in MW
| AUH2624 | AUH | 24.0273 | 54.9623 | Existing | OD | Possible | #N/A | 0 | 1952594.2 | Depend to Connect AUH2623 |  | stay in MW
| AUH2629 | AUH | 24.4232 | 54.3974 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2630 | AUH | 24.4527 | 54.3388 | Existing | OD | Possible | #N/A | 0 | 195220.452 |  |  | stay in MW
| AUH2623 | AUH | 24.0695 | 54.8199 | Existing | OD | Possible | #N/A | 0 | 779117.755 | Depend to Connect AUH2622 |  | stay in MW
| AUH2641 | AUH | 24.5206 | 54.6104 | Existing | OD | Possible | #N/A | 0 | 551911.91 |  |  | stay in MW
| AUH2646 | AUH | 24.3519 | 54.5583 | Existing | OD | Possible | #N/A | 0 | 243297.68 |  |  | stay in MW
| AUH2650 | AUH | 24.3643 | 54.552 | Existing | OD | Possible | #N/A | 0 | 295934.1 |  |  | stay in MW
| AUH2658 | AUH | 24.4147 | 54.5395 | Existing | OD | Site survey required | #N/A | 0 | 230000 | tentative cost |  | stay in MW
| AUH2659 | AUH | 24.4077 | 54.531 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2666 | AUH | 24.5841 | 54.7118 | Existing | OD | Possible | #N/A | 0 | 397905.98 |  |  | stay in MW
| AUH2662 | AUH | 24.5932 | 54.7543 | Existing | OD | Possible | #N/A | 0 | 570142.055 |  |  | stay in MW
| AUH2689 | AUH | 24.4193 | 54.5295 | Existing | OD | Possible | #N/A | 0 | 240319.755 | Depend to Connect AUH2110 |  | stay in MW
| AUH2681 | AUH | 24.3892 | 54.2207 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2691 | AUH | 24.2425 | 54.932 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2768 | AUH | 24.0695 | 53.9119 | Existing | OD | Possible | #N/A | 0 | 597413.4051 |  |  | stay in MW
| AUH2709 | AUH | 24.9015 | 54.8865 | Existing | OD | Possible | #N/A | 0 | 911211.3485 |  |  | stay in MW
| AUH2772 | AUH | 24.2542 | 54.3862 | Existing | OD | Possible | #N/A | 0 | 827625.33 |  |  | stay in MW
| AUH2719 | AUH | 24.4408 | 54.6267 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2722 | AUH | 24.3281 | 54.6607 | Existing | OD | Possible | #N/A | 0 | 369055.815 |  |  | stay in MW
| AUH2780 | AUH | 23.6249 | 53.3678 | Existing | OD | Possible | #N/A | 0 | 655834.1033 | Depend to Connect AUH2989 |  | stay in MW
| AUH2730 | AUH | 24.1157 | 51.7771 | Existing | OD | Possible | #N/A | 0 | 1288372.6 | depend on AUH6479 |  | stay in MW
| AUH2736 | AUH | 23.8158 | 52.7462 | Existing | OD | Possible | #N/A | 0 | 1477145.6796 |  |  | stay in MW
| AUH2754 | AUH | 24.5228 | 54.3629 | Existing | OD | Possible | #N/A | 0 | 446484.74 | Depend to Connect AUH2300 |  | stay in MW
| AUH2785 | AUH | 23.9607 | 52.1218 | Existing | OD | Possible | #N/A | 0 | 658396.0404 |  |  | stay in MW
| AUH2770 | AUH | 24.3127 | 54.5364 | Existing | OD | Possible | #N/A | 0 | 192038.73 |  |  | stay in MW
| AUH2788 | AUH | 23.1463 | 53.9628 | Existing | OD | Possible | #N/A | 0 | 912782.9721 |  |  | stay in MW
| AUH2765 | AUH | 24.3254 | 54.4573 | Existing | OD | Site survey required | #N/A | 0 | 690000 | tentative cost- depend to connect AUH3182 |  | stay in MW
| AUH2769 | AUH | 24.3171 | 54.4584 | Existing | OD | Site survey required | #N/A | 0 | 287500 | tentative cost-depend to connect AUH3180 |  | stay in MW
| AUH2771 | AUH | 24.1844 | 52.626 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2774 | AUH | 24.6116 | 55.1303 | Existing | OD | Possible | #N/A | 0 | 1405342.435 | Depend to Connect AUH2615 |  | stay in MW
| AUH2789 | AUH | 23.5287 | 53.265 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH2790 | AUH | 24.1712 | 51.9938 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3187 | AUH | 24.4523 | 54.4692 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3189 | AUH | 24.5837 | 54.6756 | Existing | OD | Possible | #N/A | 0 | 389711.77 |  |  | stay in MW
| AUH2794 | AUH | 24.5256 | 54.6656 | Existing | OD | Possible | #N/A | 0 | 345870.435 | Depend to Connect AUH3519 |  | stay in MW
| AUH2791 | AUH | 23.1401 | 53.6434 | Existing | OD | Possible | #N/A | 0 | 1030445.08 |  |  | stay in MW
| AUH2803 | AUH | 24.4833 | 54.6012 | Existing | OD | Possible | #N/A | 0 | 195500 |  |  | stay in MW
| AUH2810 | AUH | 24.5036 | 54.3923 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2819 | AUH | 24.8233 | 54.8008 | Existing | OD | Possible | #N/A | 0 | 1705722.4557 |  |  | stay in MW
| AUH3214 | AUH | 24.3311 | 54.6001 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH2825 | AUH | 24.4561 | 54.6731 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2828 | AUH | 24.364 | 54.8219 | Existing | OD | Possible | #N/A | 0 | 740832.53 |  |  | stay in MW
| AUH2841 | AUH | 24.4485 | 54.5085 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2824 | AUH | 24.4577 | 54.6754 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH2843 | AUH | 24.5392 | 54.4246 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2842 | AUH | 24.4599 | 54.5039 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2852 | AUH | 24.4431 | 54.526 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2854 | AUH | 24.1273 | 52.7296 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2869 | AUH | 24.2479 | 51.6288 | Existing | OD | Possible | #N/A | 0 | 2015484.2218 |  |  | stay in MW
| AUH2873 | AUH | 24.4557 | 54.6661 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2880 | AUH | 24.1335 | 52.8134 | Existing | OD | Site survey required | #N/A | 0 | 590593.31 |  |  | stay in MW
| AUH2939 | AUH | 23.7565 | 53.6474 | Existing | OD | Possible | #N/A | 0 | 1454351.7099 |  |  | stay in MW
| AUH2942 | AUH | 23.8986 | 53.8613 | Existing | OD | Possible | #N/A | 0 | 619649.4773 |  |  | stay in MW
| AUH2943 | AUH | 23.7269 | 53.8558 | Existing | OD | Possible | #N/A | 0 | 1004384.9055 | Depend to Connect AUH2983 |  | stay in MW
| AUH2944 | AUH | 23.7809 | 54.0624 | Existing | OD | Possible | #N/A | 0 | 2359673.155 | Depend to Connect AUH3296 |  | stay in MW
| AUH2945 | AUH | 23.9278 | 54.1924 | Existing | OD | Possible | #N/A | 0 | 1669588.63 | Depend to Connect AUH2946 |  | stay in MW
| AUH2946 | AUH | 23.76 | 54.2746 | Existing | OD | Possible | #N/A | 0 | 3356562.73 | Depend to Connect AUH2944 |  | stay in MW
| AUH2955 | AUH | 23.5487 | 53.2968 | Existing | OD | Site survey required | #N/A | 0 | 0 | CICPA / LONG ROUTE |  | stay in MW
| AUH2958 | AUH | 23.79 | 52.6829 | Existing | OD | Possible | #N/A | 0 | 67886.4241 | Proposed route is dependent on AUH2959 proposal |  | stay in MW
| AUH2959 | AUH | 23.8484 | 52.4785 | Existing | OD | Possible | #N/A | 0 | 2756457.655 | Depend to Connect AUH2968 |  | stay in MW
| AUH2961 | AUH | 23.524 | 52.9965 | Existing | OD | Possible | #N/A | 0 | 2195809.08 |  |  | stay in MW
| AUH2968 | AUH | 23.7865 | 52.5683 | Existing | OD | Possible | #N/A | 0 | 1801797.805 | Depend to Connect AUH2958 |  | stay in MW
| AUH2969 | AUH | 24.1793 | 52.572 | Existing | OD | Possible | #N/A | 0 | 1199368.005 |  |  | stay in MW
| AUH2971 | AUH | 24.1136 | 53.435 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2964 | AUH | 23.347 | 53.1158 | Existing | OD | Possible | #N/A | 0 | 2899354.93 | Depend to Connect AUH2961 |  | stay in MW
| AUH2965 | AUH | 23.209 | 53.1895 | Existing | OD | Possible | #N/A | 0 | 2416204.28 | Depend to Connect AUH2966 |  | stay in MW
| AUH2966 | AUH | 23.0965 | 53.3392 | Existing | OD | Possible | #N/A | 0 | 1760747.98 |  |  | stay in MW
| AUH2977 | AUH | 24.3188 | 54.1453 | Existing | OD | Possible | #N/A | 0 | 669712.505 | Depend to Connect AUH3679,AUH6348,AUH6425,AUH6382 |  | stay in MW
| AUH2982 | AUH | 24.1427 | 53.1558 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2987 | AUH | 23.9166 | 53.6577 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2983 | AUH | 23.6681 | 53.7548 | Existing | OD | Possible | #N/A | 0 | 505620.385 |  |  | stay in MW
| AUH2995 | AUH | 24.8825 | 53.069 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2989 | AUH | 23.6023 | 53.3934 | Existing | OD | Possible | #N/A | 0 | 1400746.2307 |  |  | stay in MW
| AUH2035 | AUH | 24.5268 | 54.375 | Existing | OD | Possible | #N/A | 0 | 368760.38 |  |  | stay in MW
| AUH2038 | AUH | 24.6104 | 54.5225 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3111 | AUH | 24.3119 | 54.5489 | Existing | OD | Possible | #N/A | 0 | 271499.245 |  |  | stay in MW
| AUH3105 | AUH | 24.615 | 54.4782 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3118 | AUH | 24.2685 | 54.5623 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3122 | AUH | 24.4518 | 54.3093 | Existing | OD | internal connection -ste survey required | #N/A | 0 |  |  |  | stay in MW
| AUH3116 | AUH | 23.6508 | 53.8022 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3117 | AUH | 24.2772 | 54.5541 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3129 | AUH | 24.5277 | 54.3914 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3136 | AUH | 24.3605 | 54.5547 | Existing | OD | Possible | #N/A | 0 | 259327.53 |  |  | stay in MW
| AUH3143 | AUH | 24.8423 | 55.028 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3132 | AUH | 24.4069 | 54.575 | Existing | OD | Possible | #N/A | 0 | 239317.645 |  |  | stay in MW
| AUH3154 | AUH | 24.4594 | 54.3007 | Existing | OD | Possible | #N/A | 0 |  |  |  | stay in MW
| AUH3157 | AUH | 24.5451 | 54.4357 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3147 | AUH | 24.1062 | 52.6705 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3168 | AUH | 24.6754 | 54.6023 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3169 | AUH | 24.4215 | 54.3933 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3170 | AUH | 24.4245 | 54.3946 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3171 | AUH | 24.4255 | 54.3937 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3159 | AUH | 24.1351 | 53.2749 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3162 | AUH | 24.3006 | 54.6147 | Existing | OD | Possible | #N/A | 0 | 341335.755 | Depend to Connect AUH3163 |  | stay in MW
| AUH3180 | AUH | 24.3182 | 54.467 | Existing | OD | Site survey required | #N/A | 0 | 149500 |  |  | stay in MW
| AUH3163 | AUH | 24.2972 | 54.62 | Existing | OD | Possible | #N/A | 0 | 352507.89 | Depend to Connect AUH3163 |  | stay in MW
| AUH3181 | AUH | 24.4871 | 54.4134 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3193 | AUH | 24.412 | 54.5354 | Existing | OD | internal connection | #N/A | 0 | 0 | Depend to Connect AUH2658 |  | stay in MW
| AUH3182 | AUH | 24.3255 | 54.4665 | Existing | OD | Site survey required | #N/A | 0 | 224250 |  |  | stay in MW
| AUH3222 | AUH | 23.9152 | 53.6994 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3393 | AUH | 24.5431 | 54.4421 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3240 | AUH | 24.1208 | 52.6855 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3242 | AUH | 24.4732 | 54.3484 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3249 | AUH | 24.0657 | 52.8215 | Existing | OD | Possible | #N/A | 0 | 1183124.83 |  |  | stay in MW
| AUH3275 | AUH | 24.4301 | 54.4364 | Existing | OD | Possible | #N/A | 0 | 127799.96 |  |  | stay in MW
| AUH2287 | AUH | 24.4888 | 52.32 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2288 | AUH | 24.5171 | 52.3104 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3281 | AUH | 24.3407 | 54.5484 | Existing | OD | Possible | #N/A | 0 | 232393.725 | Depend to Connect AUH2380 |  | stay in MW
| AUH3283 | AUH | 24.6584 | 54.5773 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3296 | AUH | 23.7981 | 53.9107 | Existing | OD | Possible | #N/A | 0 | 1610284.28 | Depend to Connect AUH2943 |  | stay in MW
| AUH2300 | AUH | 24.5165 | 54.3644 | Existing | OD | Possible | #N/A | 0 | 547310.3 | Depend to Connect AUG6056 |  | stay in MW
| AUH2289 | AUH | 24.4577 | 52.3123 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH2291 | AUH | 24.4406 | 54.8292 | Existing | OD | Possible | #N/A | 0 | 214303.765 |  |  | stay in MW
| AUH3469 | AUH | 23.085 | 53.5566 | Existing | OD | Possible | #N/A | 0 | 822885.95 |  |  | stay in MW
| AUH3312 | AUH | 23.66 | 53.8409 | Existing | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3544 | AUH | 24.3021 | 52.6388 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3558 | AUH | 24.3443 | 52.6408 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3367 | AUH | 24.2768 | 54.9562 | Existing | OD | Possible | #N/A | 0 | 1969160.41 | Depend to Connect AUH2477 |  | stay in MW
| AUH3369 | AUH | 24.4631 | 54.3719 | Existing | OD | Possible | #N/A | 0 | 297658.985 |  |  | stay in MW
| AUH3381 | AUH | 24.6317 | 54.535 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3391 | AUH | 24.5457 | 54.4475 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2394 | AUH | 24.4466 | 54.2828 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3638 | AUH | 24.4382 | 54.487 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3442 | AUH | 24.4512 | 54.3333 | Existing | OD | Possible | #N/A | 0 | 494444.57 |  |  | stay in MW
| AUH2465 | AUH | 24.3956 | 54.2969 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3466 | AUH | 22.9476 | 53.3438 | Existing | OD | Possible | #N/A | 0 | 1155910.655 |  |  | stay in MW
| AUH2474 | AUH | 24.4922 | 54.3932 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3486 | AUH | 24.1204 | 52.7246 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3496 | AUH | 24.3659 | 54.1927 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3488 | AUH | 24.476 | 54.508 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2500 | AUH | 24.4348 | 54.6356 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3489 | AUH | 24.448 | 54.5653 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2504 | AUH | 24.5779 | 51.7209 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2505 | AUH | 25.2418 | 54.2299 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2506 | AUH | 25.1478 | 52.8781 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH2507 | AUH | 25.1449 | 52.8719 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH3497 | AUH | 23.8896 | 53.937 | Existing | OD | Possible | #N/A | 0 | 1743612.405 | Depend to Connect AUH3296 |  | stay in MW
| AUH3502 | AUH | 24.8896 | 54.8441 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2503 | AUH | 24.5892 | 51.7303 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2509 | AUH | 24.3298 | 54.9156 | Existing | OD | Not possible | 7-8 month | AUH5002 | 177939.47 |  | 177939.47 | Y2024 fiber scope |  | 177939.47 | 7-8 month
| AUH3523 | AUH | 24.4029 | 54.5564 | Existing | OD | Possible | #N/A | 0 | 392235.1 |  |  | stay in MW
| AUH3536 | AUH | 24.3369 | 54.4631 | Existing | OD | Site survey required | #N/A | 0 | 224250 |  |  | stay in MW
| AUH2537 | AUH | 24.6171 | 54.4741 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3555 | AUH | 24.1783 | 54.7025 | Existing | OD | Site survey required | #N/A | 0 | 195500 |  |  | stay in MW
| AUH3540 | AUH | 24.3217 | 54.5675 | Existing | OD | Possible | #N/A | 0 | 132834.338 |  |  | stay in MW
| AUH3547 | AUH | 24.2547 | 54.6314 | Existing | OD | Possible | #N/A | 0 | 263947.54 |  |  | stay in MW
| AUH3571 | AUH | 24.4897 | 54.4438 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3606 | AUH | 24.4573 | 54.3153 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3615 | AUH | 24.2524 | 54.6268 | Existing | OD | Possible | #N/A | 0 | 116192.55 |  |  | stay in MW
| AUH3781 | AUH | 24.5376 | 54.4186 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3603 | AUH | 24.0009 | 53.7296 | Existing | OD | Possible | #N/A | 0 | 549810.2556 |  |  | stay in MW
| AUH3628 | AUH | 23.6989 | 52.3428 | Existing | OD | Possible | #N/A | 0 | 2149639.455 | AUH3621,AUH2959,AUH3808,AUH2968,AUH2958 |  | stay in MW
| AUH3629 | AUH | 23.8633 | 52.6455 | Existing | OD | Possible | #N/A | 0 | 1212746.53 | Depend to Connect AUH2958 |  | stay in MW
| AUH3630 | AUH | 24.002 | 52.6794 | Existing | OD | Possible | #N/A | 0 | 1229203.03 |  |  | stay in MW
| AUH3631 | AUH | 24.0138 | 52.849 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3621 | AUH | 23.6778 | 52.4927 | Existing | OD | Possible | #N/A | 0 | 1102853.68 | Depend to Connect AUH2959 |  | stay in MW
| AUH3635 | AUH | 24.5083 | 54.6015 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3626 | AUH | 24.8817 | 53.084 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH3641 | AUH | 23.6724 | 52.7193 | Existing | OD | Site survey required | #N/A | 0 | 1679101.6643 |  |  | stay in MW
| AUH3633 | AUH | 24.4919 | 54.4112 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3646 | AUH | 23.968 | 52.9216 | Existing | OD | Possible | #N/A | 0 | 664180.5438 |  |  | stay in MW
| AUH3647 | AUH | 23.8484 | 53.6387 | Existing | OD | Site survey required | #N/A | 0 | 1814475.1227 |  |  | stay in MW
| AUH3648 | AUH | 23.8871 | 52.965 | Existing | OD | Possible | #N/A | 0 | 1434008.4154 |  |  | stay in MW
| AUH3649 | AUH | 23.818 | 52.3769 | Existing | OD | Possible | #N/A | 0 | 1640889.805 | AUH3628,AUH3621,AUH2959,AUH3808,AUH2968,AUH2958 |  | stay in MW
| AUH3651 | AUH | 24.0532 | 52.9823 | Existing | OD | Possible | #N/A | 0 | 1098489.9273 |  |  | stay in MW
| AUH3653 | AUH | 23.6892 | 52.5855 | Existing | OD | Site survey required | #N/A | 0 | 2794527.9841 |  |  | stay in MW
| AUH3657 | AUH | 23.6508 | 53.7297 | Existing | OD | Possible | #N/A | 0 | 237691.0723 |  |  | stay in MW
| AUH3667 | AUH | 23.9721 | 53.4312 | Existing | OD | Possible | #N/A | 0 | 2509678.5947 | AUH3289 |  | stay in MW
| AUH3663 | AUH | 24.4995 | 54.4128 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3664 | AUH | 24.5063 | 54.4114 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3674 | AUH | 23.16 | 53.7318 | Existing | OD | Possible | #N/A | 0 | 594164.98 | Depend to Connect AUH6395 |  | stay in MW
| AUH3684 | AUH | 24.4697 | 52.3121 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3675 | AUH | 24.1183 | 52.7753 | Existing | OD | Site survey required | #N/A | 0 | 412061.4127 |  |  | stay in MW
| AUH3784 | AUH | 24.4599 | 54.6344 | Existing | OD | Site survey required | #N/A | 0 | 271820.4216 |  |  | stay in MW
| AUH3679 | AUH | 24.2495 | 54.1735 | Existing | OD | Possible | #N/A | 0 | 1662923.4852 |  |  | stay in MW
| AUH3685 | AUH | 24.3625 | 54.5316 | Existing | OD | Possible | #N/A | 0 | 375199.575 |  |  | stay in MW
| AUH3706 | AUH | 24.1308 | 54.28 | Existing | OD | Possible | #N/A | 0 | 812078.7211 |  |  | stay in MW
| AUH3716 | AUH | 24.4805 | 54.32 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3785 | AUH | 24.4326 | 54.6697 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3744 | AUH | 24.5386 | 54.4079 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3747 | AUH | 24.566 | 54.4583 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3748 | AUH | 24.5753 | 54.4664 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3789 | AUH | 24.4512 | 54.6325 | Existing | OD | Site survey required | #N/A | 0 | 381972.1872 |  |  | stay in MW
| AUH3755 | AUH | 24.0856 | 53.5213 | Existing | OD | Possible | 7-8 month | AUH2908 | 126056.88 |  | 126056.88 | Y2024 fiber scope
| AUH3757 | AUH | 23.3016 | 54.2218 | Existing | OD | Site survey required | #N/A | 0 | 2258850.1983 |  |  | stay in MW
| AUH3762 | AUH | 24.279 | 52.6236 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3812 | AUH | 23.7977 | 52.5935 | Existing | OD | Possible | #N/A | 0 | 459346.1147 | Depend to Connect AUH2968,AUH2958 |  | stay in MW
| AUH3817 | AUH | 24.4667 | 54.3285 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3795 | AUH | 22.928 | 53.991 | Existing | OD | Site survey required | #N/A | 0 | 1297039.8912 |  |  | stay in MW
| AUH3798 | AUH | 24.5386 | 54.4129 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3808 | AUH | 23.7779 | 52.5694 | Existing | OD | Possible | #N/A | 0 | 263950.07 | Depend to Connect AUH2968,AUH2958 |  | stay in MW
| AUH3860 | AUH | 24.7733 | 54.7872 | Existing | OD | Site survey required | #N/A | 0 | 799322.68 | Depend to Connect AUH2819 |  | stay in MW
| AUH3818 | AUH | 24.4687 | 54.3321 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3819 | AUH | 24.1394 | 52.6914 | Existing | OD | Site survey required | #N/A | 0 | 3714292.427 |  |  | stay in MW
| AUH3833 | AUH | 24.5421 | 54.4303 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2847 | AUH | 24.1483 | 54.7932 | Existing | OD | Possible | #N/A | 0 | 466657.58 |  |  | stay in MW
| AUH2849 | AUH | 24.0831 | 54.7189 | Existing | OD | Possible | #N/A | 0 | 1055239.54 | Depend to Connect AUH2623 |  | stay in MW
| AUH3796 | AUH | 22.9803 | 53.9755 | Existing | OD | Site survey required | #N/A | 0 | 993514.3142 |  |  | stay in MW
| AUH3834 | AUH | 24.608 | 54.697 | Existing | OD | Possible | #N/A | 0 | 649468.48 |  |  | stay in MW
| AUH3954 | AUH | 24.0697 | 53.5023 | Existing | OD | Possible | #N/A | 0 | 309595.471 |  |  | stay in MW
| AUH2893 | AUH | 24.3334 | 54.8067 | Existing | OD | Possible | #N/A | 0 | 570477.28 |  |  | stay in MW
| AUH2016 | AUH | 24.4328 | 54.5028 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3928 | AUH | 24.2295 | 54.6806 | Existing | OD | Possible | #N/A | 0 | 214578.04 |  |  | stay in MW
| AUH3930 | AUH | 24.3224 | 54.7558 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3946 | AUH | 24.4731 | 54.34 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3947 | AUH | 24.4739 | 54.3411 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3966 | AUH | 24.4778 | 54.3445 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3967 | AUH | 24.4765 | 54.3436 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3968 | AUH | 24.4719 | 54.3376 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3969 | AUH | 24.4704 | 54.3351 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3973 | AUH | 22.8657 | 54.0955 | Existing | OD | Possible | #N/A | 0 | 1890527.6989 |  |  | stay in MW
| AUH3387 | AUH | 24.4187 | 54.4283 | Existing | OD | Possible | #N/A | 0 | 285844.46 |  |  | stay in MW
| AUH3388 | AUH | 24.5318 | 54.4261 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3546 | AUH | 24.2701 | 52.6033 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3985 | AUH | 23.9464 | 53.7912 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3031 | AUH | 24.834 | 54.7586 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3559 | AUH | 24.3272 | 52.5652 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3043 | AUH | 24.2951 | 54.9129 | Existing | OD | Possible | #N/A | 0 | 878399.21 | Depend to Connect AUH3367 |  | stay in MW
| AUH3044 | AUH | 24.5673 | 54.999 | Existing | OD | Possible | #N/A | 0 | 222552.83 | Depend to Connect AUH2169 |  | stay in MW
| AUH3045 | AUH | 24.5189 | 55.0193 | Existing | OD | Possible | #N/A | 0 | 792249.95 |  |  | stay in MW
| AUH3560 | AUH | 23.9775 | 52.2706 | Existing | OD | Site survey required | #N/A | 0 | 203070.7167 |  |  | stay in MW
| AUH3039 | AUH | 24.5155 | 54.7499 | Existing | OD | Possible | #N/A | 0 | 616457.96 |  |  | stay in MW
| AUH3115 | AUH | 23.6457 | 53.8188 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3644 | AUH | 24.474 | 54.417 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3257 | AUH | 24.2147 | 54.7561 | Existing | OD | Possible | #N/A | 0 | 367513.78 |  |  | stay in MW
| AUH3287 | AUH | 23.7831 | 53.029 | Existing | OD | Possible | #N/A | 0 | 1549598.3948 |  |  | stay in MW
| AUH3288 | AUH | 23.8548 | 53.2884 | Existing | OD | Site survey required | #N/A | 0 | 857416.5092 |  |  | stay in MW
| AUH3291 | AUH | 23.5947 | 53.9293 | Existing | OD | Possible | #N/A | 0 | 2006362.9065 | AUH2983,AUH2943,AUH3296 |  | stay in MW
| AUH3292 | AUH | 23.684 | 53.9665 | Existing | OD | Possible | #N/A | 0 | 799475.055 | Depend to Connect AUH2983,AUH2943,AUH3296,AUH3944 |  | stay in MW
| AUH3298 | AUH | 23.5052 | 53.4082 | Existing | OD | Possible | #N/A | 0 | 3048946.7694 |  |  | stay in MW
| AUH3299 | AUH | 23.3923 | 53.3558 | Existing | OD | Possible | #N/A | 0 | 2697833.4393 |  |  | stay in MW
| AUH3300 | AUH | 23.2793 | 53.3447 | Existing | OD | Possible | #N/A | 0 | 2509215.4067 |  |  | stay in MW
| AUH2286 | AUH | 24.4731 | 52.3152 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH2290 | AUH | 24.5007 | 52.3298 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3307 | AUH | 23.3796 | 54.0066 | Existing | OD | Possible | #N/A | 0 | 4394610.7221 | AUH3294,AUH3291,AUH3296,AUH2943,AUH2983 |  | stay in MW
| AUH3308 | AUH | 23.3043 | 54.1702 | Existing | OD | Site survey required | #N/A | 0 | 1388040.5568 |  |  | stay in MW
| AUH3310 | AUH | 23.2944 | 54.2199 | Existing | OD | Site survey required | #N/A | 0 | 242581.1128 |  |  | stay in MW
| AUH3377 | AUH | 24.6088 | 54.5539 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3394 | AUH | 24.6999 | 54.6583 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3396 | AUH | 24.6689 | 54.8112 | Existing | OD | Possible | #N/A | 0 | 277978.23 |  |  | stay in MW
| AUH2393 | AUH | 23.1479 | 53.7129 | Existing | OD | Possible | #N/A | 0 | 0 | Depend to Connect AUH6352 |  | stay in MW
| AUH3402 | AUH | 24.2246 | 54.6366 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3403 | AUH | 24.222 | 54.6396 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2489 | AUH | 24.193 | 53.7773 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2490 | AUH | 24.2292 | 53.8062 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3492 | AUH | 24.3341 | 54.5436 | Existing | OD | Possible | #N/A | 0 | 306301.695 |  |  | stay in MW
| AUH3495 | AUH | 24.4074 | 54.2535 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2497 | AUH | 24.5674 | 54.548 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2499 | AUH | 24.2714 | 53.8603 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2502 | AUH | 24.1733 | 51.9889 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH3503 | AUH | 24.8846 | 54.8482 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2508 | AUH | 24.2043 | 54.9921 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3507 | AUH | 23.6666 | 54.3461 | Existing | OD | Site survey required | #N/A | 0 | 1322363.7431 |  |  | stay in MW
| AUH2517 | AUH | 24.5383 | 54.3831 | Existing | OD | Site survey required | #N/A | 0 | 0 | Depend to Connect AUH2035,AUG6056,AUH2555 |  | stay in MW
| AUH3534 | AUH | 24.6468 | 54.6505 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3898 | AUH | 24.3253 | 54.789 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3535 | AUH | 24.489 | 54.4068 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3557 | AUH | 24.1021 | 52.6494 | Existing | OD | Not possible | 7-8 month | AUH2911 | 116803.74 |  | 116803.74 | Y2024 fiber scope |  | 116803.74 | 7-8 month
| AUH3562 | AUH | 23.0638 | 53.9636 | Existing | OD | Possible | #N/A | 0 | 964222.905 |  |  | stay in MW
| AUH3564 | AUH | 24.0736 | 52.4592 | Existing | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3570 | AUH | 24.4878 | 54.4298 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3573 | AUH | 24.4681 | 54.4568 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3572 | AUH | 24.4832 | 54.4587 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3608 | AUH | 24.6794 | 55.1886 | Existing | OD | Possible | #N/A | 0 | 403443.805 |  |  | stay in MW
| AUH3611 | AUH | 24.2379 | 54.2605 | Existing | OD | Possible | #N/A | 0 | 2236299.1445 |  |  | stay in MW
| AUH2614 | AUH | 24.1722 | 54.5549 | Existing | OD | Possible | #N/A | 0 | 632500 |  |  | stay in MW
| AUH2615 | AUH | 24.6203 | 55.0384 | Existing | OD | Possible | #N/A | 0 | 839500 | Depend to Connect AUH2169 |  | stay in MW
| AUH3255 | AUH | 24.4227 | 54.5705 | Existing | OD | Possible | #N/A | 0 | 296695.975 |  |  | stay in MW
| AUH3401 | AUH | 24.5841 | 54.474 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6021 | AUH | 24.1155 | 52.8765 | Existing | OD | Possible | #N/A | 0 | 159896.23 |  |  | stay in MW
| AUH6022 | AUH | 24.1957 | 51.7755 | Existing | OD | Possible | #N/A | 0 | 649924.826 | Depend to Connect AUH6479 |  | stay in MW
| AUH6073 | AUH | 23.9804 | 53.5408 | Existing | OD | Possible | #N/A | 0 | 1545434.223 |  |  | stay in MW
| AUH6095 | AUH | 23.9062 | 53.2745 | Existing | OD | Possible | #N/A | 0 | 553175.3756 |  |  | stay in MW
| AUH2877 | AUH | 24.113 | 52.4397 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3889 | AUH | 24.4441 | 54.6757 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6096 | AUH | 23.8846 | 53.2808 | Existing | OD | Possible | #N/A | 0 | 674454.0112 |  |  | stay in MW
| AUH3915 | AUH | 24.3292 | 54.7779 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH3018 | AUH | 24.6778 | 54.965 | Existing | OD | Possible | #N/A | 0 | 1985589.6895 |  |  | stay in MW
| AUH6119 | AUH | 24.1325 | 54.5271 | Existing | OD | Possible | #N/A | 0 | 547922.215 | Depend to Connect AUH2614,AUH6349 |  | stay in MW
| AUH3246 | AUH | 24.483 | 52.3059 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3273 | AUH | 24.8663 | 54.886 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3289 | AUH | 23.8352 | 53.4419 | Existing | OD | Possible | #N/A | 0 | 2262264.2838 | Depend to Connect AUH3494 |  | stay in MW
| AUH3304 | AUH | 23.1982 | 54.1485 | Existing | OD | Possible | #N/A | 0 | 3046885.1458 |  |  | stay in MW
| AUH3337 | AUH | 24.2533 | 54.5543 | Existing | OD | Not possible | 7-8 month | AUH3119 | 222954.68 |  | 222954.68 | Y2024 fiber scope |  | 222954.68 | 7-8 month
| AUH3370 | AUH | 24.2091 | 53.913 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3438 | AUH | 24.1708 | 54.7691 | Existing | OD | Possible | #N/A | 0 | 558969 |  |  | stay in MW
| AUH2488 | AUH | 24.5727 | 54.5268 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3880 | AUH | 24.556 | 54.4566 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6424 | AUH | 24.195 | 53.4275 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6425 | AUH | 24.3049 | 54.1136 | Existing | OD | Possible | #N/A | 0 | 478726.9099 | Depend to Connect AUH3679,AUH6348 |  | stay in MW
| AUH6044 | AUH | 24.4914 | 54.4025 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6046 | AUH | 24.1376 | 52.7436 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH6433 | AUH | 24.2874 | 53.9937 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6448 | AUH | 24.0581 | 52.7107 | Existing | OD | Possible | #N/A | 0 | 476012.8393 |  |  | stay in MW
| AUH6449 | AUH | 24.5062 | 52.2812 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6454 | AUH | 23.9018 | 53.052 | Existing | OD | Possible | #N/A | 0 | 2016217.0018 |  |  | stay in MW
| AUH6117 | AUH | 24.5383 | 54.4024 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6458 | AUH | 24.0932 | 52.9559 | Existing | OD | Site survey required | #N/A | 0 | 333972.69 |  |  | stay in MW
| AUH6120 | AUH | 24.3199 | 54.546 | Existing | OD | Possible | #N/A | 0 | 281750 |  |  | stay in MW
| AUH6121 | AUH | 23.0344 | 54.0156 | Existing | OD | Possible | #N/A | 0 | 1063126.47 |  |  | stay in MW
| AUH6129 | AUH | 24.5229 | 54.653 | Existing | OD | Possible | #N/A | 0 | 539209.93 |  |  | stay in MW
| AUH6494 | AUH | 23.5641 | 53.6274 | Existing | OD | Possible | #N/A | 0 | 1934873.6376 |  |  | stay in MW
| AUH6495 | AUH | 23.9106 | 53.3255 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH6144 | AUH | 23.9884 | 51.957 | Existing | OD | Possible | #N/A | 0 | 1409432.18 |  |  | stay in MW
| AUH6150 | AUH | 24.5263 | 54.407 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6152 | AUH | 24.563 | 54.4606 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6167 | AUH | 24.2276 | 51.7223 | Existing | OD | Possible | #N/A | 0 | 2549755.482 | The route of this site passing at AUH6380 |  | stay in MW
| AUH6213 | AUH | 24.6221 | 54.8739 | Existing | OD | Possible | #N/A | 0 | 489874.6926 |  |  | stay in MW
| AUH6217 | AUH | 24.4442 | 54.3662 | Existing | OD | Possible | #N/A | 0 | 190123.52 |  |  | stay in MW
| AUH6304 | AUH | 23.1433 | 53.7744 | Existing | OD | Possible | #N/A | 0 | 548391.53 |  |  | stay in MW
| AUH6328 | AUH | 24.1736 | 52.6071 | Existing | OD | Possible | #N/A | 0 | 691098.9519 |  |  | stay in MW
| AUH6330 | AUH | 23.2227 | 53.7839 | Existing | OD | Possible | #N/A | 0 | 277568.8008 |  |  | stay in MW
| AUH6331 | AUH | 23.9349 | 53.9122 | Existing | OD | Possible | #N/A | 0 | 2534249.802 | Depend to Connect AUH3497,AUH3296,AUH2943,AUH2983 |  | stay in MW
| AUH6332 | AUH | 23.8404 | 51.9378 | Existing | OD | Possible | #N/A | 0 | 1700888.7462 |  |  | stay in MW
| AUH6335 | AUH | 23.6429 | 54.308 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6336 | AUH | 23.4229 | 54.2967 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6337 | AUH | 23.356 | 53.8922 | Existing | OD | Possible | #N/A | 0 | 3071861.9202 |  |  | stay in MW
| AUH6339 | AUH | 25.4953 | 53.1466 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6344 | AUH | 24.1672 | 54.0648 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6348 | AUH | 24.2716 | 54.115 | Existing | OD | Possible | #N/A | 0 | 1016046.6416 | Depend to Connect AUH3679 |  | stay in MW
| AUH6349 | AUH | 24.0999 | 54.5437 | Existing | OD | Possible | #N/A | 0 | 1418087.08 | Depend to Connect AUH2614 |  | stay in MW
| AUH6534 | AUH | 24.3309 | 54.5782 | Existing | OD | Possible | #N/A | 0 | 179141.71 |  |  | stay in MW
| AUH6352 | AUH | 23.1259 | 53.7138 | Existing | OD | Possible | #N/A | 0 | 801974.005 | Depend to Connect AUH6480 |  | stay in MW
| AUH6358 | AUH | 23.263 | 53.1475 | Existing | OD | Possible | #N/A | 0 | 2062810.9885 | Depend to Connect AUH2964 |  | stay in MW
| AUH6361 | AUH | 23.879 | 53.5282 | Existing | OD | Possible | #N/A | 0 | 1651676.685 |  |  | stay in MW
| AUH6362 | AUH | 24.1735 | 53.6576 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6364 | AUH | 24.2807 | 51.7506 | Existing | OD | Possible | #N/A | 0 | 1212746.53 | Depend to Connect AUH6022 |  | stay in MW
| AUH6366 | AUH | 23.031 | 53.9417 | Existing | OD | Possible | #N/A | 0 | 2863104.2354 |  |  | stay in MW
| AUH6372 | AUH | 24.2361 | 54.1072 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6373 | AUH | 24.1573 | 53.0393 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6378 | AUH | 23.1148 | 53.6038 | Existing | OD | Possible | #N/A | 0 | 221480.0262 |  |  | stay in MW
| AUH6379 | AUH | 23.8076 | 52.1716 | Existing | OD | Possible | #N/A | 0 | 4561737.7616 |  |  | stay in MW
| AUH6380 | AUH | 24.1721 | 51.7503 | Existing | OD | Possible | #N/A | 0 | 1258682.107 |  |  | stay in MW
| AUH6382 | AUH | 24.3154 | 54.1262 | Existing | OD | Possible | #N/A | 0 | 590288.56 | Depend to Connect AUH3679,AUH6348,AUH6425 |  | stay in MW
| AUH6385 | AUH | 23.154 | 53.8281 | Existing | OD | Possible | #N/A | 0 | 868135.23 |  |  | stay in MW
| AUH6390 | AUH | 23.1372 | 53.7469 | Existing | OD | Possible | #N/A | 0 | 525657.18 |  |  | stay in MW
| AUH6393 | AUH | 24.0729 | 54.3205 | Existing | OD | Site survey required | #N/A | 0 | 507823.21 |  |  | stay in MW
| AUH6395 | AUH | 23.1512 | 53.7524 | Existing | OD | Possible | #N/A | 0 | 507823.21 |  |  | stay in MW
| AUH6396 | AUH | 24.7527 | 54.6779 | Existing | OD | Possible | #N/A | 0 | 322998.43 |  |  | stay in MW
| AUH6423 | AUH | 24.2768 | 53.3264 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6581 | AUH | 24.2624 | 52.5932 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6428 | AUH | 25.2042 | 53.2408 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6440 | AUH | 23.4436 | 53.0579 | Existing | OD | Possible | #N/A | 0 | 1422292.63 | Depend to Connect AUH2961,AUH6443 |  | stay in MW
| AUH6443 | AUH | 23.6054 | 52.9525 | Existing | OD | Possible | #N/A | 0 | 27269.03 | Depend to Connect AUH2961 |  | stay in MW
| AUH6445 | AUH | 24.0294 | 53.1775 | Existing | OD | Possible | #N/A | 0 | 686998.8645 |  |  | stay in MW
| AUH6468 | AUH | 23.62 | 53.7629 | Existing | OD | Possible | #N/A | 0 | 1377716.1 |  |  | stay in MW
| AUH6469 | AUH | 23.1538 | 53.2643 | Existing | OD | Possible | #N/A | 0 | 1313222.605 | Depend to Connect AUH2966 |  | stay in MW
| AUH6470 | AUH | 23.9583 | 52.5361 | Existing | OD | Possible | #N/A | 0 | 1690055.1395 |  |  | stay in MW
| AUH6472 | AUH | 23.2796 | 54.2383 | Existing | OD | Site survey required | #N/A | 0 | 653204.5138 |  |  | stay in MW
| AUH6479 | AUH | 24.0909 | 51.7831 | Existing | OD | Possible | #N/A | 0 | 486137.2 |  |  | stay in MW
| AUH6480 | AUH | 23.143 | 53.6896 | Existing | OD | Possible | #N/A | 0 | 692556.565 |  |  | stay in MW
| AUH6497 | AUH | 24.1204 | 53.4547 | Existing | OD | Possible | #N/A | 0 | 792557.23 |  |  | stay in MW
| AUH6498 | AUH | 24.2943 | 54.1584 | Existing | OD | Possible | #N/A | 0 | 973497.9641 | Depend to Connect AUH3679 |  | stay in MW
| AUH6097 | AUH | 24.0194 | 52.0198 | Existing | OD | Not possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6518 | AUH | 24.5075 | 54.5573 | Existing | OD | Possible | #N/A | 0 | 221855.47 |  |  | stay in MW
| AUH6519 | AUH | 24.0398 | 52.4124 | Existing | OD | Site survey required | #N/A | 0 | 588292.3023 |  |  | stay in MW
| AUH6556 | AUH | 24.288 | 55.0579 | Existing | OD | Possible | #N/A | 0 | 1021113.3912 | The route of this site passing at AUH2477 |  | stay in MW
| AUH6525 | AUH | 24.5867 | 54.4758 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6527 | AUH | 24.5706 | 54.4632 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6531 | AUH | 24.5441 | 54.4324 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3923 | AUH | 24.5642 | 54.6836 | Existing | OD | Possible | #N/A | 0 | 262655.9796 |  |  | stay in MW
| AUH6535 | AUH | 24.4202 | 54.4629 | Existing | OD | Possible | #N/A | 0 | 215839.13 |  |  | stay in MW
| AUH6536 | AUH | 24.5624 | 54.4571 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH6545 | AUH | 24.425 | 54.559 | Existing | OD | Possible | #N/A | 0 | 338727.095 |  |  | stay in MW
| AUH6546 | AUH | 24.4203 | 54.56 | Existing | OD | Possible | #N/A | 0 | 140816.35 |  |  | stay in MW
| AUH6168 | AUH | 23.2129 | 53.7433 | Existing | OD | Site survey required | #N/A | 0 | 684742.775 |  |  | stay in MW
| AUH6590 | AUH | 24.4936 | 54.3893 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3971 | AUH | 24.2171 | 55.0912 | Existing | OD | Possible | 7-8 month | AUH5001 | 123725.18 |  | 123725.18 | Y2024 fiber scope
| AUH6595 | AUH | 24.2083 | 54.6197 | Existing | OD | Possible | #N/A | 0 | 257039.0151 |  |  | stay in MW
| AUH6555 | AUH | 24.2418 | 55.05 | Existing | OD | Possible | #N/A | 0 | 721868.3952 |  |  | stay in MW
| AUH6604 | AUH | 24.6932 | 54.7199 | Existing | OD | Possible | #N/A | 0 | 725358.636 |  |  | stay in MW
| AUH6605 | AUH | 24.6981 | 54.7729 | Existing | OD | Possible | #N/A | 0 | 377832.615 |  |  | stay in MW
| AUH6589 | AUH | 24.8731 | 54.8347 | Existing | OD | Site survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUV6260 | AUH | 24.4352 | 54.4683 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUV6269 | AUH | 24.4723 | 54.3223 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUV6270 | AUH | 24.4731 | 54.3416 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUV6273 | AUH | 22.9735 | 53.767 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUV6272 | AUH | 22.9837 | 53.7961 | Existing | OD |  | #N/A | 0 | 0 |  |  | stay in MW
| AUH2798 | AUH | 24.7613 | 54.6807 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2868 | AUH | 24.3758 | 51.5937 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2940 | AUH | 23.8291 | 53.6172 | Existing | OD | Site survey required | #N/A | 0 | 1231694.5496 |  |  | stay in MW
| AUH3155 | AUH | 24.4348 | 54.4682 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3290 | AUH | 23.9248 | 53.1612 | Existing | OD | Possible | #N/A | 0 | 1916257.5466 |  |  | stay in MW
| AUH3293 | AUH | 23.5817 | 53.8484 | Existing | OD | Possible | #N/A | 0 | 2802606.4366 | Depend to Connect AUH2983 |  | stay in MW
| AUH3294 | AUH | 23.4864 | 53.9508 | Existing | OD | Possible | #N/A | 0 | 542224.4415 |  |  | stay in MW
| AUH3295 | AUH | 24.002 | 53.0341 | Existing | OD | Possible | #N/A | 0 | 1876154.1442 |  |  | stay in MW
| AUH3297 | AUH | 23.6477 | 53.1901 | Existing | OD | Possible | #N/A | 0 | 1273741.3055 |  |  | stay in MW
| AUH3301 | AUH | 23.631 | 54.1348 | Existing | OD | Possible | #N/A | 0 | 2346459.0718 |  |  | stay in MW
| AUH3302 | AUH | 23.4781 | 54.1053 | Existing | OD | Possible | #N/A | 0 | 3180151.9987 | AUH3292,AUH2943,AUH3296,AUH2983 |  | stay in MW
| AUH3529 | AUH | 22.7535 | 54.3977 | Existing | OD | Possible | #N/A | 0 | 936602.2733 |  |  | stay in MW
| AUH3797 | AUH | 24.7928 | 54.7037 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH3949 | AUH | 24.5185 | 54.6728 | Existing | OD | Possible | #N/A | 0 | 235221.805 |  |  | stay in MW
| AUH3955 | AUH | 24.4657 | 54.3277 | Existing | OD | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH2254 | AUH | 24.3115 | 54.6703 | New | OD | Possible | #N/A | 0 | 115765.5769 |  |  | MW 2024
| AUH3913 | AUH | 24.2602 | 54.6219 | New | OD | Possible | #N/A | 0 | 126909.5811 |  |  | MW 2024
| AUH3405 | AUH | 24.3991 | 54.5496 | New | OD | Possible | #N/A | 0 | 156162.9629 |  |  | MW 2024
| AAN3509 | AUH | 24.2069 | 55.6112 | New | OD | Possible | #N/A | 0 | 149083.3299 |  |  | MW 2024
| AAN3663 | AUH | 24.1005 | 55.9235 | New | OD | Possible | #N/A | 0 | 133505.4663 |  |  | MW 2024
| AUH1071 | AUH | 24.5471 | 54.4658 | New | OD | Possible | #N/A | 0 | 35000 |  |  | Y2024 fiber scope
| AUH6122 | AUH | 24.5594 | 54.8898 | New | OD | Possible | #N/A | 0 | 217923.8945 |  |  | MW 2024
| AUH6585 | AUH | 24.6934 | 54.6712 | New | OD | Possible | #N/A | 0 | 119724.592 |  |  | MW 2024
| AAN3407 | AUH | 24.219 | 55.7713 | New | OD | Possible | #N/A | 0 | 170715.4594 |  |  | MW 2024
| AAN3752 | AUH | 24.5485 | 55.6042 | New | OD | Possible | #N/A | 0 | 224617.7164 |  |  | MW 2024
| AUH1066 | AUH | 23.6475 | 53.6985 | New | OD | Possible | #N/A | 0 | 227486.0733 |  |  | MW 2024
| AUH1331 | AUH | 22.9738 | 53.7639 | New | OD | Possible | #N/A | 0 | 237155.092 |  |  | MW 2024
| AUH1010 | AUH | 24.3668 | 54.6438 | New | OD | Possible | #N/A | 0 | 128567.0847 |  |  | MW 2024
| AUH1276 | AUH | 23.6226 | 53.7161 | New | OD | Possible | #N/A | 0 | 222675.3061 |  |  | MW 2024
| AAN3426 | AUH | 24.2325 | 55.5633 | New | OD | Possible | #N/A | 0 | 313337.9379 |  |  | MW 2024
| AUH3917 | AUH | 24.3717 | 54.7164 | New | OD | Possible | #N/A | 0 | 222197.4939 |  |  | MW 2024
| AUH2011 | AUH | 24.6233 | 54.8143 | New | OD | Possible | #N/A | 0 | 261514.6089 |  |  | MW 2024
| AAN3750 | AUH | 24.6333 | 55.691 | New | OD | Possible | #N/A | 0 | 350261.5404 |  |  | MW 2024
| AAN3229 | AUH | 24.7388 | 55.7778 | New | OD | Possible | #N/A | 0 | 428420.926 |  |  | MW 2024
| AAN3208 | AUH | 24.3291 | 55.7909 | New | OD | Possible | #N/A | 0 | 184238.1371 |  |  | MW 2024
| AAN3228 | AUH | 24.7434 | 55.7892 | New | OD | Possible | #N/A | 0 | 398198.5649 |  |  | MW 2024
| AAN3508 | AUH | 24.2611 | 55.7468 | New | OD | Possible | #N/A | 0 | 499370.0964 |  |  | MW 2024
| AUH3820 | AUH | 24.1207 | 52.6444 | New | OD | Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH2896 | AUH | 23.1177 | 53.8165 | New | OD | Possible | #N/A | 0 | 389105.2949 |  |  | MW 2024
| AUH6338 | AUH | 24.2142 | 54.9206 | New | OD | Possible | #N/A | 0 | 456647.4569 |  |  | MW 2024
| AUH6613 | AUH | 24.1914 | 54.9634 | New | OD | Possible | #N/A | 0 | 552368.6652 |  |  | MW 2024
| AAN3674 | AUH | 24.1669 | 55.3016 | New | OD | Possible | #N/A | 0 | 654811.8894 |  |  | MW 2024
| AAN3753 | AUH | 24.1734 | 55.1661 | New | OD | Possible | #N/A | 0 | 685577.3538 |  |  | MW 2024
| AAN3660 | AUH | 24.1813 | 55.3902 | New | OD | Possible | #N/A | 0 | 758378.4174 |  |  | MW 2024
| AAN3740 | AUH | 24.1526 | 55.4444 | New | OD | Possible | #N/A | 0 | 2128814.3028 | The route of this site passing at AAN2588 but it is not mentioned at this list, also this site is dependent on AAN2326 which is available in this list. |  | MW 2024
| AUH6471 | AUH | 23.2808 | 54.2498 | New | OD | Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH6598 | AUH | 23.6741 | 53.8386 | New | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH3016 | AUH | 24.6073 | 55.0033 | New | OD | Possible | #N/A | 0 | 1139584.1004 | depend on AUH2169 |  | MW 2024
| AUH1327 | AUH | 23.707 | 53.8066 | New | OD | Possible | #N/A | 0 | 2055671.3772 | this site is dependent on AUH2983 which is in this list. |  | MW 2024
| AUH2747 | AUH | 23.5493 | 53.3131 | New | OD | Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AAN3658 | AUH | 23.4209 | 55.4303 | New | OD | Possible | #N/A | 0 | 6133532.1024 | this site is dependent on AAN3231,AAN2849,AAN2383,AAN3287,AAN2426,AAN2270,AAN2423,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 which are in this list. |  | MW 2024
| AUH1319 | AUH | 24.3211 | 54.7965 | New | OD | Riyad city - site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH3875 | AUH | 24.3218 | 54.7826 | New | OD | Riyad city - site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH1315 | AUH | 24.3653 | 54.7813 | New | OD | Riyad city - site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH3788 | AUH | 24.4614 | 54.6508 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH3734 | AUH | 24.4878 | 54.4013 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH3186 | AUH | 24.4989 | 54.4045 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH6302 | AUH | 25.127 | 52.879 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH6600 | AUH | 25.3185 | 53.4621 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH3914 | AUH | 24.3299 | 54.7856 | New | OD | Riyad city - site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH3992 | AUH | 23.1132 | 53.858 | New | OD | Possible | #N/A | 0 | 229888.4891 |  |  | MW 2024
| AAN3738 | AUH | 23.3731 | 55.3709 | New | OD | Possible | #N/A | 0 | 1107485.4924 | this site is dependent on AAN2425,AAN3231,AAN2849,AAN2383,AAN3287,AAN2426,AAN2270,AAN2423,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 |  | MW 2024
| AAN3505 | AUH | 23.6362 | 55.5412 | New | OD | Possible | #N/A | 0 | 5723285.454 | The Proposed route of this site can cover the connection of sites (AAN3396,AAN3230,AAN2427,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258) |  | MW 2024
| AUH1035 | AUH | 23.6412 | 55.5412 | New | OD | Possible | #N/A | 0 | 224987.2047 |  |  | MW 2024
| AUH3989 | AUH | 23.8205 | 53.583 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH3986 | AUH | 23.8332 | 53.7528 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH3990 | AUH | 23.8457 | 53.5867 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH3984 | AUH | 23.8772 | 53.6111 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH3610 | AUH | 23.9614 | 52.227982 | New | OD | Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AAN3741 | AUH | 23.9892 | 55.0932 | New | OD | Possible | #N/A | 0 | 1955560.2708 | this site is dependent on AAN2394,AAN2393 |  | MW 2024
| AAN3385 | AUH | 24.0072 | 55.4399 | New | OD | Possible | #N/A | 0 | 530957.6352 |  |  | MW 2024
| AUH2881 | AUH | 24.0556 | 53.3355 | New | OD | Possible | #N/A | 0 | 351448.6514 |  |  | MW 2024
| AUH3005 | AUH | 24.0937 | 53.4096 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH1079 | AUH | 24.0943 | 51.6343 | New | OD | Possible | #N/A | 0 | 416573.5586 |  |  | MW 2024
| AAN3662 | AUH | 24.117 | 55.3748 | New | OD | Possible | #N/A | 0 | 874293.867 | The route of this site passing at AAN2326,AAN2588 but they are not mentioned at this list |  | MW 2024
| AUH6419 | AUH | 24.1277 | 52.7574 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AAN3737 | AUH | 24.1287 | 55.2585 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH3485 | AUH | 24.134 | 52.7179 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH6554 | AUH | 24.1429 | 52.7354 | New | OD | NOT POSSIBLE | #N/A | 0 | 0 |  |  | MW 2024
| AUH1677 | AUH | 24.1653 | 54.9158 | New | OD | Possible | #N/A | 0 | 462682.4322 |  |  | MW 2024
| AUH1431 | AUH | 24.1701 | 52.6487 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AAN3665 | AUH | 24.1722 | 55.4341 | New | OD | Possible | #N/A | 0 | 541982.9282 |  |  | MW 2024
| AUH1671 | AUH | 24.1756 | 54.8698 | New | OD | Possible | #N/A | 0 | 664069.871 |  |  | MW 2024
| AUH6486 | AUH | 24.1769 | 53.8611 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AAN3722 | AUH | 24.1845 | 55.3344 | New | OD | Possible | #N/A | 0 | 314645.2438 |  |  | MW 2024
| AUH1687 | AUH | 24.1948 | 54.8994 | New | OD | Possible | #N/A | 0 | 424929.3359 | The route of this site passing at AUH3445 but it is not mentioned at this list |  | MW 2024
| AAN3528 | AUH | 24.2001 | 55.6903 | New | OD | Possible | #N/A | 0 | 370574.4928 |  |  | MW 2024
| AUH1682 | AUH | 24.2027 | 54.8725 | New | OD | Possible | #N/A | 0 | 404795.934 | The route of this site passing at AUH3445 but it is not mentioned at this list |  | MW 2024
| AUH1347 | AUH | 24.2458 | 54.4407 | New | OD | Possible | #N/A | 0 | 347428.7969 | This site is dependent on AUH1345 which is in this list. |  | MW 2024
| AUH1345 | AUH | 24.2578 | 54.453 | New | OD | Possible | #N/A | 0 | 271440.3404 |  |  | MW 2024
| AUH2740 | AUH | 24.282 | 54.568 | New | OD | Possible | #N/A | 0 | 161335.7989 |  |  | MW 2024
| AUH1892 | AUH | 24.3338 | 54.5686 | New | OD | Possible | #N/A | 0 | 212366.7313 |  |  | MW 2024
| AUH1324 | AUH | 24.3396 | 54.7756 | New | OD | Riyad city - site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH2486 | AUH | 24.3491 | 54.6912 | New | OD | Possible | #N/A | 0 | 842253.33 |  |  | MW 2024
| AUH1893 | AUH | 24.3554 | 54.4961 | New | OD | Possible | #N/A | 0 | 186376.4207 | due to asphlat cost |  | MW 2024
| AUH6575 | AUH | 24.3668 | 54.5129 | New | OD | Possible | #N/A | 0 | 129368.3846 |  |  | MW 2024
| AUH1326 | AUH | 24.3676 | 54.7593 | New | OD | Riyad city - site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH1894 | AUH | 24.409 | 54.6003 | New | OD | Possible | #N/A | 0 | 372022.7682 |  |  | MW 2024
| AUH2644 | AUH | 24.4309 | 54.6421 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH2516 | AUH | 24.4316 | 54.514 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH2515 | AUH | 24.4429 | 54.6473 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH6422 | AUH | 24.4598 | 53.371 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AAN3735 | AUH | 24.4729 | 55.3866 | New | OD | Possible | #N/A | 0 | 308061.2297 |  |  | MW 2024
| AUH3645 | AUH | 24.4784 | 54.4094 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH6463 | AUH | 24.5115 | 54.6551 | New | OD | Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AAN3723 | AUH | 24.5317 | 55.6729 | New | OD | Possible | #N/A | 0 | 358513.4455 |  |  | MW 2024
| AUH3096 | AUH | 24.5336 | 54.9101 | New | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH2745 | AUH | 24.5395 | 54.4364 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH1139 | AUH | 24.5435 | 54.6214 | New | OD | Possible | #N/A | 0 | 496761.4201 |  |  | MW 2024
| AUH6069 | AUH | 24.5451 | 54.8633 | New | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH1082 | AUH | 24.554 | 54.7593 | New | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH3481 | AUH | 24.5563 | 54.8097 | New | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AUH1339 | AUH | 24.5605 | 54.757 | New | OD | Military - Site survey required | #N/A | 0 | 0 |  |  | MW 2024
| AAN3744 | AUH | 24.6522 | 55.7046 | New | OD | Possible | #N/A | 0 | 175311.0627 |  |  | MW 2024
| AAN3657 | AUH | 24.7022 | 55.6018 | New | OD | Possible | #N/A | 0 | 293536.9271 |  |  | MW 2024
| AUH2731 | AUH | 24.7374 | 55.1103 | New | OD | Not possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH2988 | AUH | 24.7924 | 52.5558 | New | OD | Not Possible | #N/A | 0 | 0 |  |  | MW 2024
| AUH0917 | AUH | 24.4249 | 54.6505 | Existing | ibs | Possible | #N/A | 0 | 196967.8514 |  |  | stay in MW
| AUH0860 | AUH | 24.4978 | 54.3683 | Existing | ibs | Possible | #N/A | 0 | 202297.7011 |  |  | stay in MW
| AAN0014 | AUH | 24.2307 | 55.7334 | Existing | ibs | POSSIBLE | #N/A | 0 | 116261.7281 |  |  | stay in MW
| AAN0005 | AUH | 24.2386 | 55.7371 | Existing | ibs | Possible | #N/A | 0 | 135595.2037 |  |  | stay in MW
| RAK0503 | AUH | 25.6901 | 55.7759 | Existing | ibs | NE Region | n/a | 0 | 0 |  |  | stay in MW
| RAK0527 | AUH | 25.6853 | 55.7733 | Existing | ibs | NE Region | n/a | 0 | 0 |  |  | stay in MW
| AUH0789 | AUH | 24.49847 | 54.3905 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| AUH0691 | AUH | 24.3891 | 54.2218 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0420 | AUH | 24.4388 | 54.5743 | Existing | ibs | Possible | #N/A | 0 | 216467.8848 |  |  | stay in MW
| AUH0862 | AUH | 24.4995 | 54.3708 | Existing | ibs | POSSIBLE | #N/A | 0 | 152591.04 |  |  | stay in MW
| AUH0923 | AUH | 24.5001 | 54.3712 | Existing | ibs | Possible | #N/A | 0 | 131049.42 |  |  | stay in MW
| AAN0027 | AUH | 23.6373 | 55.5656 | Existing | ibs | Possible | #N/A | 0 | 4197157.896 |  |  | stay in MW
| AUH5673B | AUH | 24.4292 | 54.6408 | Existing | ibs | Possible | #N/A | 0 | 248391.8219 |  |  | stay in MW
| AUH5532C | AUH | 24.457 | 54.634 | Existing | ibs | Possible | #N/A | 0 | 316874.6993 |  |  | stay in MW
| AAN5399D | AUH | 24.5761 | 55.7474 | Existing | ibs | Possible | #N/A | 0 | 112411.743 |  |  | stay in MW
| AUH5532A | AUH | 24.366 | 54.1927 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH5403D | AUH | 24.2772 | 52.6095 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH5818F | AUH | 24.2525 | 54.5551 | Existing | ibs | Possible | 7-8 month | AUH3119 | 258032.6967 |  | 258032.6967 | Y2024 fiber scope |  | 195027.25 | 7-8 month
| AUH5818E | AUH | 24.3267 | 54.61 | Existing | ibs | Possible | #N/A | 0 | 324000 |  |  | stay in MW
| AUH0682 | AUH | 24.4847 | 54.3634 | Existing | ibs | Possible | #N/A | 0 | 155096.0435 |  |  | stay in MW
| AUH0891 | AUH | 24.4756 | 52.3092 | Existing | ibs | NE Region | #N/A | 0 | 0 |  |  | stay in MW
| AUH0191 | AUH | 24.3661 | 52.5946 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN0007 | AUH | 24.0779 | 55.7682 | Existing | ibs | Possible | #N/A | 0 | 3779216.0048 |  |  | stay in MW
| AUH0548 | AUH | 24.4779 | 54.3769 | Existing | ibs | Possible | #N/A | 0 | 130800 |  |  | stay in MW
| AUH0564 | AUH | 24.45177 | 54.3355 | Existing | ibs | Possible | #N/A | 0 | 313695.483 |  |  | stay in MW
| AUH0903 | AUH | 24.5149 | 54.3826 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0931 | AUH | 24.0853 | 53.4981 | Existing | ibs | Possible | #N/A | 0 | 187128.3727 |  |  | stay in MW
| AUH0900 | AUH | 24.4525 | 54.311 | Existing | ibs | Possible | #N/A | 0 | 586264.0947 |  |  | stay in MW
| AUH0829 | AUH | 24.545 | 54.4349 | Existing | ibs | Possible | #N/A | 0 | 579948.624 |  |  | stay in MW
| AUH0921 | AUH | 24.4451 | 54.6253 | Existing | ibs | POSSIBLE | #N/A | 0 | 184261.92 |  |  | stay in MW
| AUH0901 | AUH | 24.4512 | 54.3099 | Existing | ibs | Possible | #N/A | 0 | 143506.4779 |  |  | stay in MW
| AUH0865 | AUH | 24.4663 | 54.4066 | Existing | ibs | Possible | #N/A | 0 | 167165.4979 |  |  | stay in MW
| AUH0866 | AUH | 24.4673 | 54.4076 | Existing | ibs | Possible | 7-8 month | AUH DC | 81189.8 |  | 81189.8 | Y2024 fiber scope
| AUH0868 | AUH | 24.4702 | 54.4015 | Existing | ibs | Possible | #N/A | 0 | 309771.5091 |  |  | stay in MW
| AUH0867 | AUH | 24.467 | 54.4044 | Existing | ibs | Possible | #N/A | 0 | 617947.93 |  |  | stay in MW
| AUH0975 | AUH | 24.4105 | 54.4847 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AAN0061 | AUH | 24.2226 | 55.7236 | Existing | ibs | Possible | #N/A | 0 | 314850.84 |  |  | stay in MW
| AUH0411 | AUH | 24.5025 | 54.368 | Existing | ibs | Possible | #N/A | 0 | 142931.1631 |  |  | stay in MW
| AUH0545 | AUH | 24.5022 | 54.3676 | Existing | ibs | Exact Coordinates Required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0956 | AUH | 24.4689 | 54.3376 | Existing | ibs | Possible | #N/A | 0 | 187754.52 |  |  | stay in MW
| AAN0040 | AUH | 24.1752 | 55.7391 | Existing | ibs | Possible | #N/A | 0 | 258450.6349 |  |  | stay in MW
| AUH0567 | AUH | 24.5824 | 51.7309 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0566 | AUH | 24.58 | 51.7268 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0870 | AUH | 24.5383 | 54.4242 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| AAN0017 | AUH | 24.286 | 55.6226 | Existing | ibs | Possible | #N/A | 0 | 556585.3743 |  |  | stay in MW
| AUH0874 | AUH | 24.4544 | 54.345 | Existing | ibs | POSSIBLE | #N/A | 0 | 245131.92 |  |  | stay in MW
| AUH0760 | AUH | 24.4851 | 54.3814 | Existing | ibs | Possible | 7-8 month | AUH6005 | 82800 |  | 82800 | Y2024 fiber scope
| AUH0872 | AUH | 24.4196 | 54.529 | Existing | ibs | POSSIBLE | #N/A | 0 | 271711.92 |  |  | stay in MW
| AUH5673J | AUH | 24.4826 | 52.3241 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5089 | AUH | 24.5119 | 54.4064 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5078 | AUH | 24.488379 | 54.395 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5065 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5062 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5064 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5061 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5063 | AUH | 24.4938 | 54.4089 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5080 | AUH | 24.4988 | 54.4032 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5092 | AUH | 24.4917 | 54.3956 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5098 | AUH | 24.5079 | 54.4056 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5093 | AUH | 24.492 | 54.3952 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5090 | AUH | 24.4907 | 54.3961 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5086 | AUH | 24.49992 | 54.40972 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5099 | AUH | 24.4995 | 54.3948 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5081 | AUH | 24.4988 | 54.4032 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5094 | AUH | 24.4922 | 54.3946 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5087 | AUH | 24.49992 | 54.40972 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5097 | AUH | 24.489 | 54.4124 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5096 | AUH | 24.489 | 54.4124 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5095 | AUH | 24.4916 | 54.3948 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5085 | AUH | 24.5123 | 54.4057 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| AUH0794 | AUH | 24.5422 | 54.4304 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5101 | AUH | 24.4995 | 54.3948 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5079 | AUH | 24.4878 | 54.3945 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5140 | AUH | 24.5013 | 54.3698 | Existing | ibs | Possible | #N/A | 0 | 128446.9087 |  |  | stay in MW
| IAD5172 | AUH | 24.4486 | 54.3377 | Existing | ibs | Possible | #N/A | 0 | 138890.5989 |  |  | stay in MW
| IAD5135 | AUH | 24.3299 | 54.6037 | Existing | ibs | Possible | 7-8 month | AUH6501 | 282309.384 |  | 282309.384 | Y2024 fiber scope |  | 303841.53 | 7-8 month
| AUH0452 | AUH | 24.4515 | 54.6039 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0824 | AUH | 24.4519 | 54.6054 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5191 | AUH | 24.431 | 54.4329 | Existing | ibs | Possible | #N/A | 0 | 111072.6503 |  |  | stay in MW
| IAD5132 | AUH | 24.5148 | 54.3787 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5251 | AUH | 24.4548 | 54.3423 | Existing | ibs | Possible | #N/A | 0 | 274972.8467 |  |  | stay in MW
| IAD5276 | AUH | 24.4981 | 54.4053 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5275 | AUH | 24.4992 | 54.4042 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5195 | AUH | 24.4876 | 54.4059 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5277 | AUH | 24.4991 | 54.405 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5292 | AUH | 24.5109 | 54.4087 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| AUH0864 | AUH | 24.4182 | 54.6581 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5293 | AUH | 24.498 | 54.4108 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5384 | AUH | 24.4134 | 54.4598 | Existing | ibs | Possible | #N/A | 0 | 232074.4142 |  |  | stay in MW
| IAD5315 | AUH | 24.5022 | 54.4096 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5294 | AUH | 24.4985 | 54.4108 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5316 | AUH | 24.5003 | 54.4057 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| AAN0088 | AUH | 23.4198 | 55.4134 | Existing | ibs | Possible | #N/A | 0 | 4350737.2407 |  |  | stay in MW
| IAD5365 | AUH | 24.5211 | 54.438 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5381 | AUH | 24.5 | 54.4036 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5295 | AUH | 24.4815 | 54.4056 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5350 | AUH | 24.5781 | 51.7258 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH5818G | AUH | 24.312 | 54.1193 | Existing | ibs | Possible | #N/A | 0 | 296569.6417 |  |  | stay in MW
| IAD5088 | AUH | 24.4992 | 54.4043 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5507 | AUH | 24.452 | 54.3334 | Existing | ibs | NOT POSSIBLE | 7-8 month | 0 | 0 |  |  | stay in MW
| IAD5575 | AUH | 24.4198 | 54.4646 | Existing | ibs | Possible | #N/A | 0 | 291139.525 |  |  | stay in MW
| IAD5591 | AUH | 24.419 | 54.4625 | Existing | ibs | Possible | #N/A | 0 | 115281.96 |  |  | stay in MW
| IAD5620 | AUH | 24.4927 | 54.3668 | Existing | ibs | Possible | 7-8 month | AUH6005 | 82800 |  | 82800 | Y2024 fiber scope
| IAD5407 | AUH | 24.4991 | 54.4091 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5405 | AUH | 24.483 | 54.4062 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5532 | AUH | 24.4756 | 54.3503 | Existing | ibs | Possible | #N/A | 0 | 310020 |  |  | stay in MW
| IAD5410 | AUH | 24.5057 | 54.4067 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5576 | AUH | 24.4202 | 54.4618 | Existing | ibs | Possible | #N/A | 0 | 184481.9601 |  |  | stay in MW
| IAD5318 | AUH | 24.5037 | 54.4099 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5408 | AUH | 24.4971 | 54.4088 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5406 | AUH | 24.4821 | 54.4074 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5573 | AUH | 24.4715 | 54.408 | Existing | ibs | Possible | #N/A | 0 | 338099.7413 |  |  | stay in MW
| IAD5604 | AUH | 24.5005 | 54.3709 | Existing | ibs | Possible | #N/A | 0 | 452856.1074 |  |  | stay in MW
| IAD5699 | AUH | 24.4159 | 54.5735 | Existing | ibs | Possible | #N/A | 0 | 133657.2802 |  |  | stay in MW
| AUH5462E | AUH | 24.478 | 54.3326 | Existing | ibs | Possible | #N/A | 0 | 234272.1667 |  |  | stay in MW
| IAD5587 | AUH | 24.4295 | 54.5372 | Existing | ibs | Possible | #N/A | 0 | 455253.367 |  |  | stay in MW
| IAD5676 | AUH | 24.5107 | 54.4058 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5749 | AUH | 24.4102 | 54.5651 | Existing | ibs | Possible | #N/A | 0 | 128771.4381 |  |  | stay in MW
| IAD5289 | AUH | 25.3551 | 52.7265 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5077 | AUH | 24.4875 | 54.3952 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5282 | AUH | 24.4928 | 54.3931 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5713 | AUH | 24.4166 | 54.5111 | Existing | ibs | Possible | #N/A | 0 | 254589.1804 |  |  | stay in MW
| IAD5668 | AUH | 24.4136 | 54.4537 | Existing | ibs | Possible | #N/A | 0 | 254589.1804 |  |  | stay in MW
| IAD5284 | AUH | 24.4928 | 54.3931 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5283 | AUH | 24.4928 | 54.3931 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5671 | AUH | 24.4706 | 54.3415 | Existing | ibs | Possible | 7-8 month | AUH6003 | 84132.54 |  | 84132.54 | Y2024 fiber scope
| IAD5281 | AUH | 24.4928 | 54.3931 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5745 | AUH | 24.5387 | 54.4092 | Existing | ibs | Possible | #N/A | 0 | 159865.759 |  |  | stay in MW
| IAD5675 | AUH | 24.4846 | 54.4042 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5719 | AUH | 24.4209 | 54.4975 | Existing | ibs | Possible | #N/A | 0 | 133819.5878 |  |  | stay in MW
| IAD5617 | AUH | 24.4968 | 54.4073 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5754 | AUH | 24.4884 | 54.3751 | Existing | ibs | Possible | #N/A | 0 | 189238.296 |  |  | stay in MW
| IAD5595 | AUH | 24.5098 | 54.4053 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5504 | AUH | 24.4175 | 54.4424 | Existing | ibs | POSSIBLE | #N/A | 0 | 114974.64 |  |  | stay in MW
| IAD5311 | AUH | 24.4857 | 54.4037 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5766 | AUH | 24.43 | 54.583 | Existing | ibs | Possible | #N/A | 0 | 143527.3328 |  |  | stay in MW
| IAD5190 | AUH | 24.5283 | 54.3908 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH5818H | AUH | 24.5309 | 54.383 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5480 | AUH | 24.4906 | 54.4 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5464 | AUH | 24.4882 | 54.4084 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5489 | AUH | 24.3371 | 52.6464 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5490 | AUH | 24.326 | 52.5719 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5577 | AUH | 24.4682 | 54.3408 | Existing | ibs | Possible | 7-8 month | AUH6003 | 48000 |  | 48000 | Y2024 fiber scope
| IAD5746 | AUH | 24.4867 | 54.4038 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5780 | AUH | 24.3272 | 54.7501 | Existing | ibs | Possible | #N/A | 0 | 803492.2073 |  |  | stay in MW
| IAD5783 | AUH | 24.4539 | 54.3676 | Existing | ibs | Possible | #N/A | 0 | 221408.2156 |  |  | stay in MW
| IAD5313 | AUH | 24.4892 | 54.3949 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5312 | AUH | 24.4897 | 54.3945 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5771 | AUH | 24.4837 | 54.4054 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5770 | AUH | 24.4837 | 54.4054 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5750 | AUH | 24.5113 | 54.4088 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5622 | AUH | 24.4436 | 54.6756 | Existing | ibs | Possible | #N/A | 0 | 408648.9066 |  |  | stay in MW
| IAD5828 | AUH | 24.4213 | 54.5971 | Existing | ibs | Possible | 4-5 month | Khazna DC | 48000 |  | 48000 | Y2024 fiber scope |  | 48000 | 4-5 month
| IAD5747 | AUH | 23.8336 | 53.6152 | Existing | ibs | Possible | #N/A | 0 | 278431.3432 |  |  | stay in MW
| IAD5763 | AUH | 23.5517 | 53.2943 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5682 | AUH | 24.4176 | 54.4885 | Existing | ibs | Possible | #N/A | 0 | 184376.7217 |  |  | stay in MW
| IAD5765 | AUH | 23.548 | 53.294 | Existing | ibs | Possible | #N/A | 0 | 2983623.9729 |  |  | stay in MW
| IAD5767 | AUH | 24.8947 | 53.0762 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5260 | AUH | 24.4429 | 54.5844 | Existing | ibs | Possible | #N/A | 0 | 120000 |  |  | stay in MW
| IAD5859 | AUH | 24.4973 | 54.3946 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5818 | AUH | 24.4913 | 54.4128 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5217 | AUH | 24.4719 | 54.3505 | Existing | ibs | POSSIBLE | #N/A | 0 | 131835.6 |  |  | stay in MW
| IAD5821 | AUH | 24.5066 | 54.405 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5799 | AUH | 24.5058 | 54.4053 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5811 | AUH | 24.4958 | 54.3932 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5357 | AUH | 24.4349 | 54.4728 | Existing | ibs | Possible | #N/A | 0 | 783028.6935 |  |  | stay in MW
| IAD5817 | AUH | 24.4979 | 54.4118 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5822 | AUH | 24.5062 | 54.4051 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5815 | AUH | 24.1826 | 54.9934 | Existing | ibs | Possible | #N/A | 0 | 187515.199 |  |  | stay in MW
| IAD5569 | AUH | 24.5096 | 54.4074 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5752 | AUH | 25.1444 | 52.8719 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5853 | AUH | 24.5143 | 54.3761 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5751 | AUH | 25.1458 | 52.871 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5707 | AUH | 24.5021 | 54.408 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| AAN0131 | AUH | 24.2953 | 55.6237 | Existing | ibs | Possible | #N/A | 0 | 289689.8496 |  |  | stay in MW
| IAD5802 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5891 | AUH | 24.5383 | 54.3831 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5800 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5903 | AUH | 24.5016 | 54.4116 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5812 | AUH | 24.4499 | 54.632 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5409 | AUH | 24.4859 | 54.4072 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5801 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5708 | AUH | 24.5101 | 54.4097 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5722 | AUH | 23.9784 | 52.2653 | Existing | ibs | Possible | #N/A | 0 | 250916.5348 |  |  | stay in MW
| IAD5800 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5800 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5800 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5800 | AUH | 24.4882 | 54.4004 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD0995A | AUH | 24.1124 | 52.7359 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5931 | AUH | 23.6226 | 53.7161 | Existing | ibs | Possible | #N/A | 0 | 284585.9225 |  |  | stay in MW
| IAD5271 | AUH | 24.4944 | 54.4029 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5273 | AUH | 24.4944 | 54.4029 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5920 | AUH | 24.4988 | 54.4113 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5883 | AUH | 24.5065 | 54.4073 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5148 | AUH | 24.4906 | 54.3934 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5936 | AUH | 24.5213 | 54.4332 | Existing | ibs | Possible | #N/A | 0 | 110943.5312 |  |  | stay in MW
| IAD5998 | AUH | 24.4788 | 54.4116 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD0989E | AUH | 24.272 | 54.6874 | Existing | ibs | Possible | #N/A | 0 | 287820.8538 |  |  | stay in MW
| IAD5594 | AUH | 24.5029 | 54.4103 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5973 | AUH | 24.4866 | 54.4008 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD0994E | AUH | 24.121 | 52.7238 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0006 | AUH | 24.4595 | 54.7215 | Existing | ibs | Possible | #N/A | 0 | 168850.4977 |  |  | stay in MW
| AUH0056 | AUH | 24.4154 | 54.4394 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0059 | AUH | 24.4154 | 54.4394 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5596 | AUH | 24.4932 | 54.4005 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| AUH0005 | AUH | 24.3531 | 54.4061 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| AUH0028 | AUH | 24.7637 | 54.682 | Existing | ibs | Possible | #N/A | 0 | 626837.55 |  |  | stay in MW
| IAD5173 | AUH | 24.5194 | 54.3716 | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5975 | AUH | 24.5644 | 54.4596 | Existing | ibs | Possible | #N/A | 0 | 205898.0887 |  |  | stay in MW
| IAD5571 | AUH | 24.5083 | 54.4063 | Existing | ibs | PIS with ETC | #N/A | 0 | 0 |  |  | stay in MW
| IAD5790 | AUH | 24.4461 | 54.5888 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| IAD5961 | AUH | 24.3654 | 54.6902 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0053 | AUH | 24.3394 | 54.6085 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0074 | AUH | 24.5068 | 54.4051 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0054 | AUH | 24.3396 | 54.6091 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0081 | AUH | 25.4945 | 53.1477 | Existing | ibs | NOT POSSIBLE | #N/A | 0 | 0 |  |  | stay in MW
| IAD5188 | AUH | 24.4935 | 54.3692 | Existing | ibs | Possible | 7-8 month | AUH6005 | 36000 |  | 36000 | Y2024 fiber scope
| AUH0070 | AUH | 24.4171 | 54.4683 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| IAD5785 | AUH | 24.4434 | 54.587 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0062 | AUH | 24.4968 | 54.4078 | Existing | ibs | Site Survey required | #N/A | 0 | 0 |  |  | stay in MW
| AUH0064 | AUH | 24.3713 | 54.8434 | Existing | ibs | POSSIBLE | #N/A | 0 | 271788.24 |  |  | stay in MW
IBS-FTK-19-490 | IAD5223 | AUH | 24.502 | 54.3716 | New | ibs | Possible | 0 | 0 | 168243.624 |  |  | MW 2024
IBS-FTK-19-1604 | IAD5388 | AUH | 24.4201 | 54.4628 | New | ibs | Possible | 0 | 0 | 133800.408 |  |  | MW 2024
IBS-SS-21-0316 | IAD5810 | AUH | 24.4826 | 54.4067 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-74 | IAD5193 | AUH | 24.5115 | 54.4083 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-561 | IAD5503 | AUH | 24.4363 | 54.4666 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-1363 | IAD5537 | AUH | 24.4787 | 54.3712 | New | ibs | Possible | 0 | 0 | 130186.656 |  |  | MW 2024
IBS-FTK-23-0230 | AUH0524 | AUH | 24.4604 | 54.3125 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-3436 | IAD5716 | AUH | 24.4555 | 54.6153 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-1964 | AUH0073 | AUH | 24.4975 | 54.3719 | New | ibs | Possible | 0 | 0 | 113564.16 |  |  | MW 2024
IBS-FTK-22-1087 | AUH0052 | AUH | 24.4912 | 54.3585 | New | ibs | Possible | 7-8 month | AUH6005 | 24412.63 |  | 24412.63 | Y2024 fiber scope
IBS-FTK-22-0161 | IAD5959 | AUH | 24.4551 | 54.6159 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-0160 | IAD5958 | AUH | 24.4543 | 54.6153 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-21-3677 | IAD5939 | AUH | 24.4944 | 54.3877 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-21-3667 | IAD5911 | AUH | 24.437 | 54.6179 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-21-3465 | IAD5863 | AUH | 24.4217 | 54.4619 | New | ibs | Possible | 0 | 0 | 257427.36 |  |  | MW 2024
IBS-SS-23-1455 | AAN0142 | AUH | 24.2336 | 55.694 | New | ibs | Possible | 0 | 0 | 144574.5024 |  |  | MW 2024
IBS-SS-23-1315 | AUH0102 | AUH | 24.4006 | 54.7327 | New | ibs | Possible | 0 | 0 | 429382.4256 |  |  | MW 2024
IBS-SS-23-1302 | IAJ5876 | AUH | 24.2779 | 54.6492 | New | ibs | Possible | 0 | 0 | 252303.2352 |  |  | MW 2024
IBS-SS-23-1137 | AUH0103 | AUH | 24.4038 | 54.5923 | New | ibs | Possible | 0 | 0 | 136588.3776 |  |  | MW 2024
IBS-SS-22-0020 | IAD5972 | AUH | 23.9685 | 52.2375 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-21-2052 | IAD5897 | AUH | 24.1232 | 52.736 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-21-2051 | IAD5898 | AUH | 24.129 | 52.7182 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-21-0312 |  | AUH | 24.4081 | 54.4503 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-21-0198 | AUH0019 | AUH | 24.4339 | 54.5809 | New | ibs | Possible | 0 | 0 | 379394.352 |  |  | MW 2024
IBS-SS-21-0172 | IAD5978 | AUH | 24.4962 | 54.4104 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-20-1863 | IAD5955 | AUH | 25.2423 | 53.3026 | New | ibs | Wrong location | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-20-0298 |  | AUH | 24.1169 | 52.7651 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-20-0295 |  | AUH | 24.1236 | 52.7313 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-20-0250 | IAD5803 | AUH | 23.2785 | 54.2391 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-20-0243 |  | AUH | 24.4288 | 54.5147 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-20-0119 |  | AUH | 24.4212 | 54.4549 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-20-0091 |  | AUH | 24.4953 | 54.3939 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-20-0082 |  | AUH | 24.4284 | 54.4515 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-20-0042 |  | AUH | 24.4731 | 54.4027 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-19-95 | IAD5197 | AUH | 22.9229 | 53.9907 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-94 | IAD5198 | AUH | 22.9481 | 53.8416 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-553 |  | AUH | 24.7886 | 52.554 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-19-1299 |  | AUH | 24.4517 | 54.3626 | New | ibs | Possible | 0 | #N/A | 141901.776 |  |  | MW 2024
IBS-SS-19-1247 | IAD5439 | AUH | 24.4954 | 54.3662 | New | ibs | Possible | 0 | 0 | 167144.616 |  |  | MW 2024
IBS-FTK-23-1023 | AAN0141 | AUH | 24.0789 | 55.7687 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-23-0865 | AUH0085 | AUH | 25.0074 | 53.3577 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-23-0807 | AUH0083 | AUH | 24.3994 | 52.8825 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-23-0016 | AUH0093 | AUH | 24.4934 | 54.3881 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-5052 | AUH0088 | AUH | 24.6788 | 55.1844 | New | ibs | Possible | 0 | 0 | 338204.448 |  |  | MW 2024
IBS-FTK-22-2054 | IAD5977 | AUH | 24.4185 | 54.4419 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-1459 | AUH0089 | AUH | 24.4823 | 54.3522 | New | ibs | Possible | 0 | 0 | 114483.816 |  |  | MW 2024
IBS-FTK-21-3839 | IAD5937 | AUH | 24.4929 | 54.3724 | New | ibs | Possible | 0 | 0 | 178646.04 |  |  | MW 2024
IBS-FTK-21-3838 | IAD5034 | AUH | 24.4552 | 54.6171 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-21-0093 | IAD5829 | AUH | 24.2392 | 54.5789 | New | ibs | Not possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-20-1470 | IAD5728 | AUH | 23.9678 | 52.2262 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-20-1469 | IAD5727 | AUH | 23.9698 | 52.2358 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-19-1683 | IAD5402 | AUH | 24.4319 | 54.434 | New | ibs | Possible | 0 | 0 | 138780.288 |  |  | MW 2024
IBS-FTK-19-1606 | IAD5386 | AUH | 24.4965 | 54.3723 | New | ibs | Possible | 0 | 0 | 130560.624 |  |  | MW 2024
IBS-FTK-19-1587 | IAD5414 | AUH | 24.4898 | 54.3618 | New | ibs | Possible | 0 | 0 | 140287.608 |  |  | MW 2024
IBS-SS-20-0120 | IAD5796 | AUH | 24.4153 | 54.4841 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-1254 |  | AUH | 24.4841 | 54.3638 | New | ibs | Possible | 0 | #N/A | 242834.976 |  |  | MW 2024
IBS-SS-23-1475 |  | AUH | 24.5 | 54.3942 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1456 |  | AUH | 24.3156 | 54.5337 | New | ibs | Possible | 0 | #N/A | 153400.1472 |  |  | MW 2024
IBS-SS-23-1304 |  | AUH | 24.6265 | 54.7101 | New | ibs | Possible | 0 | #N/A | 114530.3712 |  |  | MW 2024
IBS-SS-23-1242 |  | AUH | 24.4656 | 54.6002 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1220 |  | AUH | 24.4919 | 54.398 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1203 |  | AUH | 24.4354 | 54.6179 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1198 |  | AUH | 24.5034 | 54.411 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1185 |  | AUH | 24.4286 | 54.6187 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1184 |  | AUH | 24.4286 | 54.6187 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1183 |  | AUH | 24.4286 | 54.6187 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1154 |  | AUH | 24.3602 | 54.7396 | New | ibs | Site Survey required | 0 | #N/A |  |  |  | MW 2024
IBS-SS-23-1153 |  | AUH | 24.3628 | 54.7624 | New | ibs | Site Survey required | 0 | #N/A |  |  |  | MW 2024
IBS-SS-23-1143 |  | AUH | 24.6081 | 55.776 | New | ibs | Wrong location | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1142 |  | AUH | 24.2134 | 55.4837 | New | ibs | Wrong location | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1133 |  | AUH | 24.5018 | 54.4105 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1093 |  | AUH | 24.4189 | 54.4645 | New | ibs | Possible | 0 | #N/A | 149560.488 |  |  | MW 2024
IBS-SS-23-1078 |  | AUH | 24.4879 | 54.3655 | New | ibs | Possible | 0 | #N/A | 164818.3824 |  |  | MW 2024
IBS-SS-23-1006 |  | AUH | 24.4142 | 54.547 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-1000 |  | AUH | 24.4354 | 54.6179 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-0787 |  | AUH | 24.5035 | 54.411 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-23-0707 |  | AUH | 24.4971 | 54.4048 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-5101 |  | AUH | 24.5623 | 54.4582 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-5100 |  | AUH | 24.4924 | 54.3856 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-5091 |  | AUH | 24.4143 | 54.5105 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-4595 |  | AUH | 24.4971 | 54.4048 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-4530 |  | AUH | 24.3008 | 54.5667 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-4297 |  | AUH | 24.3931 | 54.7563 | New | ibs | Wrong location | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-3142 |  | AUH | 24.4832 | 54.3602 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-0089 |  | AUH | 24.5082 | 54.4115 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-0088 |  | AUH | 24.5082 | 54.4115 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-21-0740 | AUH0016 | AUH | 24.4644 | 54.372 | New | ibs | Possible | 0 | 0 | 345889.872 |  |  | MW 2024
IBS-SS-21-0200 | AUH0021 | AUH | 24.4286 | 54.4556 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-21-0174 |  | AUH | 24.4984 | 54.4062 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-21-0171 |  | AUH | 24.5053 | 54.4104 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-21-0170 |  | AUH | 24.5083 | 54.4091 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-21-0169 |  | AUH | 24.5071 | 54.4103 | New | ibs | Not Possible | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-21-0164 | AUH0017 | AUH | 24.4335 | 54.4152 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-20-0231 | IAD5798 | AUH | 24.4155 | 54.4827 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-79 | AAN0115 | AUH | 24.5953 | 55.4115 | New | ibs | Possible | 0 | 0 | 2753045.568 |  |  | MW 2024
IBS-SS-19-1216 | AUH0013 | AUH | 24.5331 | 54.4288 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-Hunt-22-1981 |  | AUH | 24.4851 | 54.3522 | New | ibs | Wrong location | 0 | #N/A | 0 |  |  | MW 2024
IBS-Hunt-22-1504 |  | AUH | 24.4327 | 54.6234 | New | ibs | Site Survey required | 0 | #N/A | 0 |  |  | MW 2024
IBS-FTK-23-1367 |  | AUH | 24.4976 | 54.3822 | New | ibs | Wrong location | 0 | #N/A | 0 |  |  | MW 2024
IBS-SS-22-5001 | AUH0099 | AUH | 24.4856 | 54.4107 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-22-4593 | AUH0039 | AUH | 24.4471 | 54.395 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-589 | AUH0061 | AUH | 24.4982 | 54.3916 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-19-288 | IAD5309 | AUH | 24.4293 | 54.4362 | New | ibs | Possible | 0 | 0 | 162641.736 |  |  | MW 2024
IBS-FTK-22-4359 | IAD5046 | AUH | 24.3007 | 54.6166 | New | ibs | Possible | 0 | 0 | 162462.384 |  |  | MW 2024
IBS-FTK-21-3324 | AUH0095 | AUH | 24.4848 | 54.4085 | New | ibs | Not Possible | 0 | 0 |  |  |  | MW 2024
IBS-FTK-19-600 | IAD5237 | AUH | 24.4554 | 54.6173 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-19-518 | IAD5221 | AUH | 24.453 | 54.615 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-4538 | AUH0040 | AUH | 23.8959 | 52.8027 | New | ibs | Possible | 0 | 0 | 125057.952 |  |  | MW 2024
IBS-FTK-22-4537 | AUH0036 | AUH | 23.6467 | 53.7089 | New | ibs | Possible | 7-8 month | AUH2938 | 18000 |  | 18000 | Y2024 fiber scope
IBS-FTK-22-2191 | IAD5997 | AUH | 24.6081 | 54.1504 | New | ibs | Wrong location | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-2190 | IAD5996 | AUH | 24.5172 | 54.0259 | New | ibs | Wrong location | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-22-1819 | IAD5982 | AUH | 24.4739 | 54.3491 | New | ibs | Possible | 0 | 0 | 191105.28 |  |  | MW 2024
IBS-FTK-20-1468 | IAD5971 | AUH | 23.9665 | 52.2251 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-19-1521 | IAD5491 | AUH | 24.4892 | 54.3602 | New | ibs | Possible | 0 | 0 | 156608.64 |  |  | MW 2024
IBS-SS-19-259 | IAD5298 | AUH | 24.4597 | 54.3012 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-SS-18-1164 | IAD5183 | AUH | 24.4929 | 54.4058 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-19-1434 | IAD0989B | AUH | 23.6665 | 54.3459 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-19-1034 | IAD0995D | AUH | 24.3391 | 54.5251 | New | ibs | Possible | 0 | 0 | 151899.696 |  |  | MW 2024
IBS-FTK-18-0202 | IAD0993E | AUH | 23.28 | 54.2501 | New | ibs | Site Survey required | 0 | 0 | 0 |  |  | MW 2024
IBS-FTK-18-017 | AUH5532B | AUH | 24.3871 | 54.2213 | New | ibs | Not Possible | 0 | 0 | 0 |  |  | MW 2024
| AAN2815 | AAN | 24.2627 | 55.7681 | Existing | OD | Possible | 4-5 month | AAN6001 | 81090 | 0 | 81090 | Y2024 fiber scope
| AAN3167 | AAN | 24.2163 | 55.4768 | Existing | OD | Taawun | to be shared by OSP Team | AAN5002 |  | 0 | 0 | Y2024 fiber scope
| AAN3212 | AAN | 24.1502 | 55.6406 | Existing | OD | Taawun | to be shared by OSP Team | AAN2009 |  |  | 0 | Y2024 fiber scope
| AAN3214 | AAN | 24.1571 | 55.6481 | Existing | OD | Taawun | to be shared by OSP Team | AAN2009 |  |  | 0 | Y2024 fiber scope
| AAN3258 | AAN | 23.8173 | 55.5204 | Existing | OD | Possible | 8-12 month | AAN2265 | 1124360.405 | 0 | 1124360.405 | Y2024 fiber scope
| AAN3300 | AAN | 24.2706 | 55.7472 | Existing | OD | OSP Provisioned | 4-5 month | AAN6001 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AAN3308 | AAN | 24.2288 | 55.7499 | Existing | OD | Possible | 4-5 month | AAN6001 | 34500 | 0 | 34500 | Y2024 fiber scope
| AAN3312 | AAN | 24.1711 | 55.6583 | Existing | OD | Possible | 4-5 month | AAN6001 | 65000 | 0 | 65000 | Y2024 fiber scope
| AAN3392 | AAN | 24.2062 | 55.4661 | Existing | OD | Possible | 4-5 month | AAN5002 | 25000 | 0 | 25000 | Y2024 fiber scope
| AAN3529 | AAN | 24.198 | 55.7271 | Existing | OD | Possible | 4-5 month | AAN2006 | 25000 | 0 | 25000 | Y2024 fiber scope
| AAN3530 | AAN | 24.1962 | 55.7258 | Existing | OD | Possible | 4-5 month | AAN6001 | 25000 | 0 | 25000 | Y2024 fiber scope
| AAN3605 | AAN | 24.2219 | 55.7578 | Existing | OD | OSP Provisioned | 4-5 month | AAN6001 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AAN2523 | AAN | 24.2553 | 55.6941 | Existing | OD | Possible | 4-5 month | AAN6001 | 70000 | 2023 scope | 70000 | Y2024 fiber scope |  | 70000 | 4-5 month
| AAN2856 | AAN | 24.0379 | 55.4657 | Existing | OD | OSP Provisioned | 4-5 month | AAN5002 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AAG6104 | AAN | 24.0919 | 55.9237 | Existing | OD | Possible | 4-5 month | AAN2305 | 35071.584 | 0 | 35071.584 | Y2024 fiber scope
| AUG4246 | AUH | 24.5008 | 54.6187 | Existing | OD | Taawun | to be shared by OSP Team | AUH2439 |  | 0 | 0 | Y2024 fiber scope
| AUG4273 | AUH | 24.5069 | 54.6215 | Existing | OD | Taawun | to be shared by OSP Team | AUH2439 |  | 0 | 0 | Y2024 fiber scope
| AUG4289 | AUH | 24.4644 | 54.656 | Existing | OD | Possible | #N/A | 0 | 526733.928 | 0 |  | stay in MW
| AUG4447 | AUH | 24.4511 | 54.6773 | Existing | OD | Possible | 8-12 month | Khazna DC | 161962 | 2023 scope | 161962 | Y2024 fiber scope |  | 161962 | 8-12 month
| AUH2091 | AUH | 24.4517 | 54.356 | Existing | OD | Possible | 4-5 month | AUH1314 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2105 | AUH | 24.4054 | 54.5043 | Existing | OD | Possible | 4-5 month | AUH6501 | 28944.36 | 0 | 28944.36 | Y2024 fiber scope
| AUH2157 | AUH | 24.4315 | 54.5689 | Existing | OD | Possible | 4-5 month | AUH2553 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2186 | AUH | 24.4817 | 54.3552 | Existing | OD | Possible | 4-5 month | AUH6003 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2187 | AUH | 24.4586 | 54.3595 | Existing | OD | Possible | 4-5 month | AUH6003 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2247 | AUH | 24.492 | 54.3734 | Existing | OD | Possible | 4-5 month | AUH6005 | 81291.6 | Dependent on IAD5562 | 81291.6 | Y2024 fiber scope
| AUH2272 | AUH | 24.4263 | 54.4754 | Existing | OD | Possible | #N/A | 0 | 564860.304 | 0 |  | stay in MW
| AUH2274 | AUH | 24.8344 | 54.8861 | Existing | OD | Possible | 4-5 month | AUH2178 | 19563.36 | 0 | 19563.36 | Y2024 fiber scope |  | 19563.36 | 4-5 month
| AUH2313 | AUH | 24.47 | 54.3402 | Existing | OD | Tabreed | 4-5 month | AUH6003 | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH2401 | AUH | 24.2885 | 54.6405 | Existing | OD | Possible | 4-5 month | AUH5002 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2443 | AUH | 24.5133 | 54.3718 | Existing | OD | Taawun | to be shared by OSP Team | AUH6005 |  | 0 | 0 | Y2024 fiber scope
| AUH2487 | AUH | 24.8032 | 54.7072 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2541 | AUH | 24.4083 | 54.4981 | Existing | OD | Possible | 7-8 month | AUH6501 | 144154 | 2023 scope | 144154 | Y2024 fiber scope |  | 144154 | 7-8 month
| AUH2566 | AUH | 24.7825 | 54.8547 | Existing | OD | Possible | 7-8 month | KIZAD DC | 152268.576 | 0 | 152268.576 | Y2024 fiber scope |  | 169857.16 | 7-8 month
| AUH2584 | AUH | 24.4982 | 54.5925 | Existing | OD | Possible | 4-5 month | AUH0619 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2581 | AUH | 24.2562 | 54.6278 | Existing | OD | OSP Provisioned | 4-5 month | AUH5002 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH2648 | AUH | 24.4509 | 54.6014 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH2695 | AUH | 24.7876 | 54.7289 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2696 | AUH | 24.7952 | 54.7156 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2697 | AUH | 24.7881 | 54.711 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2700 | AUH | 24.7918 | 54.7231 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2733 | AUH | 24.7736 | 54.7119 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2734 | AUH | 24.7829 | 54.7054 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2781 | WR | 24.094 | 52.4771 | Existing | OD | Possible | #N/A | 0 | 155276.856 | 0 |  | stay in MW
| AUH2752 | AUH | 24.4308 | 54.6198 | Existing | OD | Possible | 4-5 month | Khazna DC | 48000 | 0 | 48000 | Y2024 fiber scope
| AUH2822 | AUH | 24.4535 | 54.6708 | Existing | OD | Possible | 4-5 month | Khazna DC | 60000 | 0 | 60000 | Y2024 fiber scope
| AUH2861 | WR | 24.0745 | 53.5411 | Existing | OD | Possible | 4-5 month | AUH2908 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2888 | AUH | 24.5027 | 54.5996 | Existing | OD | Site survey | #N/A | 0 |  | 0 |  | stay in MW
| AUH3236 | AUH | 24.4172 | 54.3325 | Existing | OD | Taawun | to be shared by OSP Team | AUH1336 |  | 0 | 0 | Y2024 fiber scope
| AUH3108 | AUH | 24.5162 | 54.9708 | Existing | OD | Possible | 8-12 month | AUH2142 | 423982.29 | 0 | 423982.29 | Y2024 fiber scope |  | 423982.29 | 8-12 month
| AUH3113 | AUH | 24.8053 | 54.6411 | Existing | OD | Site survey | #N/A | 0 |  | 0 |  | stay in MW
| AUH3119 | AUH | 24.2651 | 54.5562 | Existing | OD | Possible | 4-5 month | AUH2692 | 25000 | 0 | 25000 | Y2024 fiber scope |  | 25000 | 4-5 month
| AUH3114 | AUH | 24.7939 | 54.6508 | Existing | OD | Site survey | #N/A | 0 |  | 0 |  | stay in MW
| AUH3413 | AUH | 24.3347 | 54.6793 | Existing | OD | Taawun | to be shared by OSP Team | AUH2414 |  | 0 | 0 | Y2024 fiber scope
| AUH3239 | AUH | 24.4984 | 54.6253 | Existing | OD | Taawun | to be shared by OSP Team | AUH2439 |  | 0 | 0 | Y2024 fiber scope
| AUH3274 | AUH | 24.4718 | 54.3474 | Existing | OD | Possible | 4-5 month | AUH6003 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2255 | AUH | 24.7987 | 54.723 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2299 | AUH | 24.4507 | 54.6076 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH3390 | AUH | 24.7411 | 54.8902 | Existing | OD | OSP Ready | OSP Ready | AUH5004 |  | 0 | 0 | Y2024 fiber scope
| AUH2617 | AUH | 24.437 | 54.3679 | Existing | OD | Possible | 4-5 month | AUH1341 | 132748 | 2023 scope | 132748 | Y2024 fiber scope
| AUH3395 | AUH | 24.6801 | 54.8268 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH3725 | AUH | 24.2674 | 54.6586 | Existing | OD | Taawun | to be shared by OSP Team | AUH2405 |  | 0 | 0 | Y2024 fiber scope
| AUH3484 | WR | 23.3553 | 53.7689 | Existing | OD | OSP Provisioned | 4-5 month | AUH2936 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH3494 | WR | 23.7807 | 53.5643 | Existing | OD | Possible | #N/A | 0 | 1344296.664 | Proposal of this site is passing and covering the cost to connect AUG6088 also. |  | stay in MW
| AUH3490 | WR | 24.1249 | 51.6211 | Existing | OD | Possible | 8-12 month | AUH2920 | 180777 | 2023 scope | 180777 | Y2024 fiber scope |  | 180777 | 8-12 month
| AUH3578 | WR | 24.1938 | 54.4727 | Existing | OD | OSP Ready | OSP Ready | AUH2836 |  | 0 | 0 | Y2024 fiber scope
| AUH3654 | WR | 24.0788 | 52.6478 | Existing | OD | Possible | 4-5 month | AUH2911 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH3722 | WR | 23.6454 | 53.6848 | Existing | OD | Taawun | to be shared by OSP Team | AUH2862 |  | 0 | 0 | Y2024 fiber scope
| AUH3724 | AUH | 24.2786 | 54.6791 | Existing | OD | Taawun | to be shared by OSP Team | AUH2399 |  | 0 | 0 | Y2024 fiber scope
| AUH3787 | AUH | 24.497 | 54.9263 | Existing | OD | OSP Ready | OSP Ready | AUH2142 |  | 0 | 0 | Y2024 fiber scope
| AUH3760 | WR | 23.7027 | 53.1936 | Existing | OD | OSP Ready | OSP Ready | AUH2962 |  | 0 | 0 | Y2024 fiber scope
| AUH3801 | AUH | 24.3154 | 54.6237 | Existing | OD | Possible | 4-5 month | AUH1416 | 64401.36 | 0 | 64401.36 | Y2024 fiber scope
| AUH3831 | AUH | 24.3385 | 54.4958 | Existing | OD | OSP Provisioned | 4-5 month | AUH6501 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH3879 | AUH | 24.4143 | 54.3511 | Existing | OD | Taawun | to be shared by OSP Team | AUH1336 |  | 0 | 0 | Y2024 fiber scope
| AUH3922 | WR | 23.2578 | 54.309 | Existing | OD | OSP Ready | OSP Ready | AUH2926 |  |  | 0 | Y2024 fiber scope
| AUH3313 | AUH | 24.4325 | 54.3784 | Existing | OD | Possible | 4-5 month | AUH1341 | 60000 | 0 | 60000 | Y2024 fiber scope
| AUH3974 | AUH | 24.4436 | 54.5802 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH3975 | AUH | 24.4423 | 54.5773 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH3411 | AUH | 24.3449 | 54.6792 | Existing | OD | Taawun | to be shared by OSP Team | AUH2414 |  |  | 0 | Y2024 fiber scope
| AUH3072 | AUH | 24.2991 | 54.6729 | Existing | OD | Taawun | to be shared by OSP Team | AUH2399 |  | 0 | 0 | Y2024 fiber scope
| AUH3064 | AUH | 24.4406 | 54.7299 | Existing | OD | Possible | #N/A | 0 | 462162.12 | 0 |  | stay in MW
| AUH3085 | AUH | 24.8207 | 54.6589 | Existing | OD | Not possible | #N/A | 0 | 0 | 0 |  | stay in MW
| AUH3084 | AUH | 24.4032 | 54.6888 | Existing | OD | Taawun | to be shared by OSP Team | AUH2414 |  | 0 | 0 | Y2024 fiber scope
| AUH3149 | AUH | 24.3235 | 54.5313 | Existing | OD | Possible | #N/A | 0 | 156824.88 | 0 |  | stay in MW
| AUH2200 | AUH | 24.5011 | 54.3773 | Existing | OD | Possible | 4-5 month | AUH6005 | 75156.7378 | 0 | 75156.7378 | Y2024 fiber scope
| AUH3086 | AUH | 24.7912 | 54.6661 | Existing | OD | Not possible | #N/A | 0 | 0 | 0 |  | stay in MW
| AUH3087 | AUH | 24.7876 | 54.6936 | Existing | OD | Not possible | #N/A | 0 | 0 | 0 |  | stay in MW
| AUH3219 | AUH | 24.4183 | 54.5703 | Existing | OD | Possible | 7-8 month | AUH2553 | 135740.4211 | 0 | 135740.4211 | Y2024 fiber scope
| AUH3305 | AUH | 24.2919 | 54.6404 | Existing | OD | OSP Ready | OSP Ready | AUH2204 |  | 0 | 0 | Y2024 fiber scope
| AUH2318 | AUH | 24.4673 | 54.3848 | Existing | OD | Possible | 4-5 month | AUH DC | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH3334 | AUH | 24.842 | 55.0352 | Existing | OD | Taawun | to be shared by OSP Team | AUH2179 |  | 0 | 0 | Y2024 fiber scope
| AUH2335 | AUH | 24.4793 | 54.3794 | Existing | OD | Possible | 4-5 month | AUH6005 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH3336 | AUH | 24.5484 | 54.7009 | Existing | OD | Taawun | to be shared by OSP Team | AUH2437 |  | 0 | 0 | Y2024 fiber scope
| AUH3842 | AUH | 24.5319 | 54.4141 | Existing | OD | Taawun | to be shared by OSP Team | AUH6005 |  | 0 | 0 | Y2024 fiber scope
| AUH2523 | AUH | 24.3712 | 54.5377 | Existing | OD | Possible | 4-5 month | AUH6501 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH3822 | AUH | 24.4441 | 54.5881 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH2855 | AUH | 24.5481 | 54.8356 | Existing | OD | OSP Provisioned | 4-5 month | AUH2291 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH2250 | AUH | 24.439 | 54.6171 | Existing | OD | Possible | 4-5 month | Khazna DC | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH6142 | AUH | 24.4191 | 54.4071 | Existing | OD | Taawun | to be shared by OSP Team | AUH2219 |  | 0 | 0 | Y2024 fiber scope
| AUH3266 | AUH | 24.3617 | 54.4725 | Existing | OD | OSP Ready | OSP Ready | AUH2118 |  | 0 | 0 | Y2024 fiber scope
| AUH2283 | AUH | 24.439 | 54.5714 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH6143 | AUH | 24.4169 | 54.4102 | Existing | OD | Taawun | to be shared by OSP Team | AUH2219 |  | 0 | 0 | Y2024 fiber scope
| AUH6154 | AUH | 24.3355 | 54.597 | Existing | OD | Possible | 7-8 month | AUH6501 | 130000 | 0 | 130000 | Y2024 fiber scope
| AUH6000 | AUH | 24.4516 | 54.6126 | Existing | OD | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
| AUH6116 | AUH | 24.4053 | 54.7143 | Existing | OD | Taawun | to be shared by OSP Team | AUH2426 |  | 0 | 0 | Y2024 fiber scope
| AUH6118 | AUH | 24.4488 | 54.3467 | Existing | OD | Possible | 8-12 month | AUH1314 | 160000 | 2023 scope | 160000 | Y2024 fiber scope |  | 160000 | 8-12 month
| AUH6141 | AUH | 24.4174 | 54.4039 | Existing | OD | Taawun | to be shared by OSP Team | AUH2219 |  | 0 | 0 | Y2024 fiber scope
| AUH6145 | WR | 23.983 | 51.8327 | Existing | OD | Possible | 4-5 month | AUH2918 | 25000 |  | 25000 | Y2024 fiber scope
| AUH6354 | WR | 23.74 | 53.9794 | Existing | OD | Possible | #N/A | 0 | 3790450.9 | The proposed route of this site can cover the connection to AUH2983,AUH1327,AUH2943 without extra charges |  | stay in MW
| AUH6543 | AUH | 24.7442 | 54.7263 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| AUH6413 | WR | 24.8975 | 53.0715 | Existing | OD | Not possible | #N/A | 0 | 0 | 0 |  | stay in MW
| AUH6414 | WR | 24.8927 | 53.0797 | Existing | OD | Not possible | #N/A | 0 | 0 | 0 |  | stay in MW
| AUH6429 | WR | 23.8416 | 52.8196 | Existing | OD | Taawun | to be shared by OSP Team | AUH3148 |  | 0 | 0 | Y2024 fiber scope
| AUH6430 | WR | 23.8327 | 52.819 | Existing | OD | Taawun | to be shared by OSP Team | AUH3148 |  | 0 | 0 | Y2024 fiber scope
| AUH6431 | WR | 24.1009 | 53.4967 | Existing | OD | Possible | #N/A | 0 | 674158.728 | 0 |  | stay in MW
| AUH6441 | WR | 23.8262 | 54.2371 | Existing | OD | Possible | #N/A | 0 | 2249689.94 | The proposed route of this site can cover the connection to AUH1342 without extra charges |  | stay in MW
| AUH1076 | AUH | 24.839 | 55.0217 | Existing | OD | Taawun | to be shared by OSP Team | AUH2179 |  | 0 | 0 | Y2024 fiber scope
| AUH2529 | AUH | 24.7101 | 54.8364 | Existing | OD | Taawun | to be shared by OSP Team | KIZAD DC |  | 0 | 0 | Y2024 fiber scope
| AUH2748 | AUH | 24.4014 | 54.6486 | Existing | OD | Taawun | to be shared by OSP Team | AUH1416 |  | 0 | 0 | Y2024 fiber scope
| AUH2060 | AUH | 24.3623 | 54.6887 | Existing | OD | Possible | 4-5 month | AUH1416 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH6466 | WR | 24.0779 | 52.6446 | Existing | OD | Possible | 4-5 month | AUH2911 | 35000 | 0 | 35000 | Y2024 fiber scope
| AUH6476 | WR | 23.1899 | 53.7921 | Existing | OD | Possible | 4-5 month | AUH2934 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH2820 | AUH | 24.3302 | 54.7117 | Existing | OD | Taawun | to be shared by OSP Team | AUH2399 |  | 0 | 0 | Y2024 fiber scope
| AUH6076 | AUH | 24.5244 | 54.4422 | Existing | OD | Taawun | to be shared by OSP Team | AUH2251 |  | 0 | 0 | Y2024 fiber scope
| AUH6593 | AUH | 24.3659 | 54.4843 | Existing | OD | Possible | 4-5 month | AUH6501 | 35000 | 0 | 35000 | Y2024 fiber scope
| AUH6140 | AUH | 24.4201 | 54.4047 | Existing | OD | Taawun | to be shared by OSP Team | AUH2219 |  | 0 | 0 | Y2024 fiber scope
| AUH3410 | AUH | 24.3391 | 54.6735 | Existing | OD | Taawun | to be shared by OSP Team | AUH2414 |  | 0 | 0 | Y2024 fiber scope
| AUH6632 | AUH | 24.4412 | 54.5682 | Existing | OD | Taawun | to be shared by OSP Team | AUH2410 |  | 0 | 0 | Y2024 fiber scope
| AUH7017 | AUH | 24.4816 | 54.6058 | Existing | OD | Possible | 4-5 month | AUH0699 | 28000 | 0 | 28000 | Y2024 fiber scope
| AUH7018 | AUH | 24.4816 | 54.6058 | Existing | OD | Possible | 4-5 month | AUH0699 | 28000 | 0 | 28000 | Y2024 fiber scope
| AUH7019 | AUH | 24.4816 | 54.6058 | Existing | OD | Possible | 4-5 month | AUH0699 | 25000 | 0 | 25000 | Y2024 fiber scope
| AUH3415 | AUH | 24.3412 | 54.6843 | Existing | OD | Taawun | to be shared by OSP Team | AUH2414 |  | 0 | 0 | Y2024 fiber scope
| AUH6451 | WR | 22.8952 | 54.3323 | Existing | OD | OSP Provisioned | 4-5 month | AUH2950 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH3888 | AUH | 24.4479 | 54.5967 | New | OD | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH6014 | AUH | 24.4479 | 54.605 | New | OD | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH3902 | AUH | 24.1995 | 55.023 | New | OD | Possible | 4-5 month | AUH5001 | 25000 |  | 25000 | Y2024 fiber scope
| AUH6132 | AUH | 24.4674 | 54.3221 | New | OD | Possible | 4-5 month | AUH1314 | 25395.12 |  | 25395.12 | Y2024 fiber scope
| AUH3920 | AUH | 24.4425 | 54.4059 | New | OD | Possible | 4-5 month | AUH DC | 37687.68 |  | 37687.68 | Y2024 fiber scope
| AAN3703 | AAN | 24.2045 | 55.3665 | New | OD | Possible | 4-5 month | AAN5002 | 26965.128 |  | 26965.128 | Y2024 fiber scope
| AUH3047 | AUH | 24.4341 | 54.7663 | New | OD | Possible | 4-5 month | AUH2291 | 37499.832 |  | 37499.832 | Y2024 fiber scope
| AUH1330 | WR | 22.9675 | 53.7918 | New | OD | Possible | 4-5 month | AUH2934 | 29370.48 |  | 29370.48 | Y2024 fiber scope
| AAN3439 | AAN | 24.1811 | 55.7078 | New | OD | OSP Ready | OSP Ready | AAN2006 |  |  | 0 | Y2024 fiber scope
| AAN3655 | AAN | 24.183 | 55.7644 | New | OD | Possible | 4-5 month | AAN6001 | 64033.752 |  | 64033.752 | Y2024 fiber scope
| AUH3158 | AUH | 24.4872 | 54.6159 | New | OD | Possible | 4-5 month | Khazna DC | 56184.24 |  | 56184.24 | Y2024 fiber scope
| AUH6033 | AUH | 24.8531 | 54.8084 | New | OD | Taawun | to be shared by OSP Team | AUH2178 |  |  | 0 | Y2024 fiber scope
| AUH2231 | AUH | 24.4342 | 54.4531 | New | OD | Possible | 4-5 month | AUH1218 | 65865.96 |  | 65865.96 | Y2024 fiber scope
| AUH2726 | AUH | 24.3435 | 54.9204 | New | OD | OSP Provisioned | 7-8 month | AUH5002 | 89631.48 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 89631.48 | Y2024 fiber scope
| AUH6183 | AUH | 24.4683 | 54.8391 | New | OD | Possible | 7-8 month | AUH2291 | 138000 |  | 138000 | Y2024 fiber scope
| AUH2657 | AUH | 24.3164 | 54.6823 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH1085 | AUH | 24.4283 | 54.7192 | New | OD | Taawun | to be shared by OSP Team | AUH2426 |  |  | 0 | Y2024 fiber scope
| AUH6153 | AUH | 24.7146 | 54.8201 | New | OD | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| AUH6492 | WR | 22.8954 | 54.3683 | New | OD | Possible | #N/A | 0 | 325829.4389 |  |  | MW 2024
| AUH6106 | WR | 23.7351 | 53.4999 | New | OD | OSP Provisioned | 4-5 month | AUH2938 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AAN3388 | AAN | 24.1833 | 55.7317 | New | OD | OSP Provisioned | 4-5 month | AAN6001 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH3066 | AUH | 24.2438 | 54.475 | New | OD | Possible | 4-5 month | AUH6501 | 25000 |  | 25000 | Y2024 fiber scope
| AUH6523 | AUH | 24.3034 | 54.5907 | New | OD | OSP Provisioned | 4-5 month | AUH6501 | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH3912 | AUH | 24.3442 | 54.5247 | New | OD | Possible | 4-5 month | AUH6501 | 20000 |  | 20000 | Y2024 fiber scope
| AUH6628 | AUH | 24.3124 | 54.7087 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH1356 | AUH | 24.3124 | 54.7006 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH1362 | AUH | 24.3178 | 54.7106 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH6624 | AUH | 24.3188 | 54.7022 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH6630 | AUH | 24.3225 | 54.7218 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH1375 | AUH | 24.3372 | 54.711 | New | OD | Taawun | to be shared by OSP Team | AUH2399 |  |  | 0 | Y2024 fiber scope
| AUH3417 | AUH | 24.3499 | 54.6728 | New | OD | Taawun | to be shared by OSP Team | AUH2414 |  |  | 0 | Y2024 fiber scope
| AUH3150 | AUH | 24.3627 | 54.6704 | New | OD | Taawun | to be shared by OSP Team | AUH2414 |  |  | 0 | Y2024 fiber scope
| AUH1401 | AUH | 24.3941 | 54.677 | New | OD | Taawun | to be shared by OSP Team | AUH2414 |  |  | 0 | Y2024 fiber scope
| AUH1917 | AUH | 24.4276 | 54.3337 | New | OD | Taawun | to be shared by OSP Team | AUH1336 |  |  | 0 | Y2024 fiber scope
| AUH1461 | AUH | 24.4355 | 54.7128 | New | OD | Taawun | to be shared by OSP Team | AUH2426 |  |  | 0 | Y2024 fiber scope
| AUH1174 | AUH | 24.4917 | 54.3593 | New | OD | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH1047 | AUH | 24.5018 | 54.6196 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AUH1049 | AUH | 24.5065 | 54.6189 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AUH1349 | AUH | 24.508 | 54.6071 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AUH1891 | AUH | 24.5123 | 54.613 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AUH6176 | AUH | 24.5159 | 54.4918 | New | OD | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| AUH6173 | AUH | 24.5318 | 54.4753 | New | OD | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| AUH2782 | AUH | 24.519922 | 54.4448 | New | OD | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| AUH3090 | AUH | 24.5483 | 54.7988 | New | OD | OSP Provisioned | 4-5 month | KIZAD DC | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH3093 | AUH | 24.5633 | 54.7981 | New | OD | OSP Provisioned | 4-5 month | KIZAD DC | 25000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 25000 | Y2024 fiber scope
| AUH1033 | AUH | 24.407 | 54.5425 | New | OD | Possible | 4-5 month | AUH2553 | 25000 |  | 25000 | Y2024 fiber scope
| AUH3359 | AUH | 24.3633 | 54.5913 | New | OD | Taawun | to be shared by OSP Team | AUH1415 |  |  | 0 | Y2024 fiber scope
| AUH3766 | AUH | 24.4022 | 54.7064 | New | OD | Taawun | to be shared by OSP Team | AUH2426 |  |  | 0 | Y2024 fiber scope
| AUH3765 | AUH | 24.4027 | 54.6985 | New | OD | Taawun | to be shared by OSP Team | AUH2426 |  |  | 0 | Y2024 fiber scope
| AUH1046 | AUH | 24.5019 | 54.6314 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AAN3675 | AAN | 24.1752 | 55.7081 | New | OD | Possible | 4-5 month | AAN6001 | 25000 |  | 25000 | Y2024 fiber scope
| AAN3445 | AAN | 24.1774 | 55.6432 | New | OD | Possible | #N/A | 0 | 179000 |  |  | MW 2024
| AAN3672 | AAN | 24.2001 | 55.6521 | New | OD | Possible | 4-5 month | AAN6001 | 34997.375 | 0 | 34997.375 | Y2024 fiber scope
| AUH3908 | AUH | 24.3483 | 54.5449 | New | OD | OSP Ready | OSP Ready | AUH2132 |  |  | 0 | Y2024 fiber scope
| AUH3821 | AUH | 24.4113 | 54.3601 | New | OD | Taawun | to be shared by OSP Team | AUH1336 |  |  | 0 | Y2024 fiber scope
| AUH6009 | AUH | 24.4148 | 54.4099 | New | OD | Taawun | to be shared by OSP Team | AUH2219 |  |  | 0 | Y2024 fiber scope
| AUH2194 | AUH | 24.4681 | 54.5983 | New | OD | OSP Ready | OSP Ready | AUH2012 |  |  | 0 | Y2024 fiber scope
| AUH1048 | AUH | 24.504 | 54.6255 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AUH1068 | AUH | 24.5089 | 54.6119 | New | OD | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
| AUH1194 | AUH | 24.5249 | 54.6903 | New | OD | Possible | 4-5 month | Khazna DC | 55200 |  | 55200 | Y2024 fiber scope
| AUH2538 | AUH | 24.6901 | 54.8536 | New | OD | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| AUH2324 | AUH | 24.7121 | 54.8751 | New | OD | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| IAD5904 | AUH | 24.5205 | 54.4369 | Existing | ibs | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| AUH0537 | AUH | 24.4337 | 54.4397 | Existing | ibs | Possible | 4-5 month | AUH1218 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0553 | AUH | 24.4837 | 54.3782 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0981 | AUH | 24.4352 | 54.4184 | Existing | ibs | Possible | 4-5 month | AUH1218 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0676 | AUH | 24.0896 | 52.6444 | Existing | ibs | Possible | 4-5 month | AUH2911 | 20000 |  | 20000 | Y2024 fiber scope
| AAN0003 | AUH | 24.2586 | 55.6164 | Existing | ibs | Possible | 4-5 month | AAN2541 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0927 | AUH | 24.418 | 54.4401 | Existing | ibs | OSP Ready | OSP Ready | AUH2219 |  | Dependent on AUH0785 | 0 | Y2024 fiber scope
| DXB0371 | AUH | 25.283 | 55.3177 | Existing | ibs | Dubai Region | n/a | 0 |  | Dubai Region |  | stay in MW
| AUH0896 | AUH | 23.6514 | 53.6758 | Existing | ibs | Possible | 4-5 month | AUH2938 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0575 | AUH | 24.503 | 54.3706 | Existing | ibs | Possible | 4-5 month | AUH6005 | 60000 |  | 60000 | Y2024 fiber scope
| AUH0890 | AUH | 24.3263 | 54.616 | Existing | ibs | OSP Ready | OSP Ready | AUH2134 |  |  | 0 | Y2024 fiber scope
| AUH0417 | AUH | 24.4923 | 54.3673 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0419 | AUH | 24.4385 | 54.5724 | Existing | ibs | Not Possible | #N/A | 0 |  | Upon Approval from owner |  | stay in MW
| AUH0745 | AUH | 24.439077 | 54.5712 | Existing | ibs | Site Survey required | #N/A | 0 |  | Depends on Owner's approval |  | stay in MW
| AUH0418 | AUH | 24.5728 | 54.6943 | Existing | ibs | Possible | 4-5 month | KIZAD DC | 20000 |  | 20000 | Y2024 fiber scope
| AUH0481 | AUH | 24.4951 | 54.374 | Existing | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
| AUH0405 | AUH | 24.453072° | 54.398531° | Existing | ibs | Possible | 7-8 month | AUH DC | 85000 |  | 85000 | Y2024 fiber scope
| AUH0527 | AUH | 24.4712 | 54.3737 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| AUH0529 | AUH | 24.4713 | 54.3745 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| AUH0528 | AUH | 24.4718 | 54.3739 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| AAN5399B | AUH | 24.5939 | 55.7461 | Existing | ibs | OSP Provisioned | 4-5 month | AAN5004 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH5560A | AUH | 24.778891° | 54.737421° | Existing | ibs | Site Survey required | #N/A | 0 |  |  |  | stay in MW
| AUH5560B | AUH | 24.7783 | 54.7375 | Existing | ibs | Site Survey required | #N/A | 0 |  |  |  | stay in MW
| AUH5811E | AUH | 24.383 | 54.4994 | Existing | ibs | Possible | 4-5 month | AUH6501 | 20000 |  | 20000 | Y2024 fiber scope
| AUH5532D | AUH | 24.5582 | 54.8878 | Existing | ibs | Possible | #N/A | 0 | 311463.192 |  |  | stay in MW
| AUH5532E | AUH | 24.5582 | 54.8878 | Existing | ibs | Possible | #N/A | 0 | 180000 | Same location of AUH5532D |  | stay in MW
| AUH5673C | AUH | 24.5332 | 54.6783 | Existing | ibs | Possible | 4-5 month | Khazna DC | 81385.104 | 0 | 81385.104 | Y2024 fiber scope
| AUH5673D | AUH | 24.5332 | 54.6783 | Existing | ibs | Possible | #N/A | 0 | 252000 | Dependent on AUH5673C |  | stay in MW
| AAN0052 | AUH | 24.2245 | 55.7828 | Existing | ibs | OSP Provisioned | 4-5 month | AAN6001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AAN0031 | AUH | 24.2284 | 55.7435 | Existing | ibs | Possible | 4-5 month | AAN6001 | 20000 |  | 20000 | Y2024 fiber scope
| AUH5564A | AUH | 24.45177 | 54.3355 | Existing | ibs | Possible | #N/A | 0 | 502216.2 | Route Proposal of this site can cover the connection to AUH2630 without extra charges |  | stay in MW
| AUH0744 | AUH | 24.4306 | 54.4367 | Existing | ibs | Possible | 4-5 month | AUH1218 | 74322.36 |  | 74322.36 | Y2024 fiber scope
| AUH0876 | AUH | 24.4787 | 54.3812 | Existing | ibs | Possible | #N/A | 0 | 168308.28 |  |  | stay in MW
| AUH0795 | AUH | 24.4986 | 54.3703 | Existing | ibs | Possible | 4-5 month | AUH6005 | 48457.44 | Dependent on AUH0544 | 48457.44 | Y2024 fiber scope
| AUH0953 | AUH | 24.4715 | 54.3411 | Existing | ibs | Possible | 4-5 month | AUH6003 | 50000 |  | 50000 | Y2024 fiber scope
| AAN0036 | AUH | 24.208 | 55.8044 | Existing | ibs | OSP Provisioned | 4-5 month | AAN6001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0850 | AUH | 24.4673 | 54.3857 | Existing | ibs | Possible | 4-5 month | AUH DC | 10000 | 2023 scope | 10000 | Y2024 fiber scope |  | 10000 | 4-5 month
| AUH0990 | AUH | 23.8547 | 52.8068 | Existing | ibs | Possible | 4-5 month | AUH2962 | 26909.16 |  | 26909.16 | Y2024 fiber scope
| AUH0844 | AUH | 24.493633 | 54.3669 | Existing | ibs | Possible | 8-12 month | AUH6005 | 205597.44 |  | 205597.44 | Y2024 fiber scope
| AUH0428 | AUH | 24.4878 | 54.365 | Existing | ibs | Possible | 7-8 month | AUH6005 | 149681.52 |  | 149681.52 | Y2024 fiber scope
| AUH0717 | AUH | 24.8576 | 54.8965 | Existing | ibs | OSP Provisioned | 4-5 month | KIZAD DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0451 | AUH | 24.4929 | 54.3662 | Existing | ibs | Possible | 7-8 month | AUH6005 | 92537.64 | Dependent on AUH0844 | 92537.64 | Y2024 fiber scope
| AUH0915 | AUH | 24.1271 | 51.6232 | Existing | ibs | Possible | #N/A | 0 | 318345.984 |  |  | stay in MW
| AUH0552 | AUH | 24.4621 | 54.3293 | Existing | ibs | OSP Provisioned | 4-5 month | AUH1314 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0434 | AUH | 24.4632 | 54.3263 | Existing | ibs | OSP Provisioned | 4-5 month | AUH1314 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0926 | AUH | 24.7945 | 54.6525 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| AUH0925 | AUH | 24.8029 | 54.6417 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| AUH0907 | AUH | 24.7801 | 54.7088 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| AUH0539 | AUH | 24.449 | 54.3965 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| AUH0857 | AUH | 24.449 | 54.3965 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| AUH0826 | AUH | 24.4201 | 54.4417 | Existing | ibs | Possible | 7-8 month | AUH1219 | 146921.04 |  | 146921.04 | Y2024 fiber scope
| AUH0511 | AUH | 24.5334 | 54.3985 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| AUH0849 | AUH | 24.5334 | 54.3985 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| AUH0672 | AUH | 24.2964 | 54.6362 | Existing | ibs | Possible | 4-5 month | AUH5002 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0781 | AUH | 24.4946 | 54.3761 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0871 | AUH | 24.5346 | 54.4191 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| AUH0407 | AUH | 24.4693 | 54.3408 | Existing | ibs | Tabreed | 4-5 month | AUH6003 | 50000 |  | 50000 | Y2024 fiber scope
| AUH0662 | AUH | 24.4156 | 54.446 | Existing | ibs | Possible | #N/A | 0 | 265321.008 |  |  | stay in MW
| AUH0562 | AUH | 24.4286 | 54.6415 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH2131 |  |  | 0 | Y2024 fiber scope
| AUH0491 | AUH | 24.4537 | 54.3093 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH1314 |  |  | 0 | Y2024 fiber scope
| AUH0881 | AUH | 24.4759 | 54.3722 | Existing | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0742 | AUH | 24.4301 | 54.4365 | Existing | ibs | Possible | 7-8 month | AUH1218 | 128051.28 | Dependent on IAD5240 | 128051.28 | Y2024 fiber scope
| AUH0748 | AUH | 24.4585 | 54.3202 | Existing | ibs | OSP Provisioned | 4-5 month | AUH1314 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0922 | AUH | 24.4986 | 54.3721 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0984 | AUH | 24.0859 | 52.6654 | Existing | ibs | OSP Provisioned | 4-5 month | AUH2911 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0912 | AUH | 24.5315 | 54.4033 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| AUH0483 | AUH | 24.483246 | 54.3604 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| AUH0764 | AUH | 24.4832 | 54.3604 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| AUH0544 | AUH | 24.4983 | 54.370564° | Existing | ibs | Possible | 7-8 month | AUH6005 | 103070.88 | Dependent on IAD5693 | 103070.88 | Y2024 fiber scope
| AUH0512 | AUH | 24.5056 | 54.3756 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0884 | AUH | 24.5377 | 54.4256 | Existing | ibs | Exact location is required | #N/A | 0 |  |  |  | stay in MW
| AUH0823 | AUH | 24.4939 | 54.3628 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0531 | AUH | 23.5337 | 53.801 | Existing | ibs | OSP Provisioned | 4-5 month | AUH2937 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AAN0050 | AUH | 24.1957 | 55.6441 | Existing | ibs | OSP Provisioned | 4-5 month | AAN6001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AAN0038 | AUH | 24.1957 | 55.6504 | Existing | ibs | OSP Provisioned | 4-5 month | AAN6001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AAN0016 | AUH | 24.1969 | 55.6523 | Existing | ibs | OSP Provisioned | 4-5 month | AAN6001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0937 | AUH | 24.4865 | 54.3598 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0661 | AUH | 24.3301 | 54.605 | Existing | ibs | Site survey | #N/A | 0 |  |  |  | stay in MW
| AAN0010 | AUH | 24.2294 | 55.7501 | Existing | ibs | OSP Provisioned | 4-5 month | AAN6001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0969 | AUH | 24.4596 | 54.3791 | Existing | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0913 | AUH | 24.4601 | 54.3794 | Existing | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| AUH0728 | AUH | 24.3223 | 54.6093 | Existing | ibs | Possible | #N/A | 0 | 389471.136 |  |  | stay in MW
| AUH0785 | AUH | 24.4185 | 54.4403 | Existing | ibs | Possible | #N/A | 0 | 303127.92 |  |  | stay in MW
| IAD0990B | AUH | 24.2892 | 54.4945 | Existing | ibs | Possible | 4-5 month | AUH6501 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5176 | AUH | 24.5432 | 54.4328 | Existing | ibs | Exact location is required | #N/A | 0 |  |  |  | stay in MW
| AUH0599 | AUH | 24.3057 | 54.1118 | Existing | ibs | Possible | #N/A | 0 | 3484848.792 | Proposed route of this site is covering the connection to AUH3679 , AUH6348 , AUH6425 with no extra charges |  | stay in MW
| IAD5150 | AUH | 24.306 | 54.1135 | Existing | ibs | Not Possible | #N/A | 0 |  | Same Location of AUH0599 |  | stay in MW
| AUH0797 | AUH | 24.3067 | 54.1148 | Existing | ibs | Not Possible | #N/A | 0 |  | Same Location of AUH0599 |  | stay in MW
| IAD5123 | AUH | 24.4857 | 54.3582 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| AUH0650 | AUH | 24.449831 | 54.6065 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0736 | AUH | 24.449831 | 54.6065 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0570 | AUH | 24.4517 | 54.6039 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0735 | AUH | 24.449831 | 54.6065 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0743 | AUH | 24.449831 | 54.6065 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0859 | AUH | 24.4931 | 54.3747 | Existing | ibs | Possible | 7-8 month | AUH6005 | 133377.84 |  | 133377.84 | Y2024 fiber scope
| IAD5122 | AUH | 24.3983 | 54.4713 | Existing | ibs | OSP Ready | OSP Ready | AUH2099 |  |  | 0 | Y2024 fiber scope
| IAD5226 | AUH | 24.5012 | 54.3734 | Existing | ibs | Possible | 4-5 month | AUH6005 | 71056.44 |  | 71056.44 | Y2024 fiber scope
| IAD5240 | AUH | 24.4297 | 54.4364 | Existing | ibs | Possible | 8-12 month | AUH1218 | 219727.08 |  | 219727.08 | Y2024 fiber scope
| IAD5133 | AUH | 24.4839 | 54.599 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | Khazna DC |  |  | 0 | Y2024 fiber scope
| IAD5186 | AUH | 24.4489 | 54.5996 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5175 | AUH | 24.4915 | 54.376 | Existing | ibs | Possible | 7-8 month | AUH6005 | 100057.68 |  | 100057.68 | Y2024 fiber scope
| IAD5230 | AUH | 24.4513 | 54.6012 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5228 | AUH | 24.4508 | 54.6014 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5232 | AUH | 24.4505 | 54.599 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5310 | AUH | 24.3563 | 54.7043 | Existing | ibs | Possible | 4-5 month | AUH1416 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5231 | AUH | 24.4505 | 54.599 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5181 | AUH | 24.4191 | 54.4651 | Existing | ibs | Possible | #N/A | 0 | 228397.32 |  |  | stay in MW
| IAD5224 | AUH | 24.4453 | 54.5844 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5185 | AUH | 24.4935 | 54.3681 | Existing | ibs | Possible | 4-5 month | AUH6005 | 77711.4 |  | 77711.4 | Y2024 fiber scope
| AUH0469 | AUH | 24.504 | 54.3695 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5335 | AUH | 24.4203 | 54.461 | Existing | ibs | Possible | 4-5 month | AUH1219 | 39294.72 |  | 39294.72 | Y2024 fiber scope
| IAD5234 | AUH | 24.4539 | 54.6161 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0550 | AUH | 24.5036 | 54.3692 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | 2023 scope | 30000 | Y2024 fiber scope
| IAD5326 | AUH | 24.508210° | 54.37713° | Existing | ibs | Possible | 7-8 month | AUH6005 | 94018.32 | Dependent on IAD5677 | 94018.32 | Y2024 fiber scope
| IAD5324 | AUH | 24.508210° | 54.37713° | Existing | ibs | Not Possible | #N/A | 0 | 0 |  |  | stay in MW
| IAD5396 | AUH | 24.5321 | 54.421234 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| IAD5413 | AUH | 24.4306 | 54.433509 | Existing | ibs | Possible | #N/A | 0 | 228915.72 |  |  | stay in MW
| IAD5460 | AUH | 24.4719 | 54.340777 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6003 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5494 | AUH | 24.3165 | 54.535747 | Existing | ibs | Possible | 4-5 month | AUH6501 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5412 | AUH | 24.5037 | 54.375181 | Existing | ibs | Possible | #N/A | 0 | 156871.08 |  |  | stay in MW
| IAD5519 | AUH | 24.5028 | 54.373955 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5514 | AUH | 24.4633 | 54.376111 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| IAD5515 | AUH | 24.4464 | 54.4001 | Existing | ibs | Possible | #N/A | 0 | 151865.28 |  |  | stay in MW
| IAD5352 | AUH | 24.493 | 54.368292 | Existing | ibs | Possible | #N/A | 0 | 170080.56 |  |  | stay in MW
| IAD5511 | AUH | 24.4654 | 54.385122 | Existing | ibs | Possible | 4-5 month | AUH DC | 44222.76 |  | 44222.76 | Y2024 fiber scope
| IAD5493 | AUH | 24.4741 | 54.37426 | Existing | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5428 | AUH | 24.4919 | 54.370764 | Existing | ibs | Possible | 4-5 month | AUH6005 | 75498.48 | Depend to Connect IAD5544 | 75498.48 | Y2024 fiber scope
| IAD5444 | AUH | 24.4774 | 54.370914 | Existing | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5470 | AUH | 24.5088 | 54.377394 | Existing | ibs | Exact location is required | #N/A | 0 |  |  |  | stay in MW
| IAD5478 | AUH | 24.4694 | 54.341802 | Existing | ibs | Possible | 4-5 month | AUH6003 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5481 | AUH | 24.4875 | 54.356215 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5502 | AUH | 24.499 | 54.374894 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 2023 scope | 20000 | Y2024 fiber scope
| IAD5528 | AUH | 24.4775 | 54.364722 | Existing | ibs | Possible | 4-5 month | AUH6003 | 20000 | 0 | 20000 | Y2024 fiber scope
| IAD5499 | AUH | 24.4936 | 54.363141 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 0 | 20000 | Y2024 fiber scope
| IAD5554 | AUH | 24.4865 | 54.352446 | Existing | ibs | Possible | 7-8 month | AUH6003 | 105040.8 | 0 | 105040.8 | Y2024 fiber scope
| IAD5574 | AUH | 24.4637 | 54.37589 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 | 0 | 20000 | Y2024 fiber scope
| IAD5542 | AUH | 24.4939 | 54.3685 | Existing | ibs | Possible | 4-5 month | AUH6005 | 77014.8 | 0 | 77014.8 | Y2024 fiber scope
| IAD5558 | AUH | 24.4826 | 54.3601 | Existing | ibs | Not Possible | #N/A | 0 |  | 0 |  | stay in MW
| IAD5586 | AUH | 24.4207 | 54.462517 | Existing | ibs | Possible | 7-8 month | AUH1219 | 112165.56 | 0 | 112165.56 | Y2024 fiber scope
| IAD5565 | AUH | 24.493 | 54.372439 | Existing | ibs | Possible | 7-8 month | AUH6005 | 87356.88 | Dependent on IAD5557 | 87356.88 | Y2024 fiber scope
| IAD5608 | AUH | 24.4845 | 54.375855 | Existing | ibs | Exact location is required | #N/A | 0 |  | 0 |  | stay in MW
| IAD5562 | AUH | 24.4918 | 54.3729 | Existing | ibs | Possible | 7-8 month | AUH6005 | 85613.76 | 0 | 85613.76 | Y2024 fiber scope
| IAD5506 | AUH | 24.4513 | 54.33303 | Existing | ibs | Possible | 7-8 month | AUH1314 | 111034.8 | Dependent on AUH5564A | 111034.8 | Y2024 fiber scope
| IAD5387 | AUH | 24.5229 | 54.4332201 | Existing | ibs | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| IAD5395 | AUH | 24.4321 | 54.433221 | Existing | ibs | Possible | #N/A | 0 | 152248.86 |  |  | stay in MW
| IAD5661 | AUH | 24.3339 | 54.530503 | Existing | ibs | Possible | 4-5 month | AUH6501 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5557 | AUH | 24.4925 | 54.371389 | Existing | ibs | Possible | 7-8 month | AUH6005 | 83083.32 |  | 83083.32 | Y2024 fiber scope
| IAD5583 | AUH | 24.5042 | 54.36977 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 2023 scope | 20000 | Y2024 fiber scope
| IAD5582 | AUH | 24.5042 | 54.36977 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 2023 scope | 20000 | Y2024 fiber scope
| IAD5584 | AUH | 24.4862 | 54.366155 | Existing | ibs | Possible | 7-8 month | AUH6005 | 100747.8 |  | 100747.8 | Y2024 fiber scope
| IAD5473 | AUH | 24.4659 | 54.339502 | Existing | ibs | Possible | 7-8 month | AUH6003 | 83041.2 |  | 83041.2 | Y2024 fiber scope
| IAD5606 | AUH | 24.4754 | 54.372818 | Existing | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5426 | AUH | 24.4901 | 54.356933 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5627 | AUH | 24.4498 | 54.613396 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5544 | AUH | 24.4923 | 54.371292 | Existing | ibs | Possible | 4-5 month | AUH6005 | 44912.88 | Dependent on IAD5557 | 44912.88 | Y2024 fiber scope
| IAD5446 | AUH | 24.4916 | 54.379202 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5652 | AUH | 24.4957 | 54.366445 | Existing | ibs | Possible | #N/A | 0 | 157480.2 |  |  | stay in MW
| IAD5419 | AUH | 24.5506 | 54.45188 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| IAD5629 | AUH | 24.469 | 54.3395628 | Existing | ibs | Tabreed | 4-5 month | AUH6003 | 50000 |  | 50000 | Y2024 fiber scope
| IAD5553 | AUH | 24.4945 | 54.376913 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | 2023 scope | 30000 | Y2024 fiber scope
| IAD5393 | AUH | 24.4802 | 54.320011 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH1314 |  |  | 0 | Y2024 fiber scope
| IAD5518 | AUH | 24.4557 | 54.338391 | Existing | ibs | Possible | 7-8 month | AUH1314 | 111890.16 |  | 111890.16 | Y2024 fiber scope
| IAD5463 | AUH | 24.5388 | 54.410286 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| IAD5290 | AUH | 24.4787 | 54.35352 | Existing | ibs | Possible | 7-8 month | AUH6003 | 104807.52 |  | 104807.52 | Y2024 fiber scope
| IAD5321 | AUH | 24.4113 | 54.473855 | Existing | ibs | OSP Provisioned | 4-5 month | AUH1219 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5684 | AUH | 24.3162 | 54.61018 | Existing | ibs | Possible | 4-5 month | AUH1416 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5482 | AUH | 24.4779 | 54.371821 | Existing | ibs | Possible | 7-8 month | AUH6005 | 98755.2 | Depend to Connect IAD5610 | 98755.2 | Y2024 fiber scope
| IAD5693 | AUH | 24.4973 | 54.371666 | Existing | ibs | Possible | 7-8 month | AUH6005 | 149568.12 | 0 | 149568.12 | Y2024 fiber scope
| IAD5649 | AUH | 24.4944 | 54.3706 | Existing | ibs | OSP Ready | OSP Ready | AUH6005 |  | 0 | 0 | Y2024 fiber scope
| IAD5624 | AUH | 24.4789 | 54.3719 | Existing | ibs | Exact location is required | #N/A | 0 |  | 0 |  | stay in MW
| IAD5702 | AUH | 24.4901 | 54.360366 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 2023 scope | 20000 | Y2024 fiber scope
| IAD5512 | AUH | 24.4289 | 54.43656 | Existing | ibs | Possible | 4-5 month | AUH1218 | 66322.8 | 0 | 66322.8 | Y2024 fiber scope
| IAD5626 | AUH | 24.4494 | 54.612106 | Existing | ibs | Tabreed | 4-5 month | AUH6003 | 50000 |  | 50000 | Y2024 fiber scope
| IAD5551 | AUH | 24.4994 | 54.375739 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 0 | 20000 | Y2024 fiber scope
| IAD5679 | AUH | 24.4709 | 54.341826 | Existing | ibs | Tabreed | 4-5 month | AUH6003 | 50000 | 0 | 50000 | Y2024 fiber scope
| IAD5299 | AUH | 24.4934 | 54.372935 | Existing | ibs | Possible | 7-8 month | AUH6005 | 96095.16 | Dependent on IAD5565 | 96095.16 | Y2024 fiber scope
| IAD5610 | AUH | 24.4786 | 54.371168 | Existing | ibs | Possible | 7-8 month | AUH6005 | 123816.6 |  | 123816.6 | Y2024 fiber scope
| IAD5236 | AUH | 24.4441 | 54.588274 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5445 | AUH | 24.484 | 54.376111 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5270 | AUH | 24.4487 | 54.59514 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5730 | AUH | 24.4957 | 54.366566 | Existing | ibs | Possible | 4-5 month | AUH6005 | 54570 | 2023 scope | 54570 | Y2024 fiber scope |  | 54570 | 4-5 month
| IAD5486 | AUH | 24.4766 | 54.365194 | Existing | ibs | Possible | 4-5 month | AUH6003 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5338 | AUH | 24.4827 | 54.357054 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6003 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5320 | AUH | 24.5005 | 54.371276 | Existing | ibs | Possible | #N/A | 0 | 251197.2 |  |  | stay in MW
| IAD5127 | AUH | 24.4208 | 54.441844 | Existing | ibs | Possible | 4-5 month | AUH1219 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5741 | AUH | 24.4982 | 54.373124 | Existing | ibs | Not Possible | 4-5 month | AUH6005 | 20000 | 2023 scope | 20000 | Y2024 fiber scope |  | 20000 | 4-5 month
| IAD5662 | AUH | 24.4914 | 54.378012 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5605 | AUH | 24.4894 | 54.369063 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5328 | AUH | 24.4905 | 54.362305 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 | 2023 scope | 20000 | Y2024 fiber scope
| IAD5748 | AUH | 24.5387 | 54.407628 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| IAD5560 | AUH | 24.4593 | 54.38039 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| IAD5358 | AUH | 24.4308 | 54.43531 | Existing | ibs | Possible | 7-8 month | AUH1218 | 130928.4 |  | 130928.4 | Y2024 fiber scope
| IAD5585 | AUH | 24.4672 | 54.385426 | Existing | ibs | Possible | 4-5 month | AUH DC | 10000 | 2023 scope | 10000 | Y2024 fiber scope |  | 10000 | 4-5 month
| IAD5735 | AUH | 24.485 | 54.354158 | Existing | ibs | Possible | 4-5 month | AUH6003 | 78855.12 |  | 78855.12 | Y2024 fiber scope
| IAD5269 | AUH | 24.4433 | 54.589247 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0438 | AUH | 24.4961 | 54.365741 | Existing | ibs | Possible | 4-5 month | AUH6005 | 72213.12 |  | 72213.12 | Y2024 fiber scope |  | 72213.12 | 4-5 month
| IAD5431 | AUH | 24.4541 | 54.338766 | Existing | ibs | Possible | 4-5 month | AUH1314 | 36019.86 |  | 36019.86 | Y2024 fiber scope
| IAD5738 | AUH | 23.6764 | 53.7015 | Existing | ibs | Possible | 4-5 month | AUH2938 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5721 | AUH | 24.4231 | 54.419992 | Existing | ibs | Possible | 4-5 month | AUH1218 | 42000 | 2023 scope | 42000 | Y2024 fiber scope |  | 42000 | 4-5 month
| IAD5529 | AUH | 24.4962 | 54.381075 | Existing | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5366 | AUH | 24.4916 | 54.600414 | Existing | ibs | Possible | 4-5 month | Khazna DC | 20000 |  | 20000 | Y2024 fiber scope
| IAD5677 | AUH | 24.507 | 54.376693 | Existing | ibs | Possible | 8-12 month | AUH6005 | 181197 |  | 181197 | Y2024 fiber scope
| AUH0987 | AUH | 24.481 | 54.321804 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH1314 |  |  | 0 | Y2024 fiber scope
| AUH0985 | AUH | 24.4813 | 54.321821 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH1314 |  |  | 0 | Y2024 fiber scope
| AUH0986 | AUH | 24.481 | 54.321804 | Existing | ibs | Possible | 4-5 month | AUH1314 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5680 | AUH | 24.4942 | 54.38277 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5403 | AUH | 24.466 | 54.373807 | Existing | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
| IAD5263 | AUH | 24.4449 | 54.586397 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5149 | AUH | 24.4292 | 54.436973 | Existing | ibs | Possible | 7-8 month | AUH1218 | 86563.08 |  | 86563.08 | Y2024 fiber scope
| IAD5253 | AUH | 24.4431 | 54.585918 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5733 | AUH | 24.4419 | 54.580414 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5819 | AUH | 24.4668 | 54.384886 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| IAD5631 | AUH | 24.482 | 54.350771 | Existing | ibs | Possible | 7-8 month | AUH6003 | 115855.92 |  | 115855.92 | Y2024 fiber scope
| IAD5262 | AUH | 24.4449 | 54.586994 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5865 | AUH | 24.4534 | 54.61388 | Existing | ibs | Possible | 4-5 month | Khazna DC | 20000 |  | 20000 | Y2024 fiber scope
| IAD5264 | AUH | 24.4442 | 54.584727 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5476 | AUH | 24.4728 | 54.347985 | Existing | ibs | Possible | 7-8 month | AUH6003 | 84408.48 |  | 84408.48 | Y2024 fiber scope
| IAD5265 | AUH | 24.4471 | 54.593398 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5268 | AUH | 24.4518 | 54.608529 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5841 | AUH | 24.4692 | 54.338111 | Existing | ibs | Tabreed | 4-5 month | AUH6003 | 50000 |  | 50000 | Y2024 fiber scope
| IAD5364 | AUH | 24.4451 | 54.574677 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5391 | AUH | 24.5051 | 54.375152 | Existing | ibs | Possible | 4-5 month | AUH6005 | 37179 |  | 37179 | Y2024 fiber scope
| IAD5840 | AUH | 23.9111 | 52.802119 | Existing | ibs | OSP Ready | OSP Ready | AUH3148 |  |  | 0 | Y2024 fiber scope
| IAD5461 | AUH | 24.4702 | 54.340753 | Existing | ibs | Tabreed | 4-5 month | AUH6003 | 50000 |  | 50000 | Y2024 fiber scope
| IAD5498 | AUH | 24.4953 | 54.370187 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5720 | AUH | 24.4907 | 54.363931 | Existing | ibs | Possible | 7-8 month | AUH6005 | 145621.8 |  | 145621.8 | Y2024 fiber scope
| IAD5878 | AUH | 24.4427 | 54.581421 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5912 | AUH | 24.4451 | 54.587443 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5340 | AUH | 24.5204 | 54.435564 | Existing | ibs | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| IAD5949 | AUH | 24.4171 | 54.440300 | Existing | ibs | Possible | #N/A | 0 | 65856.24 | Dependent on AUH0785 |  | stay in MW
| IAD5663 | AUH | 24.4751 | 54.349701 | Existing | ibs | Possible | 7-8 month | AUH6003 | 140363.28 |  | 140363.28 | Y2024 fiber scope
| IAD5861 | AUH | 24.8187 | 54.656422 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| IAD5345 | AUH | 24.4896 | 54.617654 | Existing | ibs | Exact location is required | #N/A | 0 |  |  |  | stay in MW
| IAD5932 | AUH | 24.4744 | 54.347273 | Existing | ibs | Possible | 4-5 month | AUH6003 | 57717.36 |  | 57717.36 | Y2024 fiber scope
| IAD5343 | AUH | 24.4896 | 54.617654 | Existing | ibs | Exact location is required | #N/A | 0 |  |  |  | stay in MW
| IAD5882 | AUH | 24.4441 | 54.590312 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5881 | AUH | 24.4521 | 54.609754 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5892 | AUH | 24.351 | 54.7136 | Existing | ibs | OSP Provisioned | 4-5 month | AUH1416 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5952 | AUH | 24.5377 | 54.409937 | Existing | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
| IAD5873 | AUH | 24.4497 | 54.393044 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH DC |  |  | 0 | Y2024 fiber scope
| IAD5258 | AUH | 24.4433 | 54.586452 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5947 | AUH | 24.4416 | 54.580850 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5485 | AUH | 24.4856 | 54.366536 | Existing | ibs | Possible | 4-5 month | AUH6005 | 78174.72 | dependent on IAD5584 | 78174.72 | Y2024 fiber scope
| IAD5808 | AUH | 24.4853 | 54.3544129 | Existing | ibs | Not Possible | #N/A | 0 | 0 | same Location of IAD5735 |  | stay in MW
| IAD5768 | AUH | 23.7806 | 53.5643 | Existing | ibs | OSP Provisioned | 4-5 month | AUH2938 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5347 | AUH | 24.4896 | 54.617654 | Existing | ibs | Exact location is required | #N/A | 0 |  |  |  | stay in MW
| IAD5788 | AUH | 24.4483 | 54.604995 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5789 | AUH | 24.4482 | 54.604458 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5962 | AUH | 24.4424 | 54.578879 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5830 | AUH | 24.4437 | 54.590566 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5951 | AUH | 24.4443 | 54.589451 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5943 | AUH | 24.4411 | 54.58014 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5948 | AUH | 24.4435 | 54.580210 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5465 | AUH | 24.4264 | 54.407617 | Existing | ibs | OSP Provisioned | 4-5 month | AUH1218 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
| IAD5970 | AUH | 24.4824 | 54.352426 | Existing | ibs | Possible | 7-8 month | AUH6003 | 149428.8 |  | 149428.8 | Y2024 fiber scope
| IAD5522 | AUH | 24.4423 | 54.580767 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5791 | AUH | 24.4406 | 54.576771 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5980 | AUH | 24.4212 | 54.47281 | Existing | ibs | Possible | 4-5 month | AUH1219 | 20000 |  | 20000 | Y2024 fiber scope
| IAD5924 | AUH | 24.4498 | 54.609977 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5969 | AUH | 24.4215 | 54.459719 | Existing | ibs | Possible | 8-12 month | AUH1219 | 166672.08 | dependent on IAD5335 | 166672.08 | Y2024 fiber scope
| IAD5807 | AUH | 24.4199 | 54.442110 | Existing | ibs | Tabreed | 4-5 month | AUH1219 | 50000 | Same location of IAD0826 | 50000 | Y2024 fiber scope
| IAD5890 | AUH | 24.4462 | 54.598425 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5732 | AUH | 24.441 | 54.578666 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5267 | AUH | 24.4475 | 54.598718 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5686 | AUH | 24.4907 | 54.370941 | Existing | ibs | Possible | 7-8 month | AUH6005 | 119944.8 |  | 119944.8 | Y2024 fiber scope
| IAD5966 | AUH | 24.4429 | 54.579548 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AAN0113 | AUH | 24.1859 | 55.780282 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AAN6001 |  |  | 0 | Y2024 fiber scope
| IAD5889 | AUH | 24.4409 | 54.579559 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0001 | AUH | 24.4654 | 54.334555 | Existing | ibs | Possible | 4-5 month | AUH6003 | 20000 |  | 20000 | Y2024 fiber scope
| IAD0988E | AUH | 24.7929 | 54.711548 | Existing | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
| IAD5999 | AUH | 24.5218 | 54.432285 | Existing | ibs | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
| IAD5166 | AUH | 24.444 | 54.591633 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5256 | AUH | 24.4533 | 54.609863 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5643 | AUH | 24.4464 | 54.589494 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5359 | AUH | 24.4351 | 54.467212 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| IAD5933 | AUH | 24.4425 | 54.577308 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5786 | AUH | 24.4447 | 54.585579 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5976 | AUH | 24.5661 | 54.457889 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| IAD5974 | AUH | 24.562 | 54.459586 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| AUH0050 | AUH | 24.5037 | 54.4156 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| AUH0051 | AUH | 24.5037 | 54.4156 | Existing | ibs | Not Possible | #N/A | 0 |  |  |  | stay in MW
| IAD5888 | AUH | 24.4301 | 54.433679 | Existing | ibs | Possible | 4-5 month | AUH1218 | 62292.24 | Dependent on IAD5240 | 62292.24 | Y2024 fiber scope
| AUH0075 | AUH | 24.4712 | 54.34566 | Existing | ibs | Possible | 4-5 month | AUH6003 | 20000 | 0 | 20000 | Y2024 fiber scope
| IAD0986B | AUH | 24.189 | 54.46595 | Existing | ibs | Possible | 4-5 month | AUH2921 | 20000 | 0 | 20000 | Y2024 fiber scope
| AUH0007 | AUH | 24.4297 | 54.434015 | Existing | ibs | Possible | 4-5 month | AUH1218 | 16841.52 | Dependent on IAD5888 | 16841.52 | Y2024 fiber scope
| IAD5855 | AUH | 24.4412 | 54.579198 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| AUH0065 | AUH | 24.4409 | 54.578107 | Existing | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
| IAD5826 | AUH | 24.4946 | 54.377658 | Existing | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-4615 | AUH0078 | AUH | 24.2649 | 54.458765 | New | ibs | OSP Ready | OSP Ready | AUH2536 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-4282 | IAD5165 | AUH | 24.4868 | 54.363957 | New | ibs | OSP Ready | OSP Ready | AUH6003 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-1259 | IAD5168 | AUH | 24.4466 | 54.588999 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-0716 | IAD5167 | AUH | 24.443 | 54.586736 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-20-1619 | IAD5839 | AUH | 24.4904 | 54.360944 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1650 | IAD5421 | AUH | 24.4802 | 54.372696 | New | ibs | OSP Ready | OSP Ready | AUH2055 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1605 | IAD5389 | AUH | 24.4204 | 54.463101 | New | ibs | Possible | 4-5 month | AUH1219 | 63549.36 | Dependent on IAD5586 | 63549.36 | Y2024 fiber scope
IBS-FTK-19-1115 | IAD5261 | AUH | 24.446 | 54.597594 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-22-2030 | AUH0086 | AUH | 24.7028 | 54.79035 | New | ibs | Possible | 4-5 month | KIZAD DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-0012 | IAD5954 | AUH | 24.3323 | 54.625806 | New | ibs | OSP Ready | OSP Ready | AUH2134 |  |  | 0 | Y2024 fiber scope
IBS-SS-20-0191 | IAD5543 | AUH | 24.4651 | 54.385009 | New | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-19-1223 | IAD5641 | AUH | 24.4913 | 54.381239 | New | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-19-1194 | IAD5398 | AUH | 24.4966 | 54.374074 | New | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-18-0335 | AAN0041 | AUH | 24.2005 | 55.676094 | New | ibs | Possible | 4-5 month | AAN6001 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-22-4624 | AUH0029 | AUH | 24.7139 | 54.877890 | New | ibs | Possible | 4-5 month | KIZAD DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-22-4535 | AUH0011 | AUH | 24.4504 | 54.612533 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-3430 | IAD5033 | AUH | 24.4047 | 54.596096 | New | ibs | Possible | 4-5 month | Khazna DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-22-1776 | IAD5963 | AUH | 24.5017 | 54.376426 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-22-1374 | IAD5965 | AUH | 24.4996 | 54.373355 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-1091 | AUH0094 | AUH | 24.4815 | 54.37246 | New | ibs | Possible | 4-5 month | AUH6005 | 44717.16 | dependent on Proposed route of IBS-SS-22-1630 | 44717.16 | Y2024 fiber scope
IBS-FTK-22-0968 | IAD5981 | AUH | 24.4423 | 54.581685 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
IBS-FTK-22-0159 | IAD5957 | AUH | 24.4443 | 54.583191 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
IBS-FTK-21-3842 | AUH0035 | AUH | 24.4721 | 54.368118 | New | ibs | Possible | 4-5 month | AUH6003 | 20000 | 0 | 20000 | Y2024 fiber scope
IBS-FTK-21-3818 | AUH0033 | AUH | 24.4471 | 54.592913 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
IBS-FTK-21-3616 | IAD5905 | AUH | 24.3262 | 54.532083 | New | ibs | Possible | 4-5 month | AUH6501 | 20000 | 0 | 20000 | Y2024 fiber scope
IBS-FTK-21-3577 | IAD5880 | AUH | 24.4955 | 54.375290 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  | 0 | 0 | Y2024 fiber scope
IBS-FTK-21-3321 | IAD5858 | AUH | 24.4229 | 54.45419 | New | ibs | Possible | 4-5 month | AUH1219 | 20000 | 0 | 20000 | Y2024 fiber scope
IBS-FTK-21-3111 | AAN0134 | AUH | 24.2264 | 55.758197 | New | ibs | OSP Ready | OSP Ready | AAN6001 |  | 0 | 0 | Y2024 fiber scope
IBS-FTK-21-3052 | AUH0034 | AUH | 24.4476 | 54.596064 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
IBS-FTK-21-0804 | IAD5834 | AUH | 24.4436 | 54.576193 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
IBS-FTK-20-1675 | IAD5926 | AUH | 24.4912 | 54.358588 | New | ibs | Possible | 4-5 month | AUH6005 | 24206.16 | dependent on the proposed route of IBS-FTK-22-1087 | 24206.16 | Y2024 fiber scope
IBS-FTK-20-0113 | IAD5520 | AUH | 24.4438 | 54.589311 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 | 0 | 50000 | Y2024 fiber scope
IBS-FTK-19-1612 | IAD5632 | AUH | 24.5002 | 54.372633 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 | 0 | 20000 | Y2024 fiber scope
IBS-FTK-19-1611 | IAD5634 | AUH | 24.5021 | 54.373711 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  | 0 | 0 | Y2024 fiber scope
IBS-FTK-19-1552 | IAD5124 | AUH | 24.4043 | 54.472918 | New | ibs | Possible | 4-5 month | AUH1219 | 20000 | 0 | 20000 | Y2024 fiber scope
IBS-SS-20-0271 | IAD5709 | AUH | 24.492 | 54.375955 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  | 0 | 0 | Y2024 fiber scope
IBS-SS-22-5010 | AUH0043 | AUH | 24.43 | 54.463462 | New | ibs | OSP Ready | OSP Ready | AUH1219 |  | 0 | 0 | Y2024 fiber scope
IBS-SS-22-4499 | AUH0100 | AUH | 24.5181 | 54.44064 | New | ibs | Taawun | to be shared by OSP Team | AUH2251 |  | 0 | 0 | Y2024 fiber scope
IBS-SS-22-2674 | IAD5201 | AUH | 24.4207 | 54.46018 | New | ibs | Possible | 4-5 month | AUH1219 | 75798.48 | Same Location of IAD5969 | 75798.48 | Y2024 fiber scope
IBS-SS-21-1227 | IAD5885 | AUH | 24.1008 | 52.654670 | New | ibs | OSP Provisioned | 4-5 month | AUH2911 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-21-1226 | IAD5886 | AUH | 23.8996 | 52.805360 | New | ibs | OSP Provisioned | 4-5 month | AUH2898 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-21-0736 |  | AUH | 24.4623 | 54.381692 | New | ibs | OSP Provisioned | 4-5 month | AUH DC | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-21-0357 | AUH0044 | AUH | 24.4587 | 54.325717 | New | ibs | OSP Provisioned | 4-5 month | AUH1314 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-21-0310 |  | AUH | 24.4947 | 54.378916 | New | ibs | Possible | 4-5 month | AUH6005 | 59408.76 |  | 59408.76 | Y2024 fiber scope
IBS-SS-21-0309 |  | AUH | 24.2132 | 55.667430 | New | ibs | OSP Ready | OSP Ready | AAN2049 |  |  | 0 | Y2024 fiber scope
IBS-SS-21-0192 | AAN0120 | AUH | 24.1838 | 55.735236 | New | ibs | Possible | 4-5 month | AAN6001 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-21-0167 | IAD5805 | AUH | 24.4971 | 54.365216 | New | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-20-1841 | IAD5794 | AUH | 24.3371 | 54.588646 | New | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH6501 |  |  | 0 | Y2024 fiber scope
IBS-SS-20-0218 |  | AUH | 24.4383 | 54.4125 | New | ibs | Possible | 4-5 month | AUH1341 | 69355.8 |  | 69355.8 | Y2024 fiber scope
IBS-SS-20-0123 |  | AUH | 24.4569 | 54.3937333 | New | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-19-560 | IAD5795 | AUH | 24.5008 | 54.794794 | New | ibs | Site survey to confirm that the scope is internal connection | to be shared by OSP Team | AUH2291 |  |  | 0 | Y2024 fiber scope
IBS-SS-19-1229 | IAD5868 | AUH | 24.5015 | 54.377832 | New | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-19-119 | IAD5199 | AUH | 24.4302 | 54.641835 | New | ibs | OSP Ready | OSP Ready | AUH2131 |  |  | 0 | Y2024 fiber scope
IBS-SS-18-0364 | IAD5139 | AUH | 24.4616 | 54.323536 | New | ibs | OSP Ready | OSP Ready | AUH1314 |  |  | 0 | Y2024 fiber scope
IBS-FTK-23-0782 | AUH0096 | AUH | 24.4463 | 54.381451 | New | ibs | OSP Ready | OSP Ready | AUH2336 |  |  | 0 | Y2024 fiber scope
IBS-FTK-23-0265 | AUH0069 | AUH | 24.4602 | 54.598858 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-FTK-23-0124 | AUH0042 | AUH | 24.443 | 54.57872 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-4993 | AUH0030 | AUH | 24.447 | 54.589696 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-4991 | AUH0024 | AUH | 24.4472 | 54.590455 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-4652 | AUH0068 | AUH | 24.46 | 54.598135 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-4621 | AUH0025 | AUH | 24.4794 | 54.371346 | New | ibs | Possible | 4-5 month | AUH6005 | 34000.56 | dependent on the proposed route of IBS-FTK-22-4619 | 34000.56 | Y2024 fiber scope
IBS-FTK-22-4620 | AUH0041 | AUH | 24.4404 | 54.577444 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-4619 | AUH0026 | AUH | 24.4798 | 54.371933 | New | ibs | Possible | 4-5 month | AUH6005 | 75963.84 |  | 75963.84 | Y2024 fiber scope
IBS-FTK-22-4574 | AUH0012 | AUH | 24.4461 | 54.597108 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-2017 | IAD5910 | AUH | 24.4441 | 54.580616 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-22-1386 | IAD5964 | AUH | 24.5026 | 54.375626 | New | ibs | Possible | 4-5 month | AUH6005 | 45941.46 |  | 45941.46 | Y2024 fiber scope
IBS-FTK-21-3821 | IAD5917 | AUH | 24.4516 | 54.612595 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3820 | IAD5960 | AUH | 24.4844 | 54.374333 | New | ibs | Possible | 4-5 month | AUH6005 | 61717.44 |  | 61717.44 | Y2024 fiber scope
IBS-FTK-21-3690 | IAD5985 | AUH | 24.4613 | 54.607406 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-FTK-21-3615 | IAD5938 | AUH | 24.4485 | 54.608922 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3444 | IAD5872 | AUH | 24.4546 | 54.615515 | New | ibs | OSP Ready | OSP Ready | AUH1410 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-1886 | IAD5787 | AUH | 24.4444 | 54.585095 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-20-1609 | IAD5907 | AUH | 24.4899 | 54.355087 | New | ibs | OSP Ready | OSP Ready | AUH6003 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-1579 | IAD5906 | AUH | 24.4696 | 54.342621 | New | ibs | OSP Ready | OSP Ready | AUH6003 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-1389 | IAD5642 | AUH | 24.4903 | 54.371569 | New | ibs | Possible | 4-5 month | AUH6005 | 49614.36 |  | 49614.36 | Y2024 fiber scope
IBS-FTK-20-1050 | IAD5592 | AUH | 24.4958 | 54.374267 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-0998 | IAD5430 | AUH | 24.4893 | 54.368988 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-663 | IAD5235 | AUH | 24.4756 | 54.37271 | New | ibs | OSP Ready | OSP Ready | AUH1336 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1602 | IAD5400 | AUH | 24.4735 | 54.346902 | New | ibs | OSP Provisioned | 4-5 month | AUH6003 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-FTK-19-1495 | IAD5392 | AUH | 24.4759 | 54.351397 | New | ibs | OSP Provisioned | 4-5 month | AUH6003 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-23-1473 |  | AUH | 24.1326 | 51.63075 | New | ibs | Possible | 4-5 month | AUH2920 | 12643.9344 |  | 12643.9344 | Y2024 fiber scope
IBS-SS-23-1472 |  | AUH | 24.5285 | 54.40381 | New | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1460 |  | AUH | 24.4924 | 54.37317 | New | ibs | Possible | 4-5 month | AUH6005 | 46148.16 |  | 46148.16 | Y2024 fiber scope
IBS-SS-23-1454 |  | AUH | 24.4457 | 54.59525 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-23-1432 |  | AUH | 24.4852 | 54.598016 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1431 |  | AUH | 24.4852 | 54.598016 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1430 |  | AUH | 24.4852 | 54.598016 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1429 |  | AUH | 24.4852 | 54.598016 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1358 |  | AUH | 24.3174 | 54.53073 | New | ibs | Possible | 4-5 month | AUH6501 | 31358.616 |  | 31358.616 | Y2024 fiber scope
IBS-SS-23-1336 |  | AUH | 24.4852 | 54.598016 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1331 |  | AUH | 24.501 | 54.6256 | New | ibs | Taawun | to be shared by OSP Team | AUH2439 |  |  | 0 | Y2024 fiber scope
IBS-SS-23-1182 |  | AUH | 24.4515 | 54.61266 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-23-1152 |  | AUH | 24.4442 | 54.58556 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-23-1141 |  | AUH | 24.4956 | 54.37942 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-23-1138 |  | AUH | 24.4513 | 54.61195 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-23-1092 |  | AUH | 24.4988 | 54.37681 | New | ibs | Possible | 4-5 month | AUH6005 | 81048.66 |  | 81048.66 | Y2024 fiber scope
IBS-SS-23-1027 |  | AUH | 24.4773 | 54.37091 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-23-1001 |  | AUH | 24.49 | 54.379326 | New | ibs | Possible | 4-5 month | AUh6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-23-0867 |  | AUH | 24.6161 | 54.73137 | New | ibs | Possible | 4-5 month | KIZAD DC | 71931.6 |  | 71931.6 | Y2024 fiber scope
IBS-SS-23-0717 |  | AUH | 24.447 | 54.59205688 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-23-0716 |  | AUH | 24.4475 | 54.591003 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-23-0716 |  | AUH | 24.4475 | 54.591003 | New | ibs | Tabreed | 4-5 month | Khazna DC |  |  | 0 | Y2024 fiber scope
IBS-SS-23-0715 |  | AUH | 24.3512 | 54.650711 | New | ibs | Possible | 4-5 month | AUH1416 | 66296.64 |  | 66296.64 | Y2024 fiber scope
IBS-SS-23-0714 |  | AUH | 24.4475 | 54.59119 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-22-4613 |  | AUH | 24.5402 | 54.399355 | New | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-SS-22-4394 |  | AUH | 24.5358 | 54.40386 | New | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-SS-22-4313 |  | AUH | 23.6599 | 53.70364 | New | ibs | Possible | 4-5 month | AUH2938 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-3144 |  | AUH | 24.496 | 54.600205 | New | ibs | Possible | 4-5 month | AUH2410 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-3143 |  | AUH | 24.4459 | 54.592 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-SS-22-2032 |  | AUH | 24.5015 | 54.376635 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-1630 |  | AUH | 24.4816 | 54.37314 | New | ibs | Possible | 7-8 month | AUH6005 | 82705.44 |  | 82705.44 | Y2024 fiber scope
IBS-SS-22-0050 |  | AUH | 24.5337 | 54.40698 | New | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-SS-22-0049 |  | AUH | 24.5334 | 54.406947 | New | ibs | Taawun | to be shared by OSP Team | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-SS-22-0011 |  | AUH | 24.2296 | 55.737194 | New | ibs | OSP Ready | OSP Ready | OLD |  |  | 0 | Y2024 fiber scope
IBS-SS-21-1228 | AUH0022 | AUH | 24.0581 | 51.762000 | New | ibs | OSP Ready | OSP Ready | AUH2919 |  |  | 0 | Y2024 fiber scope
IBS-SS-21-0739 | AUH0014 | AUH | 24.0977 | 53.483113 | New | ibs | Possible | 4-5 month | AUH2908 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-21-0208 |  | AUH | 24.2056 | 55.679721 | New | ibs | Possible | 7-8 month | AAN6001 | 84009.24 |  | 84009.24 | Y2024 fiber scope
IBS-SS-21-0203 | AUH0015 | AUH | 24.1708 | 55.059798 | New | ibs | OSP Provisioned | 4-5 month | AUH5001 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-21-0194 | AUH0018 | AUH | 24.4964 | 54.934536 | New | ibs | OSP Provisioned | 4-5 month | AUH2291 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-20-1584 |  | AUH | 24.1974 | 55.677687 | New | ibs | OSP Ready | OSP Ready | OLD site |  |  | 0 | Y2024 fiber scope
IBS-SS-20-0230 |  | AUH | 24.4308 | 54.4639 | New | ibs | Possible | 4-5 month | AUH1219 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-19-1221 |  | AUH | 24.5029 | 54.372428 | New | ibs | Possible | 4-5 month | AUH6005 | 65775.12 |  | 65775.12 | Y2024 fiber scope
IBS-Hunt-23-0873 |  | AUH | 24.4988 | 54.376825 | New | ibs | Exact location is required | 0 | #N/A |  | Same Location of IBS-SS-23-1092 |  | MW 2024
IBS-Hunt-22-1458 |  | AUH | 24.4797 | 54.370069 | New | ibs | Possible | 4-5 month | AUH6005 | 42268.56 |  | 42268.56 | Y2024 fiber scope
IBS-FTK-23-1537 |  | AUH | 24.4032 | 54.590125 | New | ibs | Possible | 4-5 month | AUH2553 | 40455.96 |  | 40455.96 | Y2024 fiber scope
IBS-FTK-23-1074 |  | AUH | 24.4575 | 54.594613 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-2012 |  | AUH | 24.4465 | 54.589929 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3619 |  | AUH | 24.4848 | 54.628197 | New | ibs | Taawun | to be shared by OSP Team | AUH2410 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-1299 |  | AUH | 24.4459 | 54.595013 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-19-1653 | IAD5401 | AUH | 24.4854 | 54.352898 | New | ibs | OSP Ready | OSP Ready | AUH2018 |  |  | 0 | Y2024 fiber scope
IBS-SS-22-5155 | IAD5753 | AUH | 24.4074 | 54.505876 | New | ibs | Possible | 4-5 month | AUH6501 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-4597 | AUH0072 | AUH | 24.4814 | 54.355202 | New | ibs | Possible | 4-5 month | AUH6003 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-4592 | AUH0038 | AUH | 24.447 | 54.394344 | New | ibs | Possible | 4-5 month | AUH1341 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-4591 | AUH0037 | AUH | 24.4477 | 54.395333 | New | ibs | Possible | 4-5 month | AUH1341 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-3145 | AUH0063 | AUH | 24.4942 | 54.377133 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-22-0023 | IAD5941 | AUH | 24.3986 | 54.56586 | New | ibs | Possible | 4-5 month | AUH2553 | 81611.52 |  | 81611.52 | Y2024 fiber scope
IBS-SS-20-0221 | IAD5915 | AUH | 24.46 | 54.303518 | New | ibs | OSP Ready | OSP Ready | AUH1222 |  |  | 0 | Y2024 fiber scope
IBS-SS-20-0188 | IAD5625 | AUH | 24.4659 | 54.386143 | New | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-19-1352 | IAD5475 | AUH | 24.4842 | 54.36751 | New | ibs | Possible | 4-5 month | AUH6005 | 39203.04 |  | 39203.04 | Y2024 fiber scope
IBS-FTK-23-0140 | AUH0071 | AUH | 24.5205 | 54.447264 | New | ibs | Taawun | to be shared by OSP Team | AUH2251 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-5126 | AUH0046 | AUH | 24.4137 | 54.4652766 | New | ibs | Possible | 4-5 month | AUH1219 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-22-0002 | IAD5923 | AUH | 24.4494 | 54.608818 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3851 | IAD5927 | AUH | 24.4405 | 54.578805 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3846 | IAD5929 | AUH | 24.4462 | 54.580232 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3780 | IAD5902 | AUH | 24.4515 | 54.608006 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3685 | IAD5894 | AUH | 24.4428 | 54.582161 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3684 | IAD5887 | AUH | 24.4475 | 54.592792 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3656 | IAD5928 | AUH | 24.448 | 54.596585 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3614 | IAD5893 | AUH | 24.4486 | 54.609383 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3445 | IAD5833 | AUH | 24.4445 | 54.588762 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3260 | IAD5838 | AUH | 24.4463 | 54.599964 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3240 | IAD5871 | AUH | 24.4461 | 54.59449 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3228 | IAD5916 | AUH | 24.4431 | 54.588525 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3134 | IAD5836 | AUH | 24.4413 | 54.579684 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-3117 | IAD5837 | AUH | 24.4518 | 54.611777 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-2056 | IAD5856 | AUH | 24.4473 | 54.595353 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-1206 | IAD5835 | AUH | 24.4432 | 54.579141 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-1205 | IAD5832 | AUH | 24.4437 | 54.588833 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-21-0806 | IAD5831 | AUH | 24.4443 | 54.591338 | New | ibs | Tabreed | 4-5 month | Khazna DC | 50000 |  | 50000 | Y2024 fiber scope
IBS-FTK-20-1772 | IAD5908 | AUH | 24.4873 | 54.360769 | New | ibs | OSP Ready | OSP Ready | AUH2018 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-1352 | IAD5718 | AUH | 24.4902 | 54.362035 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-18-0797 | IAD0994A | AUH | 24.7794 | 54.73807 | New | ibs | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
IBS-FTK-18-0598 | IAD5128 | AUH | 24.5002 | 54.390022 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-18-0265 | IAD0992B | AUH | 24.5421 | 54.7954 | New | ibs | Site survey | 0 | 0 |  |  |  | MW 2024
IBS-SS-19-1240 | IAD5471 | AUH | 24.4938 | 54.361565 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-5136 | AUH0048 | AUH | 24.3974 | 54.558277 | New | ibs | Possible | 4-5 month | AUH2553 | 30051 |  | 30051 | Y2024 fiber scope
IBS-FTK-22-5090 | IAD5909 | AUH | 24.4707 | 54.345747 | New | ibs | Possible | 4-5 month | AUH6003 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-22-4490 | AUH0047 | AUH | 24.3986 | 54.567070 | New | ibs | Possible | 4-5 month | AUH2553 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-20-1862 | IAD5845 | AUH | 24.497 | 54.374035 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-20-1690 | IAD5869 | AUH | 24.5023 | 54.37699 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-20-1051 | IAD5516 | AUH | 24.4962 | 54.374022 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1622 | IAD5390 | AUH | 24.4914 | 54.368293 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1613 | IAD5635 | AUH | 24.5005 | 54.375246 | New | ibs | OSP Ready | OSP Ready | AUH5635 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1557 | IAD5397 | AUH | 24.4311 | 54.622142 | New | ibs | OSP Ready | OSP Ready | Khazna DC |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1505 | IAD5377 | AUH | 24.4664 | 54.386211 | New | ibs | Possible | 4-5 month | AUH DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-19-1448 | AUH0060 | AUH | 24.4973 | 54.374592 | New | ibs | OSP Ready | OSP Ready | AUH6005 |  |  | 0 | Y2024 fiber scope
IBS-FTK-18-0208 | IAD5305 | AUH | 23.6592 | 53.704342 | New | ibs | OSP Provisioned | 4-5 month | AUH2938 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-SS-20-0219 | IAD5639 | AUH | 24.4206 | 54.4279 | New | ibs | Possible | 4-5 month | AUH1219 | 20000 |  | 20000 | Y2024 fiber scope
IBS-SS-19-89 | IAD5673 | AUH | 24.4725 | 54.341260 | New | ibs | OSP Ready | OSP Ready | AUH6003 |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1674 | IAD0988D | AUH | 24.8005 | 54.64395 | New | ibs | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
IBS-FTK-19-1673 | IAD0988A | AUH | 24.8026 | 54.642984 | New | ibs | Taawun | to be shared by OSP Team | KIZAD DC |  |  | 0 | Y2024 fiber scope
IBS-FTK-18-0166 | AAN5397A | AUH | 24.2213 | 55.7108 | New | ibs | OSP Ready | OSP Ready | AAN6001 |  |  | 0 | Y2024 fiber scope
IBS-FTK-22-4397 |  | AUH | 24.8733 | 55.072836 | New | ibs | Not Possible | n/a | #N/A |  | Dubai Region |  | MW 2024
IBS-FTK-18-1072 | IAD0994D | AUH | 24.485 | 54.380038 | New | ibs | OSP Provisioned | 4-5 month | AUH6005 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-FTK-18-0449 | IAD0994C | AUH | 24.485 | 54.380038 | New | ibs | Possible | 4-5 month | AUH6005 | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-19-1583 | IAD0996C | AUH | 24.3461 | 54.464808 | New | ibs | OSP Provisioned | 4-5 month | AUH6501 | 30000 | OSP provisioned cost is depended on the availability of the internal network inside the plot | 30000 | Y2024 fiber scope
IBS-FTK-19-1128 | IAD0996B | AUH | 24.4453 | 54.610908 | New | ibs | Possible | 4-5 month | Khazna DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-19-1127 | IAD0996A | AUH | 24.445 | 54.609788 | New | ibs | Possible | 4-5 month | Khazna DC | 20000 |  | 20000 | Y2024 fiber scope
IBS-FTK-18-0179 | IAD0991A | AUH | 24.4224 | 54.449635 | New | ibs | OSP Ready | OSP Ready | AUH1222 |  |  | 0 | Y2024 fiber scope
| AUH1896 | AUH | 22.9843 | 53.796 | New | OD | possible | 4-5 month |  | 210000 |  |  | MW 2024 | additional
| AUH6346 | AUH | 24.3269 | 54.2136 | New | OD | Not Possible | [5 empty] | MW 2024 | additional
| AAN3734 | AUH | 24.216 | 55.7592 | New | OD | Possible | 3-4 months |  | 40000 |  | 40000 | Y2024 fiber scope | additional
| AUH3185 | AUH | 24.5198 | 54.9656 | Existing | OD | Possible | 7-8 month |  | 228157.78 |  |  | stay in MW | additional
| AUH3501 | AUH | 24.331037° | 54.590068° | Existing | OD | Possible | 7-8 month |  | 346067.48 |  |  | stay in MW | additional
| IAD0992B | AUH | 24.5421 | 54.7954 | Existing | ibs | Possible | 7-8 month |  | 252527.12 |  |  | stay in MW | additional
| AUH0924 | AUH | 24.412217° | 54.492036° | Existing | ibs | Possible | 4-5 month |  | 40155.94 |  | 40155.94 | Y2024 fiber scope | additional
| AUH1816 | AUH | 24.5026 | 54.3804 | New | OD | Possible | 4-5 months |  | 100000 |  | 100000 | Y2024 fiber scope | additional
| AAN3235 | AUH | 24.3025 | 55.6738 | New | OD | Not Possible | [5 empty] | MW 2024 | additional
| AUH2472 | AUH |  |  | New | OD | Not Possible | [5 empty] | MW 2024 | additional
| AUH2834 | AUH |  |  | New | OD | [6 empty] | MW 2024 | additional
| AUH3901 | AUH |  |  | New | OD | [6 empty] | MW 2024 | additional
| AUH3991 | AUH |  |  | New | OD | [6 empty] | MW 2024 | additional
| AUH6473 | AUH | 24.2182 | 54.134033° | New | OD | Not Possible |  |  |  | more than 15Km away from existing fiber network |  | MW 2024 | additional
| AUH2875 | AUH | 24.029630° | 53.095220° | New | OD | [6 empty] | MW 2024 | additional
| AUH2876 | AUH | 24.0529° | 52.914640° | New | OD | [6 empty] | MW 2024 | additional
| AUH0110 | AUH | 24.6161 | 54.7314 | New | ibs |  | 3-4 months |  | 85000 |  |  | Y2024 fiber scope
| AAN2443 | AUH | 24.1882 | 55.7809 | New | OD |  |  |  |  | Civil completed |  | Y2024 fiber scope | added (carry forward from Y2023)
| AAN3169 | AUH | 24.2232 | 55.4833 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AAN3253 | AUH | 24.158 | 55.6547 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AAN3261 | AUH | 24.2025 | 55.7373 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AAN3328 | AUH | 24.0949 | 55.4622 | New | OD |  |  |  | 1680099.31 | VVIP site survey required- initial cost provided |  | MW 2024 | added (carry forward from Y2023)
| AAN3371 | AUH | 24.304 | 55.5154 | New | OD |  |  |  | 1060000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AAN3436 | AUH | 24.3349 | 55.0962 | New | OD |  |  |  | 1800000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AAN3572 | AUH | 24.5639 | 55.3962 | New | OD |  |  |  | 1920000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AAN3622 | AUH | 23.8401 | 55.4758 | New | OD |  |  |  | 820000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AAN3627 | AUH | 24.2323 | 55.7618 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AAN3633 | AUH | 24.1364 | 55.648 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AAN3644 | AUH | 24.101 | 55.3162 | New | OD |  |  |  | 475000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AAN3645 | AUH | 23.9308 | 55.4395 | New | OD |  |  |  | 535000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AAN3673 | AUH | 24.1934 | 55.6497 | New | OD |  |  |  |  | Civil in progress |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUG6219 | AUH | 23.9697 | 52.2587 | New | OD |  |  |  | 270000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUG6237 | AUH | 24.4149 | 54.3683 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUG6238 | AUH | 24.3957 | 54.3989 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUG6241 | AUH | 24.4026 | 54.4169 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1080 | AUH | 24.4801 | 54.6045 | New | OD |  |  |  |  | Civil completed |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1148 | AUH | 24.8273 | 54.6678 | New | OD |  |  |  | 30000 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1896 | AUH | 22.9843 | 53.796 | New | OD |  |  |  | 240000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH2271 | AUH | 24.5285 | 54.9922 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH2278 | AUH | 24.4393 | 54.4642 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH2472 | AUH | 24.3492 | 54.342 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH2645 | AUH | 24.5405 | 54.8341 | New | OD |  |  |  | 20000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH2721 | AUH | 24.4337 | 54.6202 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH2834 | AUH | 24.3794 | 54.3467 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH2874 | AUH | 24.1182 | 52.5315 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3059 | AUH | 24.4214 | 54.5178 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3089 | AUH | 24.5126 | 54.7841 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3151 | AUH | 24.4126 | 54.486 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3152 | AUH | 24.4111 | 54.4858 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3167 | AUH | 24.1975 | 54.7319 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3185 | AUH | 24.5197 | 54.9656 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3247 | AUH | 24.1869 | 51.9901 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3455 | AUH | 24.544 | 54.8552 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3506 | AUH | 23.8958 | 53.7393 | New | OD |  |  |  | 3470000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3671 | AUH | 23.6832 | 53.6384 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3759 | AUH | 23.5903 | 53.3258 | New | OD |  |  |  | 2250000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3779 | AUH | 24.5172 | 54.0259 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3782 | AUH | 24.5006 | 54.5732 | New | OD |  |  |  |  | not possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3901 | AUH | 24.5973 | 54.9326 | New | OD |  |  |  | 464000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3903 | AUH | 24.4831 | 54.6123 | New | OD |  |  |  | 102000 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3981 | AUH | 22.9594 | 53.8197 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3988 | AUH | 23.9383 | 53.6955 | New | OD |  |  |  | 2067286.92 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3991 | AUH | 23.7942 | 53.643 | New | OD |  |  |  | 1800000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6158 | AUH | 24.331 | 54.4575 | New | OD |  |  |  | 595000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6170 | AUH | 24.5377 | 54.4736 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6172 | AUH | 24.532 | 54.4661 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6174 | AUH | 24.5306 | 54.4838 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6178 | AUH | 24.521 | 54.4959 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6180 | AUH | 24.5242 | 54.4916 | New | OD |  |  |  |  | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6342 | AUH | 24.6081 | 54.1504 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6367 | AUH | 22.9742 | 53.8823 | New | OD |  |  |  | 1400000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6450 | AUH | 24.3163 | 53.8025 | New | OD |  |  |  |  | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6452 | AUH | 22.9003 | 54.3362 | New | OD |  |  |  |  | OSP Ready |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6504 | AUH | 24.4187 | 54.4807 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6537 | AUH | 24.4181 | 54.4207 | New | OD |  |  |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6559 | AUH | 24.4348 | 54.4682 | New | OD |  | 3-4 months |  | 140000 | possible but inside Mina Palace where access is not guaranteed |  | MW 2024 | added (carry forward from Y2023)
| AUH0113 | AUH | 24.3156 | 54.5337 | New | ibs |  |  |  | 210000 | Possible |  | MW 2024 | additional
| AUH6568 | AUH | 24.3553 | 54.5025 | New | OD |  |  |  | 20000 | Possible | replacement of AUG4439 | Y2024 fiber scope | additional
| AUH6070 | AUH | 24.506524° | 54.390338° | New | OD |  |  |  | 0 | Not Possible in 2024 |  | MW 2024 | added (carry forward from Y2023)
| AUH3767 | AUH | 24.407630 | 54.710920 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6625 | AUH | 24.316030 | 54.690930 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3693 | AUH | 24.781340° | 54.908440° | New | OD |  | 5-6 month |  | 45000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6569 | AUH | 24.34735 | 54.48821 | New | OD |  |  |  | 0 | OSP Ready under AUG4442 |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3972 | AUH | 24.449176 | 55.04104 | New | OD |  | 3-4 month |  | 34681.08 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3412 | AUH | 24.345115 | 54.670096 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3034 | AUH | 24.617375 | 55.071867 | New | OD |  | 11 month |  | 1464333.82 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3414 | AUH | 24.327614 | 54.647089 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3416 | AUH | 24.355015 | 54.667817 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1353 | AUH | 24.323706 | 54.711624 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3135 | AUH | 24.36447 | 54.67562 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3427 | AUH | 24.321086 | 54.649753 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3426 | AUH | 24.330473 | 54.656187 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6171 | AUH | 24.539140° | 54.481710° | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6603 | AUH | 24.3719 | 54.7295 | New | OD |  | 3-4 month |  | 35000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6587 | AUH | 23.91548 | 53.45061 | New | OD |  | 11 month |  | 2466741.9 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH1354 | AUH | 24.319963 | 54.695626 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1391 | AUH | 24.324102 | 54.702484 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3595 | AUH | 23.79233 | 53.49242 | New | OD |  | 11 month |  | 1124068.52 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3999 | AUH | 22.934340 | 53.431420 | New | OD |  | 10 -11 month |  | 841006.12 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6623 | AUH | 24.33168 | 54.70599 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3425 | AUH | 24.336891 | 54.655851 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1393 | AUH | 24.399706 | 54.675502 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6175 | AUH | 24.521364° | 54.487114° | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6622 | AUH | 24.32665 | 54.71682 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3023 | AUH | 24.081398 | 52.766387 | New | OD |  | 6-7 month |  | 300000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6215 | AUH | 24.410371 | 54.547116 | New | OD |  | 6-7 month |  | 100000 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3483 | AUH | 24.15769 | 52.57144 | New | OD |  | 11 month |  | 1160000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6138 | AUH | 24.4132 | 51.5443 | New | OD |  |  |  | 0 | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH6079 | AUH | 24.5191 | 54.4354 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH2997 | AUH | 24.3198 | 54.5169 | New | OD |  | 3-4 month |  | 40000 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6626 | AUH | 24.322 | 54.6881 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH2245 | AUH | 24.3154 | 54.6584 | New | OD |  | 4-5 month |  | 170000 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH2233 | AUH | 24.4083 | 54.699 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6627 | AUH | 24.3349 | 54.7178 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6629 | AUH | 24.3393 | 54.703 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6421 | AUH | 24.5865 | 53.3207 | New | OD |  |  |  | 0 | Not Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH3418 | AUH | 24.3503 | 54.6637 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1351 | AUH | 24.3289 | 54.7257 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3929 | AUH | 24.4934 | 54.5274 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3420 | AUH | 24.3417 | 54.6619 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH2846 | AUH | 24.1583 | 54.7582 | New | OD |  | 4 -5 month |  | 20000 | OSP Provisioned |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6179 | AUH | 24.505374° | 54.486854° | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3419 | AUH | 24.3349 | 54.6645 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1437 | AUH | 24.2077 | 54.9627 | New | OD |  |  |  |  | OSP Ready under AUH2437 |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH1878 | AUH | 24.534071° | 54.479964° | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3385 | AUH | 24.2961 | 54.5418 | New | OD |  | 4-5 month |  | 40000 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3935 | AUH | 24.4085 | 55.002 | New | OD |  | 4-5 month |  | 30000 | Possible |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3248 | AUH | 24.3574 | 54.6769 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3067 | AUH | 24.3652 | 54.6827 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3861 | AUH | 24.7355 | 54.781 | New | OD |  | 11 month |  | 492407.1 | Possible |  | MW 2024 | added (carry forward from Y2023)
| AUH1880 | AUH | 24.528484° | 54.487021° | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3054 | AUH | 24.3702 | 54.6738 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH6086 | AUH | 23.9734 | 52.2709 | New | OD |  |  |  | 0 | Taawun |  | Y2024 fiber scope | added (carry forward from Y2023)
| AUH3652 | AUH | 24.8475 | 53.6525 | New | OD |  |  |  |  | not possible |  | VSAT | additional
| AUH0114 | AUH | 24.3672 | 54.7413 | New | IBS |  |  |  |  | not possible | not possible because we don’t have corridor inside Al Shamkha. | MW 2024 | additional
| IAD5759 | AUH | 24.4829 | 54.3527 | New | IBS |  | 3-4 month |  | 30000 | Possible |  | Y2024 fiber scope | additional
| AUH3749 | AUH |  |  | New | [5 empty] | not possible | falling inside Taawun boundary and no possibility to connect it unless we go through the boundary | MW 2024 | additional
| AAN3376 | AUH | 24.4828 | 55.3124 |  |  | OSP ready | [5 empty] | existing fiber | additional
| AUH3040 | AUH | 24.17 | 54.6445 |  |  | Possible | 7 months |  | 432951.7 |  |  | existing fiber | additional
| AUH3350 | AUH | 24.3745 | 54.623 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH3349 | AUH | 24.3829 | 54.6136 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH3353 | AUH | 24.3605 | 54.6008 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH3839 | AUH | 24.4559 | 54.3254 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH2728 | AUH | 24.0976 | 53.501 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH3887 | AUH | 23.0108 | 53.731 |  |  | Possible | 6 months |  | 366097.5 |  |  | existing fiber | additional
| AUH6182 | AUH | 23.0876 | 54.0419 |  |  | Possible | 5 months |  | 200000 |  |  | existing fiber | additional
| AAN3620 | AUH | 23.9299 | 55.3617 |  |  | Possible | 10 months |  | 1288498.9 | The route of this site passing at AAN3339,AAN2408 but they are not mentioned at this list |  | MW 2024 | additional
| AAN3635 | AUH | 24.5655 | 55.7614 |  |  | Possible | 5 months |  | 200000 |  |  | MW 2024 | additional
| AAN3544 | AUH | 24.3127 | 55.6512 |  |  | Possible | 8 months |  | 635241.04 |  |  | MW 2024 | additional
| AAN3443 | AUH | 24.3 | 55.7148 |  |  | Possible | 5 months |  | 200000 |  |  | MW 2024 | additional
| AAN3119 | AUH | 24.4717 | 55.3452 |  |  | Possible | 4 months |  | 238000 |  |  | existing fiber | additional
| AAN3603 | AUH | 23.624 | 55.5149 |  |  | Possible | 7 months |  | 450907.04 | This site is dependent on AAN3396,AAN3230,AAN2427,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 |  | MW 2024 | additional
| AAN3604 | AUH | 23.6081 | 55.4178 |  |  | Possible | 10 months |  | 1352195.36 |  |  | MW 2024 | additional
| AUH3361 | AUH | 24.3549 | 54.5995 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH2801 | AUH | 24.4596 | 54.5549 |  |  | Not Possible | [5 empty] | MW 2024 | additional
| AUH3943 | AUH | 24.3664 | 54.611 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH3463 | AUH | 24.0568 | 55.0547 |  |  | Possible | 7 months |  | 577201.8 | The route of this site passing at AAN2394 but it is not mentioned at this list, also this site is dependent on AAN2393 which is in this list. |  | MW 2024 | additional
| AUH3097 | AUH | 24.568 | 54.7945 |  |  | Possible |  |  | 220000 | Military-site survey required |  | MW 2024 | additional
| AUH3726 | AUH | 24.2689 | 54.6724 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH6134 | AUH | 24.1882 | 54.6697 |  |  | Possible | 5 months |  | 204893.76 |  |  | existing fiber | additional
| AUH3347 | AUH | 24.3826 | 54.6311 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH6571 | AUH | 24.3746 | 54.5044 |  |  | Possible | 3 months |  | 25000 |  |  | existing fiber | additional
| AUH3505 | AUH | 23.9776 | 53.7965 |  |  | Site survey required |  |  |  | CICPA Gate Pass is Required for Site Survey |  | MW 2024 | additional
| AUH3941 | AUH | 24.7063 | 54.7393 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN3728 | AUH | 24.3012 | 55.1264 |  |  | Possible | 10 months |  | 1500000 |  |  | MW 2024 | additional
| AUH1155 | AUH | 24.6167 | 54.7386 |  |  | Possible | 3 months |  | 45000 |  |  | Y2024 fiber scope | additional
| AUH1341 | AUH | 24.2281 | 54.6854 |  |  | Possible | 4 months |  | 280688 |  |  | MW 2024 | additional
| AAN3111 | AUH | 24.2958 | 55.7521 |  |  | Possible | 8 months |  | 356727.1 |  |  | MW 2024 | additional
| AAN3410 | AUH | 24.1721 | 55.9582 |  |  | Possible | 7 months |  | 370000 |  |  | MW 2024 | additional
| AAN3411 | AUH | 24.1671 | 55.9183 |  |  | Possible | 5 months |  | 157619.88 |  |  | Y2024 fiber scope | additional
| AAN3632 | AUH | 24.3238 | 55.8118 |  |  | Possible | 3 months |  | 25000 |  |  | Y2024 fiber scope | additional
| AAN3736 | AUH | 24.0975 | 55.2283 |  |  | Possible | 7 months |  | 528416.36 |  |  | MW 2024 | additional
| AAN3196 | AUH | 24.1345 | 55.8453 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN3112 | AUH | 24.1914 | 55.7412 |  |  | Possible | 4 months |  | 313598.88 |  |  | MW 2024 | additional
| AAN3575 | AUH | 24.1997 | 55.7826 |  |  | Possible | 3 months |  | 25000 |  |  | Y2024 fiber scope | additional
| AUH1717 | AUH | 24.434 | 54.6252 |  |  | Possible | 5 months |  | 50000 |  |  | existing fiber | additional
| AAN3199 | AUH | 24.1158 | 55.8388 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN2943 | AUH | 24.2927 | 55.7942 |  |  | Possible | 4 months |  | 220875.38 |  |  | MW 2024 | additional
| AAN3641 | AUH | 24.1708 | 55.703 |  |  | Possible | 4 months |  | 280000 |  |  | MW 2024 | additional
| AAN3245 | AUH | 24.3143 | 55.5379 |  |  | Possible | 10 months |  | 1500000 | this site is dependent on AAN3371 which is in this list. |  | MW 2024 | additional
| AAN3309 | AUH | 24.2082 | 55.8046 |  |  | OSP Provisioned |  |  | 40000 |  |  | Y2024 fiber scope | additional
| AAN3705 | AUH | 24.1241 | 55.8521 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN3759 | AUH | 24.6844 | 55.7044 |  |  | Possible | 3 months |  | 156416.78 |  |  | Y2024 fiber scope | additional
| AAN3710 | AUH | 24.1282 | 55.8317 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN3757 | AUH | 24.2186 | 55.4446 |  |  | Possible | 3 months |  | 25000 |  |  | Y2024 fiber scope | additional
| AAN3783 | AUH | 24.189 | 55.5292 |  |  | Possible | 4 months |  | 120000 |  |  | Y2024 fiber scope | additional
| AAN3743 | AUH | 24.6015 | 55.6225 |  |  | Possible | 7 months |  | 366281.94 | this site is dependent on AAN3611 which is in this list. |  | MW 2024 | additional
| AAN3558 | AUH | 24.2136 | 55.7197 |  |  | Possible | 3 months |  | 134358.18 |  |  | Y2024 fiber scope | additional
| AAN3611 | AUH | 24.6253 | 55.6471 |  |  | Possible | 8 months |  | 630162.58 |  |  | MW 2024 | additional
| AUH3099 | AUH | 24.0912 | 53.5178 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN3511 | AUH | 24.2109 | 55.6258 |  |  | Possible | 3 months |  | 113218.6 |  |  | Y2024 fiber scope | additional
| AUH3813 | AUH | 24.5048 | 54.6131 |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH3970 | AUH | 24.456518° | 54.600285° |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AAN3390 | AUH | 24.082200° | 55.678020° |  |  | Possible | 4 months |  | 55000 |  |  | Y2024 fiber scope | additional
| AUH1726 | AUH | 24.298820° | 54.600748° |  |  | Possible | 5 months |  | 105000 |  |  | Y2024 fiber scope | additional
| AUH1751 | AUH | 24.499969° | 54.394800° |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH1756 | AUH | 24.500644° | 54.399442° |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH1767 | AUH | 24.506221° | 54.398301° |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH1776 | AUH | 24.510828° | 54.397013° |  |  | Taawun | [5 empty] | Y2024 fiber scope | additional
| AUH1848 | AUH | 24.1261 | 54.2366 |  |  | Possible |  |  | 680000 |  |  | MW 2024 | additional
| AUH6596 | AUH | 24.104470° | 52.793222° |  |  | Site survey required |  |  |  | CICPA Gate Pass is Required for Site Survey |  | MW 2024 | additional
| AUH1332 | AUH | 24.52436 | 54.671444 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH1338 | AUH | 24.52294 | 54.670598 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AAN3607 | AUH | 24.066224 | 55.892893 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AAN3551 | AUH | 24.313755 | 55.803783 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH3926 | AUH | 24.36764 | 54.59737 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH2787 | AUH | 24.042404 | 53.645424 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH6615 | AUH | 23.66484 | 53.43065 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH3167 | AUH | 24.19755 | 54.731912 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH3909 | AUH | 24.35134 | 54.5216 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH3937 | AUH | 24.0687167 | 52.6634795 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH3270 | AUH | 24.32469 | 54.51827 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AAN3305 | AUH | 24.125726 | 55.676943 |  |  | OSP ready | [5 empty] | Y2024 fiber scope | additional
| AUH0115 | AUH | [7 empty] | 66000 |  |  | Y2024 fiber scope | additional
Note on N1039: Alvin Laquindanum: tbc
Note on K1053: Alvin Laquindanum: permitting already started
Note on K1062: Alvin Laquindanum: as agreed with Abdalla; 10K-60K is the value before but for budgetary purposes; we consider 50K each for all Tabreed cases.
Note on K1098: Alvin Laquindanum: permitting already started
Note on K1139: Alvin Laquindanum: permitting already started
Note on H1714: Alvin Laquindanum: not possible this year Y2024

## Sheet2
Site Code | Latitude | Longitude | Region | Site Type | OSP Scope status | OSP Status | Cost | Timeline | Remarks | Transport Feedback
AAG6105 | 24.301 | 55.12645 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3376 | 24.482847 | 55.312434 | AAN | OD | Not 2024 scope | OSP ready |  |  |  | existing fiber | #N/A | #N/A | #N/A | AAN3376
AAN2944 | 24.54658 | 55.20779 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3314 | 24.232158 | 55.538544 | AAN | OD | Not 2024 scope | OSP ready
AUG6244 | 24.421783 | 54.680092 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3562 | 24.385085 | 55.080896 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3621 | 24.165144 | 55.674168 | AAN | OD | Not 2024 scope | OSP ready
AUH1332 | 24.52436 | 54.671444 | AUH | OD | Not 2024 scope | OSP ready
AUH2016 | 24.4328 | 54.5029 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1338 | 24.52294 | 54.670598 | AUH | OD | Not 2024 scope | OSP ready
AUH2244 | 24.524151 | 54.896038 | AUH | OD | Not 2024 scope | OSP ready
AUH2250 | 24.43895 | 54.61713 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH2139 | 24.402359 | 54.750036 | AUH | OD | Not 2024 scope | OSP ready
AAN3586 | 24.772756 | 55.78012 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2429 | 24.475705 | 54.85195 | AUH | OD | Not 2024 scope | OSP Ready
AUH2668 | 24.34168 | 54.50059 | AUH | OD | Not 2024 scope | OSP Ready under AUH2668
AUH2443 | 24.51324 | 54.37183 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2496 | 24.46796 | 54.3794 | AUH | OD | Not 2024 scope | OSP ready
AUH2716 | 24.20244 | 54.46275 | AUH | OD | Not 2024 scope | OSP ready
AUH3031 | 24.833996 | 54.758568 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3536 | 24.506082 | 55.632166 | AAN | OD | Not 2024 scope | OSP ready
AUH2821 | 24.46147 | 54.824555 | AUH | OD | Not 2024 scope | OSP ready
AAN3578 | 24.155369 | 55.711152 | AAN | OD | Not 2024 scope | OSP ready
AAN3607 | 24.066224 | 55.892893 | AAN | OD | Not 2024 scope | OSP ready
AAN3579 | 24.154937 | 55.700203 | AAN | OD | Not 2024 scope | OSP ready
AUH3072 | 24.299067 | 54.672818 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3613 | 24.366577 | 55.79303 | AAN | OD | Not 2024 scope | OSP ready
AAN3545 | 24.227858 | 55.757993 | AAN | OD | Not 2024 scope | OSP ready
AAN3573 | 24.622802 | 55.737799 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3040 | 24.17001 | 54.64447 | AUH | OD | Not 2024 scope | Possible | 432951.7 | 7 months |  | existing fiber | existing | AUH3040 | #N/A | AUH3040
AAN3549 | 24.081033 | 55.600666 | AAN | OD | Not 2024 scope | OSP ready
AAN3531 | 23.9613823 | 55.0328846 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3350 | 24.374456 | 54.622955 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope |  | wala ito sa main list na nasa shared folder
AAN3593 | 24.217903 | 55.795748 | AAN | OD | Not 2024 scope | OSP ready
AUH3130 | 24.3982 | 54.5017 | AUH | OD | Not 2024 scope | OSP ready
AAN3514 | 24.201039 | 55.797567 | AAN | OD | Not 2024 scope | OSP ready
AAN3551 | 24.313755 | 55.803783 | AAN | OD | Not 2024 scope | OSP ready
AUH3349 | 24.38288 | 54.61361 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3388 | 24.532192 | 54.426428 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3354 | 24.37306 | 54.616 | AUH | OD | Not 2024 scope | OSP ready
AUH3353 | 24.360467 | 54.60076 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3924 | 24.441999 | 54.413716 | AUH | OD | Not 2024 scope | OSP ready
AUH3926 | 24.36764 | 54.59737 | AUH | OD | Not 2024 scope | OSP ready
AUH3927 | 24.397 | 54.62778 | AUH | OD | Not 2024 scope | OSP ready
AUH3915 | 24.329216 | 54.777928 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3982 | 24.41834 | 54.85376 | AUH | OD | Not 2024 scope | OSP ready
AUH3930 | 24.322423 | 54.755837 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3993 | 24.39067 | 54.62157 | AUH | OD | Not 2024 scope | OSP ready
AUH3994 | 24.38042 | 54.59773 | AUH | OD | Not 2024 scope | OSP ready
AUH3995 | 24.35809 | 54.59494 | AUH | OD | Not 2024 scope | OSP ready
AUH3997 | 24.38212 | 54.60859 | AUH | OD | Not 2024 scope | OSP ready
AUH3998 | 24.378657 | 54.61962 | AUH | OD | Not 2024 scope | OSP ready
AUH3996 | 24.383157 | 54.62216 | AUH | OD | Not 2024 scope | OSP ready
AUH6077 | 24.56455 | 54.86075 | AUH | OD | Not 2024 scope | OSP ready
AUH6087 | 24.50643 | 54.84874 | AUH | OD | Not 2024 scope | OSP ready
AUH6094 | 24.523834 | 55.074304 | AUH | OD | Not 2024 scope | OSP ready
AUH6115 | 24.3941 | 54.49145 | AUH | OD | Not 2024 scope | OSP ready
AUH6116 | 24.405282 | 54.714307 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3789 | 24.451171 | 54.632523 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6135 | 24.477003 | 54.350968 | AUH | OD | Not 2024 scope | OSP ready
AUH6123 | 24.344307 | 54.532692 | AUH | OD | Not 2024 scope | OSP ready
AUH3728 | 24.42378 | 54.71385 | AUH | OD | Not 2024 scope | OSP ready
AUH6142 | 24.41908326 | 54.40712 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6141 | 24.41743 | 54.40387 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6213 | 24.62205 | 54.87386 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3784 | 24.459717 | 54.634538 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6143 | 24.41689052 | 54.41032406 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3791 | 24.5711 | 54.762578 | AUH | OD | Not 2024 scope | OSP ready
AUH3785 | 24.43265 | 54.66972 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3827 | 24.67808 | 54.78419 | AUH | OD | Not 2024 scope | OSP ready
AUH6567 | 24.37668 | 54.50046 | AUH | OD | Not 2024 scope | OSP ready
AUH6606 | 24.638 | 54.7296 | AUH | OD | Not 2024 scope | OSP ready
AUH6396 | 24.752662 | 54.677874 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3352 | 24.36115 | 54.60802 | AUH | OD | Not 2024 scope | OSP ready
AUH6565 | 24.3692 | 54.51547 | AUH | OD | Not 2024 scope | OSP ready
AUH6604 | 24.6932 | 54.7199 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3792 | 24.48773 | 54.878103 | AUH | OD | Not 2024 scope | OSP ready
AUH3842 | 24.53187 | 54.414114 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3839 | 24.455915 | 54.325364 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3725 | 24.26741 | 54.65862 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6217 | 24.44421 | 54.366158 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6543 | 24.74417 | 54.72634 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3411 | 24.34488 | 54.67922 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6564 | 24.28014 | 54.64608 | AUH | OD | Not 2024 scope | OSP ready
AUH2393 | 23.14793 | 53.71295 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2728 | 24.09762 | 53.50104 | WR | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2526 | 24.24488 | 54.34147 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUG6245 | 22.894434 | 54.364027 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2787 | 24.042404 | 53.645424 | WR | OD | Not 2024 scope | OSP ready
AUH2785 | 23.960921 | 52.122008 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2788 | 23.144221 | 53.955931 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2790 | 24.171191 | 51.993812 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3722 | 23.645359 | 53.68481 | WR | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3621 | 23.67784 | 52.49267 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3887 | 23.01076 | 53.73097 | WR | OD | Not 2024 scope | Possible | 366097.5 | 6 months |  | existing fiber | #N/A | #N/A | #N/A | AUH3887
AUH3922 | 23.25762 | 54.30911 | WR | OD | Y2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH3796 | 22.980199 | 53.975256 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3790 | 23.85301 | 52.8033 | WR | OD | Not 2024 scope | OSP ready
AUH6046 | 24.137586 | 52.743603 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6144 | 23.98838 | 51.95702 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6182 | 23.08757 | 54.04193 | WR | OD | Not 2024 scope | Possible | 200000 | 5 months |  | existing fiber | #N/A | #N/A | #N/A | AUH6182
AUH6212 | 23.68209 | 53.70767 | WR | OD | Not 2024 scope | OSP ready
AUH6331 | 23.934895 | 53.912213 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6429 | 23.841578 | 52.819605 | WR | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6339 | 25.4945 | 53.1477 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6573 | 24.0336 | 52.74772 | WR | OD | Not 2024 scope | OSP ready
AUH6615 | 23.66484 | 53.43065 | WR | OD | Not 2024 scope | OSP ready
AUH6494 | 23.564075 | 53.627429 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6021 | 24.11546 | 52.876519 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6472 | 23.279526 | 54.238202 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6137 | 22.991876 | 53.752265 | WR | OD | Not 2024 scope | OSP ready
AUH2781 | 24.093949 | 52.477117 | WR | OD | Not 2024 scope | Possible | 129397.38 | 4 months |  | to be via MW
AUH6099 | 23.16601 | 53.78077 | WR | OD | Not 2024 scope | OSP ready
AUH6145 | 23.98301 | 51.83271 | WR | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3646 | 24.306499 | 55.770422 | AAN | OD | Not 2024 scope | OSP ready
AAN3643 | 24.16953 | 55.54007 | AAN | OD | Not 2024 scope | OSP ready
AAN3662 | 24.117 | 55.37479 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3620 | 23.92988 | 55.36166 | AAN | OD | Not 2024 scope | Possible | 1288498.9 | 10 months | The route of this site passing at AAN3339,AAN2408 but they are not mentioned at this list | MW 2024 | existing | AAN3620 | #N/A | #N/A
AAN3400 | 24.182881 | 55.648042 | AAN | OD | Not 2024 scope | OSP ready
AAN3635 | 24.56546 | 55.76141 | AAN | OD | Not 2024 scope | Possible | 200000 | 5 months |  | MW 2024 | #N/A | #N/A | #N/A | #N/A
AAN3568 | 24.286991 | 55.409327 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3544 | 24.31274 | 55.65119 | AAN | OD | Not 2024 scope | Possible | 635241.04 | 8 months |  | MW 2024 | existing | AAN3544 | #N/A | #N/A
AAN3650 | 24.196181 | 55.642637 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1085 | 24.428277 | 54.719175 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3328 | 24.094919 | 55.462199 | AAN | OD | Not 2024 scope | VVIP site survey required- initial cost provided | 1680099.31 |  | Site Located inside Al Rawda Palace Subject to Site Survey and Approval | to be via MW
AUH1082 | 24.554038 | 54.759306 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3660 | 24.18131 | 55.39022 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3443 | 24.29998 | 55.71477 | AAN | OD | Not 2024 scope | Possible | 200000 | 5 months |  | MW 2024 | existing | AAN3443 | AAN3443 | #N/A
AUH2271 | 24.52848 | 54.992232 | AUH | OD | Not 2024 scope | OSP ready |  |  |  | Y2024 fiber scope
AAN3436 | 24.334922 | 55.096225 | AAN | OD | Not 2024 scope | Possible | 1800000 |  | Subject to Site Survey and access approval | to be via MW
AAN3498 | 24.39172 | 55.51459 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3371 | 24.30397 | 55.51539 | AAN | OD | Not 2024 scope | Possible | 1060000 | 9 months |  | to be via MW
AAN3119 | 24.471723 | 55.345157 | AAN | OD | Not 2024 scope | Possible | 238000 | 4 months |  | existing fiber | #N/A | #N/A | #N/A | AAN3119
AAN3572 | 24.563894 | 55.396215 | AAN | OD | Not 2024 scope | Possible | 1920000 | 11 months |  | to be via MW
AAN3640 | 23.877232 | 55.397175 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3542 | 24.227683 | 55.299804 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3636 | 24.436774 | 55.802528 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3214 | 24.1571 | 55.648123 | AAN | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3612 | 24.38852 | 55.76346 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3603 | 23.624035 | 55.514912 | AAN | OD | Not 2024 scope | Possible | 450907.04 | 7 months | This site is dependent on AAN3396,AAN3230,AAN2427,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 | MW 2024 | existing | AAN3603 | #N/A | #N/A
AAN2443 | 24.188218 | 55.780921 | AAN | OD | Not 2024 scope | CW completed | 20000 |  |  | Y2024 fiber scope
AAN3423 | 24.4156 | 55.71829 | AAN | OD | Not 2024 scope | OSP ready
AAN3212 | 24.15023 | 55.64064 | AAN | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3292 | 24.16654 | 55.666 | AAN | OD | Not 2024 scope | OSP ready
AAG6104 | 24.09191 | 55.92368 | AAN | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3604 | 23.60812 | 55.41776 | AAN | OD | Not 2024 scope | Possible | 1352195.36 | 10 months |  | MW 2024 | #N/A | #N/A | #N/A | #N/A
AAN3627 | 24.232301 | 55.761793 | AAN | OD | Not 2024 scope | OSP ready |  |  |  | Y2024 fiber scope
AUH2516 | 24.431561 | 54.514014 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3633 | 24.13643 | 55.64802 | AAN | OD | Not 2024 scope | OSP ready |  |  |  | Y2024 fiber scope
AAN3622 | 23.840134 | 55.475823 | AAN | OD | Not 2024 scope | Possible | 820000 | 9 months |  | to be via MW
AAN3675 | 24.17522 | 55.70808 | AAN | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH2060 | 24.362494 | 54.688758 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3655 | 24.18296 | 55.76441 | AAN | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3253 | 24.158048 | 55.654721 | AAN | OD | Not 2024 scope | OSP ready |  |  |  | Y2024 fiber scope
AUH2472 | 24.349191 | 54.342041 | AUH | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AAN3642 | 24.12512 | 55.93796 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2442 | 24.464208 | 54.345332 | AUH | OD | Not 2024 scope | OSP ready
AUH2731 | 24.737414 | 55.110291 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2815 | 24.19643 | 54.58858 | AUH | OD | Not 2024 scope | OSP ready
AUH2834 | 24.379442 | 54.346653 | AUH | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH3923 | 24.56428 | 54.68364 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3415 | 24.341237 | 54.684324 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3167 | 24.19755 | 54.731912 | AUH | OD | Not 2024 scope | OSP ready
AUH3361 | 24.3549 | 54.59946 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3645 | 24.478428 | 54.409421 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3410 | 24.339076 | 54.673534 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2801 | 24.45957 | 54.5549 | AUH | OD | Not 2024 scope | Not Possible |  |  |  | MW 2024 | #N/A | #N/A | #N/A | #N/A
AUH3151 | 24.412641 | 54.486011 | AUH | OD | Not 2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH2820 | 24.33024 | 54.71164 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3908 | 24.3482679 | 54.544936 | AUH | OD | Y2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH3152 | 24.41106 | 54.485752 | AUH | OD | Not 2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH6170 | 24.538379 | 54.473671 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3909 | 24.35134 | 54.5216 | AUH | OD | Not 2024 scope | OSP ready
AUH2721 | 24.433704 | 54.620203 | AUH | OD | Not 2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH3939 | 24.340402 | 54.610518 | AUH | OD | Not 2024 scope | OSP ready
AUH6076 | 24.52444 | 54.44127 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2657 | 24.316424 | 54.682335 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6154 | 24.335496 | 54.597045 | AUH | OD | Y2024 scope | 2023 carry forward scope |  |  |  | Y2024 fiber scope
AUH3943 | 24.36643 | 54.61102 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6152 | 24.563191 | 54.460706 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3724 | 24.278608 | 54.679085 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3463 | 24.05678 | 55.05474 | AUH | OD | Not 2024 scope | Possible | 577201.8 | 7 months | The route of this site passing at AAN2394 but it is not mentioned at this list, also this site is dependent on AAN2393 which is in this list. | MW 2024 | existing | AUH3463 | AUH3463 | #N/A
AUH3381 | 24.63165 | 54.53509 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3097 | 24.568023 | 54.794495 | AUH | OD | Not 2024 scope | Possible | 220000 |  | Military-site survey required | MW 2024 | existing | AUH3097 | #N/A | #N/A
AUH6555 | 24.241769 | 55.050028 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3726 | 24.26893 | 54.67236 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6140 | 24.42014 | 54.40466 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3413 | 24.334691 | 54.679302 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6134 | 24.18824 | 54.6697 | AUH | OD | Not 2024 scope | Possible | 204893.76 | 5 months |  | existing fiber | #N/A | #N/A | #N/A | AUH6134
AUH6044 | 24.491428 | 54.402455 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3194 | 24.599409 | 54.704999 | AUH | OD | Not 2024 scope | OSP ready
AUH6174 | 24.529144 | 54.484364 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6180 | 24.524476 | 54.491837 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3971 | 24.21706 | 55.09123 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH6172 | 24.531737 | 54.466198 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3347 | 24.382617 | 54.631091 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6158 | 24.330991 | 54.457508 | AUH | OD | Not 2024 scope | Possible | 595000 | 5 months |  | to be via MW
AUH6178 | 24.52005 | 54.495437 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3391 | 24.54569 | 54.44753 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6556 | 24.28798 | 55.05795 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6561 | 24.366 | 54.5372 | AUH | OD | Not 2024 scope | OSP ready
AUH6571 | 24.374616 | 54.504382 | AUH | OD | Not 2024 scope | Possible | 25000 | 3 months |  | existing fiber | #N/A | #N/A | #N/A | AUH6571
AUH6566 | 24.377324 | 54.511416 | AUH | OD | Not 2024 scope | OSP ready
AUH3247 | 24.186907 | 51.990115 | WR | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH3505 | 23.977647 | 53.796505 | WR | OD | Not 2024 scope | Site survey required |  |  | CICPA Gate Pass is Required for Site Survey | MW 2024 | #N/A | #N/A | #N/A | #N/A
AUH6167 | 24.22763 | 51.72228 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2730 | 24.11572 | 51.77708 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3944 | 24.070725 | 51.751627 | WR | OD | Not 2024 scope | OSP ready
AUH3988 | 23.938314 | 53.695519 | WR | OD | Not 2024 scope | Site survey required |  |  | CICPA Gate Pass is Required for Site Survey | to be via MW
AUH6367 | 22.97419 | 53.882317 | WR | OD | Not 2024 scope | Possible | 1250000 | 10 months |  | to be via MW
AUH6418 | 24.06584 | 53.41871 | WR | OD | Not 2024 scope | OSP ready
AUH3985 | 23.946182 | 53.791065 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3820 | 24.120656 | 52.644371 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3937 | 24.0687167 | 52.6634795 | WR | OD | Not 2024 scope | OSP ready
AUH3779 | 24.517165 | 54.025866 | WR | OD | Not 2024 scope | Not Possible | 0 |  | Wrong Coordinates | to be via MW
AUG6219 | 23.96966 | 52.258664 | WR | OD | Not 2024 scope | Possible | 270000 | 7 months |  | to be via MW
AUH3610 | 23.961445 | 52.227982 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6342 | 24.608115 | 54.15045 | WR | OD | Not 2024 scope | Not Possible | 0 |  | Wrong Coordinates | to be via MW
AUH6450 | 24.3163 | 53.8025 | WR | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH3506 | 23.895778 | 53.739291 | WR | OD | Not 2024 scope | Site survey required |  |  | CICPA Gate Pass is Required for Site Survey | to be via MW
AUH6121 | 23.03439 | 54.01563 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6168 | 23.21291 | 53.74327 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2736 | 23.81579 | 52.74623 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6097 | 24.019351 | 52.019775 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6452 | 22.900283 | 54.33621 | WR | OD | Not 2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH6492 | 22.89541 | 54.36831 | WR | OD | Not 2024 scope | Possible | 1750000 | 3 months |  | to be via MW
AUH3455 | 24.544023 | 54.855214 | AUH | OD | Not 2024 scope | OSP Provisioned | 35000 |  |  | Y2024 fiber scope
AAN3261 | 24.20251 | 55.737268 | AAN | OD | Not 2024 scope | OSP ready |  |  |  | Y2024 fiber scope
AUH3941 | 24.706274 | 54.739298 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3645 | 23.930829 | 55.439516 | AAN | OD | Not 2024 scope | Possible | 550000 | 7 months |  | to be via MW
AUH6537 | 24.4181 | 54.4207 | AUH | OD | Not 2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH3782 | 24.5006 | 54.57317 | AUH | OD | Not 2024 scope | Not possible |  |  |  | to be via MW
AUH6504 | 24.418733 | 54.480683 | AUH | OD | Not 2024 scope | OSP Provisioned | 20000 |  |  | Y2024 fiber scope
AUH6419 | 24.12775 | 52.7574 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3912 | 24.34419 | 54.52475 | AUH | OD | Y2024 scope | CW completed | 20000 |  |  | Y2024 fiber scope
AUH3788 | 24.4614 | 54.65076 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3984 | 23.8771811 | 53.611061 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3759 | 23.590275 | 53.325769 | WR | OD | Not 2024 scope | Possible | 2250000 | 7 months |  | to be via MW
AAN3663 | 24.09913 | 55.92586 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3991 | 23.794207 | 53.6430319 | WR | OD | Not 2024 scope | Possible | 1800000 | 7 months |  | to be via MW
AUH3990 | 23.845683 | 53.58666 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3167 | 24.19755 | 54.731912 | AUH | OD | Not 2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH1071 | 24.547052 | 54.465783 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3728 | 24.30125 | 55.12642 | AAN | OD | Not 2024 scope | Possible | 1500000 | 10 months |  | MW 2024 | 02-Leased | #N/A | #N/A | #N/A
AUH3066 | 24.243765 | 54.474987 | AUH | OD | Y2024 scope | CW completed | 20000 |  |  | Y2024 fiber scope
AAN3644 | 24.101 | 55.316214 | AAN | OD | Not 2024 scope | Possible | 475000 | 7 months |  | to be via MW
AUH3986 | 23.833221 | 53.752777 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3989 | 23.820512 | 53.58302 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3671 | 23.683202 | 53.638408 | WR | OD | Not 2024 scope | OSP Provisioned | 35000 |  |  | Y2024 fiber scope
AUH2874 | 24.1182 | 52.53151 | WR | OD | Not 2024 scope | OSP Provisioned | 20000 |  |  | Y2024 fiber scope
AUH2748 | 24.401350 | 54.648612 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1155 | 24.616716 | 54.738591 | AUH | OD | Not 2024 scope | Possible | 45000 | 3 months |  | Y2024 fiber scope | #N/A | #N/A | #N/A | #N/A
AUH2529 | 24.710134 | 54.836378 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1076 | 24.839023 | 55.021670 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1341 | 24.228142 | 54.685448 | AUH | OD | Not 2024 scope | Possible | 280688 | 4 months |  | MW 2024 | existing | AUH1341 | #N/A | #N/A
AUH6070 | 24.506524 | 54.390338 | AUH | OD | Not 2024 scope | Not Possible in 2024 |  |  |  | to be via MW
AUH6559 | 24.434831 | 54.468248 | AUH | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH6589 | 24.873113 | 54.834713 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3111 | 24.295812 | 55.752072 | AAN | OD | Not 2024 scope | Possible | 356727.1 | 8 months |  | MW 2024 | 02-Leased | #N/A | #N/A | #N/A
AAN3208 | 24.329120 | 55.790891 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3388 | 24.183333 | 55.731667 | AAN | OD | Y2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AAN3385 | 24.007247 | 55.439937 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3229 | 24.738850 | 55.777840 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3410 | 24.172060 | 55.958240 | AAN | OD | Not 2024 scope | Possible | 370000 | 7 months |  | MW 2024 | 01-Not Leased | #N/A | #N/A | #N/A
AAN3674 | 24.166887 | 55.301574 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3657 | 24.702180 | 55.601770 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3411 | 24.167057 | 55.918268 | AAN | OD | Not 2024 scope | Possible | 157619.88 | 5 months |  | Y2024 fiber scope | 03-BP Received | #N/A | #N/A | #N/A
AAN3672 | 24.200065 | 55.652100 | AAN | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3665 | 24.172250 | 55.434060 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3741 | 23.989220 | 55.093180 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3505 | 23.636246 | 55.541230 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3722 | 24.184490 | 55.334360 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3740 | 24.152610 | 55.444410 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1046 | 24.501918 | 54.631355 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3744 | 24.652160 | 55.704570 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3723 | 24.531726 | 55.672895 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3737 | 24.128650 | 55.258480 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2254 | 24.311549 | 54.670290 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2231 | 24.434192 | 54.453060 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH1356 | 24.312412 | 54.700600 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1049 | 24.506545 | 54.618949 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1047 | 24.501812 | 54.619621 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1035 | 23.641220 | 53.719310 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1331 | 22.973780 | 53.763880 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3767 | 24.407630 | 54.710920 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6625 | 24.316030 | 54.690930 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3992 | 23.113230 | 53.857960 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1349 | 24.508026 | 54.607130 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1362 | 24.317792 | 54.710636 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3693 | 24.781340 | 54.908440 | AUH | OD | Not 2024 scope | OSP Provisioned | 50000 |  | the site ID is OSP Provisioned on the system while the coodinates leads to another location; however the provided cost is for this coordinates | Y2024 fiber scope
AUH3917 | 24.371652 | 54.716364 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1330 | 22.967526 | 53.791847 | WR | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH6624 | 24.318810 | 54.702160 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6569 | 24.347350 | 54.488210 | AUH | OD | Not 2024 scope | OSP Ready under AUG4442 |  |  |  | Y2024 fiber scope
AUH1917 | 24.427629 | 54.333732 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6173 | 24.531817° | 54.475263° | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6554 | 24.142889 | 52.735394 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3972 | 24.449176 | 55.04104 | AUH | OD | Not 2024 scope | Possible | 45000 |  |  | Y2024 fiber scope
AUH2896 | 23.117652 | 53.816520 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3412 | 24.345115 | 54.670096 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6176 | 24.515882° | 54.491771° | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3920 | 24.442544 | 54.405869 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH3901 | 24.5973 | 54.932625 | AUH | OD | Not 2024 scope | Possible | 480000 | 3 months |  | to be via MW
AUH1401 | 24.394052 | 54.677023 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3005 | 24.093747 | 53.409615 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3673 | 24.193358 | 55.649712 | AAN | OD | Not 2024 scope | CW in progress |  |  |  | Y2024 fiber scope
AUH3034 | 24.617375 | 55.071867 | AUH | OD | Not 2024 scope | Possible | 1464333.82 |  |  | to be via MW
AUH3414 | 24.327614 | 54.647089 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3416 | 24.355015 | 54.667817 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1353 | 24.323706 | 54.711624 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6486 | 24.17689 | 53.86111 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6302 | 25.12696 | 52.879008 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3135 | 24.36447 | 54.67562 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3427 | 24.321086 | 54.649753 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3417 | 24.3499 | 54.672809 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3426 | 24.330473 | 54.656187 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6171 | 24.539140° | 54.481710° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3150 | 24.36273 | 54.67043 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6603 | 24.3719 | 54.7295 | AUH | OD | Not 2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH6587 | 23.91548 | 53.45061 | WR | OD | Not 2024 scope | Possible | 2466741.9 |  |  | to be via MW
AUH1354 | 24.319963 | 54.695626 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1391 | 24.324102 | 54.702484 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2782 | 24.519922 | 54.4448 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2740 | 24.28198 | 54.56798 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2745 | 24.53949 | 54.43637 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3595 | 23.79233 | 53.49242 | WR | OD | Not 2024 scope | Possible | 1124068.52 |  |  | to be via MW
AUH3999 | 22.93434 | 53.43142 | WR | OD | Not 2024 scope | Possible | 841006.12 |  |  | to be via MW
AUH6623 | 24.33168 | 54.70599 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3425 | 24.336891 | 54.655851 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1393 | 24.399706 | 54.675502 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6575 | 24.366762 | 54.51286 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6175 | 24.521364° | 54.487114° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2324 | 24.712117 | 54.875053 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6622 | 24.32665 | 54.71682 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6338 | 24.214237 | 54.920623 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3359 | 24.363341 | 54.591276 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3632 | 24.3238 | 55.81175 | AAN | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Y2024 fiber scope | 02-Leased | #N/A | #N/A | #N/A
AUH3023 | 24.081398 | 52.766387 | WR | OD | Not 2024 scope | Possible | 300000 |  |  | to be via MW
AAN3736 | 24.097510 | 55.228250 | AAN | OD | Not 2024 scope | Possible | 528416.36 | 7 months |  | MW 2024 | 01-Not Leased | #N/A | #N/A | #N/A
AUH2881 | 24.055555 | 53.335467 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3508 | 24.261099 | 55.746826 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUG6238 | 24.39571 | 54.398934 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3426 | 24.232504 | 55.563274 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6215 | 24.410371 | 54.547116 | AUH | OD | Not 2024 scope | Possible | 100000 |  |  | Y2024 fiber scope
AUH3483 | 24.15769 | 52.57144 | WR | OD | Not 2024 scope | Possible | 1160000 |  |  | to be via MW
AAN3738 | 23.373055 | 55.370937 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3196 | 24.134516 | 55.845265 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3112 | 24.191437 | 55.741211 | AAN | OD | Not 2024 scope | Possible | 313598.88 | 4 months |  | MW 2024 | 01-Not Leased | #N/A | #N/A | #N/A
AAN3575 | 24.199720 | 55.782576 | AAN | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Y2024 fiber scope | 01-Not Leased | #N/A | #N/A | #N/A
AAN3407 | 24.219005 | 55.771266 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1717 | 24.434034 | 54.625235 | AUH | OD | Not 2024 scope | Possible | 50000 | 5 months |  | existing fiber | #N/A | #N/A | #N/A | AUH1717
AAN3528 | 24.200105 | 55.690302 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUG6237 | 24.414858 | 54.368265 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3199 | 24.115846 | 55.838763 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN2943 | 24.292712 | 55.794188 | AAN | OD | Not 2024 scope | Possible | 220875.38 | 4 months |  | MW 2024 | 01-Not Leased | #N/A | #N/A | #N/A
AUH6138 | 24.413181 | 51.544342 | WR | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH3485 | 24.134018 | 52.71787 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3658 | 23.42092 | 55.43033 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3509 | 24.206868 | 55.611189 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3641 | 24.170849 | 55.702970 | AAN | OD | Not 2024 scope | Possible | 280000 | 4 months |  | MW 2024 | 01-Not Leased | #N/A | #N/A | #N/A
AUH6079 | 24.51909 | 54.43536 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUG6241 | 24.40257 | 54.416902 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3245 | 24.314310 | 55.537865 | AAN | OD | Not 2024 scope | Possible | 497594.74 | 7 months | this site is dependent on AAN3371 which is in this list. | existing fiber | 02-Leased | #N/A | #N/A | AAN3245
AAN3309 | 24.208221 | 55.804607 | AAN | OD | Not 2024 scope | OSP Provisioned | 40000 |  |  | Y2024 fiber scope | 01-Not Leased | #N/A | #N/A | #N/A
AUH2997 | 24.319751 | 54.516899 | AUH | OD | Not 2024 scope | Possible | 40000 |  |  | Y2024 fiber scope
AAN3439 | 24.181136 | 55.707796 | AAN | OD | Y2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AAN3228 | 24.743447 | 55.789222 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3705 | 24.124121 | 55.852140 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3750 | 24.633300 | 55.691030 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1010 | 24.366769 | 54.643784 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3752 | 24.548542 | 55.604233 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6628 | 24.312398 | 54.708664 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1324 | 24.339560 | 54.775640 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3703 | 24.204468 | 55.366495 | AAN | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3735 | 24.472946 | 55.386580 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3753 | 24.173417 | 55.166053 | AAN | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1174 | 24.491743 | 54.359308 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH1079 | 24.094280 | 51.634333 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3759 | 24.684420 | 55.704370 | AAN | OD | Not 2024 scope | Possible | 156416.78 | 3 months |  | Y2024 fiber scope | 01-Not Leased | #N/A | #N/A | #N/A
AAN3710 | 24.128241 | 55.831722 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6626 | 24.322040 | 54.688080 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3757 | 24.218610 | 55.444570 | AAN | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Y2024 fiber scope | 01-Not Leased | #N/A | #N/A | #N/A
AUH1033 | 24.407048 | 54.542460 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH1326 | 24.367610 | 54.759298 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1892 | 24.333770° | 54.568579 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1315 | 24.365330 | 54.781300 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2245 | 24.315420 | 54.658390 | AUH | OD | Not 2024 scope | Possible | 170000 |  |  | to be via MW
AAN3783 | 24.189000 | 55.529230 | AAN | OD | Not 2024 scope | Possible | 120000 | 4 months |  | Y2024 fiber scope | 01-Not Leased | #N/A | #N/A | #N/A
AUH1194 | 24.524884 | 54.690312 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH1339 | 24.560480 | 54.756970 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3743 | 24.601490 | 55.622480 | AAN | OD | Not 2024 scope | Possible | 366281.94 | 7 months | this site is dependent on AAN3611 which is in this list. | MW 2024 | 02-Leased | #N/A | #N/A | #N/A
AUH1327 | 23.707001 | 53.806582 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1048 | 24.503966 | 54.625536 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1066 | 23.647460 | 53.698530 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1319 | 24.321070 | 54.796460 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6463 | 24.511543 | 54.655083 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6523 | 24.303357 | 54.590701 | AUH | OD | Y2024 scope | OSP Provisioned | 20000 |  |  | Y2024 fiber scope
AUH1347 | 24.245790 | 54.440720 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1068 | 24.508868 | 54.611915 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1345 | 24.257790 | 54.452990 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2233 | 24.408279 | 54.699020 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6183 | 24.468262 | 54.839138 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH6630 | 24.322530 | 54.721810 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1687 | 24.194808 | 54.899352 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6346 | 24.326900 | 54.213600 | WR | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH3914 | 24.329940 | 54.785570 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6627 | 24.334950 | 54.717782 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3913 | 24.260154 | 54.621876 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6629 | 24.339329 | 54.702997 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6421 | 24.586504 | 53.320659 | WR | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AUH3418 | 24.350251 | 54.663726 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3481 | 24.55635 | 54.80969 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2538 | 24.6901 | 54.8536 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3765 | 24.4027 | 54.69849 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6106 | 23.735062 | 53.499948 | WR | OD | Y2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH3090 | 24.54832 | 54.79882 | AUH | OD | Y2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH3016 | 24.607292 | 55.003319 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2747 | 23.548962° | 53.313183° | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3821 | 24.411314 | 54.360145 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3096 | 24.53356 | 54.91009 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6132 | 24.467353 | 54.3221 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH1351 | 24.328854 | 54.725713 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1891 | 24.51234 | 54.61301 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3186 | 24.498851 | 54.404451 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3875 | 24.321777 | 54.782575 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6033 | 24.8531 | 54.80836 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2988 | 24.792439 | 52.555845 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3902 | 24.19946 | 55.02303 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH1375 | 24.337172 | 54.711004 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1894 | 24.408976 | 54.60032 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1682 | 24.20267 | 54.87254 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AAN3445 | 24.17743 | 55.643196 | AAN | OD | Not 2024 scope | OSP Ready |  |  |  | to be via MW
AUH6613 | 24.1914 | 54.9634 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1431 | 24.1701 | 52.6487 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2644 | 24.430911 | 54.642139 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3734 | 24.487816 | 54.40131 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3929 | 24.493413 | 54.527364 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6009 | 24.414782 | 54.409939 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6600 | 25.318472 | 53.462056 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3888 | 24.447875 | 54.596675 | AUH | OD | Y2024 scope | Tabreed | 50000 |  |  | Y2024 fiber scope
AUH3420 | 24.341654 | 54.661894 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6585 | 24.69345 | 54.67124 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2846 | 24.158257 | 54.758194 | AUH | OD | Not 2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH6153 | 24.714601 | 54.820081 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1276 | 23.622615 | 53.716117 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6179 | 24.505374° | 54.486854° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6422 | 24.459799 | 53.371002 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6069 | 24.545138 | 54.863254 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH2194 | 24.468052 | 54.59833 | AUH | OD | Y2024 scope | OSP Ready |  |  |  | Y2024 fiber scope
AUH1139 | 24.543515 | 54.621379 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3093 | 24.56334 | 54.79812 | AUH | OD | Y2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH2486 | 24.3491 | 54.6912 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1893 | 24.355412 | 54.49611 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3419 | 24.33492 | 54.664484 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1437 | 24.2077 | 54.9627 | AUH | OD | Not 2024 scope | OSP Ready under AUH2437 |  |  |  | Y2024 fiber scope
AUH1878 | 24.534071° | 54.479964° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3766 | 24.40219 | 54.70641 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3385 | 24.2961 | 54.5418 | AUH | OD | Not 2024 scope | Possible | 40000 |  |  | Y2024 fiber scope
AUH2011 | 24.62331 | 54.81433 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3047 | 24.4341 | 54.76632 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AUH2515 | 24.442911 | 54.647307 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3935 | 24.408451 | 55.002043 | AUH | OD | Not 2024 scope | Possible | 30000 |  |  | Y2024 fiber scope
AUH3248 | 24.35737 | 54.6769 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1677 | 24.16531 | 54.91577 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1461 | 24.435477 | 54.712847 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3067 | 24.36517 | 54.68265 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6122 | 24.559397 | 54.889753 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3861 | 24.735534 | 54.781031 | AUH | OD | Not 2024 scope | Possible | 492407.1 |  |  | to be via MW
AAN3558 | 24.213612 | 55.719689 | AAN | OD | Not 2024 scope | Possible | 134358.18 | 3 months |  | Y2024 fiber scope | 01-Not Leased | #N/A | #N/A | #N/A
AUH1880 | 24.528484° | 54.487021° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6598 | 23.6741 | 53.8386 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3405 | 24.399107 | 54.549596 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH6014 | 24.44788 | 54.604984 | AUH | OD | Y2024 scope | Tabreed | 50000 |  |  | Y2024 fiber scope
AUH3054 | 24.37022 | 54.6738 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6471 | 23.280838 | 54.249824 | WR | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH1671 | 24.1756 | 54.86981 | AUH | OD | Not 2024 scope |  |  |  |  | to be via MW
AUH3158 | 24.487174 | 54.615889 | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3588 | 24.71145 | 55.77616 | AAN | OD | Not 2024 scope | OSP ready
AAN3611 | 24.62533 | 55.64709 | AAN | OD | Not 2024 scope | Possible | 630162.58 | 8 months |  | MW 2024 | 04-CW started | #N/A | #N/A | #N/A
AAN2947 | 24.13505 | 55.62148 | AAN | OD | Not 2024 scope | OSP ready
AUH3270 | 24.32469 | 54.51827 | AUH | OD | Not 2024 scope | OSP ready
AAN3305 | 24.125726 | 55.676943 | AAN | OD | Not 2024 scope | OSP ready
AAN3321 | 24.216867 | 55.803001 | AAN | OD | Not 2024 scope | OSP ready
AUH3089 | 24.512571 | 54.784080 | AUH | OD | Not 2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH2278 | 24.439255 | 54.464182 | AUH | OD | Not 2024 scope | Not Possible |  |  |  | to be via MW
AAN3169 | 24.223202 | 55.483279 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AAN3585 | 24.2088 | 55.333025 | AAN | OD | Not 2024 scope | OSP ready
AUH3099 | 24.091241 | 53.517785 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH2645 | 24.540508 | 54.834147 | AUH | OD | Not 2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AUH6430 | 23.832692 | 52.818951 | AUH | OD | Y2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3185 | 24.51967 | 54.965623 | AUH | OD | Y2024 scope | CW completed | 20000 |  |  | to be via MW
AUH3059 | 24.42143 | 54.517774 | AUH | OD | Not 2024 scope | OSP Provisioned | 25000 |  |  | Y2024 fiber scope
AAN3446 | 24.16709 | 55.64658 | AAN | OD | Not 2024 scope | OSP ready
AAN3511 | 24.21089 | 55.625819 | AAN | OD | Not 2024 scope | Possible | 113218.6 | 3 months |  | Y2024 fiber scope | 04-CW started | #N/A | #N/A | #N/A
AUH2519 | 24.383702 | 54.888585 | AUH | OD | Not 2024 scope | OSP ready
AUH3981 | 22.95939 | 53.81969 | AUH | OD | Not 2024 scope | OSP ready |  |  |  | Y2024 fiber scope
AUH2726 | 24.343536 | 54.920393 | AUH | OD | Y2024 scope | OSP Provisioned | 20000 |  |  | Y2024 fiber scope
AUH3813 | 24.504757 | 54.613114 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6086 | 23.973377 | 52.270874 | WR | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH3903 | 24.483150° | 54.612270° | AUH | OD | Not 2024 scope | Possible | 102000 |  |  | Y2024 fiber scope
AUH1896 | 22.984270° | 53.796000° | AUH | OD | Not 2024 scope | Possible | 250000 |  |  | to be via MW
AUH1080 | 24.480053 | 54.604457 | AUH | OD | Not 2024 scope | CW in progress |  |  |  | Y2024 fiber scope
AUH1816 | 24.502614 | 54.380424 | AUH | OD | Not 2024 scope | CW in progress |  |  |  | Y2024 fiber scope
AUH3970 | 24.456518° | 54.600285° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH6568 | 24.355260° | 54.502450° | AUH | OD | Y2024 scope |  |  |  |  | Y2024 fiber scope
AAN3390 | 24.082200° | 55.678020° | AAN | OD | Not 2024 scope | Possible | 55000 | 4 months |  | Y2024 fiber scope | #N/A | #N/A | #N/A | #N/A
AUH1726 | 24.298820° | 54.600748° | AUH | OD | Not 2024 scope | Possible | 105000 | 5 months |  | Y2024 fiber scope | #N/A | #N/A | #N/A | #N/A
AUH1751 | 24.499969° | 54.394800° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1756 | 24.500644° | 54.399442° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1767 | 24.506221° | 54.398301° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1776 | 24.510828° | 54.397013° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Y2024 fiber scope
AUH1848 | 24.1260579 | 54.236613 | AUH | OD | Not 2024 scope | Possible | 680000 |  |  | MW 2024 | #N/A | #N/A | #N/A | #N/A
AUH6596 | 24.104470° | 52.793222° | AUH | OD | Not 2024 scope | Site survey required |  |  | CICPA Gate Pass is Required for Site Survey | MW 2024 | #N/A | #N/A | #N/A | #N/A

## Sheet3
AUH1332 | Not 2024 scope | OSP ready
AUH1338 | Not 2024 scope | OSP ready
AAN3607 | Not 2024 scope | OSP ready
AAN3551 | Not 2024 scope | OSP ready
AUH3926 | Not 2024 scope | OSP ready
AUH2787 | Not 2024 scope | OSP ready
AUH6615 | Not 2024 scope | OSP ready
AUH3167 | Not 2024 scope | OSP ready
AUH3909 | Not 2024 scope | OSP ready
AUH3937 | Not 2024 scope | OSP ready
AUH3270 | Not 2024 scope | OSP ready
AAN3305 | Not 2024 scope | OSP ready

## Sheet1
AAN3376 | 24.482847 | 55.312434 | AAN | OD | Not 2024 scope | OSP ready |  |  |  | Transport feedback required | existing fiber
AUH3040 | 24.17001 | 54.64447 | AUH | OD | Not 2024 scope | Possible | 432951.7 | 7 months |  | Transport feedback required | existing fiber
AUH3350 | 24.374456 | 54.622955 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH3349 | 24.38288 | 54.61361 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH3353 | 24.360467 | 54.60076 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH3839 | 24.455915 | 54.325364 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH2728 | 24.09762 | 53.50104 | WR | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH3887 | 23.01076 | 53.73097 | WR | OD | Not 2024 scope | Possible | 366097.5 | 6 months |  | Transport feedback required | existing fiber
AUH6182 | 23.08757 | 54.04193 | WR | OD | Not 2024 scope | Possible | 200000 | 5 months |  | Transport feedback required | existing fiber
AAN3620 | 23.92988 | 55.36166 | AAN | OD | Not 2024 scope | Possible | 1288498.9 | 10 months | The route of this site passing at AAN3339,AAN2408 but they are not mentioned at this list | Transport feedback required | MW 2024
AAN3635 | 24.56546 | 55.76141 | AAN | OD | Not 2024 scope | Possible | 200000 | 5 months |  | Transport feedback required | MW 2024
AAN3544 | 24.31274 | 55.65119 | AAN | OD | Not 2024 scope | Possible | 635241.04 | 8 months |  | Transport feedback required | MW 2024
AAN3443 | 24.29998 | 55.71477 | AAN | OD | Not 2024 scope | Possible | 200000 | 5 months |  | Transport feedback required | MW 2024
AAN3119 | 24.471723 | 55.345157 | AAN | OD | Not 2024 scope | Possible | 238000 | 4 months |  | Transport feedback required | existing fiber
AAN3603 | 23.624035 | 55.514912 | AAN | OD | Not 2024 scope | Possible | 450907.04 | 7 months | This site is dependent on AAN3396,AAN3230,AAN2427,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 | Transport feedback required | MW 2024
AAN3604 | 23.60812 | 55.41776 | AAN | OD | Not 2024 scope | Possible | 1352195.36 | 10 months |  | Transport feedback required | MW 2024
AUH3361 | 24.3549 | 54.59946 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH2801 | 24.45957 | 54.5549 | AUH | OD | Not 2024 scope | Not Possible |  |  |  | Transport feedback required | MW 2024
AUH3943 | 24.36643 | 54.61102 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH3463 | 24.05678 | 55.05474 | AUH | OD | Not 2024 scope | Possible | 577201.8 | 7 months | The route of this site passing at AAN2394 but it is not mentioned at this list, also this site is dependent on AAN2393 which is in this list. | Transport feedback required | MW 2024
AUH3097 | 24.568023 | 54.794495 | AUH | OD | Not 2024 scope | Possible | 220000 |  | Military-site survey required | Transport feedback required | MW 2024
AUH3726 | 24.26893 | 54.67236 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH6134 | 24.18824 | 54.6697 | AUH | OD | Not 2024 scope | Possible | 204893.76 | 5 months |  | Transport feedback required | existing fiber
AUH3347 | 24.382617 | 54.631091 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH6571 | 24.374616 | 54.504382 | AUH | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Transport feedback required | existing fiber
AUH3505 | 23.977647 | 53.796505 | WR | OD | Not 2024 scope | Site survey required |  |  | CICPA Gate Pass is Required for Site Survey | Transport feedback required | MW 2024
AUH3941 | 24.706274 | 54.739298 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN3728 | 24.30125 | 55.12642 | AAN | OD | Not 2024 scope | Possible | 1500000 | 10 months |  | Transport feedback required | MW 2024
AUH1155 | 24.616716 | 54.738591 | AUH | OD | Not 2024 scope | Possible | 45000 | 3 months |  | Transport feedback required | Y2024 fiber scope
AUH1341 | 24.228142 | 54.685448 | AUH | OD | Not 2024 scope | Possible | 280688 | 4 months |  | Transport feedback required | MW 2024
AAN3111 | 24.295812 | 55.752072 | AAN | OD | Not 2024 scope | Possible | 356727.1 | 8 months |  | Transport feedback required | MW 2024
AAN3410 | 24.172060 | 55.958240 | AAN | OD | Not 2024 scope | Possible | 370000 | 7 months |  | Transport feedback required | MW 2024
AAN3411 | 24.167057 | 55.918268 | AAN | OD | Not 2024 scope | Possible | 157619.88 | 5 months |  | Transport feedback required | Y2024 fiber scope
AAN3632 | 24.3238 | 55.81175 | AAN | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Transport feedback required | Y2024 fiber scope
AAN3736 | 24.097510 | 55.228250 | AAN | OD | Not 2024 scope | Possible | 528416.36 | 7 months |  | Transport feedback required | MW 2024
AAN3196 | 24.134516 | 55.845265 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN3112 | 24.191437 | 55.741211 | AAN | OD | Not 2024 scope | Possible | 313598.88 | 4 months |  | Transport feedback required | MW 2024
AAN3575 | 24.199720 | 55.782576 | AAN | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Transport feedback required | Y2024 fiber scope
AUH1717 | 24.434034 | 54.625235 | AUH | OD | Not 2024 scope | Possible | 50000 | 5 months |  | Transport feedback required | existing fiber
AAN3199 | 24.115846 | 55.838763 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN2943 | 24.292712 | 55.794188 | AAN | OD | Not 2024 scope | Possible | 220875.38 | 4 months |  | Transport feedback required | MW 2024
AAN3641 | 24.170849 | 55.702970 | AAN | OD | Not 2024 scope | Possible | 280000 | 4 months |  | Transport feedback required | MW 2024
AAN3245 | 24.314310 | 55.537865 | AAN | OD | Not 2024 scope | Possible | 497594.74 | 7 months | this site is dependent on AAN3371 which is in this list. | Transport feedback required | MW 2024
AAN3309 | 24.208221 | 55.804607 | AAN | OD | Not 2024 scope | OSP Provisioned | 40000 |  |  | Transport feedback required | Y2024 fiber scope
AAN3705 | 24.124121 | 55.852140 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN3759 | 24.684420 | 55.704370 | AAN | OD | Not 2024 scope | Possible | 156416.78 | 3 months |  | Transport feedback required | Y2024 fiber scope
AAN3710 | 24.128241 | 55.831722 | AAN | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN3757 | 24.218610 | 55.444570 | AAN | OD | Not 2024 scope | Possible | 25000 | 3 months |  | Transport feedback required | Y2024 fiber scope
AAN3783 | 24.189000 | 55.529230 | AAN | OD | Not 2024 scope | Possible | 120000 | 4 months |  | Transport feedback required | Y2024 fiber scope
AAN3743 | 24.601490 | 55.622480 | AAN | OD | Not 2024 scope | Possible | 366281.94 | 7 months | this site is dependent on AAN3611 which is in this list. | Transport feedback required | MW 2024
AAN3558 | 24.213612 | 55.719689 | AAN | OD | Not 2024 scope | Possible | 134358.18 | 3 months |  | Transport feedback required | Y2024 fiber scope
AAN3611 | 24.62533 | 55.64709 | AAN | OD | Not 2024 scope | Possible | 630162.58 | 8 months |  | Transport feedback required | MW 2024
AUH3099 | 24.091241 | 53.517785 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN3511 | 24.21089 | 55.625819 | AAN | OD | Not 2024 scope | Possible | 113218.6 | 3 months |  | Transport feedback required | Y2024 fiber scope
AUH3813 | 24.504757 | 54.613114 | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH3970 | 24.456518° | 54.600285° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AAN3390 | 24.082200° | 55.678020° | AAN | OD | Not 2024 scope | Possible | 55000 | 4 months |  | Transport feedback required | Y2024 fiber scope
AUH1726 | 24.298820° | 54.600748° | AUH | OD | Not 2024 scope | Possible | 105000 | 5 months |  | Transport feedback required | Y2024 fiber scope
AUH1751 | 24.499969° | 54.394800° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH1756 | 24.500644° | 54.399442° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH1767 | 24.506221° | 54.398301° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH1776 | 24.510828° | 54.397013° | AUH | OD | Not 2024 scope | Taawun |  |  |  | Transport feedback required | Y2024 fiber scope
AUH1848 | 24.1260579 | 54.236613 | AUH | OD | Not 2024 scope | Possible | 680000 |  |  | Transport feedback required | MW 2024
AUH6596 | 24.104470° | 52.793222° | AUH | OD | Not 2024 scope | Site survey required |  |  | CICPA Gate Pass is Required for Site Survey | Transport feedback required | MW 2024

## OD
164 | 164 | 164 | 164 | 164
Sitecode | Region | Latitude | Longitude | Site Type | Scope | Status | Cost | Depandancy | Transport Feedback
AAG6105 | AAN | 24.301 | 55.1264 | Existing | OD | Possible | 1168587.036 |  | to be via MW
AAN2200 | AAN | 23.631 | 55.561 | Existing | OD | Possible | 465948.03 | Depend to Connect AAN2269 | to be via MW
AAN2263 | AAN | 24.1044 | 55.7408 | Existing | OD | Possible | 412056.04 |  | to be via MW
AAN2268 | AAN | 23.7534 | 55.526 | Existing | OD | Possible | 1041620.78 | Depend to Connect AAN3258 | to be via MW
AAN2269 | AAN | 23.6385 | 55.566 | Existing | OD | Possible | 1227183.055 | Depend to Connect AAN2421 | to be via MW
AAN2270 | AAN | 23.5403 | 55.4962 | Existing | OD | Possible | 1123293.78 | Depend to Connect AAN2423 | to be via MW
AAN2271 | AAN | 23.399 | 55.4231 | Existing | OD | Possible | 381278.82 | Depend to Connect AAN2424 | to be via MW
AAN2272 | AAN | 23.3157 | 55.3571 | Existing | OD | Possible | 1410819.31 | Depend to Connect AAN2425 | to be via MW
AAN2273 | AAN | 23.4725 | 55.2967 | Existing | OD | Possible | 1490477.395 | Depend to Connect AAN2383 | to be via MW
AAN2312 | AAN | 24.1454 | 55.5525 | Existing | OD | Possible | 232515.625 | Depend to Connect AAN3276 | to be via MW
AAN2314 | AAN | 24.1776 | 55.4679 | Existing | OD | Possible | 581935.88 |  | to be via MW
AAN2326 | AAN | 24.1206 | 55.4058 | Existing | OD | Possible | 710997.505 | Depend to Connect AAN2588 | to be via MW
AAN2383 | AAN | 23.4285 | 55.4105 | Existing | OD | Possible | 1027449.905 | Depend to Connect AAN3287 | to be via MW
AAN2393 | AAN | 24.0934 | 55.101 | Existing | OD | Possible | 756039.555 |  | to be via MW
AAN2394 | AAN | 24.0304 | 55.1079 | Existing | OD | Possible | 1077294.815 | Depend to Connect AAN2393 | to be via MW
AAN2396 | AAN | 23.9825 | 55.1826 | Existing | OD | Possible | 490163.465 | Depend to Connect AAN3323 | to be via MW
AAN2398 | AAN | 24.0061 | 55.4082 | Existing | OD | Site survey required |  |  | to be via MW
AAN2408 | AAN | 23.8806 | 55.4038 | Existing | OD | Possible | 974941.48 |  | to be via MW
AAN2421 | AAN | 23.7064 | 55.5682 | Existing | OD | Possible | 1377790.505 | Depend to Connect AAN2268 | to be via MW
AAN2422 | AAN | 23.6429 | 55.5335 | Existing | OD | Possible | 328536.255 | Depend to Connect AAN3396 | to be via MW
AAN2423 | AAN | 23.5887 | 55.5346 | Existing | OD | Possible | 854510.375 | Depend to Connect AAN2200 | to be via MW
AAN2424 | AAN | 23.4184 | 55.4229 | Existing | OD | Possible | 411812.24 | Depend to Connect AAN2424 | to be via MW
AAN2425 | AAN | 23.3991 | 55.4009 | Existing | OD | Possible | 381654.18 | Depend to Connect AAN3231 | to be via MW
AAN2426 | AAN | 23.4875 | 55.4572 | Existing | OD | Possible | 1136245.655 | Depend to Connect AAN2270 | to be via MW
AAN2427 | AAN | 23.6323 | 55.5543 | Existing | OD | Possible | 208440.375 | Depend to Connect AAN2200 | to be via MW
AAN2429 | AAN | 24.0325 | 55.6523 | Existing | OD | Possible | 632676.755 | Depend to Connect AAN3113 | to be via MW
AAN2436 | AAN | 24.2127 | 55.9538 | Existing | OD | Possible | 611344.255 |  | to be via MW
AAN2472 | AAN | 24.1399 | 55.4788 | Existing | OD | Possible | 808895.395 | Depend to Connect AAN3280 | to be via MW
AAN2486 | AAN | 24.4368 | 55.1946 | Existing | OD | Possible | 999138.63 |  | to be via MW
AAN2490 | AAN | 24.5756 | 55.3429 | Existing | OD | Possible | 1418931.755 |  | to be via MW
AAN2504 | AAN | 23.584 | 55.4508 | Existing | OD | Possible | 1101991.755 | Depend to Connect AAN2270 | to be via MW
AAN2511 | AAN | 23.9867 | 55.2575 | Existing | OD | Possible | 1585477.63 | Depend to Connect AAN3318 | to be via MW
AAN2513 | AAN | 24.5961 | 55.3952 | Existing | OD | Not possible | 0 |  | to be via MW
AAN2530 | AAN | 24.0895 | 55.9822 | Existing | OD | Possible | 696735.205 |  | to be via MW
AAN2815 | AAN | 24.2627 | 55.7681 | Existing | OD | Possible | 100711.25 |  | Y2024 fiber scope
AAN2849 | AAN | 23.4138 | 55.4064 | Existing | OD | Possible | 265715.09 | Depend to Connect AAN2383 | to be via MW
AAN2871 | AAN | 24.1773 | 55.738 | Existing | OD | Possible | 316791.19 |  | to be via MW
AAN2873 | AAN | 24.6086 | 55.4612 | Existing | OD | Possible | 732147.155 | Depend to Connect AAN3134 | to be via MW
AAN2896 | AAN | 23.3976 | 55.412 | Existing | OD | Possible | 205831.715 | Depend to Connect AAN2425 | to be via MW
AAN2912 | AAN | 23.6423 | 55.554 | Existing | OD | Possible | 399622.24 | Depend to Connect AAN3230 | to be via MW
AAN2914 | AAN | 24.0819 | 56.0133 | Existing | OD | Possible | 612807.055 | Depend to Connect AAN2530 | to be via MW
AAN2944 | AAN | 24.5466 | 55.2078 | Existing | OD | Possible | 958765.9296 |  | to be via MW
AAN3109 | AAN | 24.1073 | 55.748 | Existing | OD | Possible | 219429.66 | Depend to Connect AAN2263 | to be via MW
AAN3113 | AAN | 24.0472 | 55.692 | Existing | OD | Possible | 662054.655 |  | to be via MW
AAN3115 | AAN | 23.6492 | 55.4803 | Existing | OD | Possible | 780340.32 | Depend to Connect AAN2422 | to be via MW
AAN3116 | AAN | 23.5031 | 55.4143 | Existing | OD | Possible | 894213.205 | Depend to Connect AAN2426 | to be via MW
AAN3134 | AAN | 24.5946 | 55.4099 | Existing | OD | Possible | 1143328.045 | Depend to Connect AAN2490 | to be via MW
AAN3154 | AAN | 23.4124 | 55.4235 | Existing | OD | Possible | 184688.16 | Depend to Connect AAN2424 | to be via MW
AAN3167 | AAN | 24.2163 | 55.4768 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3212 | AAN | 24.1502 | 55.6406 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3213 | AAN | 24.1543 | 55.644 | Existing | OD | Possible | 172034.4509 |  | to be via MW
AAN3214 | AAN | 24.1571 | 55.6481 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3223 | AAN | 24.1195 | 55.9681 | Existing | OD | Possible | 446797.54 | Depend to Connect AAN2530 | to be via MW
AAN3230 | AAN | 23.6353 | 55.5489 | Existing | OD | Possible | 210658.955 | Depend to Connect AAN2427 | to be via MW
AAN3231 | AAN | 23.416 | 55.4151 | Existing | OD | Possible | 334765.345 | Depend to Connect AAN2849 | to be via MW
AAN3257 | AAN | 24.4142 | 55.097 | Existing | OD | Possible | 1247278.27 |  | to be via MW
AAN3258 | AAN | 23.8173 | 55.5204 | Existing | OD | Possible | 1124360.405 |  | Y2024 fiber scope
AAN3276 | AAN | 24.1421 | 55.5427 | Existing | OD | Possible | 882015.8384 |  | to be via MW
AAN3279 | AAN | 24.0981 | 55.3651 | Existing | OD | Possible | 789623.005 | Depend to Connect AAN2326 | to be via MW
AAN3280 | AAN | 24.1416 | 55.4198 | Existing | OD | Possible | 425050.58 | Depend to Connect AAN2326 | to be via MW
AAN3283 | AAN | 24.6272 | 55.402 | Existing | OD | Possible | 1278106.78 |  | to be via MW
AAN3284 | AAN | 23.8182 | 55.4609 | Existing | OD | Possible | 799454.24 | Depend to Connect AAN3258 | to be via MW
AAN3286 | AAN | 23.9699 | 55.5181 | Existing | OD | Possible | 722212.305 |  | to be via MW
AAN3287 | AAN | 23.4576 | 55.4414 | Existing | OD | Possible | 564626.08 | Depend to Connect AAN2426 | to be via MW
AAN3289 | AAN | 24.5254 | 55.1481 | Existing | OD | Possible | 1341159.555 | Depend to Connect AAN2944 | to be via MW
AAN3297 | AAN | 24.4059 | 55.1992 | Existing | OD | Possible | 598727.605 | Depend to Connect AAN2486 | to be via MW
AAN3298 | AAN | 24.4019 | 55.1852 | Existing | OD | Possible | 206593.59 | Depend to Connect AAN3297 | to be via MW
AAN3300 | AAN | 24.2706 | 55.7472 | Existing | OD | OSP Provisioned | 34500 |  | Y2024 fiber scope
AAN3308 | AAN | 24.2288 | 55.7499 | Existing | OD | Possible | 34500 |  | Y2024 fiber scope
AAN3312 | AAN | 24.1711 | 55.6583 | Existing | OD | Possible | 76294.68 |  | Y2024 fiber scope
AAN3318 | AAN | 23.997 | 55.3738 | Existing | OD | Possible | 1170037.3366 | Depend to Connect AAN2398 | to be via MW
AAN3323 | AAN | 23.9908 | 55.2132 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN3326 | AAN | 24.4101 | 55.7332 | Existing | OD | Possible | 552070.38 |  | to be via MW
AAN3330 | AAN | 24.0928 | 55.5482 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN3339 | AAN | 23.9051 | 55.411 | Existing | OD | Possible | 356682.965 | Depend to Connect AAN2408 | to be via MW
AAN3340 | AAN | 24.5608 | 55.3452 | Existing | OD | Possible | 1272325.155 | Depend to Connect AAN2490 | to be via MW
AAN3346 | AAN | 24.2121 | 55.7633 | Existing | OD | Possible | 346486.03 |  | to be via MW
AAN3351 | AAN | 24.3615 | 55.6997 | Existing | OD | Possible | 592784.98 |  | to be via MW
AAN3357 | AAN | 24.446 | 55.4571 | Existing | OD | Site survey required | 1441423.8 | tentative cost | to be via MW
AAN3366 | AAN | 24.3378 | 55.6578 | Existing | OD | Possible | 918105.605 |  | to be via MW
AAN3372 | AAN | 24.3346 | 55.3227 | Existing | OD | Possible | 1100598.53 |  | to be via MW
AAN3392 | AAN | 24.2062 | 55.4661 | Existing | OD | Possible | 40250 |  | Y2024 fiber scope
AAN3396 | AAN | 23.6299 | 55.5378 | Existing | OD | Possible | 298609.805 | Depend to Connect AAN3230 | to be via MW
AAN3419 | AAN | 24.1062 | 55.984 | Existing | OD | Possible | 364935.595 | Depend to Connect AAN2914 | to be via MW
AAN3420 | AAN | 24.1217 | 55.6032 | Existing | OD | Possible | 640852.68 |  | to be via MW
AAN3422 | AAN | 24.1365 | 55.1617 | Existing | OD | Possible | 544732 |  | to be via MW
AAN3438 | AAN | 24.1027 | 55.0523 | Existing | OD | Possible | 619091 | Depend to Connect AAN2393 | to be via MW
AAN3498 | AAN | 24.3917 | 55.5146 | Existing | OD | Possible | 2067656.0976 |  | to be via MW
AAN3520 | AAN | 24.0662 | 55.5048 | Existing | OD | Possible | 719329.37 |  | to be via MW
AAN3529 | AAN | 24.198 | 55.7271 | Existing | OD | OSP Ready | 0 |  | Y2024 fiber scope
AAN3530 | AAN | 24.1962 | 55.7258 | Existing | OD | Possible | 43467.01 |  | Y2024 fiber scope
AAN3531 | AAN | 23.9614 | 55.0329 | Existing | OD | Possible | 1893070.43 | Depend to Connect AAN2394,AAN2393 | to be via MW
AAN3534 | AAN | 24.6708 | 55.8315 | Existing | OD | Possible | 1206097.1304 |  | to be via MW
AAN3535 | AAN | 24.0644 | 55.1755 | Existing | OD | Possible | 1280666.68 | Depend to Connect AAN2394 | to be via MW
AAN3537 | AAN | 24.4801 | 55.2305 | Existing | OD | Possible | 514799.455 |  | to be via MW
AAN3542 | AAN | 24.2277 | 55.2998 | Existing | OD | Possible | 664472.0049 |  | to be via MW
AAN3552 | AAN | 24.7168 | 55.6544 | Existing | OD | Possible | 620255.145 |  | to be via MW
AAN3554 | AAN | 24.3377 | 55.714 | Existing | OD | Possible | 589188.93 |  | to be via MW
AAN3555 | AAN | 24.7457 | 55.7613 | Existing | OD | Site survey required | 622711.43 |  | to be via MW
AAN3559 | AAN | 24.5241 | 55.327 | Existing | OD | Possible | 667204.93 |  | to be via MW
AAN3562 | AAN | 24.3851 | 55.0809 | Existing | OD | Possible | 1463336.8476 |  | to be via MW
AAN3566 | AAN | 24.6346 | 55.6148 | Existing | OD | Possible | 687470.805 | Depend to Connect AAN3566 | to be via MW
AAN3567 | AAN | 24.6413 | 55.6643 | Existing | OD | Possible | 563004.81 |  | to be via MW
AAN3568 | AAN | 24.2853 | 55.4098 | Existing | OD | Possible | 375683.61 |  | to be via MW
AAN3570 | AAN | 24.4108 | 55.1278 | Existing | OD | Possible | 542525.61 | Depend to Connect AAN3257 | to be via MW
AAN3573 | AAN | 24.6228 | 55.7378 | Existing | OD | Possible | 434684.1852 |  | to be via MW
AAN3582 | AAN | 24.2251 | 55.7293 | Existing | OD | Possible | 195232.05 |  | to be via MW
AAN3586 | AAN | 24.7727 | 55.7802 | Existing | OD | Possible | 646216.28 | Depend to Connect AAN3555 | to be via MW
AAN3605 | AAN | 24.2219 | 55.7578 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AAN3608 | AAN | 24.0342 | 55.8694 | Existing | OD | Possible | 341131.055 |  | to be via MW
AAN3609 | AAN | 24.0458 | 55.8918 | Existing | OD | Possible | 326442.105 | Depend to Connect AAN3608 | to be via MW
AAN3612 | AAN | 24.3883 | 55.7604 | Existing | OD | Possible | 520232.63 |  | to be via MW
AAN3617 | AAN | 24.0589 | 55.8523 | Existing | OD | Possible | 283502.83 |  | to be via MW
AAN3636 | AAN | 24.4368 | 55.8025 | Existing | OD | Possible | 540903.9444 |  | to be via MW
AAN3642 | AAN | 24.1239 | 55.9381 | Existing | OD | Possible | 677611.3812 |  | to be via MW
AAN3650 | AAN | 24.196181 | 55.6426 | Existing | OD | Possible | 110603.7708 |  | to be via MW
AAN3654 | AAN | 24.7794 | 55.7911 | Existing | OD | Possible | 234155.18 | Depend to Connect AAN3586 | to be via MW
AAN3939 | AAN | 24.3047 | 55.7832 | Existing | OD | Site survey required | 0 |  | to be via MW
AAN3942 | AAN | 24.303 | 55.782 | Existing | OD | Site survey required | 0 |  | to be via MW
AAN2523 | AAN | 24.2553 | 55.6941 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AAN2813 | AAN | 24.0666 | 55.7775 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN2814 | AAN | 24.0599 | 55.7781 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN2856 | AAN | 24.0379 | 55.4657 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AAN2922 | AAN | 24.3032 | 55.7873 | Existing | OD | Site survey required | 0 |  | to be via MW
AAN2311 | AAN | 24.1534 | 55.5832 | Existing | OD | Possible | 627587.43 | Depend to Connect AAN2312 | to be via MW
AAN2560 | AAN | 24.1689 | 55.6333 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN2804 | AAN | 24.0944 | 55.761 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN2810 | AAN | 24.0828 | 55.7691 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN3282 | AAN | 24.483 | 55.6989 | Existing | OD | Possible | 975813.065 |  | to be via MW
AAN2542 | AAN | 24.7837 | 55.813 | Existing | OD | Possible | 586409.61 | Depend to Connect AAN3654 | to be via MW
AAN2514 | AAN | 22.7068 | 55.2122 | Existing | OD | Not Possible | 0 |  | to be via MW
AAN3640 | AAN | 23.8772 | 55.3972 | Existing | OD | Possible | 117316.56 | covering AAN2408 | to be via MW
AAG6104 | AAN | 24.0919 | 55.9237 | Existing | OD | Possible | 40332.3216 |  | Y2024 fiber scope
AUG4246 | AUH | 24.5008 | 54.6187 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUG4264 | AUH | 24.4824 | 54.6114 | Existing | OD | Possible | 212603.26 |  | to be via MW
AUG4273 | AUH | 24.5069 | 54.6215 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUG4279 | AUH | 24.4841 | 54.4059 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG4289 | AUH | 24.4644 | 54.656 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUG4357 | AUH | 24.289 | 54.6333 | Existing | OD | Possible | 537277.815 |  | to be via MW
AUG4375 | AUH | 24.2939 | 54.6255 | Existing | OD | Possible | 381654.18 | Depend to Connect AUG4357 | to be via MW
AUG4408 | AUH | 24.541 | 54.4413 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG4418 | AUH | 24.3923 | 54.5006 | Existing | OD | Possible | 242779.605 |  | to be via MW
AUG4447 | AUH | 24.4511 | 54.6773 | Existing | OD | Possible | 40250 |  | Y2024 fiber scope
AUG6011 | AUH | 24.5095 | 54.454 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6012 | AUH | 24.5094 | 54.4515 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6015 | AUH | 24.5076 | 54.391 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6020 | WR | 23.9612 | 52.2406 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6034 | AUH | 24.4595 | 54.6692 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6051 | AUH | 24.5603 | 54.6382 | Existing | OD | Possible | 259479.905 |  | to be via MW
AUG6052 | AUH | 24.4046 | 54.5124 | Existing | OD | Possible | 430657.98 |  | to be via MW
AUG6056 | AUH | 24.5224 | 54.3721 | Existing | OD | Possible | 257880.83 | Depend to Connect AUH2555 | to be via MW
AUG6081 | AUH | 24.5118 | 54.4532 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6082 | AUH | 24.4982 | 54.9338 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6083 | AUH | 24.3213 | 54.5962 | Existing | OD | Possible | 264217.1 |  | to be via MW
AUG6093 | WR | 24.0532 | 52.4475 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6098 | AUH | 24.6436 | 55.119 | Existing | OD | Military - Site survey required | 0 |  | to be via MW
AUG6104 | WR | 23.9753 | 52.2658 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6105 | WR | 23.9707 | 52.2515 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6114 | AUH | 24.3277 | 54.6104 | Existing | OD | Not Possible | 0 |  | to be via MW
AUG6155 | AUH | 24.5027 | 54.3804 | Existing | OD | Possible | 104206.692 |  | to be via MW
AUG6244 | AUH | 24.4218 | 54.6801 | Existing | OD | Possible | 101332.94 |  | to be via MW
AUG6245 | WR | 22.8944 | 54.364 | Existing | OD | Possible | 372531.276 |  | to be via MW
AUH2128 | AUH | 24.5031 | 54.488 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2155 | AUH | 24.4119 | 54.4681 | Existing | OD | Possible | 208896.35 |  | to be via MW
AUH2010 | AUH | 24.4764 | 54.698 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2005 | AUH | 24.5013 | 54.371 | Existing | OD | Possible | 226358.87 |  | to be via MW
AUH2091 | AUH | 24.4517 | 54.356 | Existing | OD | Possible | 34500 |  | Y2024 fiber scope
AUH2100 | AUH | 24.4249 | 54.4156 | Existing | OD | Possible | 152906.99 |  | to be via MW
AUH2095 | AUH | 24.4117 | 54.4579 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH2105 | AUH | 24.4054 | 54.5043 | Existing | OD | Possible | 50738.345 |  | Y2024 fiber scope
AUH2106 | AUH | 24.4064 | 54.518 | Existing | OD | Possible | 411793.955 |  | to be via MW
AUH2110 | AUH | 24.4228 | 54.5343 | Existing | OD | Possible | 476400.955 |  | to be via MW
AUH2113 | AUH | 24.4326 | 54.58 | Existing | OD | Possible | 144010.13 |  | to be via MW
AUH2171 | AUH | 24.4241 | 54.5772 | Existing | OD | Possible | 201065.425 |  | to be via MW
AUH2243 | AUH | 24.3708 | 54.6301 | Existing | OD | Possible | 155761.29 |  | to be via MW
AUH2157 | AUH | 24.4315 | 54.5689 | Existing | OD | Possible | 34500 |  | Y2024 fiber scope
AUH2168 | AUH | 24.2234 | 54.5443 | Existing | OD | Military - Site survey required | 0 |  | to be via MW
AUH2167 | AUH | 24.0906 | 54.8973 | Existing | OD | Possible | 813466.645 |  | to be via MW
AUH2169 | AUH | 24.5979 | 54.9834 | Existing | OD | Possible | 1236760.83 |  | to be via MW
AUH2175 | AUH | 24.8157 | 54.8711 | Existing | OD | Not possible | 0 |  | to be via MW
AUH2186 | AUH | 24.4817 | 54.3552 | Existing | OD | Possible | 34500 |  | Y2024 fiber scope
AUH2187 | AUH | 24.4586 | 54.3595 | Existing | OD | Possible | 34500 |  | Y2024 fiber scope
AUH2191 | WR | 24.3662 | 52.5945 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2196 | WR | 24.3188 | 52.5987 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2197 | AUH | 24.4981 | 54.3693 | Existing | OD | Possible | 376616.03 |  | to be via MW
AUH2190 | WR | 24.2892 | 52.5616 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2201 | AUH | 24.4201 | 54.5653 | Existing | OD | Possible | 128086.333 |  | to be via MW
AUH2216 | AUH | 24.3298 | 54.5462 | Existing | OD | Possible | 299755.665 | Depend to Connect AUH2216 | to be via MW
AUH2232 | AUH | 24.4903 | 54.3725 | Existing | OD | Possible | 171040.19 |  | to be via MW
AUH2239 | AUH | 24.4181 | 54.5024 | Existing | OD | Possible | 344279.64 |  | to be via MW
AUH2240 | AUH | 24.4966 | 54.3698 | Existing | OD | Possible | 220813.34 | Depend to Connect AUH2197 | to be via MW
AUH2247 | AUH | 24.492 | 54.3734 | Existing | OD | Possible | 100904.45 |  | Y2024 fiber scope
AUH2272 | AUH | 24.4263 | 54.4754 | Existing | OD | 2023 scope | 46000 |  | Y2024 fiber scope
AUH2273 | AUH | 24.3105 | 54.5191 | Existing | OD | Possible | 359773.13 |  | to be via MW
AUH2274 | AUH | 24.8344 | 54.8861 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2313 | AUH | 24.47 | 54.3402 | Existing | OD | Possible | 0 |  | Y2024 fiber scope
AUH2317 | AUH | 24.4614 | 54.367 | Existing | OD | Possible | 437890.1 |  | to be via MW
AUH2354 | AUH | 24.4393 | 54.5199 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2357 | AUH | 24.4216 | 54.5079 | Existing | OD | Possible | 152981.32 |  | to be via MW
AUH2356 | AUH | 24.7475 | 54.6576 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2370 | AUH | 24.3586 | 54.5358 | Existing | OD | Possible | 220612.09 | Depend to Connect AUH3685 | to be via MW
AUH2379 | AUH | 24.3274 | 54.5571 | Existing | OD | Possible | 231302.72 |  | to be via MW
AUH2380 | AUH | 24.3377 | 54.5524 | Existing | OD | Possible | 266702.48 |  | to be via MW
AUH2384 | AUH | 24.3339 | 54.5559 | Existing | OD | Possible | 206678.92 | Depend to Connect AUH2380 | to be via MW
AUH2401 | AUH | 24.2885 | 54.6405 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2443 | AUH | 24.5133 | 54.3718 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2441 | AUH | 24.4341 | 54.5988 | Existing | OD | Possible | 298908.46 |  | to be via MW
AUH2445 | AUH | 24.4146 | 54.6033 | Existing | OD | Possible | 125566.66 |  | to be via MW
AUH2451 | AUH | 24.4268 | 54.552 | Existing | OD | Possible | 160295.97 |  | to be via MW
AUH2462 | AUH | 24.8431 | 54.7776 | Existing | OD | Site survey required | 619916.355 | tentative cost-Depend to Connect AUH2819 | to be via MW
AUH2470 | AUH | 24.3551 | 54.5526 | Existing | OD | Possible | 413707.785 | Depend to Connect AUH2646 | to be via MW
AUH2477 | AUH | 24.273 | 55.0048 | Existing | OD | Possible | 1366789.03 |  | to be via MW
AUH2485 | AUH | 24.5756 | 55.1724 | Existing | OD | Possible | 997276.8931 | Depend to Connect AUH2774 | to be via MW
AUH2487 | AUH | 24.8032 | 54.7072 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2491 | AUH | 24.4681 | 54.4039 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2514 | AUH | 24.7285 | 54.6411 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2526 | WR | 24.2449 | 54.3415 | Existing | OD | Possible | 649903.755 | Depend to Connect AUH2772 | to be via MW
AUH2766 | WR | 24.895 | 53.0657 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2501 | WR | 24.2127 | 52.0091 | Existing | OD |  | 0 |  | to be via MW
AUH2541 | AUH | 24.4083 | 54.4981 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2553 | AUH | 24.4128 | 54.5682 | Existing | OD | Possible | 130570.655 |  | to be via MW
AUH2555 | AUH | 24.5185 | 54.3735 | Existing | OD | Possible | 538471.992 |  | to be via MW
AUH2565 | AUH | 24.3916 | 54.648 | Existing | OD | Possible | 423618.255 |  | to be via MW
AUH2566 | AUH | 24.7825 | 54.8547 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2584 | AUH | 24.4982 | 54.5925 | Existing | OD | Possible | 23000 |  | Y2024 fiber scope
AUH2581 | AUH | 24.2562 | 54.6278 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH2610 | AUH | 24.261 | 54.5469 | Existing | OD | Not possible | 0 |  | to be via MW
AUH2612 | AUH | 24.4961 | 54.4086 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2621 | AUH | 24.1012 | 54.974 | Existing | OD | Possible | 1977388.66 | Depend to Connect AUH2622 | to be via MW
AUH2622 | AUH | 24.1187 | 54.8327 | Existing | OD | Possible | 872493.155 | Depend to Connect AUH2847 | to be via MW
AUH2624 | AUH | 24.0273 | 54.9623 | Existing | OD | Possible | 1952594.2 | Depend to Connect AUH2623 | to be via MW
AUH2629 | AUH | 24.4232 | 54.3974 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2630 | AUH | 24.4527 | 54.3388 | Existing | OD | Possible | 195220.452 |  | to be via MW
AUH2623 | AUH | 24.0695 | 54.8199 | Existing | OD | Possible | 779117.755 | Depend to Connect AUH2622 | to be via MW
AUH2641 | AUH | 24.5206 | 54.6104 | Existing | OD | Possible | 551911.91 |  | to be via MW
AUH2646 | AUH | 24.3519 | 54.5583 | Existing | OD | Possible | 243297.68 |  | to be via MW
AUH2648 | AUH | 24.4509 | 54.6014 | Existing | OD | tabreed | 60000 |  | Y2024 fiber scope
AUH2650 | AUH | 24.3643 | 54.552 | Existing | OD | Possible | 295934.1 |  | to be via MW
AUH2658 | AUH | 24.4147 | 54.5395 | Existing | OD | Site survey required | 230000 | tentative cost | to be via MW
AUH2659 | AUH | 24.4077 | 54.531 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2666 | AUH | 24.5841 | 54.7118 | Existing | OD | Possible | 397905.98 |  | to be via MW
AUH2662 | AUH | 24.5932 | 54.7543 | Existing | OD | Possible | 570142.055 |  | to be via MW
AUH2689 | AUH | 24.4193 | 54.5295 | Existing | OD | Possible | 240319.755 | Depend to Connect AUH2110 | to be via MW
AUH2681 | AUH | 24.3892 | 54.2207 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2691 | AUH | 24.2425 | 54.932 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2768 | WR | 24.0695 | 53.9119 | Existing | OD | Possible | 597413.4051 |  | to be via MW
AUH2695 | AUH | 24.7876 | 54.7289 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2696 | AUH | 24.7952 | 54.7156 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2697 | AUH | 24.7881 | 54.711 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2709 | AUH | 24.9015 | 54.8865 | Existing | OD | Possible | 911211.3485 |  | to be via MW
AUH2772 | WR | 24.2542 | 54.3862 | Existing | OD | Possible | 827625.33 |  | to be via MW
AUH2700 | AUH | 24.7918 | 54.7231 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2719 | AUH | 24.4408 | 54.6267 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2722 | AUH | 24.3281 | 54.6607 | Existing | OD | Possible | 369055.815 |  | to be via MW
AUH2780 | WR | 23.6249 | 53.3678 | Existing | OD | Possible | 655834.1033 | Depend to Connect AUH2989 | to be via MW
AUH2730 | WR | 24.1157 | 51.7771 | Existing | OD | Possible | 1288372.6 | depend on AUH6479 | to be via MW
AUH2733 | AUH | 24.7736 | 54.7119 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2734 | AUH | 24.7829 | 54.7054 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2736 | WR | 23.8158 | 52.7462 | Existing | OD | Possible | 1477145.6796 |  | to be via MW
AUH2781 | WR | 24.094 | 52.4771 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2752 | AUH | 24.4308 | 54.6198 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2754 | AUH | 24.5228 | 54.3629 | Existing | OD | Possible | 446484.74 | Depend to Connect AUH2300 | to be via MW
AUH2785 | WR | 23.9607 | 52.1218 | Existing | OD | Possible | 658396.0404 |  | to be via MW
AUH2770 | AUH | 24.3127 | 54.5364 | Existing | OD | Possible | 192038.73 |  | to be via MW
AUH2788 | WR | 23.1463 | 53.9628 | Existing | OD | Possible | 912782.9721 |  | to be via MW
AUH2765 | AUH | 24.3254 | 54.4573 | Existing | OD | Site survey required | 690000 | tentative cost- depend to connect AUH3182 | to be via MW
AUH2769 | AUH | 24.3171 | 54.4584 | Existing | OD | Site survey required | 287500 | tentative cost-depend to connect AUH3180 | to be via MW
AUH2771 | WR | 24.1844 | 52.626 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2774 | AUH | 24.6116 | 55.1303 | Existing | OD | Possible | 1405342.435 | Depend to Connect AUH2615 | to be via MW
AUH2789 | WR | 23.5287 | 53.265 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH2790 | WR | 24.1712 | 51.9938 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3187 | AUH | 24.4523 | 54.4692 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3189 | AUH | 24.5837 | 54.6756 | Existing | OD | Possible | 389711.77 |  | to be via MW
AUH2794 | AUH | 24.5256 | 54.6656 | Existing | OD | Possible | 345870.435 | Depend to Connect AUH3519 | to be via MW
AUH2791 | WR | 23.1401 | 53.6434 | Existing | OD | Possible | 1030445.08 |  | to be via MW
AUH2803 | AUH | 24.4833 | 54.6012 | Existing | OD | Possible | 195500 |  | to be via MW
AUH2810 | AUH | 24.5036 | 54.3923 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2819 | AUH | 24.8233 | 54.8008 | Existing | OD | Possible | 1705722.4557 |  | to be via MW
AUH3214 | AUH | 24.3311 | 54.6001 | Existing | OD |  | 0 |  | to be via MW
AUH2822 | AUH | 24.4535 | 54.6708 | Existing | OD | Possible | 69492.66 |  | Y2024 fiber scope
AUH2825 | AUH | 24.4561 | 54.6731 | Existing | OD | Not possible | 0 |  | to be via MW
AUH2828 | AUH | 24.364 | 54.8219 | Existing | OD | Possible | 740832.53 |  | to be via MW
AUH2841 | AUH | 24.4485 | 54.5085 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2824 | AUH | 24.4577 | 54.6754 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH2843 | AUH | 24.5392 | 54.4246 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2842 | AUH | 24.4599 | 54.5039 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2861 | WR | 24.0745 | 53.5411 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2852 | AUH | 24.4431 | 54.526 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2854 | WR | 24.1273 | 52.7296 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2869 | WR | 24.2479 | 51.6288 | Existing | OD | Possible | 2015484.2218 |  | to be via MW
AUH2873 | AUH | 24.4557 | 54.6661 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2880 | WR | 24.1335 | 52.8134 | Existing | OD | Site survey required | 590593.31 |  | to be via MW
AUH2888 | AUH | 24.5027 | 54.5996 | Existing | OD | Possible | 0 |  | Y2024 fiber scope
AUH2939 | WR | 23.7565 | 53.6474 | Existing | OD | Possible | 1454351.7099 |  | to be via MW
AUH2942 | WR | 23.8986 | 53.8613 | Existing | OD | Possible | 619649.4773 |  | to be via MW
AUH2943 | WR | 23.7269 | 53.8558 | Existing | OD | Possible | 1004384.9055 | Depend to Connect AUH2983 | to be via MW
AUH2944 | WR | 23.7809 | 54.0624 | Existing | OD | Possible | 2359673.155 | Depend to Connect AUH3296 | to be via MW
AUH2945 | WR | 23.9278 | 54.1924 | Existing | OD | Possible | 1669588.63 | Depend to Connect AUH2946 | to be via MW
AUH2946 | WR | 23.76 | 54.2746 | Existing | OD | Possible | 3356562.73 | Depend to Connect AUH2944 | to be via MW
AUH2955 | WR | 23.5487 | 53.2968 | Existing | OD | Site survey required | 0 | CICPA / LONG ROUTE | to be via MW
AUH2958 | WR | 23.79 | 52.6829 | Existing | OD | Possible | 67886.4241 | Proposed route is dependent on AUH2959 proposal | to be via MW
AUH2959 | WR | 23.8484 | 52.4785 | Existing | OD | Possible | 2756457.655 | Depend to Connect AUH2968 | to be via MW
AUH2961 | WR | 23.524 | 52.9965 | Existing | OD | Possible | 2195809.08 |  | to be via MW
AUH2968 | WR | 23.7865 | 52.5683 | Existing | OD | Possible | 1801797.805 | Depend to Connect AUH2958 | to be via MW
AUH2969 | WR | 24.1793 | 52.572 | Existing | OD | Possible | 1199368.005 |  | to be via MW
AUH2971 | WR | 24.1136 | 53.435 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2964 | WR | 23.347 | 53.1158 | Existing | OD | Possible | 2899354.93 | Depend to Connect AUH2961 | to be via MW
AUH2965 | WR | 23.209 | 53.1895 | Existing | OD | Possible | 2416204.28 | Depend to Connect AUH2966 | to be via MW
AUH2966 | WR | 23.0965 | 53.3392 | Existing | OD | Possible | 1760747.98 |  | to be via MW
AUH2977 | WR | 24.3188 | 54.1453 | Existing | OD | Possible | 669712.505 | Depend to Connect AUH3679,AUH6348,AUH6425,AUH6382 | to be via MW
AUH2982 | WR | 24.1427 | 53.1558 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2987 | WR | 23.9166 | 53.6577 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2983 | WR | 23.6681 | 53.7548 | Existing | OD | Possible | 505620.385 |  | to be via MW
AUH2995 | WR | 24.8825 | 53.069 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2989 | WR | 23.6023 | 53.3934 | Existing | OD | Possible | 1400746.2307 |  | to be via MW
AUH2035 | AUH | 24.5268 | 54.375 | Existing | OD | Possible | 368760.38 |  | to be via MW
AUH2038 | AUH | 24.6104 | 54.5225 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3236 | AUH | 24.4172 | 54.3325 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3111 | AUH | 24.3119 | 54.5489 | Existing | OD | Possible | 271499.245 |  | to be via MW
AUH3105 | AUH | 24.615 | 54.4782 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3108 | AUH | 24.5162 | 54.9708 | Existing | OD | 2023 scope | 298706.3705 |  | Y2024 fiber scope
AUH3113 | AUH | 24.8053 | 54.6411 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3118 | AUH | 24.2685 | 54.5623 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3119 | AUH | 24.2651 | 54.5562 | Existing | OD | Possible | 15353.6155 |  | Y2024 fiber scope
AUH3122 | AUH | 24.4518 | 54.3093 | Existing | OD | internal connection -ste survey required |  |  | to be via MW
AUH3114 | AUH | 24.7939 | 54.6508 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3116 | WR | 23.6508 | 53.8022 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3117 | AUH | 24.2772 | 54.5541 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3129 | AUH | 24.5277 | 54.3914 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3136 | AUH | 24.3605 | 54.5547 | Existing | OD | Possible | 259327.53 |  | to be via MW
AUH3143 | AUH | 24.8423 | 55.028 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3132 | AUH | 24.4069 | 54.575 | Existing | OD | Possible | 239317.645 |  | to be via MW
AUH3154 | AUH | 24.4594 | 54.3007 | Existing | OD | Possible |  |  | to be via MW
AUH3157 | AUH | 24.5451 | 54.4357 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3147 | WR | 24.1062 | 52.6705 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3168 | AUH | 24.6754 | 54.6023 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3169 | AUH | 24.4215 | 54.3933 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3170 | AUH | 24.4245 | 54.3946 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3171 | AUH | 24.4255 | 54.3937 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3159 | WR | 24.1351 | 53.2749 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3162 | AUH | 24.3006 | 54.6147 | Existing | OD | Possible | 341335.755 | Depend to Connect AUH3163 | to be via MW
AUH3180 | AUH | 24.3182 | 54.467 | Existing | OD | Site survey required | 149500 |  | to be via MW
AUH3163 | AUH | 24.2972 | 54.62 | Existing | OD | Possible | 352507.89 | Depend to Connect AUH3163 | to be via MW
AUH3181 | AUH | 24.4871 | 54.4134 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3193 | AUH | 24.412 | 54.5354 | Existing | OD | internal connection | 0 | Depend to Connect AUH2658 | to be via MW
AUH3182 | AUH | 24.3255 | 54.4665 | Existing | OD | Site survey required | 224250 |  | to be via MW
AUH3222 | WR | 23.9152 | 53.6994 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3393 | AUH | 24.5431 | 54.4421 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3413 | AUH | 24.3347 | 54.6793 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3239 | AUH | 24.4984 | 54.6253 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3240 | WR | 24.1208 | 52.6855 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3242 | AUH | 24.4732 | 54.3484 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3249 | WR | 24.0657 | 52.8215 | Existing | OD | Possible | 1183124.83 |  | to be via MW
AUH3274 | AUH | 24.4718 | 54.3474 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3275 | AUH | 24.4301 | 54.4364 | Existing | OD | Possible | 127799.96 |  | to be via MW
AUH2255 | AUH | 24.7987 | 54.723 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2287 | WR | 24.4888 | 52.32 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2288 | WR | 24.5171 | 52.3104 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3281 | AUH | 24.3407 | 54.5484 | Existing | OD | Possible | 232393.725 | Depend to Connect AUH2380 | to be via MW
AUH3283 | AUH | 24.6584 | 54.5773 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3296 | WR | 23.7981 | 53.9107 | Existing | OD | Possible | 1610284.28 | Depend to Connect AUH2943 | to be via MW
AUH2299 | AUH | 24.4507 | 54.6076 | Existing | OD | Possible | 0 |  | Y2024 fiber scope
AUH2300 | AUH | 24.5165 | 54.3644 | Existing | OD | Possible | 547310.3 | Depend to Connect AUG6056 | to be via MW
AUH2289 | WR | 24.4577 | 52.3123 | Existing | OD |  | 0 |  | to be via MW
AUH2291 | AUH | 24.4406 | 54.8292 | Existing | OD | Possible | 214303.765 |  | to be via MW
AUH3469 | WR | 23.085 | 53.5566 | Existing | OD | Possible | 822885.95 |  | to be via MW
AUH3312 | WR | 23.66 | 53.8409 | Existing | OD | Military - Site survey required | 0 |  | to be via MW
AUH3544 | WR | 24.3021 | 52.6388 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3558 | WR | 24.3443 | 52.6408 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3367 | AUH | 24.2768 | 54.9562 | Existing | OD | Possible | 1969160.41 | Depend to Connect AUH2477 | to be via MW
AUH3369 | AUH | 24.4631 | 54.3719 | Existing | OD | Possible | 297658.985 |  | to be via MW
AUH3381 | AUH | 24.6317 | 54.535 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3390 | AUH | 24.7411 | 54.8902 | Existing | OD | OSP Ready | 0 |  | Y2024 fiber scope
AUH3391 | AUH | 24.5457 | 54.4475 | Existing | OD | Not possible | 0 |  | to be via MW
AUH2617 | AUH | 24.437 | 54.3679 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH2394 | AUH | 24.4466 | 54.2828 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3638 | AUH | 24.4382 | 54.487 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3395 | AUH | 24.6801 | 54.8268 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3442 | AUH | 24.4512 | 54.3333 | Existing | OD | Possible | 494444.57 |  | to be via MW
AUH2465 | AUH | 24.3956 | 54.2969 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3466 | WR | 22.9476 | 53.3438 | Existing | OD | Possible | 1155910.655 |  | to be via MW
AUH3725 | AUH | 24.2674 | 54.6586 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2474 | AUH | 24.4922 | 54.3932 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3484 | WR | 23.3553 | 53.7689 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH3486 | WR | 24.1204 | 52.7246 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3494 | WR | 23.7807 | 53.5643 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH3496 | AUH | 24.3659 | 54.1927 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3488 | AUH | 24.476 | 54.508 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2500 | AUH | 24.4348 | 54.6356 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3489 | AUH | 24.448 | 54.5653 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3490 | WR | 24.1249 | 51.6211 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH2504 | AUH | 24.5779 | 51.7209 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2505 | AUH | 25.2418 | 54.2299 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2506 | WR | 25.1478 | 52.8781 | Existing | OD |  | 0 |  | to be via MW
AUH2507 | WR | 25.1449 | 52.8719 | Existing | OD |  | 0 |  | to be via MW
AUH3497 | WR | 23.8896 | 53.937 | Existing | OD | Possible | 1743612.405 | Depend to Connect AUH3296 | to be via MW
AUH3502 | AUH | 24.8896 | 54.8441 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2503 | AUH | 24.5892 | 51.7303 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2509 | AUH | 24.3298 | 54.9156 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3523 | AUH | 24.4029 | 54.5564 | Existing | OD | Possible | 392235.1 |  | to be via MW
AUH3536 | AUH | 24.3369 | 54.4631 | Existing | OD | Site survey required | 224250 |  | to be via MW
AUH2537 | AUH | 24.6171 | 54.4741 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3555 | AUH | 24.1783 | 54.7025 | Existing | OD | Site survey required | 195500 |  | to be via MW
AUH3540 | AUH | 24.3217 | 54.5675 | Existing | OD | Possible | 132834.338 |  | to be via MW
AUH3547 | AUH | 24.2547 | 54.6314 | Existing | OD | Possible | 263947.54 |  | to be via MW
AUH3578 | WR | 24.1938 | 54.4727 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3571 | AUH | 24.4897 | 54.4438 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3606 | AUH | 24.4573 | 54.3153 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3615 | AUH | 24.2524 | 54.6268 | Existing | OD | Possible | 116192.55 |  | to be via MW
AUH3781 | AUH | 24.5376 | 54.4186 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3603 | WR | 24.0009 | 53.7296 | Existing | OD | Possible | 549810.2556 |  | to be via MW
AUH3628 | WR | 23.6989 | 52.3428 | Existing | OD | Possible | 2149639.455 | AUH3621,AUH2959,AUH3808,AUH2968,AUH2958 | to be via MW
AUH3629 | WR | 23.8633 | 52.6455 | Existing | OD | Possible | 1212746.53 | Depend to Connect AUH2958 | to be via MW
AUH3630 | WR | 24.002 | 52.6794 | Existing | OD | Possible | 1229203.03 |  | to be via MW
AUH3631 | WR | 24.0138 | 52.849 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3621 | WR | 23.6778 | 52.4927 | Existing | OD | Possible | 1102853.68 | Depend to Connect AUH2959 | to be via MW
AUH3635 | AUH | 24.5083 | 54.6015 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3626 | WR | 24.8817 | 53.084 | Existing | OD |  | 0 |  | to be via MW
AUH3641 | WR | 23.6724 | 52.7193 | Existing | OD | Site survey required | 1679101.6643 |  | to be via MW
AUH3633 | AUH | 24.4919 | 54.4112 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3646 | WR | 23.968 | 52.9216 | Existing | OD | Possible | 664180.5438 |  | to be via MW
AUH3647 | WR | 23.8484 | 53.6387 | Existing | OD | Site survey required | 1814475.1227 |  | to be via MW
AUH3648 | WR | 23.8871 | 52.965 | Existing | OD | Possible | 1434008.4154 |  | to be via MW
AUH3649 | WR | 23.818 | 52.3769 | Existing | OD | Possible | 1640889.805 | AUH3628,AUH3621,AUH2959,AUH3808,AUH2968,AUH2958 | to be via MW
AUH3651 | WR | 24.0532 | 52.9823 | Existing | OD | Possible | 1098489.9273 |  | to be via MW
AUH3653 | WR | 23.6892 | 52.5855 | Existing | OD | Site survey required | 2794527.9841 |  | to be via MW
AUH3654 | WR | 24.0788 | 52.6478 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3657 | WR | 23.6508 | 53.7297 | Existing | OD | Possible | 237691.0723 |  | to be via MW
AUH3667 | WR | 23.9721 | 53.4312 | Existing | OD | Possible | 2509678.5947 | AUH3289 | to be via MW
AUH3663 | AUH | 24.4995 | 54.4128 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3664 | AUH | 24.5063 | 54.4114 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3674 | WR | 23.16 | 53.7318 | Existing | OD | Possible | 594164.98 | Depend to Connect AUH6395 | to be via MW
AUH3684 | WR | 24.4697 | 52.3121 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3675 | WR | 24.1183 | 52.7753 | Existing | OD | Site survey required | 412061.4127 |  | to be via MW
AUH3784 | AUH | 24.4599 | 54.6344 | Existing | OD | Site survey required | 271820.4216 |  | to be via MW
AUH3679 | WR | 24.2495 | 54.1735 | Existing | OD | Possible | 1662923.4852 |  | to be via MW
AUH3685 | AUH | 24.3625 | 54.5316 | Existing | OD | Possible | 375199.575 |  | to be via MW
AUH3706 | WR | 24.1308 | 54.28 | Existing | OD | Possible | 812078.7211 |  | to be via MW
AUH3716 | AUH | 24.4805 | 54.32 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3722 | WR | 23.6454 | 53.6848 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3724 | AUH | 24.2786 | 54.6791 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3785 | AUH | 24.4326 | 54.6697 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3787 | AUH | 24.497 | 54.9263 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH3744 | AUH | 24.5386 | 54.4079 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3747 | AUH | 24.566 | 54.4583 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3748 | AUH | 24.5753 | 54.4664 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3789 | AUH | 24.4512 | 54.6325 | Existing | OD | Site survey required | 381972.1872 |  | to be via MW
AUH3755 | WR | 24.0856 | 53.5213 | Existing | OD | Possible | 106611.5272 |  | to be via MW
AUH3757 | WR | 23.3016 | 54.2218 | Existing | OD | Site survey required | 2258850.1983 |  | to be via MW
AUH3760 | WR | 23.7027 | 53.1936 | Existing | OD | Possible | 41960.1493 |  | Y2024 fiber scope
AUH3762 | WR | 24.279 | 52.6236 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3812 | WR | 23.7977 | 52.5935 | Existing | OD | Possible | 459346.1147 | Depend to Connect AUH2968,AUH2958 | to be via MW
AUH3817 | AUH | 24.4667 | 54.3285 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3795 | WR | 22.928 | 53.991 | Existing | OD | Site survey required | 1297039.8912 |  | to be via MW
AUH3798 | AUH | 24.5386 | 54.4129 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3801 | AUH | 24.3154 | 54.6237 | Existing | OD | Possible | 84717.97 |  | Y2024 fiber scope
AUH3808 | WR | 23.7779 | 52.5694 | Existing | OD | Possible | 263950.07 | Depend to Connect AUH2968,AUH2958 | to be via MW
AUH3860 | AUH | 24.7733 | 54.7872 | Existing | OD | Site survey required | 799322.68 | Depend to Connect AUH2819 | to be via MW
AUH3818 | AUH | 24.4687 | 54.3321 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3819 | WR | 24.1394 | 52.6914 | Existing | OD | Site survey required | 3714292.427 |  | to be via MW
AUH3831 | AUH | 24.3385 | 54.4958 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH3833 | AUH | 24.5421 | 54.4303 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2847 | AUH | 24.1483 | 54.7932 | Existing | OD | Possible | 466657.58 |  | to be via MW
AUH2849 | AUH | 24.0831 | 54.7189 | Existing | OD | Possible | 1055239.54 | Depend to Connect AUH2623 | to be via MW
AUH3879 | AUH | 24.4143 | 54.3511 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3796 | WR | 22.9803 | 53.9755 | Existing | OD | Site survey required | 993514.3142 |  | to be via MW
AUH3834 | AUH | 24.608 | 54.697 | Existing | OD | Possible | 649468.48 |  | to be via MW
AUH3954 | WR | 24.0697 | 53.5023 | Existing | OD | Possible | 309595.471 |  | to be via MW
AUH2893 | AUH | 24.3334 | 54.8067 | Existing | OD | Possible | 570477.28 |  | to be via MW
AUH2016 | AUH | 24.4328 | 54.5028 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3928 | AUH | 24.2295 | 54.6806 | Existing | OD | Possible | 214578.04 |  | to be via MW
AUH3922 | WR | 23.2578 | 54.309 | Existing | OD | OSP Ready | 0 |  | Y2024 fiber scope
AUH3930 | AUH | 24.3224 | 54.7558 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3946 | AUH | 24.4731 | 54.34 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3947 | AUH | 24.4739 | 54.3411 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3966 | AUH | 24.4778 | 54.3445 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3967 | AUH | 24.4765 | 54.3436 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3968 | AUH | 24.4719 | 54.3376 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3969 | AUH | 24.4704 | 54.3351 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3313 | AUH | 24.4325 | 54.3784 | Existing | OD | Possible | 74052.41 |  | Y2024 fiber scope
AUH3973 | WR | 22.8657 | 54.0955 | Existing | OD | Possible | 1890527.6989 |  | to be via MW
AUH3974 | AUH | 24.4436 | 54.5802 | Existing | OD | Tabreed | 60000 |  | Y2024 fiber scope
AUH3975 | AUH | 24.4423 | 54.5773 | Existing | OD | Tabreed | 60000 |  | Y2024 fiber scope
AUH3387 | AUH | 24.4187 | 54.4283 | Existing | OD | Possible | 285844.46 |  | to be via MW
AUH3388 | AUH | 24.5318 | 54.4261 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3411 | AUH | 24.3449 | 54.6792 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3546 | WR | 24.2701 | 52.6033 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3985 | WR | 23.9464 | 53.7912 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3031 | AUH | 24.834 | 54.7586 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3559 | WR | 24.3272 | 52.5652 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3043 | AUH | 24.2951 | 54.9129 | Existing | OD | Possible | 878399.21 | Depend to Connect AUH3367 | to be via MW
AUH3044 | AUH | 24.5673 | 54.999 | Existing | OD | Possible | 222552.83 | Depend to Connect AUH2169 | to be via MW
AUH3045 | AUH | 24.5189 | 55.0193 | Existing | OD | Possible | 792249.95 |  | to be via MW
AUH3560 | WR | 23.9775 | 52.2706 | Existing | OD | Site survey required | 203070.7167 |  | to be via MW
AUH3039 | AUH | 24.5155 | 54.7499 | Existing | OD | Possible | 616457.96 |  | to be via MW
AUH3072 | AUH | 24.2991 | 54.6729 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3064 | AUH | 24.4406 | 54.7299 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH3085 | AUH | 24.8207 | 54.6589 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3084 | AUH | 24.4032 | 54.6888 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3115 | WR | 23.6457 | 53.8188 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3644 | AUH | 24.474 | 54.417 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3149 | AUH | 24.3235 | 54.5313 | Existing | OD | Taawun |  |  | Y2024 fiber scope
AUH2200 | AUH | 24.5011 | 54.3773 | Existing | OD | 2023 scope | 126500 |  | Y2024 fiber scope
AUH3086 | AUH | 24.7912 | 54.6661 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3087 | AUH | 24.7876 | 54.6936 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3219 | AUH | 24.4183 | 54.5703 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3257 | AUH | 24.2147 | 54.7561 | Existing | OD | Possible | 367513.78 |  | to be via MW
AUH3287 | WR | 23.7831 | 53.029 | Existing | OD | Possible | 1549598.3948 |  | to be via MW
AUH3288 | WR | 23.8548 | 53.2884 | Existing | OD | Site survey required | 857416.5092 |  | to be via MW
AUH3291 | WR | 23.5947 | 53.9293 | Existing | OD | Possible | 2006362.9065 | AUH2983,AUH2943,AUH3296 | to be via MW
AUH3292 | WR | 23.684 | 53.9665 | Existing | OD | Possible | 799475.055 | Depend to Connect AUH2983,AUH2943,AUH3296,AUH3944 | to be via MW
AUH3298 | WR | 23.5052 | 53.4082 | Existing | OD | Possible | 3048946.7694 |  | to be via MW
AUH3299 | WR | 23.3923 | 53.3558 | Existing | OD | Possible | 2697833.4393 |  | to be via MW
AUH3300 | WR | 23.2793 | 53.3447 | Existing | OD | Possible | 2509215.4067 |  | to be via MW
AUH2286 | WR | 24.4731 | 52.3152 | Existing | OD |  | 0 |  | to be via MW
AUH2290 | WR | 24.5007 | 52.3298 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3305 | AUH | 24.2919 | 54.6404 | Existing | OD | OSP Ready | 0 |  | Y2024 fiber scope
AUH3307 | WR | 23.3796 | 54.0066 | Existing | OD | Possible | 4394610.7221 | AUH3294,AUH3291,AUH3296,AUH2943,AUH2983 | to be via MW
AUH3308 | WR | 23.3043 | 54.1702 | Existing | OD | Site survey required | 1388040.5568 |  | to be via MW
AUH3310 | WR | 23.2944 | 54.2199 | Existing | OD | Site survey required | 242581.1128 |  | to be via MW
AUH2318 | AUH | 24.4673 | 54.3848 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3334 | AUH | 24.842 | 55.0352 | Existing | OD | Possible | 80500 |  | Y2024 fiber scope
AUH2335 | AUH | 24.4793 | 54.3794 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3336 | AUH | 24.5484 | 54.7009 | Existing | OD | 2023 scope | 273531.7901 |  | Y2024 fiber scope
AUH3377 | AUH | 24.6088 | 54.5539 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3842 | AUH | 24.5319 | 54.4141 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3394 | AUH | 24.6999 | 54.6583 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3396 | AUH | 24.6689 | 54.8112 | Existing | OD | Possible | 277978.23 |  | to be via MW
AUH2393 | WR | 23.1479 | 53.7129 | Existing | OD | Possible | 0 | Depend to Connect AUH6352 | to be via MW
AUH3402 | AUH | 24.2246 | 54.6366 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3403 | AUH | 24.222 | 54.6396 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2489 | WR | 24.193 | 53.7773 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2490 | WR | 24.2292 | 53.8062 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3492 | AUH | 24.3341 | 54.5436 | Existing | OD | Possible | 306301.695 |  | to be via MW
AUH3495 | AUH | 24.4074 | 54.2535 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2497 | AUH | 24.5674 | 54.548 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2499 | WR | 24.2714 | 53.8603 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2502 | WR | 24.1733 | 51.9889 | Existing | OD |  | 0 |  | to be via MW
AUH3503 | AUH | 24.8846 | 54.8482 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2508 | AUH | 24.2043 | 54.9921 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3507 | WR | 23.6666 | 54.3461 | Existing | OD | Site survey required | 1322363.7431 |  | to be via MW
AUH2517 | AUH | 24.5383 | 54.3831 | Existing | OD | Site survey required | 0 | Depend to Connect AUH2035,AUG6056,AUH2555 | to be via MW
AUH2523 | AUH | 24.3712 | 54.5377 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3534 | AUH | 24.6468 | 54.6505 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3898 | AUH | 24.3253 | 54.789 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3535 | AUH | 24.489 | 54.4068 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3557 | WR | 24.1021 | 52.6494 | Existing | OD | Not possible | 0 |  | to be via MW
AUH3562 | WR | 23.0638 | 53.9636 | Existing | OD | Possible | 964222.905 |  | to be via MW
AUH3564 | WR | 24.0736 | 52.4592 | Existing | OD | Military - Site survey required | 0 |  | to be via MW
AUH3570 | AUH | 24.4878 | 54.4298 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3573 | AUH | 24.4681 | 54.4568 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3572 | AUH | 24.4832 | 54.4587 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3608 | AUH | 24.6794 | 55.1886 | Existing | OD | Possible | 403443.805 |  | to be via MW
AUH3611 | WR | 24.2379 | 54.2605 | Existing | OD | Possible | 2236299.1445 |  | to be via MW
AUH2614 | AUH | 24.1722 | 54.5549 | Existing | OD | Possible | 632500 |  | to be via MW
AUH2615 | AUH | 24.6203 | 55.0384 | Existing | OD | Possible | 839500 | Depend to Connect AUH2169 | to be via MW
AUH3255 | AUH | 24.4227 | 54.5705 | Existing | OD | Possible | 296695.975 |  | to be via MW
AUH3822 | AUH | 24.4441 | 54.5881 | Existing | OD | Tabreed | 0 |  | Y2024 fiber scope
AUH3401 | AUH | 24.5841 | 54.474 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6021 | WR | 24.1155 | 52.8765 | Existing | OD | Possible | 159896.23 |  | to be via MW
AUH2855 | AUH | 24.5481 | 54.8356 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH6022 | WR | 24.1957 | 51.7755 | Existing | OD | Possible | 649924.826 | Depend to Connect AUH6479 | to be via MW
AUH6073 | WR | 23.9804 | 53.5408 | Existing | OD | Possible | 1545434.223 |  | to be via MW
AUH6095 | WR | 23.9062 | 53.2745 | Existing | OD | Possible | 553175.3756 |  | to be via MW
AUH2877 | WR | 24.113 | 52.4397 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3889 | AUH | 24.4441 | 54.6757 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6096 | WR | 23.8846 | 53.2808 | Existing | OD | Possible | 674454.0112 |  | to be via MW
AUH3915 | AUH | 24.3292 | 54.7779 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH3018 | AUH | 24.6778 | 54.965 | Existing | OD | Possible | 1985589.6895 |  | to be via MW
AUH2250 | AUH | 24.439 | 54.6171 | Existing | OD | Possible | 23000 |  | Y2024 fiber scope
AUH6119 | WR | 24.1325 | 54.5271 | Existing | OD | Possible | 547922.215 | Depend to Connect AUH2614,AUH6349 | to be via MW
AUH3246 | WR | 24.483 | 52.3059 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6142 | AUH | 24.4191 | 54.4071 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3266 | AUH | 24.3617 | 54.4725 | Existing | OD | Possible | 0 |  | Y2024 fiber scope
AUH3273 | AUH | 24.8663 | 54.886 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2283 | AUH | 24.439 | 54.5714 | Existing | OD | Possible | 0 |  | Y2024 fiber scope
AUH3289 | WR | 23.8352 | 53.4419 | Existing | OD | Possible | 2262264.2838 | Depend to Connect AUH3494 | to be via MW
AUH3304 | WR | 23.1982 | 54.1485 | Existing | OD | Possible | 3046885.1458 |  | to be via MW
AUH3337 | AUH | 24.2533 | 54.5543 | Existing | OD | Not possible | 0 |  | to be via MW
AUH6143 | AUH | 24.4169 | 54.4102 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3370 | WR | 24.2091 | 53.913 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6154 | AUH | 24.3355 | 54.597 | Existing | OD | 2023 scope | 181873.535 |  | Y2024 fiber scope
AUH3438 | AUH | 24.1708 | 54.7691 | Existing | OD | Possible | 558969 |  | to be via MW
AUH2488 | AUH | 24.5727 | 54.5268 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3880 | AUH | 24.556 | 54.4566 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6000 | AUH | 24.4516 | 54.6126 | Existing | OD | Tabreed | 0 |  | Y2024 fiber scope
AUH6424 | WR | 24.195 | 53.4275 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6425 | WR | 24.3049 | 54.1136 | Existing | OD | Possible | 478726.9099 | Depend to Connect AUH3679,AUH6348 | to be via MW
AUH6044 | AUH | 24.4914 | 54.4025 | Existing | OD | Not possible | 0 |  | to be via MW
AUH6046 | WR | 24.1376 | 52.7436 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH6433 | WR | 24.2874 | 53.9937 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6448 | WR | 24.0581 | 52.7107 | Existing | OD | Possible | 476012.8393 |  | to be via MW
AUH6449 | WR | 24.5062 | 52.2812 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6454 | WR | 23.9018 | 53.052 | Existing | OD | Possible | 2016217.0018 |  | to be via MW
AUH6116 | AUH | 24.4053 | 54.7143 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6117 | AUH | 24.5383 | 54.4024 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6118 | AUH | 24.4488 | 54.3467 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH6458 | WR | 24.0932 | 52.9559 | Existing | OD | Site survey required | 333972.69 |  | to be via MW
AUH6120 | AUH | 24.3199 | 54.546 | Existing | OD | Possible | 281750 |  | to be via MW
AUH6121 | WR | 23.0344 | 54.0156 | Existing | OD | Possible | 1063126.47 |  | to be via MW
AUH6129 | AUH | 24.5229 | 54.653 | Existing | OD | Possible | 539209.93 |  | to be via MW
AUH6494 | WR | 23.5641 | 53.6274 | Existing | OD | Possible | 1934873.6376 |  | to be via MW
AUH6495 | WR | 23.9106 | 53.3255 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH6141 | AUH | 24.4174 | 54.4039 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6144 | WR | 23.9884 | 51.957 | Existing | OD | Possible | 1409432.18 |  | to be via MW
AUH6145 | WR | 23.983 | 51.8327 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH6150 | AUH | 24.5263 | 54.407 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6152 | AUH | 24.563 | 54.4606 | Existing | OD | Not possible | 0 |  | to be via MW
AUH6167 | WR | 24.2276 | 51.7223 | Existing | OD | Possible | 2549755.482 | The route of this site passing at AUH6380 | to be via MW
AUH6213 | AUH | 24.6221 | 54.8739 | Existing | OD | Possible | 489874.6926 |  | to be via MW
AUH6217 | AUH | 24.4442 | 54.3662 | Existing | OD | Possible | 190123.52 |  | to be via MW
AUH6304 | WR | 23.1433 | 53.7744 | Existing | OD | Possible | 548391.53 |  | to be via MW
AUH6328 | WR | 24.1736 | 52.6071 | Existing | OD | Possible | 691098.9519 |  | to be via MW
AUH6330 | WR | 23.2227 | 53.7839 | Existing | OD | Possible | 277568.8008 |  | to be via MW
AUH6331 | WR | 23.9349 | 53.9122 | Existing | OD | Possible | 2534249.802 | Depend to Connect AUH3497,AUH3296,AUH2943,AUH2983 | to be via MW
AUH6332 | WR | 23.8404 | 51.9378 | Existing | OD | Possible | 1700888.7462 |  | to be via MW
AUH6335 | WR | 23.6429 | 54.308 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6336 | WR | 23.4229 | 54.2967 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6337 | WR | 23.356 | 53.8922 | Existing | OD | Possible | 3071861.9202 |  | to be via MW
AUH6339 | WR | 25.4953 | 53.1466 | Existing | OD | Not possible | 0 |  | to be via MW
AUH6344 | WR | 24.1672 | 54.0648 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6348 | WR | 24.2716 | 54.115 | Existing | OD | Possible | 1016046.6416 | Depend to Connect AUH3679 | to be via MW
AUH6349 | WR | 24.0999 | 54.5437 | Existing | OD | Possible | 1418087.08 | Depend to Connect AUH2614 | to be via MW
AUH6534 | AUH | 24.3309 | 54.5782 | Existing | OD | Possible | 179141.71 |  | to be via MW
AUH6352 | WR | 23.1259 | 53.7138 | Existing | OD | Possible | 801974.005 | Depend to Connect AUH6480 | to be via MW
AUH6354 | WR | 23.74 | 53.9794 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH6358 | WR | 23.263 | 53.1475 | Existing | OD | Possible | 2062810.9885 | Depend to Connect AUH2964 | to be via MW
AUH6361 | WR | 23.879 | 53.5282 | Existing | OD | Possible | 1651676.685 |  | to be via MW
AUH6362 | WR | 24.1735 | 53.6576 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6364 | WR | 24.2807 | 51.7506 | Existing | OD | Possible | 1212746.53 | Depend to Connect AUH6022 | to be via MW
AUH6366 | WR | 23.031 | 53.9417 | Existing | OD | Possible | 2863104.2354 |  | to be via MW
AUH6372 | WR | 24.2361 | 54.1072 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6373 | WR | 24.1573 | 53.0393 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6378 | WR | 23.1148 | 53.6038 | Existing | OD | Possible | 221480.0262 |  | to be via MW
AUH6379 | WR | 23.8076 | 52.1716 | Existing | OD | Possible | 4561737.7616 |  | to be via MW
AUH6380 | WR | 24.1721 | 51.7503 | Existing | OD | Possible | 1258682.107 |  | to be via MW
AUH6382 | WR | 24.3154 | 54.1262 | Existing | OD | Possible | 590288.56 | Depend to Connect AUH3679,AUH6348,AUH6425 | to be via MW
AUH6385 | WR | 23.154 | 53.8281 | Existing | OD | Possible | 868135.23 |  | to be via MW
AUH6390 | WR | 23.1372 | 53.7469 | Existing | OD | Possible | 525657.18 |  | to be via MW
AUH6393 | WR | 24.0729 | 54.3205 | Existing | OD | Site survey required | 507823.21 |  | to be via MW
AUH6395 | WR | 23.1512 | 53.7524 | Existing | OD | Possible | 507823.21 |  | to be via MW
AUH6396 | AUH | 24.7527 | 54.6779 | Existing | OD | Possible | 322998.43 |  | to be via MW
AUH6543 | AUH | 24.7442 | 54.7263 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6413 | WR | 24.8975 | 53.0715 | Existing | OD | Not Possible | 23221.95 |  | Y2024 fiber scope
AUH6414 | WR | 24.8927 | 53.0797 | Existing | OD | Not Possible | 27269.03 |  | Y2024 fiber scope
AUH6423 | WR | 24.2768 | 53.3264 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6581 | WR | 24.2624 | 52.5932 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6428 | WR | 25.2042 | 53.2408 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6429 | WR | 23.8416 | 52.8196 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6430 | WR | 23.8327 | 52.819 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6431 | WR | 24.1009 | 53.4967 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH6440 | WR | 23.4436 | 53.0579 | Existing | OD | Possible | 1422292.63 | Depend to Connect AUH2961,AUH6443 | to be via MW
AUH6441 | WR | 23.8262 | 54.2371 | Existing | OD | Possible | 23221.95 | Depend to Connect AUH2983,AUH2943,AUH2944,AUH2946 | Y2024 fiber scope
AUH6443 | WR | 23.6054 | 52.9525 | Existing | OD | Possible | 27269.03 | Depend to Connect AUH2961 | to be via MW
AUH6445 | WR | 24.0294 | 53.1775 | Existing | OD | Possible | 686998.8645 |  | to be via MW
AUH1076 | AUH | 24.839 | 55.0217 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2529 | AUH | 24.7101 | 54.8364 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2748 | AUH | 24.4014 | 54.6486 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2060 | AUH | 24.3623 | 54.6887 | Existing | OD | 2023 scope | 161224.94 |  | Y2024 fiber scope
AUH6466 | WR | 24.0779 | 52.6446 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH6468 | WR | 23.62 | 53.7629 | Existing | OD | Possible | 1377716.1 |  | to be via MW
AUH6469 | WR | 23.1538 | 53.2643 | Existing | OD | Possible | 1313222.605 | Depend to Connect AUH2966 | to be via MW
AUH6470 | WR | 23.9583 | 52.5361 | Existing | OD | Possible | 1690055.1395 |  | to be via MW
AUH6472 | WR | 23.2796 | 54.2383 | Existing | OD | Site survey required | 653204.5138 |  | to be via MW
AUH6476 | WR | 23.1899 | 53.7921 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH6479 | WR | 24.0909 | 51.7831 | Existing | OD | Possible | 486137.2 |  | to be via MW
AUH6480 | WR | 23.143 | 53.6896 | Existing | OD | Possible | 692556.565 |  | to be via MW
AUH2820 | AUH | 24.3302 | 54.7117 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6497 | WR | 24.1204 | 53.4547 | Existing | OD | Possible | 792557.23 |  | to be via MW
AUH6498 | WR | 24.2943 | 54.1584 | Existing | OD | Possible | 973497.9641 | Depend to Connect AUH3679 | to be via MW
AUH6097 | WR | 24.0194 | 52.0198 | Existing | OD | Not possible | 0 |  | to be via MW
AUH6518 | AUH | 24.5075 | 54.5573 | Existing | OD | Possible | 221855.47 |  | to be via MW
AUH6519 | WR | 24.0398 | 52.4124 | Existing | OD | Site survey required | 588292.3023 |  | to be via MW
AUH6556 | AUH | 24.288 | 55.0579 | Existing | OD | Possible | 1021113.3912 | The route of this site passing at AUH2477 | to be via MW
AUH6525 | AUH | 24.5867 | 54.4758 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6527 | AUH | 24.5706 | 54.4632 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6531 | AUH | 24.5441 | 54.4324 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3923 | AUH | 24.5642 | 54.6836 | Existing | OD | Possible | 262655.9796 |  | to be via MW
AUH6535 | AUH | 24.4202 | 54.4629 | Existing | OD | Possible | 215839.13 |  | to be via MW
AUH6536 | AUH | 24.5624 | 54.4571 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH6076 | AUH | 24.5244 | 54.4422 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6545 | AUH | 24.425 | 54.559 | Existing | OD | Possible | 338727.095 |  | to be via MW
AUH6546 | AUH | 24.4203 | 54.56 | Existing | OD | Possible | 140816.35 |  | to be via MW
AUH6168 | WR | 23.2129 | 53.7433 | Existing | OD | Site survey required | 684742.775 |  | to be via MW
AUH6593 | AUH | 24.3659 | 54.4843 | Existing | OD | Possible | 40541.41 |  | Y2024 fiber scope
AUH6590 | AUH | 24.4936 | 54.3893 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3971 | AUH | 24.2171 | 55.0912 | Existing | OD | Possible | 108296.9352 |  | to be via MW
AUH6140 | AUH | 24.4201 | 54.4047 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6595 | AUH | 24.2083 | 54.6197 | Existing | OD | Possible | 257039.0151 |  | to be via MW
AUH6555 | AUH | 24.2418 | 55.05 | Existing | OD | Possible | 721868.3952 |  | to be via MW
AUH6604 | AUH | 24.6932 | 54.7199 | Existing | OD | Possible | 725358.636 |  | to be via MW
AUH6605 | AUH | 24.6981 | 54.7729 | Existing | OD | Possible | 377832.615 |  | to be via MW
AUH3410 | AUH | 24.3391 | 54.6735 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6632 | AUH | 24.4412 | 54.5682 | Existing | OD | Tabreed | 60000 |  | Y2024 fiber scope
AUH7017 | AUH | 24.4816 | 54.6058 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH7018 | AUH | 24.4816 | 54.6058 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH7019 | AUH | 24.4816 | 54.6058 | Existing | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3415 | AUH | 24.3412 | 54.6843 | Existing | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6589 | AUH | 24.8731 | 54.8347 | Existing | OD | Site survey required | 0 |  | to be via MW
AUH6451 | WR | 22.8952 | 54.3323 | Existing | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUV6260 | AUH | 24.4352 | 54.4683 | Existing | OD | Not Possible | 0 |  | to be via MW
AUV6269 | AUH | 24.4723 | 54.3223 | Existing | OD |  | 0 |  | to be via MW
AUV6270 | AUH | 24.4731 | 54.3416 | Existing | OD |  | 0 |  | to be via MW
AUV6273 | WR | 22.9735 | 53.767 | Existing | OD |  | 0 |  | to be via MW
AUV6272 | WR | 22.9837 | 53.7961 | Existing | OD |  | 0 |  | to be via MW
AUH2798 | AUH | 24.7613 | 54.6807 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2868 | WR | 24.3758 | 51.5937 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH2940 | WR | 23.8291 | 53.6172 | Existing | OD | Site survey required | 1231694.5496 |  | to be via MW
AUH3155 | AUH | 24.4348 | 54.4682 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3290 | WR | 23.9248 | 53.1612 | Existing | OD | Possible | 1916257.5466 |  | to be via MW
AUH3293 | WR | 23.5817 | 53.8484 | Existing | OD | Possible | 2802606.4366 | Depend to Connect AUH2983 | to be via MW
AUH3294 | WR | 23.4864 | 53.9508 | Existing | OD | Possible | 542224.4415 |  | to be via MW
AUH3295 | WR | 24.002 | 53.0341 | Existing | OD | Possible | 1876154.1442 |  | to be via MW
AUH3297 | WR | 23.6477 | 53.1901 | Existing | OD | Possible | 1273741.3055 |  | to be via MW
AUH3301 | WR | 23.631 | 54.1348 | Existing | OD | Possible | 2346459.0718 |  | to be via MW
AUH3302 | WR | 23.4781 | 54.1053 | Existing | OD | Possible | 3180151.9987 | AUH3292,AUH2943,AUH3296,AUH2983 | to be via MW
AUH3529 | WR | 22.7535 | 54.3977 | Existing | OD | Possible | 936602.2733 |  | to be via MW
AUH3797 | AUH | 24.7928 | 54.7037 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3949 | AUH | 24.5185 | 54.6728 | Existing | OD | Possible | 235221.805 |  | to be via MW
AUH3955 | AUH | 24.4657 | 54.3277 | Existing | OD | Not Possible | 0 |  | to be via MW
AUH3888 | AUH | 24.4479 | 54.5967 | New | OD | Tabreed | 60000 |  | Y2024 fiber scope
AUH6014 | AUH | 24.4479 | 54.605 | New | OD | Tabreed | 60000 |  | Y2024 fiber scope
AUH3902 | AUH | 24.1995 | 55.023 | New | OD | Possible | 34997.375 |  | Y2024 fiber scope
AUH6132 | AUH | 24.4674 | 54.3221 | New | OD | Possible | 29625.4179 |  | Y2024 fiber scope
AUH3920 | AUH | 24.4425 | 54.4059 | New | OD | Possible | 43965.6623 |  | Y2024 fiber scope
AAN3703 | AAN | 24.2045 | 55.3665 | New | OD | Possible | 31456.9566 |  | Y2024 fiber scope
AUH3047 | AUH | 24.4341 | 54.7663 | New | OD | Possible | 43746.5228 |  | Y2024 fiber scope
AUH1330 | WR | 22.9675 | 53.7918 | New | OD | Possible | 34262.9901 |  | Y2024 fiber scope
AAN3439 | AAN | 24.1811 | 55.7078 | New | OD | OSP Ready | 0 |  | Y2024 fiber scope
AAN3655 | AAN | 24.183 | 55.7644 | New | OD | Possible | 74700.441 |  | Y2024 fiber scope
AUH3158 | AUH | 24.4872 | 54.6159 | New | OD | Possible | 65543.3639 |  | Y2024 fiber scope
AUH6033 | AUH | 24.8531 | 54.8084 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2254 | AUH | 24.3115 | 54.6703 | New | OD | Possible | 115765.5769 |  | to be via MW
AUH2231 | AUH | 24.4342 | 54.4531 | New | OD | Possible | 76837.8567 |  | Y2024 fiber scope
AUH3913 | AUH | 24.2602 | 54.6219 | New | OD | Possible | 126909.5811 |  | to be via MW
AUH2726 | AUH | 24.3435 | 54.9204 | New | OD | OSP Provisioned | 27997.9 |  | Y2024 fiber scope
AUH3405 | AUH | 24.3991 | 54.5496 | New | OD | Possible | 156162.9629 |  | to be via MW
AUH6183 | AUH | 24.4683 | 54.8391 | New | OD | OSP Provisioned | 34997.375 |  | Y2024 fiber scope
AUH2657 | AUH | 24.3164 | 54.6823 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3509 | AAN | 24.2069 | 55.6112 | New | OD | Possible | 149083.3299 |  | to be via MW
AAN3663 | AAN | 24.1005 | 55.9235 | New | OD | Possible | 133505.4663 |  | to be via MW
AUH1071 | AUH | 24.5471 | 54.4658 | New | OD | Possible | 212605.6374 |  | to be via MW
AUH6122 | AUH | 24.5594 | 54.8898 | New | OD | Possible | 217923.8945 |  | to be via MW
AUH6585 | WR | 24.6934 | 54.6712 | New | OD | Possible | 119724.592 |  | to be via MW
AAN3407 | AAN | 24.219 | 55.7713 | New | OD | Possible | 170715.4594 |  | to be via MW
AAN3752 | AAN | 24.5485 | 55.6042 | New | OD | Possible | 224617.7164 |  | to be via MW
AUH1066 | WR | 23.6475 | 53.6985 | New | OD | Possible | 227486.0733 |  | to be via MW
AUH1331 | WR | 22.9738 | 53.7639 | New | OD | Possible | 237155.092 |  | to be via MW
AUH1010 | AUH | 24.3668 | 54.6438 | New | OD | Possible | 128567.0847 |  | to be via MW
AUH1276 | WR | 23.6226 | 53.7161 | New | OD | Possible | 222675.3061 |  | to be via MW
AAN3426 | AAN | 24.2325 | 55.5633 | New | OD | Possible | 313337.9379 |  | to be via MW
AUH3917 | AUH | 24.3717 | 54.7164 | New | OD | Possible | 222197.4939 |  | to be via MW
AUH2011 | AUH | 24.6233 | 54.8143 | New | OD | Possible | 261514.6089 |  | to be via MW
AUH1085 | AUH | 24.4283 | 54.7192 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3750 | AAN | 24.6333 | 55.691 | New | OD | Possible | 350261.5404 |  | to be via MW
AUH6153 | AUH | 24.7146 | 54.8201 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3229 | AAN | 24.7388 | 55.7778 | New | OD | Possible | 428420.926 |  | to be via MW
AAN3208 | AAN | 24.3291 | 55.7909 | New | OD | Possible | 184238.1371 |  | to be via MW
AAN3228 | AAN | 24.7434 | 55.7892 | New | OD | Possible | 398198.5649 |  | to be via MW
AAN3508 | AAN | 24.2611 | 55.7468 | New | OD | Possible | 499370.0964 |  | to be via MW
AUH6492 | WR | 22.8954 | 54.3683 | New | OD | Possible | 76384.6547 |  | Y2024 fiber scope
AUH3820 | WR | 24.1207 | 52.6444 | New | OD | Site survey required | 0 |  | to be via MW
AUH2896 | WR | 23.1177 | 53.8165 | New | OD | Possible | 389105.2949 |  | to be via MW
AUH6338 | AUH | 24.2142 | 54.9206 | New | OD | Possible | 456647.4569 |  | to be via MW
AUH6613 | AUH | 24.1914 | 54.9634 | New | OD | Possible | 552368.6652 |  | to be via MW
AAN3674 | AAN | 24.1669 | 55.3016 | New | OD | Possible | 654811.8894 |  | to be via MW
AAN3753 | AAN | 24.1734 | 55.1661 | New | OD | Possible | 685577.3538 |  | to be via MW
AAN3660 | AAN | 24.1813 | 55.3902 | New | OD | Possible | 758378.4174 |  | to be via MW
AAN3740 | AAN | 24.1526 | 55.4444 | New | OD | Possible | 2128814.3028 | The route of this site passing at AAN2588 but it is not mentioned at this list, also this site is dependent on AAN2326 which is available in this list. | to be via MW
AUH6471 | WR | 23.2808 | 54.2498 | New | OD | Site survey required | 0 |  | to be via MW
AUH6598 | WR | 23.6741 | 53.8386 | New | OD | Military - Site survey required | 0 |  | to be via MW
AUH3016 | AUH | 24.6073 | 55.0033 | New | OD | Possible | 1139584.1004 | depend on AUH2169 | to be via MW
AUH1327 | AUH | 23.707 | 53.8066 | New | OD | Possible | 2055671.3772 | this site is dependent on AUH2983 which is in this list. | to be via MW
AUH2747 | WR | 23.5493 | 53.3131 | New | OD | Site survey required | 0 |  | to be via MW
AAN3658 | AAN | 23.4209 | 55.4303 | New | OD | Possible | 6133532.1024 | this site is dependent on AAN3231,AAN2849,AAN2383,AAN3287,AAN2426,AAN2270,AAN2423,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 which are in this list. | to be via MW
AUH6106 | WR | 23.7351 | 53.4999 | New | OD | OSP Provisioned | 34997.375 |  | Y2024 fiber scope
AAN3388 | AAN | 24.1833 | 55.7317 | New | OD | OSP Provisioned | 34997.375 |  | Y2024 fiber scope
AUH3066 | AUH | 24.2438 | 54.475 | New | OD | Possible | 0 |  | Y2024 fiber scope
AUH6523 | AUH | 24.3034 | 54.5907 | New | OD | OSP Provisioned | 34997.375 |  | Y2024 fiber scope
AUH3912 | AUH | 24.3442 | 54.5247 | New | OD | Possible | 34997.375 |  | Y2024 fiber scope
AUH6628 | AUH | 24.3124 | 54.7087 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1356 | AUH | 24.3124 | 54.7006 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1362 | AUH | 24.3178 | 54.7106 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6624 | AUH | 24.3188 | 54.7022 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1319 | AUH | 24.3211 | 54.7965 | New | OD | Riyad city - site survey required | 0 |  | to be via MW
AUH3875 | AUH | 24.3218 | 54.7826 | New | OD | Riyad city - site survey required | 0 |  | to be via MW
AUH6630 | AUH | 24.3225 | 54.7218 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1375 | AUH | 24.3372 | 54.711 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3417 | AUH | 24.3499 | 54.6728 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3150 | AUH | 24.3627 | 54.6704 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1315 | AUH | 24.3653 | 54.7813 | New | OD | Riyad city - site survey required | 0 |  | to be via MW
AUH1401 | AUH | 24.3941 | 54.677 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1917 | AUH | 24.4276 | 54.3337 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1461 | AUH | 24.4355 | 54.7128 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3788 | AUH | 24.4614 | 54.6508 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH3734 | AUH | 24.4878 | 54.4013 | New | OD | Not Possible | 0 |  | to be via MW
AUH1174 | AUH | 24.4917 | 54.3593 | New | OD | 2023 scope | 23635.26 |  | Y2024 fiber scope
AUH3186 | AUH | 24.4989 | 54.4045 | New | OD | Not Possible | 0 |  | to be via MW
AUH1047 | AUH | 24.5018 | 54.6196 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1049 | AUH | 24.5065 | 54.6189 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1349 | AUH | 24.508 | 54.6071 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1891 | AUH | 24.5123 | 54.613 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6176 | AUH | 24.5159 | 54.4918 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6173 | AUH | 24.5318 | 54.4753 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6302 | WR | 25.127 | 52.879 | New | OD | Not Possible | 0 |  | to be via MW
AUH6600 | WR | 25.3185 | 53.4621 | New | OD | Not Possible | 0 |  | to be via MW
AUH2782 | AUH | 24.519922 | 54.4448 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3090 | AUH | 24.5483 | 54.7988 | New | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH3093 | AUH | 24.5633 | 54.7981 | New | OD | OSP Provisioned | 28750 |  | Y2024 fiber scope
AUH1033 | AUH | 24.407 | 54.5425 | New | OD | Possible | 28750 |  | Y2024 fiber scope
AUH3914 | AUH | 24.3299 | 54.7856 | New | OD | Riyad city - site survey required | 0 |  | to be via MW
AUH3359 | AUH | 24.3633 | 54.5913 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3766 | AUH | 24.4022 | 54.7064 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3765 | AUH | 24.4027 | 54.6985 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1046 | AUH | 24.5019 | 54.6314 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH3992 | WR | 23.1132 | 53.858 | New | OD | Possible | 229888.4891 |  | to be via MW
AAN3738 | AAN | 23.3731 | 55.3709 | New | OD | Possible | 1107485.4924 | this site is dependent on AAN2425,AAN3231,AAN2849,AAN2383,AAN3287,AAN2426,AAN2270,AAN2423,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258 | to be via MW
AAN3505 | AAN | 23.6362 | 55.5412 | New | OD | Possible | 5723285.454 | The Proposed route of this site can cover the connection of sites (AAN3396,AAN3230,AAN2427,AAN2200,AAN2269,AAN2421,AAN2268,AAN3258) | to be via MW
AUH1035 | WR | 23.6412 | 55.5412 | New | OD | Possible | 224987.2047 |  | to be via MW
AUH3989 | WR | 23.8205 | 53.583 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH3986 | WR | 23.8332 | 53.7528 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH3990 | WR | 23.8457 | 53.5867 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH3984 | WR | 23.8772 | 53.6111 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH3610 | WR | 23.9614 | 52.227982 | New | OD | Site survey required | 0 |  | to be via MW
AAN3741 | AAN | 23.9892 | 55.0932 | New | OD | Possible | 1955560.2708 | this site is dependent on AAN2394,AAN2393 | to be via MW
AAN3385 | AAN | 24.0072 | 55.4399 | New | OD | Possible | 530957.6352 |  | to be via MW
AUH2881 | WR | 24.0556 | 53.3355 | New | OD | Possible | 351448.6514 |  | to be via MW
AUH3005 | WR | 24.0937 | 53.4096 | New | OD | Not Possible | 0 |  | to be via MW
AUH1079 | WR | 24.0943 | 51.6343 | New | OD | Possible | 416573.5586 |  | to be via MW
AAN3662 | AAN | 24.117 | 55.3748 | New | OD | Possible | 874293.867 | The route of this site passing at AAN2326,AAN2588 but they are not mentioned at this list | to be via MW
AUH6419 | WR | 24.1277 | 52.7574 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AAN3737 | AAN | 24.1287 | 55.2585 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH3485 | WR | 24.134 | 52.7179 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH6554 | WR | 24.1429 | 52.7354 | New | OD | NOT POSSIBLE | 0 |  | to be via MW
AUH1677 | AUH | 24.1653 | 54.9158 | New | OD | Possible | 462682.4322 |  | to be via MW
AUH1431 | WR | 24.1701 | 52.6487 | New | OD | Not Possible | 0 |  | to be via MW
AAN3665 | AAN | 24.1722 | 55.4341 | New | OD | Possible | 541982.9282 |  | to be via MW
AAN3675 | AAN | 24.1752 | 55.7081 | New | OD | Possible | 19633.3314 |  | Y2024 fiber scope
AUH1671 | AUH | 24.1756 | 54.8698 | New | OD | Possible | 664069.871 |  | to be via MW
AUH6486 | WR | 24.1769 | 53.8611 | New | OD | Not Possible | 0 |  | to be via MW
AAN3445 | AAN | 24.1774 | 55.6432 | New | OD | OSP Ready | 0 |  | Y2024 fiber scope
AAN3722 | AAN | 24.1845 | 55.3344 | New | OD | Possible | 314645.2438 |  | to be via MW
AUH1687 | AUH | 24.1948 | 54.8994 | New | OD | Possible | 424929.3359 | The route of this site passing at AUH3445 but it is not mentioned at this list | to be via MW
AAN3672 | AAN | 24.2001 | 55.6521 | New | OD | Possible | 34997.375 |  | Y2024 fiber scope
AAN3528 | AAN | 24.2001 | 55.6903 | New | OD | Possible | 370574.4928 |  | to be via MW
AUH1682 | AUH | 24.2027 | 54.8725 | New | OD | Possible | 404795.934 | The route of this site passing at AUH3445 but it is not mentioned at this list | to be via MW
AUH1347 | AUH | 24.2458 | 54.4407 | New | OD | Possible | 347428.7969 | This site is dependent on AUH1345 which is in this list. | to be via MW
AUH1345 | AUH | 24.2578 | 54.453 | New | OD | Possible | 271440.3404 |  | to be via MW
AUH2740 | AUH | 24.282 | 54.568 | New | OD | Possible | 161335.7989 |  | to be via MW
AUH1892 | AUH | 24.3338 | 54.5686 | New | OD | Possible | 212366.7313 |  | to be via MW
AUH1324 | AUH | 24.3396 | 54.7756 | New | OD | Riyad city - site survey required | 0 |  | to be via MW
AUH3908 | AUH | 24.3483 | 54.5449 | New | OD | OSP Ready | 0 |  | Y2024 fiber scope
AUH2486 | AUH | 24.3491 | 54.6912 | New | OD | Possible | 842253.33 |  | to be via MW
AUH1893 | AUH | 24.3554 | 54.4961 | New | OD | Possible | 186376.4207 |  | to be via MW
AUH6575 | AUH | 24.3668 | 54.5129 | New | OD | Possible | 129368.3846 |  | to be via MW
AUH1326 | AUH | 24.3676 | 54.7593 | New | OD | Riyad city - site survey required | 0 |  | to be via MW
AUH1894 | AUH | 24.409 | 54.6003 | New | OD | Possible | 372022.7682 |  | to be via MW
AUH3821 | AUH | 24.4113 | 54.3601 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6009 | AUH | 24.4148 | 54.4099 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2644 | AUH | 24.4309 | 54.6421 | New | OD | Not Possible | 0 |  | to be via MW
AUH2516 | AUH | 24.4316 | 54.514 | New | OD | Not Possible | 0 |  | to be via MW
AUH2515 | AUH | 24.4429 | 54.6473 | New | OD | Not Possible | 0 |  | to be via MW
AUH6422 | WR | 24.4598 | 53.371 | New | OD | Not Possible | 0 |  | to be via MW
AUH2194 | AUH | 24.4681 | 54.5983 | New | OD | OSP Ready | 0 |  | Y2024 fiber scope
AAN3735 | AAN | 24.4729 | 55.3866 | New | OD | Possible | 308061.2297 |  | to be via MW
AUH3645 | AUH | 24.4784 | 54.4094 | New | OD | Not Possible | 0 |  | to be via MW
AUH1048 | AUH | 24.504 | 54.6255 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH1068 | AUH | 24.5089 | 54.6119 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH6463 | AUH | 24.5115 | 54.6551 | New | OD | Site survey required | 0 |  | to be via MW
AUH1194 | AUH | 24.5249 | 54.6903 | New | OD | Possible | 55200 |  | Y2024 fiber scope
AAN3723 | AAN | 24.5317 | 55.6729 | New | OD | Possible | 358513.4455 |  | to be via MW
AUH3096 | AUH | 24.5336 | 54.9101 | New | OD | Military - Site survey required | 0 |  | to be via MW
AUH2745 | AUH | 24.5395 | 54.4364 | New | OD | Not Possible | 0 |  | to be via MW
AUH1139 | AUH | 24.5435 | 54.6214 | New | OD | Possible | 496761.4201 |  | to be via MW
AUH6069 | AUH | 24.5451 | 54.8633 | New | OD | Military - Site survey required | 0 |  | to be via MW
AUH1082 | AUH | 24.554 | 54.7593 | New | OD | Military - Site survey required | 0 |  | to be via MW
AUH3481 | AUH | 24.5563 | 54.8097 | New | OD | Military - Site survey required | 0 |  | to be via MW
AUH1339 | AUH | 24.5605 | 54.757 | New | OD | Military - Site survey required | 0 |  | to be via MW
AAN3744 | AAN | 24.6522 | 55.7046 | New | OD | Possible | 175311.0627 |  | to be via MW
AUH2538 | AUH | 24.6901 | 54.8536 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AAN3657 | AAN | 24.7022 | 55.6018 | New | OD | Possible | 293536.9271 |  | to be via MW
AUH2324 | AUH | 24.7121 | 54.8751 | New | OD | Taawun | 0 |  | Y2024 fiber scope
AUH2731 | AUH | 24.7374 | 55.1103 | New | OD | Not possible | 0 |  | to be via MW
AUH2988 | WR | 24.7924 | 52.5558 | New | OD | Not Possible | 0 |  | to be via MW
Note on K59: Alvin Laquindanum: tbc

## IBS
Project Code | Sitecode | Region | Latitude | Longitude | Site Type | Scope | Status | Cost | Transport Feedback
| IAD5904 | AUH | 24.5205 | 54.4369 | Existing | ibs | Possible | 67357.7781 | Y2024 fiber scope
| AUH0537 | AUH | 24.4337 | 54.4397 | Existing | ibs | Possible | 53949.7275 | Y2024 fiber scope
| AUH0553 | AUH | 24.4837 | 54.3782 | Existing | ibs | Possible | 42864 | Y2024 fiber scope
| AUH0917 | AUH | 24.4249 | 54.6505 | Existing | ibs | Possible | 196967.8514 | to be via MW
| AUH0860 | AUH | 24.4978 | 54.3683 | Existing | ibs | Possible | 202297.7011 | to be via MW
| AUH0981 | AUH | 24.4352 | 54.4184 | Existing | ibs | Possible | 28800 | Y2024 fiber scope
| AUH0676 | AUH | 24.0896 | 52.6444 | Existing | ibs | Possible | 54450 | Y2024 fiber scope
| AAN0014 | AUH | 24.2307 | 55.7334 | Existing | ibs | POSSIBLE | 116261.7281 | to be via MW
| AAN0003 | AUH | 24.2586 | 55.6164 | Existing | ibs | Possible | 30600 | Y2024 fiber scope
| AAN0005 | AUH | 24.2386 | 55.7371 | Existing | ibs | Possible | 135595.2037 | to be via MW
| AUH0927 | AUH | 24.418 | 54.4401 | Existing | ibs | Possible | 62317.3283 | Y2024 fiber scope
| DXB0371 | AUH | 25.283 | 55.3177 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0896 | AUH | 23.6514 | 53.6758 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| RAK0503 | AUH | 25.6901 | 55.7759 | Existing | ibs | NE Region | 0 | NE Region
| RAK0527 | AUH | 25.6853 | 55.7733 | Existing | ibs | NE Region | 0 | NE Region
| AUH0789 | AUH | 24.49847 | 54.3905 | Existing | ibs | PIS with ETC | 0 | to be via MW
| AUH0575 | AUH | 24.503 | 54.3706 | Existing | ibs | Possible | 40808.2022 | Y2024 fiber scope
| AUH0890 | AUH | 24.3263 | 54.616 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0417 | AUH | 24.4923 | 54.3673 | Existing | ibs | Possible | 39214.3022 | Y2024 fiber scope
| AUH0691 | AUH | 24.3891 | 54.2218 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0419 | AUH | 24.4385 | 54.5724 | Existing | ibs | Possible | 57614.0756 | Y2024 fiber scope
| AUH0745 | AUH | 24.439077 | 54.5712 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0420 | AUH | 24.4388 | 54.5743 | Existing | ibs | Possible | 216467.8848 | to be via MW
| AUH0418 | AUH | 24.5728 | 54.6943 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0862 | AUH | 24.4995 | 54.3708 | Existing | ibs | POSSIBLE | 152591.04 | to be via MW
| AUH0481 | AUH | 24.4951 | 54.374 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0405 | AUH | 24.453072° | 54.398531° | Existing | ibs | Possible | 83659.9126 | Y2024 fiber scope
| AUH0923 | AUH | 24.5001 | 54.3712 | Existing | ibs | Possible | 131049.42 | to be via MW
| AAN0027 | AUH | 23.6373 | 55.5656 | Existing | ibs | Possible | 4197157.896 | to be via MW
| AUH0527 | AUH | 24.4712 | 54.3737 | Existing | ibs | Possible | 58509.2656 | Y2024 fiber scope
| AUH0529 | AUH | 24.4713 | 54.3745 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0528 | AUH | 24.4718 | 54.3739 | Existing | ibs | Possible | 60987.3365 | Y2024 fiber scope
| AUH5673B | AUH | 24.4292 | 54.6408 | Existing | ibs | Possible | 248391.8219 | to be via MW
| AUH5532C | AUH | 24.457 | 54.634 | Existing | ibs | Possible | 316874.6993 | to be via MW
| AAN5399D | AUH | 24.5761 | 55.7474 | Existing | ibs | Possible | 112411.743 | to be via MW
| AUH5532A | AUH | 24.366 | 54.1927 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH5403D | AUH | 24.2772 | 52.6095 | Existing | ibs | Not Possible | 0 | to be via MW
| AAN5399B | AUH | 24.5939 | 55.7461 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH5560A | AUH | 24.778891° | 54.737421° | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH5560B | AUH | 24.7783 | 54.7375 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH5818F | AUH | 24.2525 | 54.5551 | Existing | ibs | Possible | 258032.6967 | to be via MW
| AUH5811E | AUH | 24.383 | 54.4994 | Existing | ibs | Possible | 98820.3151 | Y2024 fiber scope
| AUH5818E | AUH | 24.3267 | 54.61 | Existing | ibs | Possible | 324000 | to be via MW
| AUH5532D | AUH | 24.5582 | 54.8878 | Existing | ibs | Possible | 72894.0467 | Y2024 fiber scope
| AUH5532E | AUH | 24.5582 | 54.8878 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH5673C | AUH | 24.5332 | 54.6783 | Existing | ibs | Possible | 86982.234 | Y2024 fiber scope
| AUH5673D | AUH | 24.5332 | 54.6783 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AAN0052 | AUH | 24.2245 | 55.7828 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AAN0031 | AUH | 24.2284 | 55.7435 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH5564A | AUH | 24.45177 | 54.3355 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0744 | AUH | 24.4306 | 54.4367 | Existing | ibs | Possible | 47126.796 | Y2024 fiber scope
| AUH0876 | AUH | 24.4787 | 54.3812 | Existing | ibs | Possible | 63000 | Y2024 fiber scope
| AUH0795 | AUH | 24.4986 | 54.3703 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0953 | AUH | 24.4715 | 54.3411 | Existing | ibs | Tabreed network | #VALUE! | Y2024 fiber scope
| AUH0682 | AUH | 24.4847 | 54.3634 | Existing | ibs | Possible | 155096.0435 | to be via MW
| AAN0036 | AUH | 24.208 | 55.8044 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0891 | AUH | 24.4756 | 52.3092 | Existing | ibs | NE Region | 0 | NE Region
| AUH0191 | AUH | 24.3661 | 52.5946 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0850 | AUH | 24.4673 | 54.3857 | Existing | ibs | Possible | 39215.9654 | Y2024 fiber scope
| AUH0990 | AUH | 23.8547 | 52.8068 | Existing | ibs | Possible | 95872.2601 | Y2024 fiber scope
| AUH0844 | AUH | 24.493633 | 54.3669 | Existing | ibs | Possible | 98127.1469 | Y2024 fiber scope
| AUH0428 | AUH | 24.4878 | 54.365 | Existing | ibs | Possible | 35489.3579 | Y2024 fiber scope
| AUH0717 | AUH | 24.8576 | 54.8965 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0451 | AUH | 24.4929 | 54.3662 | Existing | ibs | Possible | 55469.7676 | Y2024 fiber scope
| AAN0007 | AUH | 24.0779 | 55.7682 | Existing | ibs | Possible | 3779216.0048 | to be via MW
| AUH0915 | AUH | 24.1271 | 51.6232 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0552 | AUH | 24.4621 | 54.3293 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0548 | AUH | 24.4779 | 54.3769 | Existing | ibs | Possible | 130800 | to be via MW
| AUH0434 | AUH | 24.4632 | 54.3263 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0564 | AUH | 24.45177 | 54.3355 | Existing | ibs | Possible | 313695.483 | to be via MW
| AUH0926 | AUH | 24.7945 | 54.6525 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0903 | AUH | 24.5149 | 54.3826 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0925 | AUH | 24.8029 | 54.6417 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0907 | AUH | 24.7801 | 54.7088 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0539 | AUH | 24.449 | 54.3965 | Existing | ibs | Possible | 80813.1518 | Y2024 fiber scope
| AUH0857 | AUH | 24.449 | 54.3965 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0826 | AUH | 24.4201 | 54.4417 | Existing | ibs | Possible | 42400.439 | Y2024 fiber scope
| AUH0511 | AUH | 24.5334 | 54.3985 | Existing | ibs | Possible | 84684.539 | Y2024 fiber scope
| AUH0849 | AUH | 24.5334 | 54.3985 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0672 | AUH | 24.2964 | 54.6362 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0781 | AUH | 24.4946 | 54.3761 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0871 | AUH | 24.5346 | 54.4191 | Existing | ibs | Possible | 71568.3359 | Y2024 fiber scope
| AUH0931 | AUH | 24.0853 | 53.4981 | Existing | ibs | Possible | 187128.3727 | to be via MW
| AUH0900 | AUH | 24.4525 | 54.311 | Existing | ibs | Possible | 586264.0947 | to be via MW
| AUH0407 | AUH | 24.4693 | 54.3408 | Existing | ibs | Possible | 35962.7462 | Y2024 fiber scope
| AUH0829 | AUH | 24.545 | 54.4349 | Existing | ibs | Possible | 579948.624 | to be via MW
| AUH0662 | AUH | 24.4156 | 54.446 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0562 | AUH | 24.4286 | 54.6415 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0921 | AUH | 24.4451 | 54.6253 | Existing | ibs | POSSIBLE | 184261.92 | to be via MW
| AUH0901 | AUH | 24.4512 | 54.3099 | Existing | ibs | Possible | 143506.4779 | to be via MW
| AUH0491 | AUH | 24.4537 | 54.3093 | Existing | ibs | Possible | 89811.2162 | Y2024 fiber scope
| AUH0865 | AUH | 24.4663 | 54.4066 | Existing | ibs | Possible | 167165.4979 | to be via MW
| AUH0866 | AUH | 24.4673 | 54.4076 | Existing | ibs | Possible | 105189.801 | to be via MW
| AUH0868 | AUH | 24.4702 | 54.4015 | Existing | ibs | Possible | 309771.5091 | to be via MW
| AUH0867 | AUH | 24.467 | 54.4044 | Existing | ibs | Possible | 617947.93 | to be via MW
| AUH0881 | AUH | 24.4759 | 54.3722 | Existing | ibs | OSP Provisioned | 27480 | Y2024 fiber scope
| AUH0742 | AUH | 24.4301 | 54.4365 | Existing | ibs | Possible | 71678.4416 | Y2024 fiber scope
| AUH0748 | AUH | 24.4585 | 54.3202 | Existing | ibs | OSP Provisioned | 56175.4356 | Y2024 fiber scope
| AUH0975 | AUH | 24.4105 | 54.4847 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0922 | AUH | 24.4986 | 54.3721 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AAN0061 | AUH | 24.2226 | 55.7236 | Existing | ibs | Possible | 314850.84 | to be via MW
| AUH0984 | AUH | 24.0859 | 52.6654 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0912 | AUH | 24.5315 | 54.4033 | Existing | ibs | Possible | 42000 | Y2024 fiber scope
| AUH0483 | AUH | 24.483246 | 54.3604 | Existing | ibs | Possible | 59482.5841 | Y2024 fiber scope
| AUH0764 | AUH | 24.4832 | 54.3604 | Existing | ibs | POSSIBLE | 48281.712 | Y2024 fiber scope
| AUH0411 | AUH | 24.5025 | 54.368 | Existing | ibs | Possible | 142931.1631 | to be via MW
| AUH0545 | AUH | 24.5022 | 54.3676 | Existing | ibs | Exact Coordinates Required | 0 | to be via MW
| AUH0956 | AUH | 24.4689 | 54.3376 | Existing | ibs | Possible | 187754.52 | to be via MW
| AUH0544 | AUH | 24.4983 | 54.370564° | Existing | ibs | Possible | 45340.145 | Y2024 fiber scope
| AAN0040 | AUH | 24.1752 | 55.7391 | Existing | ibs | Possible | 258450.6349 | to be via MW
| AUH0567 | AUH | 24.5824 | 51.7309 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0566 | AUH | 24.58 | 51.7268 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0512 | AUH | 24.5056 | 54.3756 | Existing | ibs | OSP Provisioned | 44416.7918 | Y2024 fiber scope
| AUH0884 | AUH | 24.5377 | 54.4256 | Existing | ibs | Possible | 32554.224 | Y2024 fiber scope
| AUH0870 | AUH | 24.5383 | 54.4242 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| AAN0017 | AUH | 24.286 | 55.6226 | Existing | ibs | Possible | 556585.3743 | to be via MW
| AUH0823 | AUH | 24.4939 | 54.3628 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0874 | AUH | 24.4544 | 54.345 | Existing | ibs | POSSIBLE | 245131.92 | to be via MW
| AUH0531 | AUH | 23.5337 | 53.801 | Existing | ibs | OSP Provisioned | 33000 | Y2024 fiber scope
| AUH0760 | AUH | 24.4851 | 54.3814 | Existing | ibs | Possible | 106800 | to be via MW
| AAN0050 | AUH | 24.1957 | 55.6441 | Existing | ibs | OSP Provisioned | 279641.6709 | Y2024 fiber scope
| AAN0038 | AUH | 24.1957 | 55.6504 | Existing | ibs | OSP Provisioned | 156029.3992 | Y2024 fiber scope
| AAN0016 | AUH | 24.1969 | 55.6523 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0937 | AUH | 24.4865 | 54.3598 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0661 | AUH | 24.3301 | 54.605 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AAN0010 | AUH | 24.2294 | 55.7501 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0969 | AUH | 24.4596 | 54.3791 | Existing | ibs | OSP Provisioned | 125040 | Y2024 fiber scope
| AUH0913 | AUH | 24.4601 | 54.3794 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| AUH0872 | AUH | 24.4196 | 54.529 | Existing | ibs | POSSIBLE | 271711.92 | to be via MW
| AUH5673J | AUH | 24.4826 | 52.3241 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0728 | AUH | 24.3223 | 54.6093 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5089 | AUH | 24.5119 | 54.4064 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5078 | AUH | 24.488379 | 54.395 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5065 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5062 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5064 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5061 | AUH | 24.4938 | 54.4089 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5063 | AUH | 24.4938 | 54.4089 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5080 | AUH | 24.4988 | 54.4032 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5092 | AUH | 24.4917 | 54.3956 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5098 | AUH | 24.5079 | 54.4056 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5093 | AUH | 24.492 | 54.3952 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5090 | AUH | 24.4907 | 54.3961 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5086 | AUH | 24.49992 | 54.40972 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5099 | AUH | 24.4995 | 54.3948 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5081 | AUH | 24.4988 | 54.4032 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5094 | AUH | 24.4922 | 54.3946 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5087 | AUH | 24.49992 | 54.40972 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5097 | AUH | 24.489 | 54.4124 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5096 | AUH | 24.489 | 54.4124 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5095 | AUH | 24.4916 | 54.3948 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5085 | AUH | 24.5123 | 54.4057 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| AUH0794 | AUH | 24.5422 | 54.4304 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5101 | AUH | 24.4995 | 54.3948 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| AUH0785 | AUH | 24.4185 | 54.4403 | Existing | ibs | Possible | 58919.8958 | Y2024 fiber scope
| IAD5079 | AUH | 24.48782 | 54.3945 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD0990B | AUH | 24.2892 | 54.4945 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5140 | AUH | 24.5013 | 54.3698 | Existing | ibs | Possible | 128446.9087 | to be via MW
| IAD5172 | AUH | 24.4486 | 54.3377 | Existing | ibs | Possible | 138890.5989 | to be via MW
| IAD5135 | AUH | 24.3299 | 54.6037 | Existing | ibs | Possible | 282309.384 | to be via MW
| IAD5176 | AUH | 24.5432 | 54.4328 | Existing | ibs | Possible | 29662.536 | Y2024 fiber scope
| AUH0599 | AUH | 24.3057 | 54.1118 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5150 | AUH | 24.306 | 54.1135 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0797 | AUH | 24.3067 | 54.1148 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5123 | AUH | 24.4857 | 54.3582 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0650 | AUH | 24.449831 | 54.6065 | Existing | ibs | Possible | 95582.4 | Y2024 fiber scope
| AUH0736 | AUH | 24.449831 | 54.6065 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0452 | AUH | 24.4515 | 54.6039 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0570 | AUH | 24.4517 | 54.6039 | Existing | ibs | Tabreed network | #VALUE! | Y2024 fiber scope
| AUH0824 | AUH | 24.4519 | 54.6054 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0735 | AUH | 24.449831 | 54.6065 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0743 | AUH | 24.449831 | 54.6065 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0859 | AUH | 24.4931 | 54.3747 | Existing | ibs | Possible | 76004.5079 | Y2024 fiber scope
| IAD5122 | AUH | 24.3983 | 54.4713 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5191 | AUH | 24.431 | 54.4329 | Existing | ibs | Possible | 111072.6503 | to be via MW
| IAD5132 | AUH | 24.5148 | 54.3787 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5226 | AUH | 24.5012 | 54.3734 | Existing | ibs | Possible | 53623.2413 | Y2024 fiber scope
| IAD5240 | AUH | 24.4297 | 54.4364 | Existing | ibs | Possible | 75894.3487 | Y2024 fiber scope
| IAD5251 | AUH | 24.4548 | 54.3423 | Existing | ibs | Possible | 274972.8467 | to be via MW
| IAD5133 | AUH | 24.4839 | 54.599 | Existing | ibs | Possible | 30840 | Y2024 fiber scope
| IAD5186 | AUH | 24.4489 | 54.5996 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5175 | AUH | 24.4915 | 54.376 | Existing | ibs | Possible | 42415.4771 | Y2024 fiber scope
| IAD5230 | AUH | 24.4513 | 54.6012 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| IAD5228 | AUH | 24.4508 | 54.6014 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| IAD5232 | AUH | 24.4505 | 54.599 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| IAD5310 | AUH | 24.3563 | 54.7043 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5231 | AUH | 24.4505 | 54.599 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| IAD5276 | AUH | 24.4981 | 54.4053 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5275 | AUH | 24.4992 | 54.4042 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5195 | AUH | 24.4876 | 54.4059 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5181 | AUH | 24.4191 | 54.4651 | Existing | ibs | Possible | 41912.664 | Y2024 fiber scope
| IAD5277 | AUH | 24.4991 | 54.405 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5292 | AUH | 24.5109 | 54.4087 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| AUH0864 | AUH | 24.4182 | 54.6581 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5293 | AUH | 24.498 | 54.4108 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5224 | AUH | 24.4453 | 54.5844 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5384 | AUH | 24.4134 | 54.4598 | Existing | ibs | Possible | 232074.4142 | to be via MW
| IAD5315 | AUH | 24.5022 | 54.4096 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5294 | AUH | 24.4985 | 54.4108 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5185 | AUH | 24.4935 | 54.3681 | Existing | ibs | POSSIBLE | 77711.4 | Y2024 fiber scope
| IAD5316 | AUH | 24.5003 | 54.4057 | Existing | ibs | PIS with ETC | 0 | to be via MW
| AUH0469 | AUH | 24.504 | 54.3695 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AAN0088 | AUH | 23.4198 | 55.4134 | Existing | ibs | Possible | 4350737.2407 | to be via MW
| IAD5365 | AUH | 24.5211 | 54.438 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5335 | AUH | 24.4203 | 54.461 | Existing | ibs | Possible | 85739.6056 | Y2024 fiber scope
| IAD5234 | AUH | 24.4539 | 54.6161 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| AUH0550 | AUH | 24.5036 | 54.3692 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5381 | AUH | 24.5 | 54.4036 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5326 | AUH | 24.508210° | 54.37713° | Existing | ibs | Possible | 30458.663 | Y2024 fiber scope
| IAD5295 | AUH | 24.4815 | 54.4056 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5324 | AUH | 24.508210° | 54.37713° | Existing | ibs | Possible | 42000 | Y2024 fiber scope
| IAD5396 | AUH | 24.5321 | 54.421234 | Existing | ibs | Possible | 42209.416 | Y2024 fiber scope
| IAD5350 | AUH | 24.5781 | 51.725809 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5413 | AUH | 24.4306 | 54.433509 | Existing | ibs | Possible | 87243.4433 | Y2024 fiber scope
| IAD5460 | AUH | 24.4719 | 54.340777 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH5818G | AUH | 24.312 | 54.119282 | Existing | ibs | Possible | 296569.6417 | to be via MW
| IAD5494 | AUH | 24.3165 | 54.535747 | Existing | ibs | Possible | 62034.5962 | Y2024 fiber scope
| IAD5412 | AUH | 24.5037 | 54.375181 | Existing | ibs | Possible | 78232.3228 | Y2024 fiber scope
| IAD5519 | AUH | 24.5028 | 54.373955 | Existing | ibs | Possible | 39999.5128 | Y2024 fiber scope
| IAD5514 | AUH | 24.4633 | 54.376111 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5515 | AUH | 24.4464 | 54.4001 | Existing | ibs | Possible | 83314.1333 | Y2024 fiber scope
| IAD5352 | AUH | 24.493 | 54.368292 | Existing | ibs | Possible | 56813.7025 | Y2024 fiber scope
| IAD5511 | AUH | 24.4654 | 54.385122 | Existing | ibs | Possible | 43731.8722 | Y2024 fiber scope
| IAD5088 | AUH | 24.4992 | 54.4043 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5493 | AUH | 24.4741 | 54.37426 | Existing | ibs | OSP Provisioned | 37818.3923 | Y2024 fiber scope
| IAD5428 | AUH | 24.4919 | 54.370764 | Existing | ibs | POSSIBLE | 75498.48 | Y2024 fiber scope
| IAD5444 | AUH | 24.4774 | 54.370914 | Existing | ibs | OSP Provisioned | 27480 | Y2024 fiber scope
| IAD5470 | AUH | 24.5088 | 54.377394 | Existing | ibs | Possible | 36628.5806 | Y2024 fiber scope
| IAD5478 | AUH | 24.4694 | 54.341802 | Existing | ibs | Possible | 39801.7583 | Y2024 fiber scope
| IAD5481 | AUH | 24.4875 | 54.356215 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5502 | AUH | 24.499 | 54.374894 | Existing | ibs | Possible | 77305.5461 | Y2024 fiber scope
| IAD5507 | AUH | 24.452 | 54.333374 | Existing | ibs | Possible | 107769.3826 | to be via MW
| IAD5528 | AUH | 24.4775 | 54.364722 | Existing | ibs | Possible | 40056.4358 | Y2024 fiber scope
| IAD5575 | AUH | 24.4198 | 54.464636 | Existing | ibs | Possible | 291139.525 | to be via MW
| IAD5499 | AUH | 24.4936 | 54.363141 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5554 | AUH | 24.4865 | 54.352446 | Existing | ibs | POSSIBLE | 37428.48 | Y2024 fiber scope
| IAD5574 | AUH | 24.4637 | 54.37589 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5591 | AUH | 24.419 | 54.462472 | Existing | ibs | Possible | 115281.96 | to be via MW
| IAD5542 | AUH | 24.4939 | 54.3685 | Existing | ibs | Possible | 49279.157 | Y2024 fiber scope
| IAD5558 | AUH | 24.4826 | 54.3601 | Existing | ibs | Possible | 66040.8 | Y2024 fiber scope
| IAD5586 | AUH | 24.4207 | 54.462517 | Existing | ibs | Possible | 71335.6838 | Y2024 fiber scope
| IAD5565 | AUH | 24.493 | 54.372439 | Existing | ibs | POSSIBLE | 87356.88 | Y2024 fiber scope
| IAD5608 | AUH | 24.4845 | 54.375855 | Existing | ibs | Possible | 32578.3421 | Y2024 fiber scope
| IAD5562 | AUH | 24.4918 | 54.3729 | Existing | ibs | Possible | 57764.5955 | Y2024 fiber scope
| IAD5620 | AUH | 24.4927 | 54.366828 | Existing | ibs | Possible | 106800 | to be via MW
| IAD5506 | AUH | 24.4513 | 54.33303 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5407 | AUH | 24.4991 | 54.40905 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5405 | AUH | 24.483 | 54.406186 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5387 | AUH | 24.5229 | 54.4332201 | Existing | ibs | Possible | 43852.4308 | Y2024 fiber scope
| IAD5395 | AUH | 24.4321 | 54.433221 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5661 | AUH | 24.3339 | 54.530503 | Existing | ibs | Possible | 71365.6841 | Y2024 fiber scope
| IAD5557 | AUH | 24.4925 | 54.371389 | Existing | ibs | POSSIBLE | 42418.08 | Y2024 fiber scope
| IAD5583 | AUH | 24.5042 | 54.36977 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5582 | AUH | 24.5042 | 54.36977 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5532 | AUH | 24.4756 | 54.350279 | Existing | ibs | Possible | 310020 | to be via MW
| IAD5584 | AUH | 24.4862 | 54.366155 | Existing | ibs | Possible | 56752.1225 | Y2024 fiber scope
| IAD5473 | AUH | 24.4659 | 54.339502 | Existing | ibs | Possible | 50619.7655 | Y2024 fiber scope
| IAD5606 | AUH | 24.4754 | 54.372818 | Existing | ibs | OSP Provisioned | 27480 | Y2024 fiber scope
| IAD5426 | AUH | 24.4901 | 54.356933 | Existing | ibs | OSP Provisioned | 78965.28 | Y2024 fiber scope
| IAD5627 | AUH | 24.4498 | 54.613396 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5410 | AUH | 24.5057 | 54.406715 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5544 | AUH | 24.4923 | 54.371292 | Existing | ibs | POSSIBLE | 44912.88 | Y2024 fiber scope
| IAD5576 | AUH | 24.4202 | 54.461811 | Existing | ibs | Possible | 184481.9601 | to be via MW
| IAD5446 | AUH | 24.4916 | 54.379202 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5652 | AUH | 24.4957 | 54.366445 | Existing | ibs | Possible | 93995.4116 | Y2024 fiber scope
| IAD5419 | AUH | 24.5506 | 54.45188 | Existing | ibs | Possible | 50596.992 | Y2024 fiber scope
| IAD5318 | AUH | 24.5037 | 54.409917 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5408 | AUH | 24.4971 | 54.408762 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5406 | AUH | 24.4821 | 54.407430 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5629 | AUH | 24.469 | 54.3395628 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| IAD5553 | AUH | 24.4945 | 54.376913 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5393 | AUH | 24.4802 | 54.320011 | Existing | ibs | Possible | 87849.3055 | Y2024 fiber scope
| IAD5573 | AUH | 24.4715 | 54.408004 | Existing | ibs | Possible | 338099.7413 | to be via MW
| IAD5604 | AUH | 24.5005 | 54.370866 | Existing | ibs | Possible | 452856.1074 | to be via MW
| IAD5518 | AUH | 24.4557 | 54.338391 | Existing | ibs | Possible | 54919.8721 | Y2024 fiber scope
| IAD5463 | AUH | 24.5388 | 54.410286 | Existing | ibs | Possible | 49329.1469 | Y2024 fiber scope
| IAD5290 | AUH | 24.4787 | 54.35352 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5321 | AUH | 24.4113 | 54.473855 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5684 | AUH | 24.3162 | 54.61018 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5699 | AUH | 24.4159 | 54.573482 | Existing | ibs | Possible | 133657.2802 | to be via MW
| IAD5482 | AUH | 24.4779 | 54.371821 | Existing | ibs | POSSIBLE | 67619.8594 | Y2024 fiber scope
| IAD5693 | AUH | 24.4973 | 54.371666 | Existing | ibs | Possible | 52949.0078 | Y2024 fiber scope
| IAD5649 | AUH | 24.4944 | 54.3706 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5624 | AUH | 24.4789 | 54.3719 | Existing | ibs | Possible | 88098.0925 | Y2024 fiber scope
| IAD5702 | AUH | 24.4901 | 54.360366 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH5462E | AUH | 24.478 | 54.332557 | Existing | ibs | Possible | 234272.1667 | to be via MW
| IAD5512 | AUH | 24.4289 | 54.43656 | Existing | ibs | Possible | 33412.6448 | Y2024 fiber scope
| IAD5626 | AUH | 24.4494 | 54.612106 | Existing | ibs | Possible | 30737.2912 | Y2024 fiber scope
| IAD5587 | AUH | 24.4295 | 54.537165 | Existing | ibs | Possible | 455253.367 | to be via MW
| IAD5551 | AUH | 24.4994 | 54.375739 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5676 | AUH | 24.5107 | 54.405842 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5679 | AUH | 24.4709 | 54.341826 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5299 | AUH | 24.4934 | 54.372935 | Existing | ibs | Possible | 44200.2016 | Y2024 fiber scope
| IAD5610 | AUH | 24.4786 | 54.371168 | Existing | ibs | Possible | 42167.7296 | Y2024 fiber scope
| IAD5236 | AUH | 24.4441 | 54.588274 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5445 | AUH | 24.484 | 54.376111 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5270 | AUH | 24.4487 | 54.59514 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5749 | AUH | 24.4102 | 54.565139 | Existing | ibs | Possible | 128771.4381 | to be via MW
| IAD5730 | AUH | 24.4957 | 54.366566 | Existing | ibs | Possible | 30287.1732 | Y2024 fiber scope
| IAD5289 | AUH | 25.3551 | 52.726507 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5486 | AUH | 24.4766 | 54.365194 | Existing | ibs | Possible | 30287.1732 | Y2024 fiber scope
| IAD5338 | AUH | 24.4827 | 54.357054 | Existing | ibs | OSP Provisioned | 35418.561 | Y2024 fiber scope
| IAD5320 | AUH | 24.5005 | 54.371276 | Existing | ibs | Possible | 36956.8824 | Y2024 fiber scope
| IAD5077 | AUH | 24.4875 | 54.3952 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5282 | AUH | 24.4928 | 54.39307 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5127 | AUH | 24.4208 | 54.441844 | Existing | ibs | Possible | 43305.8712 | Y2024 fiber scope
| IAD5713 | AUH | 24.4166 | 54.511057 | Existing | ibs | Possible | 254589.1804 | to be via MW
| IAD5668 | AUH | 24.4136 | 54.453667 | Existing | ibs | Possible | 254589.1804 | to be via MW
| IAD5284 | AUH | 24.4928 | 54.39307 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5741 | AUH | 24.4982 | 54.373124 | Existing | ibs | Possible | 57273.4664 | Y2024 fiber scope
| IAD5662 | AUH | 24.4914 | 54.378012 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5283 | AUH | 24.4928 | 54.39307 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5671 | AUH | 24.4706 | 54.341456 | Existing | ibs | Possible | 108132.5423 | to be via MW
| IAD5281 | AUH | 24.4928 | 54.39307 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5605 | AUH | 24.4894 | 54.369063 | Existing | ibs | Possible | 37264.2002 | Y2024 fiber scope
| IAD5745 | AUH | 24.5387 | 54.409213 | Existing | ibs | Possible | 159865.759 | to be via MW
| IAD5675 | AUH | 24.4846 | 54.404235 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5328 | AUH | 24.4905 | 54.362305 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5748 | AUH | 24.5387 | 54.407628 | Existing | ibs | Possible | 53887.3165 | Y2024 fiber scope
| IAD5560 | AUH | 24.4593 | 54.38039 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5719 | AUH | 24.4209 | 54.497462 | Existing | ibs | Possible | 133819.5878 | to be via MW
| IAD5617 | AUH | 24.4968 | 54.407298 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5754 | AUH | 24.4884 | 54.3751 | Existing | ibs | Possible | 189238.296 | to be via MW
| IAD5595 | AUH | 24.5098 | 54.405303 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5358 | AUH | 24.4308 | 54.43531 | Existing | ibs | Possible | 71794.7131 | Y2024 fiber scope
| IAD5504 | AUH | 24.4175 | 54.442374 | Existing | ibs | POSSIBLE | 114974.64 | to be via MW
| IAD5311 | AUH | 24.4857 | 54.403686 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5766 | AUH | 24.43 | 54.583 | Existing | ibs | Possible | 143527.3328 | to be via MW
| IAD5585 | AUH | 24.4672 | 54.385426 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5190 | AUH | 24.5283 | 54.390776 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH5818H | AUH | 24.5309 | 54.382981 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5735 | AUH | 24.485 | 54.354158 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5480 | AUH | 24.4906 | 54.399991 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5464 | AUH | 24.4882 | 54.40841 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5489 | AUH | 24.3371 | 52.646383 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5490 | AUH | 24.326 | 52.571894 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5269 | AUH | 24.4433 | 54.589247 | Existing | ibs | Possible | 42253.4823 | Y2024 fiber scope
| AUH0438 | AUH | 24.4961 | 54.365741 | Existing | ibs | Possible | 37926.4033 | Y2024 fiber scope
| IAD5577 | AUH | 24.4682 | 54.340786 | Existing | ibs | Possible | 108000 | to be via MW
| IAD5746 | AUH | 24.4867 | 54.403787 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5780 | AUH | 24.3272 | 54.750062 | Existing | ibs | Possible | 803492.2073 | to be via MW
| IAD5783 | AUH | 24.4539 | 54.36755 | Existing | ibs | Possible | 221408.2156 | to be via MW
| IAD5313 | AUH | 24.4892 | 54.394856 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5312 | AUH | 24.4897 | 54.3945 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5771 | AUH | 24.4837 | 54.405379 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5770 | AUH | 24.4837 | 54.405379 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5750 | AUH | 24.5113 | 54.408841 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5622 | AUH | 24.4436 | 54.675573 | Existing | ibs | Possible | 408648.9066 | to be via MW
| IAD5828 | AUH | 24.4213 | 54.59714 | Existing | ibs | Possible | 124879.8991 | to be via MW
| IAD5747 | AUH | 23.8336 | 53.6152 | Existing | ibs | Possible | 278431.3432 | to be via MW
| IAD5431 | AUH | 24.4541 | 54.338766 | Existing | ibs | Possible | 39016.9358 | Y2024 fiber scope
| IAD5763 | AUH | 23.5517 | 53.2943 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5682 | AUH | 24.4176 | 54.48852 | Existing | ibs | Possible | 184376.7217 | to be via MW
| IAD5765 | AUH | 23.548 | 53.294 | Existing | ibs | Possible | 2983623.9729 | to be via MW
| IAD5738 | AUH | 23.6764 | 53.7015 | Existing | ibs | Possible | 30101.3541 | Y2024 fiber scope
| IAD5721 | AUH | 24.4231 | 54.419992 | Existing | ibs | Possible | 40903.2818 | Y2024 fiber scope
| IAD5529 | AUH | 24.4962 | 54.381075 | Existing | ibs | OSP Provisioned | 99102.0593 | Y2024 fiber scope
| IAD5366 | AUH | 24.4916 | 54.600414 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5767 | AUH | 24.8947 | 53.0762 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5677 | AUH | 24.507 | 54.376693 | Existing | ibs | Possible | 38220.8174 | Y2024 fiber scope
| AUH0987 | AUH | 24.481 | 54.321804 | Existing | ibs | Possible | 40987.1625 | Y2024 fiber scope
| AUH0985 | AUH | 24.4813 | 54.321821 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0986 | AUH | 24.481 | 54.321804 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5680 | AUH | 24.4942 | 54.38277 | Existing | ibs | Possible | 92623.7983 | Y2024 fiber scope
| IAD5403 | AUH | 24.466 | 54.373807 | Existing | ibs | Possible | 30912 | Y2024 fiber scope
| IAD5260 | AUH | 24.4429 | 54.584359 | Existing | ibs | Possible | 120000 | to be via MW
| IAD5859 | AUH | 24.4973 | 54.394614 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5818 | AUH | 24.4913 | 54.412814 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5217 | AUH | 24.4719 | 54.350468 | Existing | ibs | POSSIBLE | 131835.6 | to be via MW
| IAD5263 | AUH | 24.4449 | 54.586397 | Existing | ibs | Possible | 33634.3011 | Y2024 fiber scope
| IAD5149 | AUH | 24.4292 | 54.436973 | Existing | ibs | Possible | 54108.0226 | Y2024 fiber scope
| IAD5253 | AUH | 24.4431 | 54.585918 | Existing | ibs | Possible | 33634.3011 | Y2024 fiber scope
| IAD5821 | AUH | 24.5066 | 54.405028 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5733 | AUH | 24.4419 | 54.580414 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5819 | AUH | 24.4668 | 54.384886 | Existing | ibs | Possible | 79059.0718 | Y2024 fiber scope
| IAD5799 | AUH | 24.5058 | 54.405313 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5631 | AUH | 24.482 | 54.350771 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5262 | AUH | 24.4449 | 54.586994 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5865 | AUH | 24.4534 | 54.61388 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5811 | AUH | 24.4958 | 54.393240 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5264 | AUH | 24.4442 | 54.584727 | Existing | ibs | Possible | 33000 | Y2024 fiber scope
| IAD5476 | AUH | 24.4728 | 54.347985 | Existing | ibs | POSSIBLE | 27980.592 | Y2024 fiber scope
| IAD5265 | AUH | 24.4471 | 54.593398 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5268 | AUH | 24.4518 | 54.608529 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5357 | AUH | 24.4349 | 54.472806 | Existing | ibs | Possible | 783028.6935 | to be via MW
| IAD5841 | AUH | 24.4692 | 54.338111 | Existing | ibs | Possible | 45934.1846 | Y2024 fiber scope
| IAD5364 | AUH | 24.4451 | 54.574677 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5391 | AUH | 24.5051 | 54.375152 | Existing | ibs | Possible | 43508.8648 | Y2024 fiber scope
| IAD5817 | AUH | 24.4979 | 54.411790 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5840 | AUH | 23.9111 | 52.802119 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5822 | AUH | 24.5062 | 54.405134 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5815 | AUH | 24.1826 | 54.993356 | Existing | ibs | Possible | 187515.199 | to be via MW
| IAD5461 | AUH | 24.4702 | 54.340753 | Existing | ibs | Possible | 46367.7254 | Y2024 fiber scope
| IAD5569 | AUH | 24.5096 | 54.407378 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5752 | AUH | 25.1444 | 52.871915 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5853 | AUH | 24.5143 | 54.376058 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5751 | AUH | 25.1458 | 52.87103 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5707 | AUH | 24.5021 | 54.408021 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5498 | AUH | 24.4953 | 54.370187 | Existing | ibs | Possible | 39414.995 | Y2024 fiber scope
| IAD5720 | AUH | 24.4907 | 54.363931 | Existing | ibs | POSSIBLE | 100581.0178 | Y2024 fiber scope
| AAN0131 | AUH | 24.2953 | 55.62374 | Existing | ibs | Possible | 289689.8496 | to be via MW
| IAD5878 | AUH | 24.4427 | 54.581421 | Existing | ibs | Possible | 32668.6312 | Y2024 fiber scope
| IAD5912 | AUH | 24.4451 | 54.587443 | Existing | ibs | Possible | 32668.6312 | Y2024 fiber scope
| IAD5802 | AUH | 24.4882 | 54.400391 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5891 | AUH | 24.5383 | 54.383149 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5800 | AUH | 24.4882 | 54.400391 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5903 | AUH | 24.5016 | 54.4116 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5340 | AUH | 24.5204 | 54.435564 | Existing | ibs | Possible | 49618.2696 | Y2024 fiber scope
| IAD5812 | AUH | 24.4499 | 54.631966 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5409 | AUH | 24.4859 | 54.407162 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5949 | AUH | 24.4171 | 54.440300 | Existing | ibs | Possible | 78713.542 | Y2024 fiber scope
| IAD5663 | AUH | 24.4751 | 54.349701 | Existing | ibs | Possible | 89069.1241 | Y2024 fiber scope
| IAD5801 | AUH | 24.4882 | 54.400391 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5861 | AUH | 24.8187 | 54.656422 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5345 | AUH | 24.4896 | 54.617654 | Existing | ibs | Possible | 31200 | Y2024 fiber scope
| IAD5708 | AUH | 24.5101 | 54.409661 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5932 | AUH | 24.4744 | 54.347273 | Existing | ibs | Possible | 55800 | Y2024 fiber scope
| IAD5343 | AUH | 24.4896 | 54.617654 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5722 | AUH | 23.9784 | 52.265336 | Existing | ibs | Possible | 250916.5348 | to be via MW
| IAD5882 | AUH | 24.4441 | 54.590312 | Existing | ibs | Possible | 32668.6312 | Y2024 fiber scope
| IAD5800 | AUH | 24.488 | 54.400185 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5800 | AUH | 24.488 | 54.400185 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5800 | AUH | 24.488 | 54.400185 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5800 | AUH | 24.488 | 54.400185 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5881 | AUH | 24.4521 | 54.609754 | Existing | ibs | Possible | 40393.991 | Y2024 fiber scope
| IAD0995A | AUH | 24.1124 | 52.735907 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5892 | AUH | 24.351 | 54.7136 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5952 | AUH | 24.5377 | 54.409937 | Existing | ibs | Possible | 37707.0769 | Y2024 fiber scope
| IAD5873 | AUH | 24.4497 | 54.393044 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5258 | AUH | 24.4433 | 54.586452 | Existing | ibs | Possible | 33480 | Y2024 fiber scope
| IAD5931 | AUH | 23.6226 | 53.716104 | Existing | ibs | Possible | 284585.9225 | to be via MW
| IAD5271 | AUH | 24.4944 | 54.402932 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5273 | AUH | 24.4944 | 54.402932 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5947 | AUH | 24.4416 | 54.580850 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5920 | AUH | 24.4988 | 54.411334 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5485 | AUH | 24.4856 | 54.366536 | Existing | ibs | Possible | 59002.3073 | Y2024 fiber scope
| IAD5808 | AUH | 24.4853 | 54.3544129 | Existing | ibs | Possible | 96821.826 | Y2024 fiber scope
| IAD5883 | AUH | 24.5065 | 54.407274 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5148 | AUH | 24.4906 | 54.393427 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5768 | AUH | 23.7806 | 53.5643 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5936 | AUH | 24.5213 | 54.43318 | Existing | ibs | Possible | 110943.5312 | to be via MW
| IAD5347 | AUH | 24.4896 | 54.617654 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5788 | AUH | 24.4483 | 54.604995 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5789 | AUH | 24.4482 | 54.604458 | Existing | ibs | Possible | 34599.9711 | Y2024 fiber scope
| IAD5962 | AUH | 24.4424 | 54.578879 | Existing | ibs | Possible | 43268.6023 | Y2024 fiber scope
| IAD5830 | AUH | 24.4437 | 54.590566 | Existing | ibs | Possible | 43268.6023 | Y2024 fiber scope
| IAD5951 | AUH | 24.4443 | 54.589451 | Existing | ibs | Possible | 33054.8992 | Y2024 fiber scope
| IAD5943 | AUH | 24.4411 | 54.58014 | Existing | ibs | Possible | 45199.9423 | Y2024 fiber scope
| IAD5948 | AUH | 24.4435 | 54.580210 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5465 | AUH | 24.4264 | 54.407617 | Existing | ibs | OSP Provisioned | 30000 | Y2024 fiber scope
| IAD5970 | AUH | 24.4824 | 54.352426 | Existing | ibs | Possible | 30869.3348 | Y2024 fiber scope
| IAD5522 | AUH | 24.4423 | 54.580767 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5791 | AUH | 24.4406 | 54.576771 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5980 | AUH | 24.4212 | 54.47281 | Existing | ibs | Possible | 55035.8664 | Y2024 fiber scope
| IAD5924 | AUH | 24.4498 | 54.609977 | Existing | ibs | Possible | 31702.9612 | Y2024 fiber scope
| IAD5969 | AUH | 24.4215 | 54.459719 | Existing | ibs | Possible | 85697.8039 | Y2024 fiber scope
| IAD5807 | AUH | 24.4199 | 54.442110 | Existing | ibs | Possible | 43992.6758 | Y2024 fiber scope
| IAD5890 | AUH | 24.4462 | 54.598425 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5998 | AUH | 24.4788 | 54.411630 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD0989E | AUH | 24.272 | 54.6873603 | Existing | ibs | Possible | 287820.8538 | to be via MW
| IAD5732 | AUH | 24.441 | 54.578666 | Existing | ibs | Possible | 32668.6312 | Y2024 fiber scope
| IAD5267 | AUH | 24.4475 | 54.598718 | Existing | ibs | Possible | 34599.9711 | Y2024 fiber scope
| IAD5594 | AUH | 24.5029 | 54.410281 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5686 | AUH | 24.4907 | 54.370941 | Existing | ibs | Possible | 71139.343 | Y2024 fiber scope
| IAD5966 | AUH | 24.4429 | 54.579548 | Existing | ibs | Possible | 30737.2912 | Y2024 fiber scope
| IAD5973 | AUH | 24.4866 | 54.400808 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD0994E | AUH | 24.121 | 52.723812 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0006 | AUH | 24.4595 | 54.721483 | Existing | ibs | Possible | 168850.4977 | to be via MW
| AAN0113 | AUH | 24.1859 | 55.780282 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5889 | AUH | 24.4409 | 54.579559 | Existing | ibs | Possible | 29771.6212 | Y2024 fiber scope
| AUH0001 | AUH | 24.4654 | 54.334555 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD0988E | AUH | 24.7929 | 54.711548 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| IAD5999 | AUH | 24.5218 | 54.432285 | Existing | ibs | Possible | 47841.6601 | Y2024 fiber scope
| AUH0056 | AUH | 24.4154 | 54.439358 | Existing | ibs | Not Possible | 0 | to be via MW
| AUH0059 | AUH | 24.4154 | 54.439358 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5596 | AUH | 24.4932 | 54.400451 | Existing | ibs | PIS with ETC | 0 | to be via MW
| IAD5166 | AUH | 24.444 | 54.591633 | Existing | ibs | Possible | 43608.8366 | Y2024 fiber scope
| AUH0005 | AUH | 24.3531 | 54.406101 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5256 | AUH | 24.4533 | 54.609863 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5643 | AUH | 24.4464 | 54.589494 | Existing | ibs | Possible | 31973.5402 | Y2024 fiber scope
| IAD5359 | AUH | 24.4351 | 54.467212 | Existing | ibs | Possible | 30000 | Y2024 fiber scope
| AUH0028 | AUH | 24.7637 | 54.682013 | Existing | ibs | Possible | 626837.55 | to be via MW
| IAD5933 | AUH | 24.4425 | 54.577308 | Existing | ibs | Possible | 30737.2912 | Y2024 fiber scope
| IAD5786 | AUH | 24.4447 | 54.585579 | Existing | ibs | Possible | 27408.6 | Y2024 fiber scope
| IAD5173 | AUH | 24.5194 | 54.371572 | Existing | ibs | Not Possible | 0 | to be via MW
| IAD5976 | AUH | 24.5661 | 54.457889 | Existing | ibs | Possible | 67980.5552 | Y2024 fiber scope
| IAD5974 | AUH | 24.562 | 54.459586 | Existing | ibs | Possible | 47341.1787 | Y2024 fiber scope
| IAD5975 | AUH | 24.5644 | 54.459586 | Existing | ibs | Possible | 205898.0887 | to be via MW
| IAD5571 | AUH | 24.5083 | 54.406315 | Existing | ibs | PIS with ETC | 0 | to be via MW
| AUH0050 | AUH | 24.5037 | 54.4156 | Existing | ibs | Possible | 48000 | Y2024 fiber scope
| AUH0051 | AUH | 24.5037 | 54.4156 | Existing | ibs | Possible | 51600 | Y2024 fiber scope
| IAD5790 | AUH | 24.4461 | 54.588808 | Existing | ibs | Site Survey required | 0 | to be via MW
| IAD5961 | AUH | 24.3654 | 54.690212 | Existing | ibs | Site Survey required | 0 | to be via MW
| AUH0053 | AUH | 24.3394 | 54.608523 | Existing | ibs | Site Survey required | 0 | to be via MW
| AUH0074 | AUH | 24.5068 | 54.40509 | Existing | ibs | Site Survey required | 0 | to be via MW
| IAD5888 | AUH | 24.4301 | 54.433679 | Existing | ibs | internal connection - site survey required | 0 | Y2024 fiber scope
| AUH0054 | AUH | 24.3396 | 54.609066 | Existing | ibs | Site Survey required | 0 | to be via MW
| AUH0081 | AUH | 25.4945 | 53.1477 | Existing | ibs | NOT POSSIBLE | 0 | to be via MW
| IAD5188 | AUH | 24.4935 | 54.369188 | Existing | ibs | Possible | 107276.4 | to be via MW
| AUH0070 | AUH | 24.4171 | 54.468310 | Existing | ibs | Site Survey required | 0 | to be via MW
| IAD5785 | AUH | 24.4434 | 54.586986 | Existing | ibs | Site Survey required | 0 | to be via MW
| AUH0075 | AUH | 24.4712 | 54.34566 | Existing | ibs | Possible | 34032 | Y2024 fiber scope
| IAD0986B | AUH | 24.189 | 54.46595 | Existing | ibs | internal connection - site survey required | 0 | Y2024 fiber scope
| AUH0007 | AUH | 24.4297 | 54.434015 | Existing | ibs | internal connection - site survey required | 0 | Y2024 fiber scope
| IAD5855 | AUH | 24.4412 | 54.579198 | Existing | ibs | internal connection - site survey required | 0 | Y2024 fiber scope
| AUH0065 | AUH | 24.4409 | 54.578107 | Existing | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
| AUH0062 | AUH | 24.4968 | 54.407770 | Existing | ibs | Site Survey required | 0 | to be via MW
| IAD5826 | AUH | 24.4946 | 54.377658 | Existing | ibs | Exact Coordinates Required | 0 | Y2024 fiber scope
| AUH0064 | AUH | 24.3713 | 54.843426 | Existing | ibs | POSSIBLE | 271788.24 | to be via MW
IBS-SS-22-4615 | AUH0078 | AUH | 24.2649 | 54.458765 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-22-4282 | IAD5165 | AUH | 24.4868 | 54.363957 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-22-1259 | IAD5168 | AUH | 24.4466 | 54.588999 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-0716 | IAD5167 | AUH | 24.443 | 54.586736 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-20-1619 | IAD5839 | AUH | 24.4904 | 54.360944 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-490 | IAD5223 | AUH | 24.502 | 54.37159 | New | ibs | Possible | 168243.624 | to be via MW
IBS-FTK-19-1650 | IAD5421 | AUH | 24.4802 | 54.372696 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1605 | IAD5389 | AUH | 24.4204 | 54.463101 | New | ibs | Possible | 80796.168 | Y2024 fiber scope
IBS-FTK-19-1604 | IAD5388 | AUH | 24.4201 | 54.462813 | New | ibs | Possible | 133800.408 | to be via MW
IBS-FTK-19-1115 | IAD5261 | AUH | 24.446 | 54.597594 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-22-2030 | AUH0086 | AUH | 24.7028 | 54.79035 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-0012 | IAD5954 | AUH | 24.3323 | 54.625806 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-21-0316 | IAD5810 | AUH | 24.4826 | 54.406728 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-20-0191 | IAD5543 | AUH | 24.4651 | 54.385009 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-19-74 | IAD5193 | AUH | 24.5115 | 54.408272 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-19-561 | IAD5503 | AUH | 24.4363 | 54.466631 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-19-1363 | IAD5537 | AUH | 24.4787 | 54.371195 | New | ibs | Possible | 130186.656 | to be via MW
IBS-SS-19-1223 | IAD5641 | AUH | 24.4913 | 54.381239 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-19-1194 | IAD5398 | AUH | 24.4966 | 54.374074 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-18-0335 | AAN0041 | AUH | 24.2005 | 55.676094 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-23-0230 | AUH0524 | AUH | 24.4604 | 54.3125 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-22-4624 | AUH0029 | AUH | 24.7139 | 54.877890 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-22-4535 | AUH0011 | AUH | 24.4504 | 54.612533 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-3436 | IAD5716 | AUH | 24.4555 | 54.615282 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-22-3430 | IAD5033 | AUH | 24.4047 | 54.596096 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-22-1964 | AUH0073 | AUH | 24.4975 | 54.371888 | New | ibs | Possible | 113564.16 | to be via MW
IBS-FTK-22-1776 | IAD5963 | AUH | 24.5017 | 54.376426 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-22-1374 | IAD5965 | AUH | 24.4996 | 54.373355 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-22-1091 | AUH0094 | AUH | 24.4815 | 54.37246 | New | ibs | Possible | 53660.592 | Y2024 fiber scope
IBS-FTK-22-1087 | AUH0052 | AUH | 24.4912 | 54.358477 | New | ibs | Possible | 108225.576 | to be via MW
IBS-FTK-22-0968 | IAD5981 | AUH | 24.4423 | 54.581685 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-0161 | IAD5959 | AUH | 24.4551 | 54.615944 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-22-0160 | IAD5958 | AUH | 24.4543 | 54.615254 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-22-0159 | IAD5957 | AUH | 24.4443 | 54.583191 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3842 | AUH0035 | AUH | 24.4721 | 54.368118 | New | ibs | Possible | 61006.392 | Y2024 fiber scope
IBS-FTK-21-3818 | AUH0033 | AUH | 24.4471 | 54.592913 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3677 | IAD5939 | AUH | 24.4944 | 54.387744 | New | ibs | Not Possible | 0 | to be via MW
IBS-FTK-21-3667 | IAD5911 | AUH | 24.437 | 54.617932 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-21-3616 | IAD5905 | AUH | 24.3262 | 54.532083 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-21-3577 | IAD5880 | AUH | 24.4955 | 54.375290 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-21-3465 | IAD5863 | AUH | 24.4217 | 54.461861 | New | ibs | Possible | 257427.36 | to be via MW
IBS-FTK-21-3321 | IAD5858 | AUH | 24.4229 | 54.45419 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-21-3111 | AAN0134 | AUH | 24.2264 | 55.758197 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-21-3052 | AUH0034 | AUH | 24.4476 | 54.596064 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-0804 | IAD5834 | AUH | 24.4436 | 54.576193 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-20-1675 | IAD5926 | AUH | 24.4912 | 54.358588 | New | ibs | Possible | 29047.392 | Y2024 fiber scope
IBS-FTK-20-0113 | IAD5520 | AUH | 24.4438 | 54.589311 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-19-1612 | IAD5632 | AUH | 24.5002 | 54.372633 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-19-1611 | IAD5634 | AUH | 24.5021 | 54.373711 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1552 | IAD5124 | AUH | 24.4043 | 54.472918 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-20-0271 | IAD5709 | AUH | 24.492 | 54.375955 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-23-1455 | AAN0142 | AUH | 24.2336 | 55.69402 | New | ibs | Possible | 144574.5024 | to be via MW
IBS-SS-23-1315 | AUH0102 | AUH | 24.4006 | 54.732697 | New | ibs | Possible | 429382.4256 | to be via MW
IBS-SS-23-1302 | IAJ5876 | AUH | 24.2779 | 54.649218 | New | ibs | Possible | 252303.2352 | to be via MW
IBS-SS-23-1137 | AUH0103 | AUH | 24.4038 | 54.59229 | New | ibs | Possible | 136588.3776 | to be via MW
IBS-SS-22-5010 | AUH0043 | AUH | 24.43 | 54.463462 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-22-4499 | AUH0100 | AUH | 24.5181 | 54.44064 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-2674 | IAD5201 | AUH | 24.4207 | 54.46018 | New | ibs | Possible | 90958.176 | Y2024 fiber scope
IBS-SS-22-0020 | IAD5972 | AUH | 23.9685 | 52.2375278 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-21-2052 | IAD5897 | AUH | 24.1232 | 52.736049 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-21-2051 | IAD5898 | AUH | 24.129 | 52.71817 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-21-1227 | IAD5885 | AUH | 24.1008 | 52.654670 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-1226 | IAD5886 | AUH | 23.8996 | 52.805360 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-0736 |  | AUH | 24.4623 | 54.381692 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-0357 | AUH0044 | AUH | 24.4587 | 54.325717 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-0312 |  | AUH | 24.4081 | 54.450304 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-21-0310 |  | AUH | 24.4947 | 54.378916 | New | ibs | Possible | 71290.512 | Y2024 fiber scope
IBS-SS-21-0309 |  | AUH | 24.2132 | 55.667430 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-21-0198 | AUH0019 | AUH | 24.4339 | 54.580852 | New | ibs | Possible | 379394.352 | to be via MW
IBS-SS-21-0192 | AAN0120 | AUH | 24.1838 | 55.735236 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-0172 | IAD5978 | AUH | 24.4962 | 54.410417 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-21-0167 | IAD5805 | AUH | 24.4971 | 54.365216 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-20-1863 | IAD5955 | AUH | 25.2423 | 53.302617 | New | ibs | Wrong location | 0 | to be via MW
IBS-SS-20-1841 | IAD5794 | AUH | 24.3371 | 54.588646 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-20-0298 |  | AUH | 24.1169 | 52.76505 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-0295 |  | AUH | 24.1236 | 52.7313 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-0250 | IAD5803 | AUH | 23.2785 | 54.239125 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-0243 |  | AUH | 24.4288 | 54.514748 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-20-0218 |  | AUH | 24.4383 | 54.4125 | New | ibs | Possible | 83226.96 | Y2024 fiber scope
IBS-SS-20-0123 |  | AUH | 24.4569 | 54.3937333 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-20-0119 |  | AUH | 24.4212 | 54.454873 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-0091 |  | AUH | 24.4953 | 54.393900 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-20-0082 |  | AUH | 24.4284 | 54.45155 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-0042 |  | AUH | 24.4731 | 54.4027 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-19-95 | IAD5197 | AUH | 22.9229 | 53.99075 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-19-94 | IAD5198 | AUH | 22.9481 | 53.841622 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-19-560 | IAD5795 | AUH | 24.5008 | 54.794794 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-19-553 |  | AUH | 24.7886 | 52.554 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-19-1299 |  | AUH | 24.4517 | 54.36257 | New | ibs | Possible | 141901.776 | to be via MW
IBS-SS-19-1247 | IAD5439 | AUH | 24.4954 | 54.366165 | New | ibs | Possible | 167144.616 | to be via MW
IBS-SS-19-1229 | IAD5868 | AUH | 24.5015 | 54.377832 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-19-119 | IAD5199 | AUH | 24.4302 | 54.641835 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-18-0364 | IAD5139 | AUH | 24.4616 | 54.323536 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-23-1023 | AAN0141 | AUH | 24.0789 | 55.768732 | New | ibs | Not Possible | 0 | to be via MW
IBS-FTK-23-0865 | AUH0085 | AUH | 25.0074 | 53.3576556 | New | ibs | Not Possible | 0 | to be via MW
IBS-FTK-23-0807 | AUH0083 | AUH | 24.3994 | 52.882535 | New | ibs | Not Possible | 0 | to be via MW
IBS-FTK-23-0782 | AUH0096 | AUH | 24.4463 | 54.381451 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-23-0265 | AUH0069 | AUH | 24.4602 | 54.598858 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-23-0124 | AUH0042 | AUH | 24.443 | 54.57872 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-23-0016 | AUH0093 | AUH | 24.4934 | 54.388088 | New | ibs | Not Possible | 0 | to be via MW
IBS-FTK-22-5052 | AUH0088 | AUH | 24.6788 | 55.184370 | New | ibs | Possible | 338204.448 | to be via MW
IBS-FTK-22-4993 | AUH0030 | AUH | 24.447 | 54.589696 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-4991 | AUH0024 | AUH | 24.4472 | 54.590455 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-4652 | AUH0068 | AUH | 24.46 | 54.598135 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-22-4621 | AUH0025 | AUH | 24.4794 | 54.371346 | New | ibs | Possible | 40800.672 | Y2024 fiber scope
IBS-FTK-22-4620 | AUH0041 | AUH | 24.4404 | 54.577444 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-4619 | AUH0026 | AUH | 24.4798 | 54.371933 | New | ibs | Possible | 91156.608 | Y2024 fiber scope
IBS-FTK-22-4574 | AUH0012 | AUH | 24.4461 | 54.597108 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-2054 | IAD5977 | AUH | 24.4185 | 54.441915 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-22-2017 | IAD5910 | AUH | 24.4441 | 54.580616 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-22-1459 | AUH0089 | AUH | 24.4823 | 54.352176 | New | ibs | Possible | 114483.816 | to be via MW
IBS-FTK-22-1386 | IAD5964 | AUH | 24.5026 | 54.375626 | New | ibs | Possible | 55129.752 | Y2024 fiber scope
IBS-FTK-21-3839 | IAD5937 | AUH | 24.4929 | 54.372414 | New | ibs | Possible | 178646.04 | to be via MW
IBS-FTK-21-3838 | IAD5034 | AUH | 24.4552 | 54.617077 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-21-3821 | IAD5917 | AUH | 24.4516 | 54.612595 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3820 | IAD5960 | AUH | 24.4844 | 54.374333 | New | ibs | Possible | 74060.928 | Y2024 fiber scope
IBS-FTK-21-3690 | IAD5985 | AUH | 24.4613 | 54.607406 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-21-3615 | IAD5938 | AUH | 24.4485 | 54.608922 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3444 | IAD5872 | AUH | 24.4546 | 54.615515 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-21-0093 | IAD5829 | AUH | 24.2392 | 54.578942 | New | ibs | Not possible | 0 | to be via MW
IBS-FTK-20-1886 | IAD5787 | AUH | 24.4444 | 54.585095 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-20-1609 | IAD5907 | AUH | 24.4899 | 54.355087 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-20-1579 | IAD5906 | AUH | 24.4696 | 54.342621 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-20-1470 | IAD5728 | AUH | 23.9678 | 52.226153 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-20-1469 | IAD5727 | AUH | 23.9698 | 52.235787 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-20-1389 | IAD5642 | AUH | 24.4903 | 54.371569 | New | ibs | Possible | 59537.232 | Y2024 fiber scope
IBS-FTK-20-1050 | IAD5592 | AUH | 24.4958 | 54.374267 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-20-0998 | IAD5430 | AUH | 24.4893 | 54.368988 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-663 | IAD5235 | AUH | 24.4756 | 54.37271 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1683 | IAD5402 | AUH | 24.4319 | 54.434011 | New | ibs | Possible | 138780.288 | to be via MW
IBS-FTK-19-1606 | IAD5386 | AUH | 24.4965 | 54.372266 | New | ibs | Possible | 130560.624 | to be via MW
IBS-FTK-19-1602 | IAD5400 | AUH | 24.4735 | 54.346902 | New | ibs | OSP Provisioned | 48000 | Y2024 fiber scope
IBS-FTK-19-1587 | IAD5414 | AUH | 24.4898 | 54.36178 | New | ibs | Possible | 140287.608 | to be via MW
IBS-FTK-19-1495 | IAD5392 | AUH | 24.4759 | 54.351397 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-20-0120 | IAD5796 | AUH | 24.4153 | 54.484062 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-19-1254 |  | AUH | 24.4841 | 54.363846 | New | ibs | Possible | 242834.976 | to be via MW
IBS-SS-23-1475 |  | AUH | 24.5 | 54.39423 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-23-1473 |  | AUH | 24.1326 | 51.63075 | New | ibs | Possible | 15172.7213 | Y2024 fiber scope
IBS-SS-23-1472 |  | AUH | 24.5285 | 54.40381 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-23-1460 |  | AUH | 24.4924 | 54.37317 | New | ibs | Possible | 55377.792 | Y2024 fiber scope
IBS-SS-23-1456 |  | AUH | 24.3156 | 54.53366 | New | ibs | Possible | 153400.1472 | to be via MW
IBS-SS-23-1454 |  | AUH | 24.4457 | 54.59525 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-1432 |  | AUH | 24.4852 | 54.598016 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-23-1431 |  | AUH | 24.4852 | 54.598016 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-23-1430 |  | AUH | 24.4852 | 54.598016 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-23-1429 |  | AUH | 24.4852 | 54.598016 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-23-1358 |  | AUH | 24.3174 | 54.53073 | New | ibs | Possible | 37630.3392 | Y2024 fiber scope
IBS-SS-23-1336 |  | AUH | 24.4852 | 54.598016 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-23-1331 |  | AUH | 24.501 | 54.6256 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-23-1304 |  | AUH | 24.6265 | 54.71005 | New | ibs | Possible | 114530.3712 | to be via MW
IBS-SS-23-1242 |  | AUH | 24.4656 | 54.600151 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-1220 |  | AUH | 24.4919 | 54.39803 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-23-1203 |  | AUH | 24.4354 | 54.61794 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-1198 |  | AUH | 24.5034 | 54.410984 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-23-1185 |  | AUH | 24.4286 | 54.618702 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-1184 |  | AUH | 24.4286 | 54.618702 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-1183 |  | AUH | 24.4286 | 54.618702 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-1182 |  | AUH | 24.4515 | 54.61266 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-1154 |  | AUH | 24.3602 | 54.739594 | New | ibs | Site Survey required |  | to be via MW
IBS-SS-23-1153 |  | AUH | 24.3628 | 54.7624 | New | ibs | Site Survey required |  | to be via MW
IBS-SS-23-1152 |  | AUH | 24.4442 | 54.58556 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-1143 |  | AUH | 24.6081 | 55.775986 | New | ibs | Wrong location | 0 | to be via MW
IBS-SS-23-1142 |  | AUH | 24.2134 | 55.483673 | New | ibs | Wrong location | 0 | to be via MW
IBS-SS-23-1141 |  | AUH | 24.4956 | 54.37942 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-23-1138 |  | AUH | 24.4513 | 54.61195 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-1133 |  | AUH | 24.5018 | 54.41051 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-23-1093 |  | AUH | 24.4189 | 54.46449 | New | ibs | Possible | 149560.488 | to be via MW
IBS-SS-23-1092 |  | AUH | 24.4988 | 54.37681 | New | ibs | Possible | 97258.392 | Y2024 fiber scope
IBS-SS-23-1078 |  | AUH | 24.4879 | 54.365547 | New | ibs | Possible | 164818.3824 | to be via MW
IBS-SS-23-1027 |  | AUH | 24.4773 | 54.37091 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-23-1006 |  | AUH | 24.4142 | 54.54704 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-1001 |  | AUH | 24.49 | 54.379326 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-23-1000 |  | AUH | 24.4354 | 54.61794 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-23-0867 |  | AUH | 24.6161 | 54.73137 | New | ibs | Possible | 86317.92 | Y2024 fiber scope
IBS-SS-23-0787 |  | AUH | 24.5035 | 54.41101 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-23-0717 |  | AUH | 24.447 | 54.59205688 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-0716 |  | AUH | 24.4475 | 54.591003 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-0716 |  | AUH | 24.4475 | 54.591003 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-0715 |  | AUH | 24.3512 | 54.650711 | New | ibs | Possible | 79555.968 | Y2024 fiber scope
IBS-SS-23-0714 |  | AUH | 24.4475 | 54.59119 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-23-0707 |  | AUH | 24.4971 | 54.404847 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-22-5101 |  | AUH | 24.5623 | 54.458154 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-22-5100 |  | AUH | 24.4924 | 54.385558 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-22-5091 |  | AUH | 24.4143 | 54.5104959 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-22-4613 |  | AUH | 24.5402 | 54.399355 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-4595 |  | AUH | 24.4971 | 54.404847 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-22-4530 |  | AUH | 24.3008 | 54.56675 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-22-4394 |  | AUH | 24.5358 | 54.40386 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-4313 |  | AUH | 23.6599 | 53.70364 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-22-4297 |  | AUH | 24.3931 | 54.756277 | New | ibs | Wrong location | 0 | to be via MW
IBS-SS-22-3144 |  | AUH | 24.496 | 54.600205 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-3143 |  | AUH | 24.4459 | 54.592 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-SS-22-3142 |  | AUH | 24.4832 | 54.360171 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-22-2032 |  | AUH | 24.5015 | 54.376635 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-22-1630 |  | AUH | 24.4816 | 54.37314 | New | ibs | Possible | 99246.528 | Y2024 fiber scope
IBS-SS-22-0089 |  | AUH | 24.5082 | 54.411483 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-22-0088 |  | AUH | 24.5082 | 54.411483 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-22-0050 |  | AUH | 24.5337 | 54.40698 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-0049 |  | AUH | 24.5334 | 54.406947 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-SS-22-0011 |  | AUH | 24.2296 | 55.737194 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-21-1228 | AUH0022 | AUH | 24.0581 | 51.762000 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-21-0740 | AUH0016 | AUH | 24.4644 | 54.372029 | New | ibs | Possible | 345889.872 | to be via MW
IBS-SS-21-0739 | AUH0014 | AUH | 24.0977 | 53.483113 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-0208 |  | AUH | 24.2056 | 55.679721 | New | ibs | Possible | 100811.088 | Y2024 fiber scope
IBS-SS-21-0203 | AUH0015 | AUH | 24.1708 | 55.059798 | New | ibs | OSP Provisioned | 60000 | Y2024 fiber scope
IBS-SS-21-0200 | AUH0021 | AUH | 24.4286 | 54.455618 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-21-0194 | AUH0018 | AUH | 24.4964 | 54.934536 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-21-0174 |  | AUH | 24.4984 | 54.406159 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-21-0171 |  | AUH | 24.5053 | 54.410429 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-21-0170 |  | AUH | 24.5083 | 54.409149 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-21-0169 |  | AUH | 24.5071 | 54.410304 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-21-0164 | AUH0017 | AUH | 24.4335 | 54.415209 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-1584 |  | AUH | 24.1974 | 55.677687 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-20-0231 | IAD5798 | AUH | 24.4155 | 54.482684 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-20-0230 |  | AUH | 24.4308 | 54.4639 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-19-79 | AAN0115 | AUH | 24.5953 | 55.41146 | New | ibs | Possible | 2753045.568 | to be via MW
IBS-SS-19-1221 |  | AUH | 24.5029 | 54.372428 | New | ibs | Possible | 78930.144 | Y2024 fiber scope
IBS-SS-19-1216 | AUH0013 | AUH | 24.5331 | 54.428806 | New | ibs | Not Possible | 0 | to be via MW
IBS-Hunt-23-0873 |  | AUH | 24.4988 | 54.376825 | New | ibs | Possible | 88218.288 | Y2024 fiber scope
IBS-Hunt-22-1981 |  | AUH | 24.4851 | 54.352205 | New | ibs | Wrong location | 0 | to be via MW
IBS-Hunt-22-1504 |  | AUH | 24.4327 | 54.623371 | New | ibs | Site Survey required | 0 | to be via MW
IBS-Hunt-22-1458 |  | AUH | 24.4797 | 54.370069 | New | ibs | Possible | 50722.272 | Y2024 fiber scope
IBS-FTK-23-1537 |  | AUH | 24.4032 | 54.590125 | New | ibs | Possible | 48547.152 | Y2024 fiber scope
IBS-FTK-23-1367 |  | AUH | 24.4976 | 54.382169 | New | ibs | Wrong location | 0 | to be via MW
IBS-FTK-23-1074 |  | AUH | 24.4575 | 54.594613 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-22-2012 |  | AUH | 24.4465 | 54.589929 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3619 |  | AUH | 24.4848 | 54.628197 | New | ibs | TAAWUN |  | Y2024 fiber scope
IBS-FTK-20-1299 |  | AUH | 24.4459 | 54.595013 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-19-1653 | IAD5401 | AUH | 24.4854 | 54.352898 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-22-5155 | IAD5753 | AUH | 24.4074 | 54.505876 | New | ibs | OSP ready | 0 | Y2024 fiber scope
IBS-SS-22-5001 | AUH0099 | AUH | 24.4856 | 54.410705 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-22-4597 | AUH0072 | AUH | 24.4814 | 54.355202 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-22-4593 | AUH0039 | AUH | 24.4471 | 54.394981 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-22-4592 | AUH0038 | AUH | 24.447 | 54.394344 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-22-4591 | AUH0037 | AUH | 24.4477 | 54.395333 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-22-3145 | AUH0063 | AUH | 24.4942 | 54.377133 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-22-0023 | IAD5941 | AUH | 24.3986 | 54.56586 | New | ibs | Possible | 97933.824 | Y2024 fiber scope
IBS-SS-20-0221 | IAD5915 | AUH | 24.46 | 54.303518 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-20-0188 | IAD5625 | AUH | 24.4659 | 54.386143 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-SS-19-589 | AUH0061 | AUH | 24.4982 | 54.391571 | New | ibs | Not Possible | 0 | to be via MW
IBS-SS-19-288 | IAD5309 | AUH | 24.4293 | 54.43619 | New | ibs | Possible | 162641.736 | to be via MW
IBS-SS-19-1352 | IAD5475 | AUH | 24.4842 | 54.36751 | New | ibs | Possible | 47043.648 | Y2024 fiber scope
IBS-FTK-23-0140 | AUH0071 | AUH | 24.5205 | 54.447264 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-22-5126 | AUH0046 | AUH | 24.4137 | 54.4652766 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-22-4359 | IAD5046 | AUH | 24.3007 | 54.616644 | New | ibs | Possible | 162462.384 | to be via MW
IBS-FTK-22-0002 | IAD5923 | AUH | 24.4494 | 54.608818 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3851 | IAD5927 | AUH | 24.4405 | 54.578805 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3846 | IAD5929 | AUH | 24.4462 | 54.580232 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3780 | IAD5902 | AUH | 24.4515 | 54.608006 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3685 | IAD5894 | AUH | 24.4428 | 54.582161 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3684 | IAD5887 | AUH | 24.4475 | 54.592792 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3656 | IAD5928 | AUH | 24.448 | 54.596585 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3614 | IAD5893 | AUH | 24.4486 | 54.609383 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3445 | IAD5833 | AUH | 24.4445 | 54.588762 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3324 | AUH0095 | AUH | 24.4848 | 54.408470 | New | ibs | Not Possible |  | to be via MW
IBS-FTK-21-3260 | IAD5838 | AUH | 24.4463 | 54.599964 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3240 | IAD5871 | AUH | 24.4461 | 54.59449 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3228 | IAD5916 | AUH | 24.4431 | 54.588525 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3134 | IAD5836 | AUH | 24.4413 | 54.579684 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-3117 | IAD5837 | AUH | 24.4518 | 54.611777 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-2056 | IAD5856 | AUH | 24.4473 | 54.595353 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-1206 | IAD5835 | AUH | 24.4432 | 54.579141 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-1205 | IAD5832 | AUH | 24.4437 | 54.588833 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-21-0806 | IAD5831 | AUH | 24.4443 | 54.591338 | New | ibs | Tabreed network | 10K-60K | Y2024 fiber scope
IBS-FTK-20-1772 | IAD5908 | AUH | 24.4873 | 54.360769 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-20-1352 | IAD5718 | AUH | 24.4902 | 54.362035 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-600 | IAD5237 | AUH | 24.4554 | 54.617321 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-19-518 | IAD5221 | AUH | 24.453 | 54.614988 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-18-0797 | IAD0994A | AUH | 24.7794 | 54.73807 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-18-0598 | IAD5128 | AUH | 24.5002 | 54.390022 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-18-0265 | IAD0992B | AUH | 24.5421 | 54.7954 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-19-1240 | IAD5471 | AUH | 24.4938 | 54.361565 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-22-5136 | AUH0048 | AUH | 24.3974 | 54.558277 | New | ibs | Possible | 36061.2 | Y2024 fiber scope
IBS-FTK-22-5090 | IAD5909 | AUH | 24.4707 | 54.345747 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-22-4538 | AUH0040 | AUH | 23.8959 | 52.802735 | New | ibs | Possible | 125057.952 | to be via MW
IBS-FTK-22-4537 | AUH0036 | AUH | 23.6467 | 53.708875 | New | ibs | Possible | 108053.856 | to be via MW
IBS-FTK-22-4490 | AUH0047 | AUH | 24.3986 | 54.567070 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-22-2191 | IAD5997 | AUH | 24.6081 | 54.150450 | New | ibs | Wrong location | 0 | to be via MW
IBS-FTK-22-2190 | IAD5996 | AUH | 24.5172 | 54.025866 | New | ibs | Wrong location | 0 | to be via MW
IBS-FTK-22-1819 | IAD5982 | AUH | 24.4739 | 54.349080 | New | ibs | Possible | 191105.28 | to be via MW
IBS-FTK-20-1862 | IAD5845 | AUH | 24.497 | 54.374035 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-20-1690 | IAD5869 | AUH | 24.5023 | 54.37699 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-20-1468 | IAD5971 | AUH | 23.9665 | 52.225069 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-20-1051 | IAD5516 | AUH | 24.4962 | 54.374022 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1622 | IAD5390 | AUH | 24.4914 | 54.368293 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1613 | IAD5635 | AUH | 24.5005 | 54.375246 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1557 | IAD5397 | AUH | 24.4311 | 54.622142 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1521 | IAD5491 | AUH | 24.4892 | 54.360226 | New | ibs | Possible | 156608.64 | to be via MW
IBS-FTK-19-1505 | IAD5377 | AUH | 24.4664 | 54.386211 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-19-1448 | AUH0060 | AUH | 24.4973 | 54.374592 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-18-0208 | IAD5305 | AUH | 23.6592 | 53.704342 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-SS-20-0219 | IAD5639 | AUH | 24.4206 | 54.4279 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-19-89 | IAD5673 | AUH | 24.4725 | 54.341260 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-SS-19-259 | IAD5298 | AUH | 24.4597 | 54.301153 | New | ibs | Site Survey required | 0 | to be via MW
IBS-SS-18-1164 | IAD5183 | AUH | 24.4929 | 54.405844 | New | ibs | Not Possible | 0 | to be via MW
IBS-FTK-19-1674 | IAD0988D | AUH | 24.8005 | 54.64395 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-19-1673 | IAD0988A | AUH | 24.8026 | 54.642984 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-19-1434 | IAD0989B | AUH | 23.6665 | 54.345866 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-18-0166 | AAN5397A | AUH | 24.2213 | 55.7108 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-22-4397 |  | AUH | 24.8733 | 55.072836 | New | ibs | TAAWUN | 0 | Y2024 fiber scope
IBS-FTK-19-1034 | IAD0995D | AUH | 24.3391 | 54.525134 | New | ibs | Possible | 151899.696 | to be via MW
IBS-FTK-18-1072 | IAD0994D | AUH | 24.485 | 54.380038 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-FTK-18-0449 | IAD0994C | AUH | 24.485 | 54.380038 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-19-1583 | IAD0996C | AUH | 24.3461 | 54.464808 | New | ibs | OSP Provisioned | 42000 | Y2024 fiber scope
IBS-FTK-19-1128 | IAD0996B | AUH | 24.4453 | 54.610908 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-19-1127 | IAD0996A | AUH | 24.445 | 54.609788 | New | ibs | Possible | 42000 | Y2024 fiber scope
IBS-FTK-18-0202 | IAD0993E | AUH | 23.28 | 54.250076 | New | ibs | Site Survey required | 0 | to be via MW
IBS-FTK-18-0179 | IAD0991A | AUH | 24.4224 | 54.449635 | New | ibs | OSP Ready | 0 | Y2024 fiber scope
IBS-FTK-18-017 | AUH5532B | AUH | 24.3871 | 54.221309 | New | ibs | Not Possible | 0 | to be via MW