## Sheet1
Project Code | Site Code | Project Stream | Rollout Scope | Project Scope | Site Name | Rollout Status | Latitude | Longitude | OSP Feedback | 2024 plan | Existing Media | Termination Device | EPOC | EPOC Device Name | Solution | OSP cost | OSP ECD
IBS-5G-23-1165 | FUJ0621 | 5G | 5G Passive Coloc | Add Sector | Fujeirah City Center n78 5G Passive | Design Completed | 25.1254 | 56.301451 | OSP Ready | Existing Fiber | IIB | FUJ-0621-CSG-N540-LD-1 |  | FUJ-2014-SCSG-SR7-1 | TBD |  | #N/A
IBS-5G-23-1164 | SHJ0278 | 5G | 5G Passive Coloc | Add Sector | Sharjah City Centre n78 5G Passive | Design Completed | 25.3253 | 55.392760 | OSP Ready | Existing Fiber | IIB | SHJ-0278-CSG-SAR-8-1 |  | SHJ-2016-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0084 | RAK0547 | 5G | 5G Passive Coloc | 5G Coloc | Pacific Towers – Block D | Design Completed | 25.6862 | 55.732343 | OSP Ready | Existing Fiber | IIB | RAK-0547-CSG-IXR-E-1 |  | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
IBS-5G-23-0069 | RAK0546 | 5G | 5G Passive Coloc | 5G Coloc | Pacific Towers – Block C & E | Design Completed | 25.6867 | 55.732631 | OSP Ready | Existing Fiber | IIB | RAK-0546-CSG-IXR-E-1 |  | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
IBS-5G-23-0067 | AJM0957 | 5G | 5G Passive Coloc | 5G Coloc | Yasmeen B_Podium_B1_B2 | Design Completed | 25.3968 | 55.483186 | OSP Ready | Existing Fiber | IIB | AJM-0957-CSG-IXR-E-1 |  | SHJ-2035-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0065 | AJM0982 | 5G | 5G Passive Coloc | 5G Coloc | Mheiri Tower 2 | Design Completed | 25.3925 | 55.463209 | OSP Ready | Existing Fiber | IIB | AJM-0982-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4889 | RAK0526 | 5G | 5G Passive Coloc | 5G Coloc | Royal Breeze Cluster 2 (Buildings 4) | Design Completed | 25.7021 | 55.785165 | OSP Ready | Existing Fiber | IIB | RAK-0526-IBS-SAR-M-1 |  | RAK-2028-PREAGG-SR-7-1 | New CSG |  | #N/A
IBS-5G-22-4844 | SHJ0698 | 5G | 5G Passive Coloc | 5G Coloc | Tiger 4 Tower | Design Completed | 25.307 | 55.368356 | OSP Ready | Existing Fiber | IIB | SHJ-0698-CSG-ASR920-LD-1 |  | SHJ-2580-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4795 | SHJ0738 | 5G+Migration | 5G Passive Coloc | 5G Coloc | Qadisya Tower (Block C & D) | Design Completed | 25.3022 | 55.379718 | Possible | 2024 Fiber | MW |  | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | New CSG | 20000 | 2 months
IBS-5G-24-0042 | SHJ0471 | 5G | 5G Passive Coloc | 5G Coloc | Palm Tower 3 | Project Created | 25.323 | 55.379 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2016-SCSG-SR7B-1 |  | SHJ-2017-AGGR-SR7B-1 | New CSG |  | #N/A
IBS-5G-24-0041 | AJM0937 | 5G | 5G Passive Coloc | 5G Coloc | Corniche Tower Ajman Upper Part | Project Created | 25.4029 | 55.429727 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2074-CSG-IXR-E-1 |  | SHJ-2540-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-24-0040 | SHJ0402 | 5G | 5G Passive Coloc | 5G Coloc | Sarh Al Emarat Tower | Project Created | 25.3361 | 55.375352 | OSP Ready | Existing Fiber | IIB | SHJ-0402-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-24-0037 | SHJ0675 | 5G | 5G Passive Coloc | 5G Coloc | Al Qasimi Building 147 | Project Created | 25.3153 | 55.359418 | OSP Ready | Existing Fiber | IIB | SHJ-0675-CSG-ASR920-LD-1 |  | SHJ-2580-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-24-0036 | AJM0930 | 5G | 5G Passive Coloc | 5G Coloc | Paradise lake tower B-05 | Project Created | 25.3912 | 55.5752 | OSP Ready | Existing Fiber | IIB | AJM-0930-CSG-IXR-E-1 |  | AJM-2450-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-24-0035 | AJM0932 | 5G | 5G Passive Coloc | 5G Coloc | Paradise lake tower B-09 | Project Created | 25.3928 | 55.5761 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2450-SCSG-SR7B-1 |  | UAQ-DC-AGGR-SR7S-1 | New CSG |  | #N/A
IBS-5G-24-0031 | SHJ0432 | 5G | 5G Passive Coloc | 5G Coloc | Mamzar 2 | Project Created | 25.3046 | 55.3636 | OSP Ready | Existing Fiber | IIB | SHJ-0432-CSG-SAR-X-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | TBD |  | #N/A
IBS-5G-24-0016 | ISH5191 | 5G | 5G Passive Coloc | 5G Coloc | Al Mamsha Project_Muwaileh_ (SW1,SW2,SW3,SW4,RD1,RD2,RD4RD5) | Project Created | 25.3108 | 55.46544 | OSP Ready | Existing Fiber | IIB | ISH-5191-CSG-N540-LD-1 |  | SHJ-2049-AGGR-SR7b-1 | TBD |  | #N/A
IBS-5G-24-0015 | ISH5071 | 5G | 5G Passive Coloc | 5G Coloc | aljada_Areej Appartments_Block-5,6 & 7 | Project Created | 25.3178 | 55.480683 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-3504-CSG-IXR-E-1 |  | SHJ-2049-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-24-0013 | AJM0929 | 5G | 5G Passive Coloc | 5G Coloc | Diwan Towers | Project Created | 25.4158 | 55.442201 | OSP Ready | Existing Fiber | IIB | AJM-0929-CSG-N540-LD-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-24-0011 | SHJ0467 | 5G | 5G Passive Coloc | 5G Coloc | Mamzar A95 | Project Created | 25.3054 | 55.362781 | OSP Ready | Existing Fiber | IIB | SHJ-0467-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-1533 | ISH5229 | 5G | 5G Passive Coloc | 5G Coloc | aljada_NEST Appartments_N5,N6,N7,N8,N9,N10 | Project Created | 25.3217 | 55.483134 | OSP Ready | Existing Fiber | IIB | ISH-5229-CSG-N540-LD-1 |  | SHJ-2049-AGGR-SR7b-1 | TBD |  | #N/A
IBS-5G-23-1532 | ISH5228 | 5G | 5G Passive Coloc | 5G Coloc | aljada_NEST Appartments_BF,N1,N2,N3,N 4,N11 & N12 | Project Created | 25.3217 | 55.483134 | OSP Ready | Existing Fiber | IIB | ISH-5228-CSG-N540-LD-1 |  | SHJ-2049-AGGR-SR7b-1 | TBD |  | #N/A
IBS-5G-23-0115 | SHJ0769 | 5G | 5G Passive Coloc | 5G Coloc | Tiger 59/5 | Project Created | 25.3057 | 55.367687 | OSP Ready | Existing Fiber | IIB | SHJ-0769-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0113 | RAK0523 | 5G | 5G Passive Coloc | 5G Coloc | Royal Breeze Cluster 1 (Buildings 1 & 2) | Project Created | 25.6999 | 55.782636 | OSP Ready | Existing Fiber | IIB | RAK-0523-IBS-SAR-M-1 |  | RAK-2028-PREAGG-SR-7-1 | New CSG |  | #N/A
IBS-5G-23-0102 | AJM0948 | 5G | 5G Passive Coloc | 5G Coloc | Ajman Corniche Residence Tower (T1,T2,T3,T4) | Project Created | 25.4044 | 55.430304 | OSP Ready | Existing Fiber | IIB | AJM-0948-CSG-IXR-E-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0094 | SHJ0152 | 5G | 5G Passive Coloc | 5G Coloc | Buhaira National Insurance | Project Created | 25.3006 | 55.380611 | OSP Ready | Existing Fiber | IIB | SHJ-0152-CSG-SAR-8-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | TBD |  | #N/A
IBS-5G-23-0090 | ISH5063 | 5G | 5G Passive Coloc | 5G Coloc | Maryam Beach Residence 2 | Project Created | 25.3233 | 55.361366 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2580-PREAGG-SR7-1 |  | SHJ-2226-PREAGG-SR7-1 | New CSG |  | #N/A
IBS-5G-23-0089 | ISH5092 | 5G | 5G Passive Coloc | 5G Coloc | aljada_Rehan Appartments_Block-1,2 & 3 | Project Created | 25.3184 | 55.477888 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-3504-CSG-IXR-E-1 |  | SHJ-2049-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-23-0086 | ISH5079 | 5G | 5G Passive Coloc | 5G Coloc | Al Yasat Tower 2-SHJ | Project Created | 25.3187 | 55.380281 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2580-PREAGG-SR7-1 |  | SHJ-2226-PREAGG-SR7-1 | New CSG |  | #N/A
IBS-5G-23-0081 | AJM0949 | 5G | 5G Passive Coloc | 5G Coloc | Ajman Corniche Residence Tower (T5,T6,T7) | Project Created | 25.4044 | 55.430304 | OSP Ready | Existing Fiber | IIB -Passive | AJM-0948-CSG-IXR-E-1 |  | SHJ-2540-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-23-0072 | AJM0946 | 5G | 5G Passive Coloc | 5G Coloc | Ajman Oriental Tower B | Project Created | 25.4045 | 55.451158 | OSP Ready | Existing Fiber | IIB -Passive | AJM-0945-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-23-0070 | SHJ0685 | 5G | 5G Passive Coloc | 5G Coloc | Saeed Lootah Tower_Sharjah | Project Created | 25.305 | 55.36407 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2226-SCSG-IXR-R6D-1 |  | SHJ-2022-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-23-0068 | AJM0900 | 5G | 5G Passive Coloc | 5G Coloc | Ajman One Towers_E11 Tower&NE12 Tower | Project Created | 25.3959 | 55.430971 | OSP Ready | Existing Fiber | IIB | AJM-0900-CSG-ASR920-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0066 | SHJ0734 | 5G | 5G Passive Coloc | 5G Coloc | Ali Salim 639_Al Mamzar | Project Created | 25.3043 | 55.369833 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2226-SCSG-IXR-R6D-1 |  | SHJ-2022-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-23-0063 | AJM0963 | 5G | 5G Passive Coloc | 5G Coloc | Asyad Tower | Project Created | 25.3871 | 55.468793 | OSP Ready | Existing Fiber | IIB | AJM-0963-CSG-N540-LD-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0057 | AJM0898 | 5G | 5G Passive Coloc | 5G Coloc | Ajman One Towers_S7 Tower&SE8 Tower | Project Created | 25.3959 | 55.430971 | OSP Ready | Existing Fiber | IIB | AJM-0898-CSG-ASR920-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-23-0055 | SHJ0463 | 5G | 5G Passive Coloc | 5G Coloc | Al Nahda 5 | Project Created | 25.3003 | 55.369644 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2226-SCSG-IXR-R6D-1 |  | SHJ-2022-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-23-0051 | SHJ0258 | 5G | 5G Passive Coloc | 5G Coloc | Gulf Pearl Tower | Project Created | 25.3038 | 55.381172 | OSP Ready | Existing Fiber | IIB | SHJ-0258-CSG-SAR-X-1 |  | SHJ-2017-AGGR-SR7B-1 | TBD |  | #N/A
IBS-5G-22-5013 | IAJ5806 | 5G | 5G Passive Coloc | 5G Coloc | Vision Tower | Project Created | 25.42 | 55.450152 | OSP Ready | Existing Fiber | IIB | IAJ-5806-CSG-ASR920-LD-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4978 | AJM0980 | 5G | 5G Passive Coloc | 5G Coloc | Kingstone Tower Al Nakheel 1 | Project Created | 25.4085 | 55.442975 | OSP Ready | Existing Fiber | IIB | AJM-0980-CSG-SAR-X-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4966 | AJM0951 | 5G | 5G Passive Coloc | 5G Coloc | Al Ghoroub Buildings Ajman | Project Created | 25.3939 | 55.470766 | OSP Ready | Existing Fiber | IIB -Passive | AJM-3044-CSG-ASR920-LD-1 |  | SHJ-2038-AGGR-SR7-1 | New CSG |  | #N/A
IBS-5G-22-4962 | ISH5167 | 5G | 5G Passive Coloc | 5G Coloc | Al Mamsha Project_Muwaileh_ (SS1,SS2,SS3,SS4,SN3,SN4,RD3) | Project Created | 25.3108 | 55.46544 | OSP Ready | Existing Fiber | IIB | ISH-5167-CSG-IXR-E-1 |  | SHJ-2049-AGGR-SR7b-1 | TBD |  | #N/A
IBS-5G-22-4956 | AJM0912 | 5G | 5G Passive Coloc | 5G Coloc | Tasheel Building | Project Created | 25.3901 | 55.465456 | OSP Ready | Existing Fiber | IIB | AJM-0912-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4952 | AJM0988 | 5G | 5G Passive Coloc | 5G Coloc | Smart Tower 1 Al Aamra | Project Created | 25.3809 | 55.586015 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2450-SCSG-SR7B-1 |  | UAQ-DC-AGGR-SR7S-1 | New CSG |  | #N/A
IBS-5G-22-4899 | AJM0916 | 5G | 5G Passive Coloc | 5G Coloc | Ajman Pearl Tower(B1&B2&B3) | Project Created | 25.3925 | 55.46862 | OSP Ready | Existing Fiber | IIB | AJM-0916-CSG-ASR920-LD-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4894 | SHJ0770 | 5G | 5G Passive Coloc | 5G Coloc | Tiger 60/3 | Project Created | 25.3058 | 55.367908 | OSP Ready | Existing Fiber | IIB | SHJ-0770-CSG-ASR920-LD-1 |  | SHJ-2580-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4856 | SHJ0740 | 5G | 5G Passive Coloc | 5G Coloc | Al Saud Building Muweilah | Project Created | 25.3107 | 55.455242 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2049-AGGR-SR7b-1 |  | SHJ-2049-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-22-4845 | SHJ0058 | 5G | 5G Passive Coloc | 5G Coloc | Zakher 1 | Project Created | 25.3072 | 55.369163 | OSP Ready | Existing Fiber | IIB | SHJ-0058-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4828 | SHJ0446 | 5G | 5G Passive Coloc | 5G Coloc | Al-Qassimeyah tower | Project Created | 25.3412 | 55.391508 | OSP Ready | Existing Fiber | IIB | SHJ-0446-CSG-SAR-X-1 |  | SHJ-2094-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4827 | ISH5170 | 5G | 5G Passive Coloc | 5G Coloc | aljada_Misk Appartments_1 & 2 | Project Created | 25.3197 | 55.479474 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-3504-CSG-IXR-E-1 |  | SHJ-2049-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-22-4825 | SHJ0481 | 5G | 5G Passive Coloc | 5G Coloc | Al Saada Tower @ Al Mamzar Lake | Project Created | 25.3118 | 55.363874 | OSP Ready | Existing Fiber | IIB | SHJ-0481-CSG-SAR-X-1 |  | SHJ-6501-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-22-4821 | AJM0947 | 5G | 5G Passive Coloc | 5G Coloc | Ajman Oriental Tower C | Project Created | 25.4045 | 55.451158 | OSP Ready | Existing Fiber | IIB -Passive | AJM-0945-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-22-4819 | SHJ0411 | 5G | 5G Passive Coloc | 5G Coloc | Abu Shagarah Twin Towers | Project Created | 25.3439 | 55.402001 | OSP Ready | Existing Fiber | IIB | SHJ-0411-CSG-SAR-X-1 |  | SHJ-2012-SCSG-IXR-R6D-1 | TBD |  | #N/A
IBS-5G-22-4818 | AJM0961 | 5G | 5G Passive Coloc | 5G Coloc | Yasmeen A_Site 2 | Project Created | 25.3968 | 55.483186 | OSP Ready | Existing Fiber | IIB -Passive | AJM-0960-CSG-IXR-E-1 |  | SHJ-2035-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-22-4814 | RAK0524 | 5G | 5G Passive Coloc | 5G Coloc | Royal Breeze Cluster 2 (Buildings 3 & 5) | Project Created | 25.7016 | 55.784548 | OSP Ready | Existing Fiber | IIB | RAK-0524-IBS-SAR-M-1 |  | RAK-2028-PREAGG-SR-7-1 | New CSG |  | #N/A
IBS-5G-22-4812 | IAJ5805 | 5G | 5G Passive Coloc | 5G Coloc | Nesto Complex_Ajman | Project Created | 25.3761 | 55.510800 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2304-CSG-SAR-8-1 |  | SHJ-2038-AGGR-SR7-2 | New CSG |  | #N/A
IBS-5G-22-4794 | AJM0934 | 5G | 5G Passive Coloc | 5G Coloc | Lilies Tower | Project Created | 25.391 | 55.572171 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2450-SCSG-SR7B-1 |  | UAQ-DC-AGGR-SR7S-1 | New CSG |  | #N/A
IBS-5G-22-4792 | AJM0996 | 5G | 5G Passive Coloc | 5G Coloc | EI_NW_3303_ABResidence | Project Created | 25.3989 | 55.475008 | OSP Ready | Existing Fiber | IIB | AJM-0996-CSG-IXR-E-1 |  | SHJ-2035-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4791 | AJM0914 | 5G | 5G Passive Coloc | 5G Coloc | Ajman Pearl Tower(A1&A2&A3) | Project Created | 25.3925 | 55.46862 | OSP Ready | Existing Fiber | IIB | AJM-0914-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4790 | AJM0899 | 5G | 5G Passive Coloc | 5G Coloc | Ajman One Towers_SE9 Tower&SE10 Tower | Project Created | 25.3959 | 55.430971 | OSP Ready | Existing Fiber | IIB | AJM-0899-CSG-ASR920-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4773 | AJM0856 | 5G | 5G Passive Coloc | 5G Coloc | Falcon Tower A5, A6, A7 and B1 | Project Created | 25.3989 | 55.448661 | OSP Ready | Existing Fiber | IIB -Passive | AJM-0855-CSG-SAR-X-1 |  | AJM-6001-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-22-4772 | AJM0863 | 5G | 5G Passive Coloc | 5G Coloc | Horizon Towers C&D | Project Created | 25.3935 | 55.455238 | OSP Ready | Existing Fiber | IIB | AJM-0863-CSG-ASR920-LD-1 |  | AJM-6001-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4770 | AJM0895 | 5G | 5G Passive Coloc | 5G Coloc | Ajman One Towers_N1 Tower & NW2 Tower | Project Created | 25.3959 | 55.430971 | OSP Ready | Existing Fiber | IIB -Passive | AJM-0900-CSG-ASR920-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | New CSG |  | #N/A
IBS-5G-22-4769 | AJM0896 | 5G | 5G Passive Coloc | 5G Coloc | Ajman One Towers_NW3 Tower&NW4 Tower | Project Created | 25.3959 | 55.430971 | OSP Ready | Existing Fiber | IIB | AJM-0896-CSG-ASR920-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4768 | AJM0940 | 5G | 5G Passive Coloc | 5G Coloc | Grand Mall Ajman<br><br> | Project Created | 25.3924 | 55.438924 | OSP Ready | Existing Fiber | IIB | AJM-0940-CSG-N540-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4680 | ISH5025 | 5G | 5G Passive Coloc | 5G Coloc | MIHTAB 1 TOWERS | Project Created | 25.3058 | 55.383115 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2016-SCSG-SR7B-1 |  | SHJ-2017-AGGR-SR7B-1 | New CSG |  | #N/A
IBS-5G-22-4679 | SHJ0049 | 5G | 5G Passive Coloc | 5G Coloc | AL Nahda Sahara Towers | Project Created | 25.2996 | 55.378969 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2589-CSG-SAR-8-1 |  | SHJ-2017-AGGR-SR7b-1 | New CSG |  | #N/A
IBS-5G-22-4645 | AJM0933 | 5G | 5G Passive Coloc | 5G Coloc | Lavender Tower MBZR | Project Created | 25.3904 | 55.571870 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2450-SCSG-SR7B-1 |  | UAQ-DC-AGGR-SR7S-1 | New CSG |  | #N/A
IBS-5G-22-4641 | AJM0897 | 5G | 5G Passive Coloc | 5G Coloc | Ajman One Towers_W5 Tower&SW6 Tower | Project Created | 25.3959 | 55.430970 | OSP Ready | Existing Fiber | IIB | AJM-0897-CSG-ASR920-LD-1 |  | SHJ-2540-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-22-4629 | SHJ0486 | 5G | 5G Passive Coloc | 5G Coloc | Qadisya Tower (Block A & B) | Project Created | 25.3001 | 55.379479 | OSP Ready | Existing Fiber | IIB | SHJ-0486-CSG-ASR920-LD-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | TBD |  | #N/A
IBS-5G-22-4590 | IAJ5801 | 5G | 5G Passive Coloc | 5G Coloc | Fortune Residency | Project Created | 25.3902 | 55.572590 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2450-SCSG-SR7B-1 |  | UAQ-DC-AGGR-SR7S-1 | New CSG |  | #N/A
IBS-5G-22-2900 | FUJ0619 | 5G | 5G Passive Coloc | 5G Coloc | Fujairah Rotana Hotel & Resort | Project Created | 25.5088 | 56.363387 | OSP Ready | Existing Fiber | IIB | FUJ-0619-CSG-SAR-X-1 |  | KFN-2678-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-22-2896 | KFN0704 | 5G | 5G Passive Coloc | 5G Coloc | Miramar Al Aqah Beach Resort | Project Created | 25.5012 | 56.361104 | OSP Ready | Existing Fiber | IIB | KFN-0704-CSG-SAR-X-1 |  | KFN-2678-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-22-0266 | IFU5604 | 5G | 5G Passive Coloc | 5G Coloc | Address Fujairah Beach Resort_Hotel & residences | Project Created | 25.1382 | 56.35565 | OSP Ready | 2024 Fiber | MW |  | KFN2678 | KFN-2678-SCSG-SR7-1 | New CSG |  | 0
IBS-5G-22-0261 | IUA5752 | 5G | 5G Passive Coloc | 5G Coloc | Vida Hotel, UAQ | Project Created | 25.579 | 55.564576 | OSP Ready | Existing Fiber | IIB | IUA-5752-CSG-N540-LD-1 |  |  | TBD |  | #N/A
IBS-5G-22-0251 | SHJ0450 | 5G | 5G Passive Coloc | 5G Coloc | Oasis Mall_Sharjah | Project Created | 25.3488 | 55.409654 | OSP Ready | Existing Fiber | IIB | SHJ-0450-CSG-SAR-X-1 |  | SHJ-2022-AGGR-SR7b-1 | TBD |  | #N/A
IBS-5G-22-0240 | RAK0503 | 5G | 5G Passive Coloc | 5G Coloc | Al Hamra Beach Hotel | Project Created | 25.6888 | 55.775917 | NA | 2024 MW | MW |  |  |  | New MW Link |  | #N/A
IBS-5G-22-0239 | RAK0519 | 5G+Migration | 5G Passive Coloc | 5G Coloc | Al Hamra Palace-Casa Hotel | Project Created | 25.6861 | 55.773600 | Possible | 2024 Fiber | MW |  | UAQ2018 | RAK-5001-CSG-SAR-8-1 | New CSG | 135000 | 5 months
IBS-5G-22-0226 | RAK0532 | 5G | 5G Passive Coloc | 5G Coloc | Doubletree by Hilton Resort & Spa Marjan Island RAK | Project Created | 25.6697 | 55.744027 | OSP Ready | Existing Fiber | IIB | RAK-0532-CSG-IXR-E-1 |  | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
IBS-5G-22-0215 | FUJ0629 | 5G | 5G Passive Coloc | 5G Coloc | Fujairah Mall | Project Created | 25.1237 | 56.315529 | OSP Ready | Existing Fiber | IIB | FUJ-0629-CSG-SAR-X-1 |  | FUJ-2014-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-22-0208 | RAK0505 | 5G | 5G Passive Coloc | 5G Coloc | Hilton Ras Al Khaimah Resort & Spa | Project Created | 25.8144 | 55.957630 | OSP Ready | Existing Fiber | IIB | RAK-0505-CSG-IXR-E-1 |  | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
IBS-5G-22-0204 | KFN0707 | 5G | 5G Passive Coloc | 5G Coloc | Intercontinental Hotel and Resorts Fujairah | Project Created | 25.5048 | 56.362367 | OSP Ready | Existing Fiber | IIB | KFN-0707-CSG-SAR-X-1 |  | KFN-2678-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-22-0198 | FUJ0640 | 5G | 5G Passive Coloc | 5G Coloc | Lulu Mall Fujairah | Project Created | 25.12 | 56.328209 | OSP Ready | Existing Fiber | IIB | FUJ-0640-CSG-SAR-X-1 |  | FUJ-2013-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-21-0779 | IRK5508 | 5G | 5G Passive Coloc | SS | INTERCONTINENTAL HOTEL RAK 5G | Project Created | 25.726 | 55.846733 | OSP Ready | Existing Fiber | IIB | IRK-5508-CSG-IXR-E-1 |  | RAK-2028-PREAGG-SR7-1 | TBD |  | #N/A
IBS-5G-22-4647 | SHJ0682 | 5G | 5G Passive Coloc | 5G Coloc | Al Yarmouk Tower C & D | SAQ Completed | 25.302 | 55.384450 | OSP Ready | Existing Fiber | IIB | SHJ-0682-CSG-IXR-E-1 |  | SHJ-2016-SCSG-SR7B-1 | TBD |  | #N/A
IBS-5G-21-0630 | FUJ0601 | 5G+Migration | 5G Passive Coloc | 5G Coloc | Fujeirah international Airport 5G Passive | TI Installed not integrated | 25.1126 | 56.333550 | Possible | 2024 Fiber | MW |  | FUJ2013 | FUJ-2013-SCSG-SR7-1 | New CSG | 150000 | 8 months
IBS-5G-21-3539 | SHJ0276 | 5G | 5G Passive Coloc | 5G Coloc | Sharjah International Airport | TI Started | 25.3214 | 55.521 | OSP Ready | Existing Fiber | IIB | SHJ-0276-CSG-ASR920-LD-1 |  | SHJ-2053-AGGR-SR7b-1 | TBD |  | 0
IBS-SS-22-0967 | ISH5230 | BAU | 2024 IC | SS | Al Zahia Uptown Project_site-1 | DAS Completed | 25.3135 | 55.457942 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 57000 | 2 Months
IBS-SS-22-0055 | ISH5186 | BAU | 2024 IC | SS | Mazaya Tower_AL MAZAJ FIRST | DAS Completed | 25.3369 | 55.38727 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-2057 | ISH5165 | BAU | 2024 IC | SS | Khawla Tower_Al Majaz | DAS Completed | 25.3281 | 55.377069 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-20-0484 | SHJ0656 | BAU | 2024 IC | SS | Shayba 167 Tower | DAS Completed | 25.3014 | 55.374932 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 15000 | 1 MONTH
IBS-SS-19-58 | AJM0859 | BAU | 2024 IC | SS | Al Watan University Ajman | DAS Completed | 25.3814 | 55.580901 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 40000 | 3 months
IBS-SS-19-551 | AJM0989 | BAU | 2024 IC | SS | EI_NW_3989_AjmanPrvtHsptl | DAS Completed | 25.4168 | 55.504266 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 20000 | 2 months
IBS-SS-19-160 | SHJ0742 | BAU | 2024 IC | SS | Burj Al Owais at Al Majaz 3 | DAS Completed | 25.3348 | 55.375898 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 15000 | 1 MONTH
IBS-SS-19-156 | ISH5134 | BAU | 2024 IC | SS | United Arab Bank Building Sharjah | DAS Completed | 25.3323 | 55.361094 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-22-3407 | ISH5203 | BAU | 2024 IC | FTK | Rashid Abdullah Building Al Taawun | DAS Completed | 25.3075 | 55.372986 | WIP CF 2023 | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 40000 | 2 Months
IBS-FTK-22-1840 | IAJ5851 | BAU | 2024 IC | FTK | Al Khaled Tower 3 Al Nuaimia 3 | DAS Completed | 25.391 | 55.431448 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3623 | IAJ5848 | BAU | 2024 IC | FTK | Golf Tower Emirates City Ajman | DAS Completed | 25.3947 | 55.578268 | OSP Provisioned | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 15000 | 1 MONTH
IBS-FTK-21-3606 | ISH5163 | BAU | 2024 IC | FTK | Art Tower Al Nahda Sharjah | DAS Completed | 25.3037 | 55.382845 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 15000 | 1 MONTH
IBS-FTK-21-3578 | IUA5756 | BAU | 2024 IC | FTK | Itihad Tower Umm Al Quwain | DAS Completed | 25.4948 | 55.550038 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3457 | IAJ5844 | BAU | 2024 IC | SS | Aman Complex_Ajman | DAS Completed | 25.4012 | 55.4993 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3056 | IFU5620 | BAU | 2024 IC | FTK | Etihad Rail Tunnel 6 | DAS Completed | 25.1814 | 56.238590 | Possible | 2024 MW | NA |  |  |  | New MW Link | 482385.178 | 8 months
IBS-FTK-20-1704 | ISH5008 | BAU | 2024 IC | FTK | Al Shoibi Tower 1 Al Nahda | DAS Completed | 25.3018 | 55.378463 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-19-1154 | SHJ0466 | BAU | 2024 IC | PFTK | G+5P+15 Mamzar | DAS Completed | 25.3068 | 55.370713 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-22-2182 | ISH5231 | BAU | 2024 IC | SS | Al Zahia Uptown Project_site-2 | DAS Started | 25.3135 | 55.457942 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 41829 | 2 months
IBS-SS-19-549 | ISH5193 | BAU | 2024 IC | FTK | Omis Tower Al Qassimia Sharjah | DAS Started | 25.3399 | 55.388666 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2058 | SHJ-2058-SCSG-IXR-R6-1 | Passive | 15000 | 1 MONTH
IBS-FTK-23-0209 | IAJ5871 | BAU | 2024 IC | FTK | Abdullatif Al Shaiba Tower_AJM | DAS Started | 25.3972 | 55.49316 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 15000 | 1 MONTH
IBS-FTK-22-1846 | ISH5221 | BAU | 2024 IC | FTK | PAN Emirates | DAS Started | 25.3218 | 55.457317 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 25000 | 2 months
IBS-FTK-22-1524 | IAJ5870 | BAU | 2024 IC | FTK | C4 Lake Tower | DAS Started | 25.3916 | 55.573781 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-22-0153 | IAJ5855 | BAU | 2024 IC | FTK | Residential Building (Plot 844) Rashidiya 1 | DAS Started | 25.3905 | 55.456433 | OSP Provisioned | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 15000 | 1 MONTH
IBS-FTK-21-3714 | ISH5157 | BAU | 2024 IC | FTK | Dimas Residential Tower | DAS Started | 25.314 | 55.379258 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 15000 | 1 MONTH
IBS-FTK-21-3659 | IAJ5857 | BAU | 2024 IC | FTK | Al Saada Tower | DAS Started | 25.4034 | 55.505105 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3263 | ISH5160 | BAU | 2024 IC | FTK | Sharjah City for Humanitarian Services Barashi | DAS Started | 25.2714 | 55.579414 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3060 | IFU5622 | BAU | 2024 IC | FTK | Etihad Rail Tunnel 10,11 | DAS Started | 25.1635 | 56.314719 | Possible | 2024 MW | NA |  |  |  | New MW Link | 282182.23 | 4 months
IBS-FTK-21-3057 | IFU5621 | BAU | 2024 IC | FTK | Etihad Rail Tunnel 7,8,9 | DAS Started | 25.1495 | 56.285520 | Possible | 2024 Fiber | NA | NA | FUJ5002 | FUJ-5002-SCSG-SR7-1 | Passive | 135075.193 | 4 months
IBS-FTK-21-3054 | IFU5619 | BAU | 2024 IC | FTK | Etihad Rail Tunnel 2,3 | DAS Started | 25.2532 | 56.178503 | Possible | 2024 Fiber | NA | NA | FUJ5003 | FUJ-5003-PREAGG-SRa8-1 | Passive | 162429.388 | 5 months
IBS-FTK-19-997 | AJM0858 | BAU | 2024 IC | FTK | Al Yaziah 2 Building at Rashidiya 1 | DAS Started | 25.3937 | 55.464993 | OSP Provisioned | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 15000 | 1 MONTH
IBS-FTK-19-1595 | ISH5115 | BAU | 2024 IC | FTK | Rayan Hotel Sharjah | DAS Started | 25.3436 | 55.403068 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2022 | SHJ-2022-AGGR-SR7b-1 | Passive | 15000 | 1 MONTH
IBS-FTK-19-1148 | AJM0987 | BAU | 2024 IC | FTK | Al Aamra Tower | DAS Started | 25.3872 | 55.576245 | OSP Provisioned | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 15000 | 1 MONTH
IBS-FTK-21-3827 | IRK5512 | BAU | 2024 IC | FTK | Rakia Amenity Complex 2 (Rakez Towers A3 TO A6) | DAS to Start | 25.6578 | 55.795562 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-23-1535 | IAJ5875 | BAU | 2024 IC | SS | International Charity Organization_Ajman | Design Completed | 25.4056 | 55.484269 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 45000 | 2 months
IBS-SS-23-1330 | IRK5526 | BAU | 2024 IC | SS | Zayed Educational Complex_RAK | Design Completed | 25.7064 | 55.887154 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-23-1321 | ISH5246 | BAU | 2024 IC | SS | Emirati School_Al Rahmaniya | Design Completed | 25.3493 | 55.581541 | Possible | 2024 Fiber | NA | NA | SHJ5003 | SHJ-5003-SCSG-SR7B-1 | Passive | 50000 | 2 months
IBS-SS-23-1320 | ISH5245 | BAU | 2024 IC | SS | Emirati School_Al Syouh | Design Completed | 25.2341 | 55.64664 | Possible | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | Passive | 120000 | 3 Months
IBS-SS-23-1319 | IAJ5878 | BAU | 2024 IC | SS | Emirati School_Hamidiya | Design Completed | 25.3804 | 55.535493 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 120000 | 3 Months
IBS-SS-23-1187 | IRK5527 | BAU | 2024 IC | SS | Zayed Education Complex_Awafi RAK | Design Completed | 25.708 | 55.932604 | Taawun | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | Passive |  | 0
IBS-SS-23-1181 | IFU5638 | BAU | 2024 IC | SS | Emirati School_Seeh Dibba | Design Completed | 25.5856 | 56.234592 | Possible | 2024 Fiber | NA | NA | KFN2011 | KFN-2611-CSG-ASR907-1 | Passive | 120000 | 4 months
IBS-SS-23-1005 | IFU5637 | BAU | 2024 IC | SS | Emirates School Albidiya_Fujairah | Design Completed | 25.4199 | 56.353049 | Possible | 2024 Fiber | NA | NA | KFN2677 | KFN-2677-CSG-IXR-E-1 | Passive | 150000 | 3 months
IBS-SS-23-0279 | IFU5635 | BAU | 2024 IC | SS | Air Traffic Control Tower Fujairah | Design Completed | 25.1046 | 56.3263 | Possible | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 70000 | 7 months
IBS-SS-22-4616 | ISH5236 | BAU | 2024 IC | SS | Ganda Tower_AL NAHDA | Design Completed | 25.3017 | 55.370800 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 15000 | 1 MONTH
IBS-SS-22-2181 | IBS-SS-22-2181 | BAU | 2024 IC | SS | Grand Mall_AL MUSSALLA | Design Completed | 25.3543 | 55.39524 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-22-2013 | IFU5629 | BAU | DAS 2024 | FTK | Fujairah Financial Department & e-Government & Amiri Court buildings | Design Completed | 25.1245 | 56.333678 | Possible | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 25000 | 1 MONTH
IBS-SS-22-1100 | ISH5173 | BAU | 2024 IC | SS | AL Safa Tower Al Nahda | Design Completed | 25.3021 | 55.380178 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-22-0085 | ISH5247 | BAU | 2024 IC | SS | Maryam Gate Residence_Al Khan | Design Completed | 25.3223 | 55.361112 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-22-0047 | IRK5515 | BAU | DAS 2024 | SS | Rove Hotel_Al Marjan | Design Completed | 25.6732 | 55.741885 | Possible | 2024 Fiber | NA | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | Passive | 55891 | 2 months
IBS-SS-21-3359 | ISH5168 | BAU | 2024 IC | SS | MD Al Zarooni Tower_Sharjah | Design Completed | 25.3017 | 55.36828 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 1 MONTH
IBS-SS-21-2118 | ISH5120 | BAU | DAS 2024 | SS | Gulf Sky Building-SHJ | Design Completed | 25.3127 | 55.378122 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-2115 | ISH5116 | BAU | DAS 2024 | SS | Zahrat Al Nahda Tower-SHJ | Design Completed | 25.3025 | 55.37234 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 1 MONTH
IBS-SS-21-2102 | ISH5102 | BAU | DAS 2024 | SS | Al Marsa Building-SHJ | Design Completed | 25.3449 | 55.388244 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-21-0322 | IBS-SS-21-0322 | BAU | DAS 2024 | FTK | Al Qasmia Waqf Tower | Design Completed | 25.3254 | 55.374650 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-21-0235 | ISH5075 | BAU | 2024 IC | SS | Hassan Baba399 BLDG AKA(Al Jawad Tower)-SHJ | Design Completed | 25.3036 | 55.379669 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-0234 | ISH5110 | BAU | 2024 IC | SS | Naeem Tower AKA(Al Reef 1 Tower)-SHJ | Design Completed | 25.3006 | 55.36716 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-0086 | ISH5065 | BAU | DAS 2024 | SS | Sharjah Airport Departure Extension - Site-2 | Design Completed | 25.3213 | 55.522336 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-0085 | ISH5064 | BAU | DAS 2024 | SS | Sharjah Airport Departure Extension - Site-1 | Design Completed | 25.3213 | 55.522336 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-20-0481 | ISH5069 | BAU | 2024 IC | SS | Bawadi Tower-SHJ | Design Completed | 25.3034 | 55.383647 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 35000 | 2 months
IBS-SS-20-0479 | ISH5038 | BAU | 2024 IC | SS | Jamal Building AKA(Al Naeem Tower-SHJ) | Design Completed | 25.303 | 55.378094 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-20-0458 | ISH5018 | BAU | 2024 IC | SS | Hassan Baba Tower AKA(Al Reef 2)-SHJ | Design Completed | 25.3052 | 55.382211 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 30000 | 2 months
IBS-SS-20-0415 | ISH5048 | BAU | 2024 IC | SS | Ritz Hotel SHJ | Design Completed | 25.3081 | 55.372311 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-20-0385 | ISH5036 | BAU | 2024 IC | SS | Royal Crown Hotel-SHJ | Design Completed | 25.321 | 55.3798 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-20-0321 | IFU5616 | BAU | 2024 IC | SS | Higher Colleges of Technology Fujairah Men's College | Design Completed | 25.1304 | 56.29527 | Possible | 2024 Fiber | NA | NA | FUJ5003 | FUJ-5003-PREAGG-SRa8-1 | Passive | 30000 | 2 months
IBS-SS-20-0035 | SHJ0725 | BAU | 2024 IC | SS | AL Khan Oasis_Sharjah | Design Completed | 25.31 | 55.377144 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 25000 | 2 months
IBS-SS-19-1569 | IBS-SS-19-1569 | BAU | DAS 2024 | FTK | Sharjah Group Company Building - Al Khan | Design Completed | 25.3287 | 55.369821 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-19-1004 | ISH5073 | BAU | 2024 IC | SS | Sharjah University Women's College | Design Completed | 25.2937 | 55.47604 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 35000 | 2 months
IBS-SS-18-0428 | SHJ0671 | BAU | 2024 IC | SS | Al Hilal Al Molay Tower | Design Completed | 25.3088 | 55.376445 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-23-1355 | ISH5242 | BAU | DAS 2024 | PFTK | Vida3 & 4 Project | Design Completed | 25.3161 | 55.476245 | Taawun | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive |  | 0
IBS-FTK-23-0912 | IAJ5872 | BAU | DAS 2024 | FTK | Victoria School - Telal | Design Completed | 25.2628 | 55.584223 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | Passive |  | 0
IBS-FTK-23-0864 | IFU5636 | BAU | DAS 2024 | FTK | Al Fujairah School | Design Completed | 25.0882 | 56.301248 | Possible | 2024 Fiber | NA | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | Passive | 40000 | 3 months
IBS-FTK-23-0779 | IAJ5868 | BAU | DAS 2024 | FTK | Ali Mohamed Al Qubaisi Residence Ajman | Design Completed | 25.3963 | 55.576545 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 66819.2 | 2 months
IBS-FTK-23-0171 | ISH5224 | BAU | DAS 2024 | FTK | Al Basemah Tower Al Majaz 2 | Design Completed | 25.3351 | 55.373316 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 25000 | 2 months
IBS-FTK-23-0147 | ISH5208 | BAU | DAS 2024 | FTK | Al Afrah 2 Residences Al Majaz 3 | Design Completed | 25.3351 | 55.373316 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 25000 | 2 months
IBS-FTK-23-0129 | IFU5631 | BAU | DAS 2024 | PFTK | Bidya Residences Fujairah | Design Completed | 25.123 | 56.343086 | Possible | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 25000 | 2 months
IBS-FTK-22-5043 | ISH5219 | BAU | DAS 2024 | PFTK | Hafeet 3 Al Nayeli Residences Muweilah | Design Completed | 25.304 | 55.456803 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 80000 | 3 months
IBS-FTK-22-4334 | IAJ5864 | BAU | DAS 2024 | FTK | Geepas Building | Design Completed | 25.4191 | 55.448131 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-22-1762 | ISH5220 | BAU | DAS 2024 | PFTK | Al Fayah Tower Al Taawun | Design Completed | 25.307 | 55.366787 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 25000 | 2 Months
IBS-FTK-22-1429 | ISH5218 | BAU | DAS 2024 | PFTK | Al Barakah Tower Al Taawun | Design Completed | 25.3093 | 55.374944 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 35000 | 2 months
IBS-FTK-22-1425 | ISH5244 | BAU | DAS 2024 | FTK | Al Reyyan Tower Al Taawun | Design Completed | 25.3084 | 55.37334 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 2 months
IBS-FTK-22-1341 | ISH5194 | BAU | DAS 2024 | FTK | Diamond Plaza Al Majaz 2 | Design Completed | 25.3196 | 55.380784 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 1 MONTH
IBS-FTK-22-1200 | ISH5176 | BAU | DAS 2024 | FTK | Al Falasi Building Al Majaz 3 | Design Completed | 25.3224 | 55.379802 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 2 months
IBS-FTK-22-0970 | IAJ5853 | BAU | DAS 2024 | FTK | Manal Mahmood M Sobh Residences Ajman Industrial 2 | Design Completed | 25.3764 | 55.459487 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 30000 | 2 months
IBS-FTK-21-3826 | IRK5511 | BAU | DAS 2024 | FTK | Rakia Amenity Complex 2 (Rakez Towers A2) | Design Completed | 25.6582 | 55.796419 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3582 | AJM5998G | BAU | DAS 2024 | FTK | ATOM Al Zoura Residential Block B Ajman | Design Completed | 25.4344 | 55.486634 | Taawun | 2024 Fiber | NA | NA | AJM2459 | AJM-2459-IBS-SAR-M-1 | Passive |  | 0
IBS-FTK-21-3441 | AJM5998F | BAU | DAS 2024 | FTK | ATOM Al Zoura Residential Block A Ajman | Design Completed | 25.4344 | 55.486353 | Taawun | 2024 Fiber | NA | NA | AJM2459 | AJM-2459-IBS-SAR-M-1 | Passive |  | 0
IBS-FTK-21-3271 | ISH5225 | BAU | DAS 2024 | PFTK | Makhawi Residence Al Qasimia | Design Completed | 25.3439 | 55.39438 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3194 | ISH5107 | BAU | DAS 2024 | FTK | The Pavilion at Nahda Sharjah | Design Completed | 25.3031 | 55.371941 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 1 MONTH
IBS-FTK-21-3180 | ISH5108 | BAU | DAS 2024 | FTK | Al Wathba Tower Al Majaz 2 | Design Completed | 25.319 | 55.384797 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-2047 | IAJ5874 | BAU | DAS 2024 | FTK | Roser Tower Ajman | Design Completed | 25.3917 | 55.572019 | OSP Provisioned | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 25000 | 2 months
IBS-FTK-21-2040 | ISH5164 | BAU | DAS 2024 | PFTK | Smart Tower 2 Al Nahda Sharjah | Design Completed | 25.3038 | 55.380778 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 60000 | 3 months
IBS-FTK-21-1998 | IRK5510 | BAU | DAS 2024 | FTK | Rakia Amenity Complex 2 (Rakez Towers A1) | Design Completed | 25.6583 | 55.796006 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-1241 | IFU5630 | BAU | DAS 2024 | FTK | J-61 Residences Fujairah | Design Completed | 25.1219 | 56.341398 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-1208 | IUA5757 | BAU | DAS 2024 | FTK | Sheikh Abdulla Building Umm Al Quwain | Design Completed | 25.4948 | 55.552122 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-1184 | ISH5128 | BAU | DAS 2024 | FTK | Residential Building by Eagle Constructions Al Nahda | Design Completed | 25.3039 | 55.374751 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 30000 | 2 months
IBS-FTK-21-0800 | IRK5504 | BAU | DAS 2024 | FTK | FAB Tower RAK | Design Completed | 25.7753 | 55.965928 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-0733 | IFU5613 | BAU | DAS 2024 | FTK | Al Kaabi Building Fujairah | Design Completed | 25.1205 | 56.326776 | Possible | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 35000 | 2 months
IBS-FTK-21-0667 | ISH5159 | BAU | DAS 2024 | PFTK | Malak Tower Al Majaz 2 | Design Completed | 25.3203 | 55.384683 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 1 MONTH
IBS-FTK-21-0095 | IAJ5856 | BAU | DAS 2024 | FTK | Ajman Kempenski Hotel | Design Completed | 25.4226 | 55.442667 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-FTK-20-1897 | ISH5077 | BAU | DAS 2024 | FTK | Malak AlKhan | Design Completed | 25.3079 | 55.373638 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 30000 | 3 months
IBS-FTK-20-1890 | ISH5032 | BAU | DAS 2024 | FTK | Private School Plot 316 Tawi Hamdeh | Design Completed | 25.1471 | 55.893522 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1838 | IRK5523 | BAU | 2024 IC | PFTK | Al Salhiya Tower RAK | Design Completed | 25.7746 | 55.963547 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1824 | IRK5502 | BAU | DAS 2024 | FTK | Expo Building RAK | Design Completed | 25.7981 | 55.968092 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1820 | IRK5517 | BAU | DAS 2024 | FTK | Al Mas Residences RAK | Design Completed | 25.787 | 55.968888 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1683 | ISH5009 | BAU | DAS 2024 | FTK | Salem Ahmed Al Moosa Enterprise Tower 1 Al Nahda | Design Completed | 25.2992 | 55.370032 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1678 | IRK5501 | BAU | DAS 2024 | FTK | United Arab Bank Building RAK | Design Completed | 25.7703 | 55.922965 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1556 | AJM0904 | BAU | 2024 IC | PFTK | Goldcrest Dreams Tower B | Design Completed | 25.3931 | 55.574266 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1421 | SHJ0720 | BAU | DAS 2024 | PFTK | Rasheed 58 | Design Completed | 25.3053 | 55.367074 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 25000 | 2 months
IBS-FTK-20-1420 | ISH5004 | BAU | DAS 2024 | PFTK | Rasheed 57 | Design Completed | 25.3055 | 55.367326 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 40000 | 2 months
IBS-FTK-19-1667 | IFU5607 | BAU | DAS 2024 | FTK | Wadi Al Helo Tunnel 1_Kalba Bound Exit | Design Completed | 24.9868 | 56.239525 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-19-1424 | ISH5243 | BAU | DAS 2024 | FTK | University City Hall | Design Completed | 25.2785 | 55.471965 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-19-982 | IBS-SS-19-982 | BAU | DAS 2024 | SS | AUS_Zone-6_Block-I | Design Received | 25.3063 | 55.492649 | Possible | 2024 MW | NA |  |  |  | New MW Link | 50000 | 3 months
IBS-SS-23-1485 | IBS-SS-23-1485 | BAU | DAS 2024 | SS | Cape Hayat - East Towers, RAK | Project Created | 25.7231 | 55.840987 | Taawun | 2024 Fiber | NA | NA | RAK2028 | RAK-2028-CSG-IXR-E-1 | Passive | 50000 | 3 months
IBS-SS-23-1484 | IBS-SS-23-1484 | BAU | DAS 2024 | SS | Al Hamra Residence, RAK | Project Created | 25.6972 | 55.7806949 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-23-1483 | IBS-SS-23-1483 | BAU | DAS 2024 | SS | Latifa Abdulrahim Abdul Rahman Al Zarooni Building, Sharjah | Project Created | 25.3561 | 55.387871 | Possible | 2024 Fiber | NA | NA | SHJ2058 | SHJ-2058-SCSG-IXR-R6-1 | Passive | 50000 | 3 months
IBS-SS-23-1464 | IBS-SS-23-1464 | BAU | DAS 2024 | SS | Al Madar Tower, RAK | Project Created | 25.7728 | 55.9673 | Possible | 2024 Fiber | NA | NA | RAK6001 | RAK-6001-AGGR-SR7S-1 | Passive | 50000 | 3 months
IBS-SS-23-1448 | IBS-SS-23-1448 | BAU | DAS 2024 | SS | Ajman Boulevard Building B | Project Created | 25.4047 | 55.483565 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-1364 | IBS-SS-23-1364 | BAU | DAS 2024 | SS | Mawarid Tower Sharjah | Project Created | 25.3298 | 55.373353 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1360 | IBS-SS-23-1360 | BAU | DAS 2024 | SS | B46 Building - Al Sheria 1 | Project Created | 25.1578 | 56.345993 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-23-1349 | IBS-SS-23-1349 | BAU | DAS 2024 | SS | Ajman Boulevard Building A | Project Created | 25.4047 | 55.483565 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-1332 | IBS-SS-23-1332 | BAU | DAS 2024 | SS | Al Mamsha Seerah Phase 1 | Project Created | 25.3064 | 55.470673 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-23-1318 | IBS-SS-23-1318 | BAU | DAS 2024 | SS | Gateway Residence 2, RAK | Project Created | 25.7192 | 55.841680 | Not Possible | 2024 MW | NA |  |  |  | New MW Link | 50000 | 3 months
IBS-SS-23-1308 | IBS-SS-23-1308 | BAU | DAS 2024 | SS | Seih Alqusaidat School, RAK | Project Created | 25.7648 | 56.003872 | Possible | 2024 Fiber | NA | NA | RAK6001 | RAK-6001-AGGR-SR7S-1 | Passive | 50000 | 3 months
IBS-SS-23-1305 | IBS-SS-23-1305 | BAU | DAS 2024 | SS | Sharjah Mall & Residences, Sharjah | Project Created | 25.3313 | 55.362705 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1303 | IBS-SS-23-1303 | BAU | DAS 2024 | SS | Sharjah University Campus Expansion - Kalba | Project Created | 25.0228 | 56.353390 | Possible | 2024 Fiber | NA | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1297 | IBS-SS-23-1297 | BAU | DAS 2024 | SS | Ajman Creek Towers | Project Created | 25.397 | 55.4554421 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-1277 | IBS-SS-23-1277 | BAU | DAS 2024 | SS | Tilal Mall and Hotel-Site 3 | Project Created | 25.2668 | 55.582142 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1276 | IBS-SS-23-1276 | BAU | DAS 2024 | SS | Tilal Mall and Hotel-Site 2 | Project Created | 25.2668 | 55.582142 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1275 | IBS-SS-23-1275 | BAU | DAS 2024 | SS | Aljada Tiraz Project-Site 2 | Project Created | 25.3137 | 55.47742 | Taawun | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-23-1271 | IBS-SS-23-1271 | BAU | DAS 2024 | SS | Tilal Mall and Hotel-Site 1 | Project Created | 25.2668 | 55.582142 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1270 | IBS-SS-23-1270 | BAU | DAS 2024 | SS | Burj Bu Khamseen (5) Tower-site-2 | Project Created | 25.3482 | 55.397653 | Possible | 2024 Fiber | NA | NA | SHJ2058 | SHJ-2058-SCSG-IXR-R6-1 | Passive | 50000 | 3 months
IBS-SS-23-1269 | IBS-SS-23-1269 | BAU | DAS 2024 | SS | Al Nuaimia Building Plot 852 | Project Created | 25.3782 | 55.458151 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-1268 | IBS-SS-23-1268 | BAU | DAS 2024 | SS | Sheikh Soud Palace_RAK | Project Created | 25.7491 | 55.938979 | Possible | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1243 | IBS-SS-23-1243 | BAU | DAS 2024 | SS | A32 Building, Fujairah | Project Created | 25.1239 | 56.326189 | Possible | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 50000 | 3 months
IBS-SS-23-1241 | IBS-SS-23-1241 | BAU | DAS 2024 | SS | Munir Ragheb Musa Alkaloti Building, Sharjah | Project Created | 25.3097 | 55.356051 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-1236 | IBS-SS-23-1236 | BAU | DAS 2024 | SS | Rimal Residence, Sharjah | Project Created | 25.321 | 55.360658 | Taawun | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-1235 | IBS-SS-23-1235 | BAU | DAS 2024 | SS | SIJI Residence, Fujairah | Project Created | 25.1211 | 56.332789 | Possible | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 50000 | 3 months
IBS-SS-23-1186 | IBS-SS-23-1186 | BAU | DAS 2024 | SS | Bay Residences Phase 2, Mina Al Arab RAK | Project Created | 25.7237 | 55.844094 | Not Possible | 2024 MW | NA |  |  |  | New MW Link | 50000 | 3 months
IBS-SS-23-1166 | IBS-SS-23-1166 | BAU | DAS 2024 | SS | Al Buhairah Building, Sharjah | Project Created | 25.3326 | 55.390034 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-23-1106 | IBS-SS-23-1106 | BAU | DAS 2024 | SS | Sheikh Abdul Aziz Al Majid Plot A62 Building, Sharjah | Project Created | 25.3173 | 55.37593 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-1098 | SHJ0457 | BAU | 2024 IC | SS | Crown Prince of Sharjah Palace (Sheikh , Mother & Majlis) Villas | Project Created | 25.247 | 55.691951 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-23-1091 | IBS-SS-23-1091 | BAU | DAS 2024 | SS | GJ Residential Building, Ajman | Project Created | 25.378 | 55.574398 | Possible | 2024 MW | NA |  |  |  | New MW Link | 50000 | 3 months
IBS-SS-23-1084 | IBS-SS-23-1084 | BAU | DAS 2024 | SS | UNI SAT General Trading | Project Created | 25.3918 | 55.43529 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-1083 | IBS-SS-23-1083 | BAU | DAS 2024 | SS | Ali Mohammed Al Qubaisi Building, Sharjah | Project Created | 25.3008 | 55.374737 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-1082 | IBS-SS-23-1082 | BAU | DAS 2024 | SS | Al Sharq Hospital, Dibba | Project Created | 25.5761 | 56.256967 | Possible | 2024 Fiber | NA | NA | KFN2011 | KFN-2611-CSG-ASR907-1 | Passive | 50000 | 3 months
IBS-SS-23-1081 | IBS-SS-23-1081 | BAU | DAS 2024 | SS | Tropical Tower, Ajman | Project Created | 25.3796 | 55.585672 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 50000 | 3 months
IBS-SS-23-1080 | IBS-SS-23-1080 | BAU | DAS 2024 | SS | Bluebay Walk Towers 1 & 2, Al Hamriya | Project Created | 25.4958 | 55.53664 | Taawun | 2024 Fiber | NA | NA | UAQ2012 | UAQ-2012-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-1019 | IBS-SS-23-1019 | BAU | DAS 2024 | SS | Sharjah University Al Dhaid - Expansion | Project Created | 25.2659 | 55.91141 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-23-0999 | IBS-SS-23-0999 | BAU | DAS 2024 | SS | Al Dar Beachfront Resorts & Apartments, Al Marjan Island RAK | Project Created | 25.6656 | 55.745894 | Possible | 2024 Fiber | NA | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | Passive | 50000 | 3 months
IBS-SS-23-0998 | IBS-SS-23-0998 | BAU | DAS 2024 | SS | H.H. Shaikha Jawaher Bint Muhammad Bin Sultan Building | Project Created | 25.3304 | 55.375053 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-0997 | IBS-SS-23-0997 | BAU | DAS 2024 | SS | Hassan Saleh Alhammadi Building | Project Created | 25.3411 | 55.387449 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-0996 | IBS-SS-23-0996 | BAU | DAS 2024 | SS | Bay Residences Phase 1 & 2, Mina Al Arab RAK | Project Created | 25.7237 | 55.844094 | Not Possible | 2024 MW | NA |  |  |  | New MW Link | 50000 | 3 months
IBS-SS-23-0971 | IBS-SS-23-0971 | BAU | DAS 2024 | SS | Medical Centre Al Rashidiya | Project Created | 25.4001 | 55.443878 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0966 | IBS-SS-23-0966 | BAU | DAS 2024 | SS | Abdullatif Abdullah Humaid Al Nuami Building | Project Created | 25.4115 | 55.44414 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0965 | IBS-SS-23-0965 | BAU | DAS 2024 | SS | Al Alia Tower | Project Created | 25.3176 | 55.364098 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-0964 | IBS-SS-23-0964 | BAU | DAS 2024 | SS | Awqaf Building | Project Created | 25.32 | 55.383 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-0963 | IBS-SS-23-0963 | BAU | DAS 2024 | SS | Al Zamalek Building Plot 0140 | Project Created | 25.386 | 55.462 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0962 | IBS-SS-23-0962 | BAU | DAS 2024 | SS | Aqaar Building Plot 106430041 | Project Created | 25.397 | 55.578906 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 50000 | 3 months
IBS-SS-23-0961 | IBS-SS-23-0961 | BAU | DAS 2024 | SS | Safari Mall RAK | Project Created | 25.7842 | 55.97562 | Possible | 2024 Fiber | NA | NA | RAK6001 | RAK-6001-AGGR-SR7S-1 | Passive | 50000 | 3 months
IBS-SS-23-0960 | IBS-SS-23-0960 | BAU | DAS 2024 | SS | Sharjah Social Empowerment Foundation Building | Project Created | 25.3408 | 55.396248 | Possible | 2024 Fiber | NA | NA | SHJ2022 | SHJ-2022-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-23-0959 | IBS-SS-23-0959 | BAU | DAS 2024 | SS | Sheikh Saleh Bin Mohamed Alsharqi Bldg. | Project Created | 25.5756 | 56.25877 | Possible | 2024 Fiber | NA | NA | KFN2011 | KFN-2611-CSG-ASR907-1 | Passive | 50000 | 3 months
IBS-SS-23-0880 | IBS-SS-23-0880 | BAU | DAS 2024 | SS | Khorfakkan Resort Site 2 | Project Created | 25.3733 | 56.348924 | Possible | 2024 Fiber | NA | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-0879 | IBS-SS-23-0879 | BAU | DAS 2024 | SS | Khorfakkan Resort Site 1 | Project Created | 25.3733 | 56.348924 | Possible | 2024 Fiber | NA | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-0788 | IBS-SS-23-0788 | BAU | DAS 2024 | SS | Bluesell Residences | Project Created | 25.381 | 55.585 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 50000 | 3 months
IBS-SS-23-0768 | IBS-SS-23-0768 | BAU | DAS 2024 | SS | Al Zamalek Building | Project Created | 25.3986 | 55.43195 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0757 | IBS-SS-23-0757 | BAU | DAS 2024 | SS | Commercial Building Plot 0113, Ajman | Project Created | 25.3978 | 55.47365 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0702 | IBS-SS-23-0702 | BAU | DAS 2024 | SS | Kaloti Real Estate-615(446A) Building, Sharjah | Project Created | 25.3292 | 55.376632 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-23-0597 | IBS-SS-23-0597 | BAU | DAS 2024 | SS | Al Mamsha Project_Muwaileh_PH-3-1C | Project Created | 25.3088 | 55.469591 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-23-0587 | IBS-SS-23-0587 | BAU | DAS 2024 | SS | Ajman Ruler Court | Project Created | 25.4172 | 55.4431278 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0307 | IBS-SS-23-0307 | BAU | DAS 2024 | SS | Al Mamsha Project_Muwaileh_PH-3 | Project Created | 25.3096 | 55.46774 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-23-0236 | IBS-SS-23-0236 | BAU | DAS 2024 | SS | ALJADA Block J Phase 3_Building 1 to 6 | Project Created | 25.3116 | 55.474768 | Taawun | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-23-0226 | IBS-SS-23-0226 | BAU | DAS 2024 | SS | Mariam Tower_Ajman | Project Created | 25.3778 | 55.460832 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 50000 | 3 months
IBS-SS-23-0225 | IBS-SS-23-0225 | BAU | DAS 2024 | SS | Shakesnpear Building,_Ajman | Project Created | 25.3861 | 55.469042 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-23-0208 | IBS-SS-23-0208 | BAU | DAS 2024 | SS | Sharjah Terraces | Project Created | 25.3204 | 55.363403 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-23-0127 | IBS-SS-23-0127 | BAU | DAS 2024 | SS | Marriott Resort RAK | Project Created | 25.6636 | 55.754434 | Possible | 2024 Fiber | NA | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | Passive | 50000 | 3 months
IBS-SS-23-0029 | IBS-SS-23-0029 | BAU | DAS 2024 | SS | Aljada Tiraz Project | Project Created | 25.3137 | 55.47742 | Taawun | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-22-5097 | IBS-SS-22-5097 | BAU | 2024 IC | SS | Westin Marriot Hotel RAK | Project Created | 25.6636 | 55.754434 | Possible | 2024 Fiber | NA | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | Passive | 50000 | 3 months
IBS-SS-22-4601 | IBS-SS-22-4601 | BAU | 2024 IC | SS | Umeed Ali Khan Building | Project Created | 25.3941 | 55.472273 | Possible | 2024 Fiber | NA | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | Passive | 50000 | 3 months
IBS-SS-22-4306 | IBS-SS-22-4306 | BAU | DAS 2024 | SS | Al Jawahra Tower | Project Created | 25.3435 | 55.386061 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-22-2192 | IBS-SS-22-2192 | BAU | 2024 IC | SS | Al Naeem 5 New Building | Project Created | 25.7754 | 55.936507 | Possible | 2024 Fiber | NA | NA | RAK2704 | RAK-2003-CSG-SAR-X-1 | Passive | 50000 | 3 months
IBS-SS-22-2031 | IBS-SS-22-2031 | BAU | 2024 IC | SS | Al Shamghoni Building | Project Created | 25.3093 | 55.372199 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-22-0965 | IBS-SS-22-0965 | BAU | 2024 IC | SS | S.S. Holding Building Sharjah | Project Created | 25.3265 | 55.377252 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-22-0048 | IBS-SS-22-0048 | BAU | DAS 2024 | SS | Shk Abdulaziz Mohamed Building | Project Created | 25.3435 | 55.402486 | Possible | 2024 Fiber | NA | NA | SHJ2022 | SHJ-2022-AGGR-SR7b-1 | Passive | 50000 | 3 months
IBS-SS-22-0046 | IBS-SS-22-0046 | BAU | DAS 2024 | SS | Hassan 381 Tower | Project Created | 25.3023 | 55.379455 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-21-0218 | IBS-SS-21-0218 | BAU | DAS 2024 | SS | Garden City Tower A5A6 | Project Created | 25.4043 | 55.507867 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-21-0217 | IBS-SS-21-0217 | BAU | DAS 2024 | SS | Garden City Tower A3A4 | Project Created | 25.4043 | 55.507867 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-20-1182 | IBS-SS-20-1182 | BAU | DAS 2024 | SS | AL MAMZAR New Bldg 12 | Project Created | 25.3272 | 55.37477 | Possible | 2024 Fiber | NA | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-SS-19-867 | IBS-SS-19-867 | BAU | DAS 2024 | SS | Ministry of Justice in Masfoot area – Ajman. | Project Created | 24.8271 | 56.067118 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-SS-19-170 | IBS-SS-19-170 | BAU | DAS 2024 | SS | Lootah Tower | Project Created | 25.3115 | 55.374037 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-SS-19-162 | SHJ0115 | BAU | 2024 IC | SS | Al Ghazal Tower | Project Created | 25.3202 | 55.37511 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 25000 | 2 months
IBS-Hunt-23-0802 | IBS-Hunt-23-0802 | BAU | DAS 2024 | SS | Sharjah Boulevard Hotel & HQ | Project Created | 25.3338 | 55.473512 | Possible | 2024 Fiber | NA | NA | SHJ2053 | SHJ-2053-AGGR-SR7B-1 | Passive | 50000 | 3 months
IBS-Hunt-23-0634 | IBS-Hunt-23-0634 | BAU | DAS 2024 | SS | Mohamed Ali Alshamsi Building | Project Created | 25.2992 | 55.367242 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-Hunt-22-1942 | IBS-Hunt-22-1942 | BAU | DAS 2024 | SS | Almazrouei 2 Building | Project Created | 25.3013 | 55.369592 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-Hunt-22-1516 | IBS-Hunt-22-1516 | BAU | DAS 2024 | SS | M.R Tower | Project Created | 25.3971 | 55.577221 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | Passive | 50000 | 3 months
IBS-Hunt-22-1434 | IBS-Hunt-22-1434 | BAU | DAS 2024 | SS | Al Teneiji Tower | Project Created | 25.313 | 55.374419 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-Hunt-22-1422 | IBS-Hunt-22-1422 | BAU | DAS 2024 | SS | Sharjah Islamic Bank Building Plot 1397 | Project Created | 25.313 | 55.369717 | Possible | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 50000 | 3 months
IBS-FTK-23-1089 | IBS-FTK-23-1089 | BAU | DAS 2024 | FTK | UAQ-Free Zone Expansion | Project Created | 25.5534 | 55.742807 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-FTK-23-0904 | IBS-FTK-23-0904 | BAU | DAS 2024 | PFTK | Victoria International Schools of Kalba | Project Created | 25.0047 | 56.345991 | Possible | 2024 Fiber | NA | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-FTK-20-1631 | IBS-FTK-20-1631 | BAU | DAS 2024 | FTK | AWAD AL JAZAIRI | Project Created | 25.3222 | 55.385390 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 50000 | 3 months
IBS-FTK-20-1481 | RAK0568 | BAU | 2024 IC | SS | Gateway Residence RAK | Project Created | 25.7168 | 55.831747 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-19-558 | SHJ0475 | BAU | 2024 IC | SS | Al Qasimia University Expansion | RFM | 25.2942 | 55.4659 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-23-0771 | SHJ0493 | BAU | 2024 IC | FTK | H.H Sheikh Al Qasimi Palace New Majlis_Add Sector | RFM | 25.2794 | 55.560828 | OSP Ready | Existing Fiber | IIB | SHJ-0493-CSG-SAR-X-1 |  | SHJ-2053-AGGR-SR7B-1 | No Action |  | 0
IBS-FTK-22-4625 | ISH5212 | BAU | 2024 IC | PFTK | Al Asak Residences Al Taawun | RFM | 25.3176 | 55.377037 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-22-4393 | SHJ0379 | BAU | 2024 IC | FTK | ABBCO Tower Renovation | RFM | 25.3028 | 55.377671 | Possible | Existing Fiber | IIB | SHJ-0379-CSG-SAR-X-1 |  | SHJ-2226-PREAGG-SR7-1 | No Action | 25000 | 1 MONTH
IBS-FTK-22-1511 | IAJ5863 | BAU | 2024 IC | FTK | Al Mowaiji Building | RFM | 25.4036 | 55.506531 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-22-0285 | SHJ0169 | BAU | 2024 IC | FTK | Petrofac 400 Tower Renovation | RFM | 25.3518 | 55.38517 | OSP Ready | Existing Fiber | IIB | SHJ-0169-CSG-SAR-X-1 |  | SHJ-2094-SCSG-SR7B-1 | No Action |  | 0
IBS-FTK-21-3737 | SHJ0290 | BAU | 2024 IC | FTK | AL Arab Mall Renovation | RFM | 25.3089 | 55.369028 | OSP Ready | Existing Fiber | IIB | SHJ-0290-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | 0
IBS-FTK-21-2039 | ISH5227 | BAU | 2024 IC | FTK | Salam Tower | RFM | 25.3331 | 55.389847 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 25000 | 1 MONTH
IBS-FTK-20-1529 | SHJ0479 | BAU | 2024 IC | FTK | AUS 2 Campus Service Center & Sports Complex (New Sector) | RFM | 25.3127 | 55.487924 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-0341-CSG-SAR-8-1 |  | SHJ-2053-AGGR-SR7b-1 | No Action |  | 0
IBS-SS-22-4303 | ISH5233 | BAU | 2024 IC | SS | Muweilah Community Building (Buildings 5,6,7 & 8) | SAQ Completed | 25.3019 | 55.454693 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-22-3099 | ISH5232 | BAU | 2024 IC | SS | Muweilah Community Building (Buildings 1,2,3,4 & 9) | SAQ Completed | 25.3019 | 55.454693 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-22-0082 | IAJ5846 | BAU | 2024 IC | SS | Garden City Towers-AJM_A3,A4,A5,A6 | SAQ Completed | 25.4048 | 55.507736 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-0317 | IBS-SS-21-0317 | BAU | DAS 2024 | SS | RAK Mangrove Hotel # 2760 | SAQ Completed | 25.7699 | 55.941965 | Possible | 2024 Fiber | NA | NA | RAK2711 | RAK-2711-SCSG-IXR-R6D-1 | Passive | 50000 | 3 months
IBS-SS-21-0224 | ISH5226 | BAU | DAS 2024 | FTK | Ibtikar 5 | SAQ Completed | 25.3206 | 55.379679 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-0221 | IAJ5867 | BAU | 2024 IC | SS | Garden City Towers-AJM_M5 & M6 | SAQ Completed | 25.3864 | 55.461882 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-21-0216 | IAJ5845 | BAU | 2024 IC | SS | Garden City Towers-AJM_M1,M2,A1,A2 | SAQ Completed | 25.4043 | 55.507867 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-19-1376 | IAJ5808 | BAU | 2024 IC | SS | Mirkaaz Mall_Ajman | SAQ Completed | 25.3618 | 55.496199 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2035 | SHJ-2035-SCSG-SR7B-1 | Passive | 15000 | 1 MONTH
IBS-FTK-23-1284 | ISH5241 | BAU | 2024 IC | PFTK | Vida1 & 2 Project | SAQ Completed | 25.3146 | 55.475124 | Taawun | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | Passive |  | 0
IBS-FTK-22-5149 | IBS-FTK-22-5149 | BAU | DAS 2024 | PFTK | Victoria International School Khorfakkan | SAQ Completed | 25.3871 | 56.31855 | Possible | 2024 MW | NA |  |  |  | New MW Link | 50000 | 3 months
IBS-FTK-22-5009 | IAJ5865 | BAU | DAS 2024 | FTK | 1045 Aamir Tower | SAQ Completed | 25.4079 | 55.509503 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-22-1547 | ISH5214 | BAU | DAS 2024 | FTK | Dr. Abdalla Belhaif Al Nuaimi Building | SAQ Completed | 25.3481 | 55.396035 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2058 | SHJ-2058-SCSG-IXR-R6-1 | Passive | 25000 | 1 MONTH
IBS-FTK-22-1546 | ISH5215 | BAU | DAS 2024 | FTK | Maysaloon Building Abu Shagarah | SAQ Completed | 25.3375 | 55.395037 | Possible | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 35000 | 3 Months
IBS-FTK-22-1216 | IAJ5847 | BAU | DAS 2024 | FTK | Khalifa Ateeq Al Remeithi Tower Al Nuaimiya 1 | SAQ Completed | 25.389 | 55.455424 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | Passive | 40269 | 2 months
IBS-FTK-21-3584 | ISH5145 | BAU | DAS 2024 | FTK | AAA Tower Al Mamzar | SAQ Completed | 25.3086 | 55.372232 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | Passive | 15000 | 1 MONTH
IBS-FTK-21-3139 | ISH5131 | BAU | DAS 2024 | FTK | Saleh Bin Saleh Bldg AL Mamzar | SAQ Completed | 25.3068 | 55.371210 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-3053 | IFU5618 | BAU | 2024 IC | FTK | Etihad Rail Tunnel 1 | SAQ Completed | 25.2765 | 56.149349 | Possible | 2024 MW | NA |  |  |  | New MW Link | 763682.843 | 6 months
IBS-FTK-21-2043 | ISH5183 | BAU | DAS 2024 | FTK | Huda Abdallah Mohamed Yarouf Alnaqbi | SAQ Completed | 25.3389 | 55.39808 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-21-0674 | ISH5143 | BAU | DAS 2024 | FTK | 72 Hotel Sharjah | SAQ Completed | 25.3366 | 55.387223 | OSP Provisioned | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 15000 | 1 MONTH
IBS-FTK-20-1566 | SHJ0906 | BAU | DAS 2024 | PFTK | SHARJAH_Al Shuwaihean New Bldg 1 | SAQ Completed | 25.3633 | 55.3888 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1437 | AJM0902 | BAU | 2024 IC | PFTK | Goldcrest Dreams A | SAQ Completed | 25.3937 | 55.574610 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1154 | SHJ0718 | BAU | DAS 2024 | PFTK | Al Faisal Tower | SAQ Completed | 25.3026 | 55.377961 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-20-1153 | SHJ0717 | BAU | 2024 IC | PFTK | Danat Al sharjah | SAQ Completed | 25.315 | 55.378775 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-19-658 | SHJ0388 | BAU | 2024 IC | PFTK | Sharjah 1 | SAQ Completed | 25.332 | 55.39242 | WIP CF 2023 | 2024 Fiber | NA | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | Passive | 45000 | 3 months
IBS-SS-20-0431 | RAK0567 | BAU | 2024 IC | SS | HCT - Ras Al Khaimah Womes's College | TI Installed not integrated | 25.7837 | 55.988696 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-20-0323 | IRK5519 | BAU | 2024 IC | SS | RAK-Dubai Aerospace Enterprise University | TI Installed not integrated | 25.5937 | 55.937858 | Not Possible | 2024 MW | NA |  |  |  | New MW Link |  | 0
IBS-SS-20-0310 | FUJ0683 | BAU | 2024 IC | SS | HCTWomensCollege | TI Installed not integrated | 25.1515 | 56.344037 | OSP Provisioned | 2024 Fiber | NA | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | Passive | 20000 | 2 Months
IBS-SS-19-550 | IRK5524 | BAU | 2024 IC | SS | Anantara Ras Al Khaimah Resort | TI Installed not integrated | 25.7217 | 55.850749 | Not Possible | 2024 MW | NA |  |  |  | New MW Link |  | 0
IBS-MOD-24-0117 | SHJ0442 | EXPANSION | Huawei Modernization | U900 Coloc | Ramiz Hypermarket @ MBZ Road | Design Completed | 25.3059 | 55.44251 | NA | 2024 MW | MW |  |  |  | TBD |  | #N/A
IBS-MOD-24-0108 | AJM0901 | EXPANSION | Huawei Modernization | U900 Coloc | Ajman One Towers_Ground Floor&Podium Floors | Design Completed | 25.3959 | 55.430971 | OSP Ready | Existing Fiber | IIB | AJM-0901-CSG-IXR-E-1 |  | SHJ-2540-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-24-0106 | SHJ0455 | EXPANSION | Huawei Modernization | U900 Coloc | Sharjah City Centre Expansion | Design Completed | 25.3258 | 55.394267 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-0278-CSG-SAR-8-1 |  | SHJ-2016-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-24-0104 | SHJ0157 | EXPANSION | Huawei Modernization | U900 Coloc | Manazil Apartments 5_Lower Part | Design Completed | 25.3142 | 55.37765 | OSP Ready | Existing Fiber | IIB | SHJ-0157-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-24-0101 | AJM0888 | EXPANSION | Huawei Modernization | U900 Coloc | Maryam Tower AJM | Design Completed | 25.3869 | 55.4582 | OSP Ready | Existing Fiber | IIB | AJM-0888-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-24-0088 | SHJ0179 | EXPANSION | Huawei Modernization | U900 Coloc | Sahara centre, AL Nahda Area, Dubai | Design Completed | 25.2973 | 55.372247 | OSP Ready | Existing Fiber | IIB | SHJ-0179-CSG-IXR-E-1 |  | SHJ-6501-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-24-0080 | SHJ0026 | EXPANSION | Huawei Modernization | U900 Coloc | Al Majaz Pearl | Design Completed | 25.3292 | 55.391841 | OSP Ready | Existing Fiber | IIB | SHJ-0026-CSG-IXR-E-1 |  | SHJ-2022-AGGR-SR7b-1 | No Action |  | #N/A
IBS-MOD-22-4439 | SHJ0107 | EXPANSION | Huawei Modernization | U900 Coloc | Manazil Apartments 2 | Design Completed | 25.3126 | 55.37586 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2580-PREAGG-SR7-1 |  | SHJ-2226-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3588 | UAQ0759 | EXPANSION | Huawei Modernization | U900 Coloc | Umm Al Quwain Federal First Instance Court | Design Completed | 25.5701 | 55.563282 | NA | 2024 MW | MW |  |  |  | TBD |  | #N/A
IBS-MOD-22-3586 | SHJ0491 | EXPANSION | Huawei Modernization | U900 Coloc | Crescent Tower | Design Completed | 25.3261 | 55.37859 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2084-SCSG-SR7B-1 |  | SHJ-2022-AGGR-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3585 | SHJ0474 | EXPANSION | Huawei Modernization | U900 Coloc | Al Dhaid Police Station | Design Completed | 25.2607 | 55.894552 | OSP Ready | Existing Fiber | IIB | SHJ-0474-CSG-SAR-X-1 |  | SHJ-5001-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3583 | SHJ0452 | EXPANSION | Huawei Modernization | U900 Coloc | Sharjah Industrial Area Police Station | Design Completed | 25.3025 | 55.428193 | OSP Ready | Existing Fiber | IIB | SHJ-0452-CSG-ASR920-LD-1 |  | SHJ-2017-AGGR-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3580 | SHJ0416 | EXPANSION | Huawei Modernization | U900 Coloc | Sharjah Transport department | Design Completed | 25.3716 | 55.451909 | OSP Ready | Existing Fiber | IIB | SHJ-0416-CSG-ASR920-LD-1 |  |  | No Action |  | #N/A
IBS-MOD-22-3578 | SHJ0409 | EXPANSION | Huawei Modernization | U900 Coloc | Al Ferasa Tower | Design Completed | 25.3426 | 55.38639 | OSP Ready | Existing Fiber | IIB | SHJ-0409-CSG-ASR920-LD-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3577 | SHJ0406 | EXPANSION | Huawei Modernization | U900 Coloc | Al Jaberi Building | Design Completed | 25.299 | 55.373913 | OSP Ready | Existing Fiber | IIB | SHJ-0406-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3575 | SHJ0404 | EXPANSION | Huawei Modernization | U900 Coloc | Al Jubail Market | Design Completed | 25.3495 | 55.379375 | OSP Ready | Existing Fiber | IIB | SHJ-0404-CSG-N540-LD-1 |  | SHJ-2058-SCSG-IXR-R6-1 | No Action |  | #N/A
IBS-MOD-22-3574 | SHJ0386 | EXPANSION | Huawei Modernization | U900 Coloc | BuKhatir Tower | Design Completed | 25.3337 | 55.375484 | OSP Ready | Existing Fiber | IIB | SHJ-0386-CSG-IXR-E-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3573 | SHJ0381 | EXPANSION | Huawei Modernization | U900 Coloc | Al Owais Tower | Design Completed | 25.3279 | 55.373294 | OSP Ready | Existing Fiber | IIB | SHJ-0381-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3572 | SHJ0370 | EXPANSION | Huawei Modernization | U900 Coloc | CAT Warehouse | Design Completed | 25.3054 | 55.402633 | OSP Ready | Existing Fiber | IIB | SHJ-0370-CSG-SAR-X-1 |  | SHJ-2020-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3571 | SHJ0368 | EXPANSION | Huawei Modernization | U900 Coloc | Yaz Building | Design Completed | 25.3004 | 55.371766 | OSP Ready | Existing Fiber | IIB | SHJ-0368-CSG-SAR-X-1 |  | NA | No Action |  | #N/A
IBS-MOD-22-3570 | SHJ0346 | EXPANSION | Huawei Modernization | U900 Coloc | Damas 2 (Formerly Damas 57) | Design Completed | 25.3037 | 55.3713 | OSP Ready | Existing Fiber | IIB | SHJ-0346-CSG-SAR-X-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-3569 | SHJ0337 | EXPANSION | Huawei Modernization | U900 Coloc | Sewa HQ | Design Completed | 25.3431 | 55.376071 | OSP Ready | Existing Fiber | IIB | SHJ-0337-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3567 | SHJ0328 | EXPANSION | Huawei Modernization | U900 Coloc | PETROFAC INT | Design Completed | 25.3299 | 55.37007222 | OSP Ready | Existing Fiber | IIB | SHJ-0328-CSG-IXR-E-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3566 | SHJ0327 | EXPANSION | Huawei Modernization | U900 Coloc | Sharjah Islamic Bank | Design Completed | 25.3165 | 55.37486 | OSP Ready | Existing Fiber | IIB | SHJ-0327-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3565 | SHJ0292 | EXPANSION | Huawei Modernization | U900 Coloc | Taawun 1 | Design Completed | 25.3147 | 55.375277 | OSP Ready | Existing Fiber | IIB | SHJ-0292-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3564 | SHJ0262 | EXPANSION | Huawei Modernization | U900 Coloc | Department of Economic Development of Sharjah | Design Completed | 25.3488 | 55.375021 | OSP Ready | Existing Fiber | IIB | SHJ-0262-CSG-ASR920-LD-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3563 | SHJ0188 | EXPANSION | Huawei Modernization | U900 Coloc | Al Sheraa Tower - SHJ Sails | Design Completed | 25.3267 | 55.378584 | OSP Ready | Existing Fiber | IIB | SHJ-0188-IBS-SAR-M-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3561 | SHJ0165 | EXPANSION | Huawei Modernization | U900 Coloc | AlHusn Tower | Design Completed | 25.3351 | 55.390667 | OSP Ready | Existing Fiber | IIB | SHJ-0165-CSG-ASR920-LD-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3560 | SHJ0147 | EXPANSION | Huawei Modernization | U900 Coloc | Al Diwan Tower | Design Completed | 25.3504 | 55.392233 | OSP Ready | Existing Fiber | IIB | SHJ-0147-CSG-IXR-E-1 |  | SHJ-2094-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3559 | SHJ0106 | EXPANSION | Huawei Modernization | U900 Coloc | Bu khamseen Tower_Lower | Design Completed | 25.3248 | 55.380149 | OSP Ready | Existing Fiber | IIB | SHJ-0106-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3558 | SHJ0079 | EXPANSION | Huawei Modernization | U900 Coloc | Al Hilal Tower | Design Completed | 25.3264 | 55.379266 | OSP Ready | Existing Fiber | IIB | SHJ-0079-IBS-SAR-M-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-3557 | RAK0557 | EXPANSION | Huawei Modernization | U900 Coloc | RAK Courts | Design Completed | 25.7771 | 55.935699 | OSP Ready | Existing Fiber | IIB | RAK-0557-CSG-IXR-E-1 |  | RAK-2711-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-3556 | RAK0529 | EXPANSION | Huawei Modernization | U900 Coloc | Ministry of Interior-General Directorate of Residence & Foreigner Affairs | Design Completed | 25.8032 | 55.972564 | OSP Ready | Existing Fiber | IIB | RAK-0529-CSG-SAR-X-1 |  | RAK-2718-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3555 | RAK0525 | EXPANSION | Huawei Modernization | U900 Coloc | DoubleTree by Hilton Hotel RAK | Design Completed | 25.7962 | 55.96882 | OSP Ready | Existing Fiber | IIB | RAK-0525-CSG-IXR-E-1 |  | RAK-2718-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3554 | RAK0517 | EXPANSION | Huawei Modernization | U900 Coloc | ACACIA Hotel | Design Completed | 25.6603 | 55.7971 | OSP Ready | Existing Fiber | IIB | RAK-0517-CSG-SAR-X-1 |  | UAQ-2016-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3553 | KFN0715 | EXPANSION | Huawei Modernization | U900 Coloc | Khorfakkan New Tunnels - A Seqb | Design Completed | 25.3471 | 56.268996 | OSP Ready | Existing Fiber | IIB | KFN-0715-CSG-SAR-M-1 |  | FUJ-5003-PREAGG-SRa8-1 | No Action |  | #N/A
IBS-MOD-22-3552 | KFN0713 | EXPANSION | Huawei Modernization | U900 Coloc | Khorfakkan New Tunnels - Al Sidra | Design Completed | 25.3156 | 56.239024 | OSP Ready | Existing Fiber | IIB | KFN-0713-IBS-SAR-M-1 |  | FUJ-5003-PREAGG-SRa8-1 | No Action |  | #N/A
IBS-MOD-22-3512 | FUJ0642 | EXPANSION | Huawei Modernization | U900 Coloc | Clifton international hotel | Design Completed | 25.1226 | 56.324096 | OSP Ready | Existing Fiber | IIB | FUJ-0642-CSG-SAR-X-1 |  | FUJ-6001-AGG-ASR9912-2 | No Action |  | #N/A
IBS-MOD-22-3511 | FUJ0635 | EXPANSION | Huawei Modernization | U900 Coloc | Ajawahir Medical Center Building (Burj Alwadi) | Design Completed | 25.1225 | 56.32297 | OSP Ready | Existing Fiber | IIB | FUJ-0635-CSG-SAR-X-1 |  | FUJ-2013-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3509 | FUJ0603 | EXPANSION | Huawei Modernization | U900 Coloc | Al Fujeirah Trade Center | Design Completed | 25.1212 | 56.331306 | OSP Ready | Existing Fiber | IIB | FUJ-0603-IBS-SAR-M-1 |  | FUJ-2013-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-3441 | AJM0918 | EXPANSION | Huawei Modernization | U900 Coloc | Ministry of Justice Ajman | Design Completed | 25.4085 | 55.508115 | OSP Ready | Existing Fiber | IIB | AJM-0918-CSG-IXR-E-1 |  | AJM-2459-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0950 | FUJ0641 | EXPANSION | Huawei Modernization | U900 Coloc | Fujairah Landmark Hotel | Design Completed | 25.1377 | 56.353948 | OSP Ready | Existing Fiber | IIB | FUJ-0641-CSG-SAR-X-1 |  | FUJ-2022-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0949 | SHJ0205 | EXPANSION | Huawei Modernization | U900 Coloc | Real State Registration Dept | Design Completed | 25.3451 | 55.375728 | OSP Ready | Existing Fiber | IIB | SHJ-0205-CSG-IXR-E-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0948 | RAK0539 | EXPANSION | Huawei Modernization | U900 Coloc | Ras Al Khaimah Traffic Department | Design Completed | 25.7235 | 55.87228 | OSP Ready | Existing Fiber | IIB | RAK-0539-CSG-SAR-X-1 |  | UAQ-2806-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0942 | SHJ0185 | EXPANSION | Huawei Modernization | U900 Coloc | Emirates ID HQ | Design Completed | 25.3076 | 55.58418 | OSP Ready | Existing Fiber | IIB | SHJ-0185-CSG-ASR920-LD-1 |  | SHJ-5003-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0932 | SHJ0401 | EXPANSION | Huawei Modernization | U900 Coloc | Flower Tower | Design Completed | 25.344 | 55.401907 | OSP Ready | Existing Fiber | IIB | SHJ-0401-IBS-SAR-M-1 |  | SHJ-2012-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0928 | SHJ0140 | EXPANSION | Huawei Modernization | U900 Coloc | Mozoon 2 | Design Completed | 25.3298 | 55.422008 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-0141-CSG-SAR-X-1 |  | SHJ-2022-AGGR-SR7b-1 | No Action |  | #N/A
IBS-MOD-22-0923 | RAK0550 | EXPANSION | Huawei Modernization | U900 Coloc | Bab Al Bahr - Fayrouz Building | Design Completed | 25.6651 | 55.747584 | OSP Ready | Existing Fiber | IIB | RAK-0550-CSG-SAR-X-1 |  | RAK-2028-PREAGG-SR-7-1 | No Action |  | #N/A
IBS-MOD-22-0922 | KFN0712 | EXPANSION | Huawei Modernization | U900 Coloc | Khorfakkan New Tunnels - Al Ghazeer | Design Completed | 25.2967 | 56.232788 | OSP Ready | Existing Fiber | IIB | KFN-0712-IBS-SAR-M-1 |  | FUJ-5003-PREAGG-SRa8-1 | No Action |  | #N/A
IBS-MOD-22-0831 | SHJ0480 | EXPANSION | Huawei Modernization | U900 Coloc | Style Tower | Design Completed | 25.3176 | 55.375893 | OSP Ready | Existing Fiber | IIB | SHJ-0480-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0820 | SHJ0186 | EXPANSION | Huawei Modernization | U900 Coloc | Hind Tower | Design Completed | 25.3152 | 55.377848 | OSP Ready | Existing Fiber | IIB | SHJ-0186-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0812 | SHJ0387 | EXPANSION | Huawei Modernization | U900 Coloc | Al Huda 2 Tower | Design Completed | 25.3275 | 55.373833 | OSP Ready | Existing Fiber | IIB | SHJ-0387-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0800 | SHJ0095 | EXPANSION | Huawei Modernization | U900 Coloc | Abdul Aziz Al Majid Tower 5 | Design Completed | 25.3004 | 55.380441 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-0152-CSG-SAR-8-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0794 | SHJ0240 | EXPANSION | Huawei Modernization | U900 Coloc | Al Rayyan Complex Tower A,B & C | Design Completed | 25.3013 | 55.382494 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-0241-CSG-SAR-X-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0792 | AJM0886 | EXPANSION | Huawei Modernization | U900 Coloc | Corniche Tower Ajman lower Part | Design Completed | 25.4029 | 55.429727 | OSP Ready | Existing Fiber | IIB -Passive | AJM-2074-CSG-IXR-E-1 |  | SHJ-2540-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0786 | SHJ0155 | EXPANSION | Huawei Modernization | U900 Coloc | Al Rund Tower | Design Completed | 25.327 | 55.369959 | OSP Ready | Existing Fiber | IIB | SHJ-0155-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0785 | SHJ0289 | EXPANSION | Huawei Modernization | U900 Coloc | Mamzar 1 | Design Completed | 25.307 | 55.366873 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-6501-PREAGG-SR7-1 |  | SHJ-2022-AGGR-SR7b-1 | No Action |  | #N/A
IBS-MOD-22-0773 | SHJ0235 | EXPANSION | Huawei Modernization | U900 Coloc | Rose 1 Tower | Design Completed | 25.3247 | 55.376151 | OSP Ready | Existing Fiber | IIB | SHJ-0235-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0759 | SHJ0270 | EXPANSION | Huawei Modernization | U900 Coloc | Dubai Islamic Bank Commercial Building | Design Completed | 25.347 | 55.38861 | OSP Ready | Existing Fiber | IIB | SHJ-0270-CSG-IXR-E-1 |  | SHJ-2094-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0752 | SHJ0325 | EXPANSION | Huawei Modernization | U900 Coloc | Taawun 3 | Design Completed | 25.3155 | 55.375542 | OSP Ready | Existing Fiber | IIB | SHJ-0325-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0724 | SHJ0462 | EXPANSION | Huawei Modernization | U900 Coloc | Al Dhaheri Tower @ Al Taawun | Design Completed | 25.3129 | 55.378617 | OSP Ready | Existing Fiber | IIB | SHJ-0462-CSG-N540-LD-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0716 | SHJ0311 | EXPANSION | Huawei Modernization | U900 Coloc | Crystal Plaza Tower | Design Completed | 25.3445 | 55.38639 | OSP Ready | Existing Fiber | IIB | SHJ-0311-CSG-SAR-X-1 |  | SHJ-2094-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0711 | SHJ0141 | EXPANSION | Huawei Modernization | U900 Coloc | Mozoon 4 | Design Completed | 25.3308 | 55.422581 | OSP Ready | Existing Fiber | IIB | SHJ-0141-CSG-SAR-X-1 |  | SHJ-2022-AGGR-SR7b-1 | No Action |  | #N/A
IBS-MOD-22-0710 | SHJ0057 | EXPANSION | Huawei Modernization | U900 Coloc | Al Bawadi 2 | Design Completed | 25.3137 | 55.37762 | OSP Ready | Existing Fiber | IIB | SHJ-0057-CSG-IXR-E-1 |  | SHJ-2017-AGGR-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0706 | RAK0538 | EXPANSION | Huawei Modernization | U900 / L800 Coloc | RAK Bank HQ | Design Completed | 25.7077 | 55.866133 | OSP Ready | Existing Fiber | IIB | RAK-0538-CSG-SAR-X-1 |  | UAQ-2806-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0704 | SHJ0129 | EXPANSION | Huawei Modernization | U900 Coloc | Al Asmawi Tower | Design Completed | 25.3062 | 55.366521 | OSP Ready | Existing Fiber | IIB | SHJ-0129-IBS-SAR-M-1 |  | SHJ-6501-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0702 | SHJ0184 | EXPANSION | Huawei Modernization | U900 Coloc | BM Twin Towers | Design Completed | 25.3037 | 55.371654 | OSP Ready | Existing Fiber | IIB | SHJ-0184-IBS-SAR-M-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0697 | SHJ0403 | EXPANSION | Huawei Modernization | U900 Coloc | Al Ohali Tower | Design Completed | 25.3331 | 55.375596 | NA | 2024 MW | MW |  |  |  | TBD |  | #N/A
IBS-MOD-22-0695 | SHJ0248 | EXPANSION | Huawei Modernization | U900 Coloc | Al Owais Nahad Tower C_D | Design Completed | 25.3011 | 55.371762 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2584-CSG-SAR-X-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0692 | SHJ0413 | EXPANSION | Huawei Modernization | U900 Coloc | Al Zain Tower | Design Completed | 25.2998 | 55.374673 | OSP Ready | Existing Fiber | IIB | SHJ-0413-CSG-SAR-X-1 |  | SHJ-6501-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0687 | SHJ0364 | EXPANSION | Huawei Modernization | U900 Coloc | Al Marwa 3 | Design Completed | 25.3194 | 55.363354 | OSP Ready | Existing Fiber | IIB | SHJ-0364-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0676 | SHJ0343 | EXPANSION | Huawei Modernization | U900 Coloc | SHARJAH DIRECTORATE OF TOWN PLANNING | Design Completed | 25.3422 | 55.3756 | NA | 2024 MW | MW |  |  |  | TBD |  | #N/A
IBS-MOD-22-0663 | SHJ0354 | EXPANSION | Huawei Modernization | U900 Coloc | Manazil Apartments 1 | Design Completed | 25.3447 | 55.392251 | OSP Ready | Existing Fiber | IIB | SHJ-0354-CSG-IXR-E-1 |  | SHJ-2022-AGGR-SR7b-1 | No Action |  | #N/A
IBS-MOD-22-0656 | AJM0882 | EXPANSION | Huawei Modernization | U900 Coloc | Royal Building | Design Completed | 25.3655 | 55.479598 | OSP Ready | Existing Fiber | IIB | AJM-0882-CSG-ASR920-LD-1 |  | AJM-2450-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0645 | SHJ0309 | EXPANSION | Huawei Modernization | U900 Coloc | SHARJAH ACQUARIUM | Design Completed | 25.3304 | 55.358447 | OSP Ready | Existing Fiber | IIB | SHJ-0309-CSG-IXR-E-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0639 | SHJ0002 | EXPANSION | Huawei Modernization | U900 Coloc | Al Shahid Tower 2 (Al Anwar) | Design Completed | 25.3247 | 55.373732 | OSP Ready | Existing Fiber | IIB | SHJ-0002-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0638 | SHJ0156 | EXPANSION | Huawei Modernization | U900 Coloc | Bu khamseen Tower_Upper | Design Completed | 25.3248 | 55.380149 | OSP Ready | Existing Fiber | IIB | SHJ-0156-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0633 | SHJ0096 | EXPANSION | Huawei Modernization | U900 Coloc | Abdul Aziz Al Majid Tower 6 | Design Completed | 25.3004 | 55.380441 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-0152-CSG-SAR-8-1 |  | SHJ-2226-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0626 | AJM0878 | EXPANSION | Huawei Modernization | U900 Coloc | Ajman Twin Towers | Design Completed | 25.3915 | 55.43718 | OSP Ready | Existing Fiber | IIB | AJM-0878-CSG-IXR-E-1 |  | AJM-6001-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0625 | SHJ0134 | EXPANSION | Huawei Modernization | U900 Coloc | Al Noor Tower | Design Completed | 25.3229 | 55.378944 | OSP Ready | Existing Fiber | IIB | SHJ-0134-IBS-SAR-M-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0623 | SHJ0136 | EXPANSION | Huawei Modernization | U900 Coloc | Yasmin 1 | Design Completed | 25.3325 | 55.42368 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2657-CSG-SAR-X-1 |  | SHJ-2021-SCSG-IXR-R6-1 | No Action |  | #N/A
IBS-MOD-22-0613 | SHJ0358 | EXPANSION | Huawei Modernization | U900 Coloc | Dejaya Tower | Design Completed | 25.3011 | 55.366014 | OSP Ready | Existing Fiber | IIB -Passive | SHJ-2020-PREAGG-SR7-1 |  | SHJ-2017-AGGR-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0612 | SHJ0217 | EXPANSION | Huawei Modernization | U900 Coloc | Sharjah Gate Tower | Design Completed | 25.3 | 55.37603 | OSP Ready | Existing Fiber | IIB | SHJ-0217-CSG-SAR-X-1 |  | SHJ-6501-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0611 | SHJ0023 | EXPANSION | Huawei Modernization | U900 Coloc | Sayegh Tower | Design Completed | 25.3213 | 55.3826 | OSP Ready | Existing Fiber | IIB | SHJ-0023-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0601 | KFN0711 | EXPANSION | Huawei Modernization | U900 Coloc | Khorfakkan New Tunnels - Al Raugh | Design Completed | 25.2892 | 56.209845 | OSP Ready | Existing Fiber | IIB | KFN-0711-IBS-SAR-M-1 |  | FUJ-5003-PREAGG-SRa8-1 | No Action |  | #N/A
IBS-MOD-22-0591 | SHJ0130 | EXPANSION | Huawei Modernization | U900 Coloc | Reveira Tower | Design Completed | 25.3312 | 55.37595833 | OSP Ready | Existing Fiber | IIB | SHJ-0130-IBS-SAR-M-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0574 | SHJ0187 | EXPANSION | Huawei Modernization | U900 Coloc | Al Nahda Tower (Al Tayer Tower) | Design Completed | 25.3011 | 55.373942 | OSP Ready | Existing Fiber | IIB | SHJ-0187-CSG-SAR-X-1 |  | SHJ-2020-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0567 | SHJ0355 | EXPANSION | Huawei Modernization | U900 Coloc | Manazil Apartments 3 | Design Completed | 25.3066 | 55.370507 | OSP Ready | Existing Fiber | IIB | SHJ-0355-IBS-SAR-M-1 |  | SHJ-6501-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0529 | SHJ0145 | EXPANSION | Huawei Modernization | U900 Coloc | Al Musalla 544 | Design Completed | 25.3548 | 55.393012 | OSP Ready | Existing Fiber | IIB | SHJ-0145-CSG-IXR-E-1 |  | SHJ-2058-SCSG-IXR-R6-1 | No Action |  | #N/A
IBS-MOD-22-0523 | SHJ0394 | EXPANSION | Huawei Modernization | U900 Coloc | Al Ameer Tower | Design Completed | 25.3026 | 55.38153 | OSP Ready | Existing Fiber | IIB | SHJ-0394-CSG-SAR-X-1 |  | NA | No Action |  | #N/A
IBS-MOD-22-0492 | SHJ0209 | EXPANSION | Huawei Modernization | U900 Coloc | Ali Omran Building at Al Nahda | Design Completed | 25.3016 | 55.379707 | OSP Ready | Existing Fiber | IIB | SHJ-0209-CSG-SAR-X-1 |  | SHJ-2017-AGGR-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0474 | SHJ0371 | EXPANSION | Huawei Modernization | U900 Coloc | Petrofac International 2 | Design Completed | 25.3293 | 55.370319 | OSP Ready | Existing Fiber | IIB | SHJ-0371-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0468 | SHJ0162 | EXPANSION | Huawei Modernization | U900 Coloc | Emesa Tower | Design Completed | 25.3185 | 55.377432 | OSP Ready | Existing Fiber | IIB | SHJ-0162-CSG-IXR-E-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0456 | FUJ0606 | EXPANSION | Huawei Modernization | U900 Coloc | Fujeirah Municipality | Design Completed | 25.1264 | 56.33364 | OSP Ready | Existing Fiber | IIB | FUJ-0606-CSG-IXR-E-1 |  | FUJ-2013-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-22-0446 | SHJ0112 | EXPANSION | Huawei Modernization | U900 Coloc | Al Nasser Tower | Design Completed | 25.3246 | 55.379311 | OSP Ready | Existing Fiber | IIB | SHJ-0112-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0425 | SHJ0125 | EXPANSION | Huawei Modernization | U900 Coloc | Al Qemmah Tower | Design Completed | 25.3101 | 55.37298 | OSP Ready | Existing Fiber | IIB | SHJ-0125-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0423 | SHJ0213 | EXPANSION | Huawei Modernization | U900 Coloc | AL Hilal Bank Tower SHJ | Design Completed | 25.3463 | 55.392357 | OSP Ready | Existing Fiber | IIB | SHJ-0213-CSG-ASR920-LD-1 |  | SHJ-2012-SCSG-IXR-R6D-1 | No Action |  | #N/A
IBS-MOD-22-0409 | KFN0714 | EXPANSION | Huawei Modernization | U900 Coloc | Khorfakkan New Tunnels - Al Saha | Design Completed | 25.3464 | 56.262599 | OSP Ready | Existing Fiber | IIB | KFN-0714-IBS-SAR-M-1 |  | FUJ-5003-PREAGG-SRa8-1 | No Action |  | #N/A
IBS-MOD-22-0405 | SHJ0018 | EXPANSION | Huawei Modernization | U900 Coloc | Abdul Aziz Tower B (Cornish Tower B) | Design Completed | 25.3287 | 55.3771 | OSP Ready | Existing Fiber | IIB | SHJ-0018-CSG-SAR-X-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-22-0383 | SHJ0210 | EXPANSION | Huawei Modernization | U900 Coloc | Al Waha Building | Design Completed | 25.314 | 55.373571 | OSP Ready | Existing Fiber | IIB | SHJ-0210-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-21-3346 | SHJ0124 | EXPANSION | Huawei Modernization | U900 Coloc | Al Durrah Tower | Design Completed | 25.3236 | 55.38299 | OSP Ready | Existing Fiber | IIB | SHJ-0124-CSG-SAR-X-1 |  | SHJ-2580-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-21-1922 | KFN0705 | EXPANSION | Huawei Modernization | U900 Coloc | Khor Fakan Cooperatice society | Design Completed | 25.3922 | 56.351623 | OSP Ready | Existing Fiber | IIB | KFN-0705-CSG-SAR-X-1 |  | FUJ-2022-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-21-1915 | FUJ0607 | EXPANSION | Huawei Modernization | U900 Coloc | Fujeirah Tower | Design Completed | 25.1214 | 56.33343 | OSP Ready | Existing Fiber | IIB | FUJ-0607-CSG-SAR-X-1 |  | FUJ-2014-PREAGG-SR7-1 | No Action |  | #N/A
IBS-MOD-21-1416 | SHJ0207 | EXPANSION | Huawei Modernization | U900 Coloc | The Blue Tower | Design Completed | 25.3353 | 55.375559 | OSP Ready | Existing Fiber | IIB | SHJ-0207-CSG-IXR-E-1 |  | SHJ-2084-SCSG-SR7B-1 | No Action |  | #N/A
IBS-MOD-21-1405 | SHJ0332 | EXPANSION | Huawei Modernization | U900 Coloc | Air Arabia Centro Hotel (Rotana near SHJ Airport) | Design Completed | 25.3201 | 55.5141 | OSP Ready | Existing Fiber | IIB | SHJ-0332-CSG-IXR-E-1 |  | SHJ-2053-AGGR-SR7B-1 | No Action |  | #N/A
IBS-MOD-21-0877 | RAK0527 | EXPANSION | Huawei Modernization | U900 Coloc | Al Hamra Palace_Waldorf Hotel | Design Completed | 25.6853 | 55.773331 | NA | 2024 MW | MW |  |  |  | TBD |  | #N/A
IBS-MOD-21-0873 | SHJ0399 | EXPANSION | Huawei Modernization | U900 Coloc | Sahara Center Extension | Design Completed | 25.298 | 55.375245 | OSP Ready | Existing Fiber | IIB | SHJ-0399-CSG-IXR-E-1 |  | SHJ-6501-PREAGG-SR7-1 | No Action |  | #N/A
IBS-FTK-23-1361 | RPT1100 | Small Cells / Repeaters | Repeaters | FTK | Repeater Madar2_BOH & BNC | DAS Started | 25.3184 | 55.477120 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-1357 | RPT1098 | Small Cells / Repeaters | Repeaters | FTK | Repeater Everyday Mall Ajman_ Basement | Design Completed | 25.3877 | 55.495512 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-1209 | RPT1086 | Small Cells / Repeaters | Repeaters | FTK | Repeater SOFT & HYGIENIC PAPER MANUFACTURING LLC | Design Completed | 25.5399 | 55.692725 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-1146 | RPT1077 | Small Cells / Repeaters | Repeaters | FTK | Repeater AIKAH- Sharjah | Design Completed | 25.3113 | 55.42224 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-22-4267 | RPT0950 | Small Cells / Repeaters | Repeaters | FTK | Repeater RAK Airport Cargo | Design Completed | 25.6182 | 55.941852 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-20-1629 | RPT0682 | Small Cells / Repeaters | Repeaters | FTK | Repeater Al Hamriya Port Sharjah | Design Completed | 25.4668 | 55.488969 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-19-1592 | RAK5600J | Small Cells / Repeaters | Small DAS | FTK | ATOM Grove Village RAK | Design Completed | 25.7703 | 55.938912 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-FTK-18-0212 | SHJ5191D | Small Cells / Repeaters | Small DAS | FTK | ATOM Sharjah Cooperative Society at Sweihat | Design Completed | 25.3483 | 55.461075 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive |  | 0
IBS-SS-23-1507 | RPT0931 | Small Cells / Repeaters | Repeaters | SS | Repeater WELLFIT MIND & BODY Community Gym | Project Created | 25.3185 | 55.4801 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-24-0007 | RPT1079 | Small Cells / Repeaters | Repeaters | SS | Repeater Emirates Health Services Training & Development - 2 | Project Created | 25.2742 | 55.468468 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-24-0006 | RPT1035 | Small Cells / Repeaters | Repeaters | SS | Repeater Emirates Health Services Training & Development - 1 | Project Created | 25.2742 | 55.468468 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-1503 | RPT1109 | Small Cells / Repeaters | Repeaters | FTK | Repeater FEN CAFÉ & Restaurant | Project Created | 25.0172 | 56.362091 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-0118 | RPT0977 | Small Cells / Repeaters | Repeaters | FTK | Repeater HH Sheikh Office Building | Project Created | 25.4961 | 55.560684 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-22-4268 | IBS-FTK-22-4268 | Small Cells / Repeaters | Small DAS | FTK | RAK Airport Civil Aviation | Project Created | 25.6159 | 55.943594 | OSP ready | 2024 Fiber | NA | NA | SLD on SPS | NA | Passive | 50000 | 3 months
IBS-FTK-21-3336 | IBS-FTK-21-3336 | Small Cells / Repeaters | Repeaters | FTK | Repeater Crown Prince of RAK Majlis | Project Created | 25.7499 | 55.933898 | Possible | 2024 Fiber | Repeater |  | NA | NA | No Action | 50000 | 3 months
IBS-FTK-21-3232 | RPT0592 | Small Cells / Repeaters | Repeaters | FTK | Repeater Al Bustan Hotel Al Khan - Basement | Project Created | 25.3339 | 55.363700 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-1195 | RPT1092 | Small Cells / Repeaters | Repeaters | FTK | Repeater AINAS AL MADINA HYPERMARKET Ajman | SAQ Completed | 25.3789 | 55.4931366 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-23-0001 | IBS-FTK-23-0001 | Small Cells / Repeaters | Repeaters | FTK | Repeater Galleria Mall Ajman | SAQ Completed | 25.3895 | 55.471947 | Possible | 2024 Fiber | Repeater |  | NA | NA | No Action | 50000 | 3 months
IBS-FTK-20-1466 | RPT0656 | Small Cells / Repeaters | Repeaters | FTK | Repeater Italian Dairy Production Warehouse LV29 | SAQ Completed | 25.4351 | 55.582428 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
IBS-FTK-19-1481 | RAK5600I | Small Cells / Repeaters | Small DAS | PFTK | ATOM AL MADINA NEW POLICE STATION | SAQ Completed | 25.7524 | 55.914232 | OSP Provisioned | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | Passive | 25000 | 2 months
IBS-FTK-19-1469 | IBS-FTK-19-1469 | Small Cells / Repeaters | Repeaters | FTK | Hanger A, Police Air Wing Department, Sharjah | SAQ Completed | 25.3307 | 55.502731 | Possible | 2024 MW | NA |  |  |  | No Action | 50000 | 3 months
IBS-FTK-23-1036 | RPT0960 | Small Cells / Repeaters | Repeaters | FTK | Repeater Norden Building SSA3 | Site On Air | 25.2644 | 55.494203 | NA | NA | Repeater | NA | NA | NA | No Action |  | #N/A
| SHJ3797 | 5G | 5G | 5G |  |  | 24.8101 | 55.7957 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 342610 | 8 MONTHS
| SHJ3739 | 5G | 5G | 5G |  |  | 24.8183 | 55.7465 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 1229806 | 8 MONTHS
| FUJ2691 | 5G | 5G | 5G |  |  | 24.8296 | 56.1276 | OSP Ready | Existing Fiber | IIB | FUJ-2691-CSG-IXR-E-1 | NA | FUJ-2433-SCSG-SR7-1 | TBD |  | #N/A
| FUJ2429 | 5G | 5G | 5G |  |  | 24.8838 | 56.1711 | OSP Ready | Existing Fiber | IIB | FUJ-2429-IBS-SAR-M-1 | NA | KLB-DC-SCSG-SR7B-1 | New CSG |  | #N/A
| FUJ2436 | 5G | 5G | 5G |  |  | 24.9084 | 56.3018 | OSP Ready | Existing Fiber | IIB | FUJ-2436-CSG-IXR-E-1 | NA | KLB-DC-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ2127 | 5G | 5G | 5G |  |  | 24.9124 | 56.1082 | OSP Ready | Existing Fiber | IIB | FUJ-2127-CSG-IXR-E-1 | NA | FUJ-2437-PREAGG-SR7-1 | TBD |  | #N/A
| FUJ3056 | 5G | 5G | 5G |  |  | 24.9148 | 56.1612 | OSP Ready | Existing Fiber | IIB | FUJ-3056-CSG-SAR-X-1 | NA | FUJ-2437-PREAGG-SR7-1 | TBD |  | #N/A
| SHJ3332 | 5G | 5G | 5G |  |  | 24.9259 | 55.7543 | OSP Ready | Existing Fiber | IIB | SHJ-3332-CSG-SAR-8-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| FUJ1060 | 5G | 5G | 5G |  |  | 24.9378 | 56.2587 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 664919 | 6 MONTHS
| FUJ2166 | 5G | 5G | 5G |  |  | 24.9413 | 56.2668 | OSP Ready | Existing Fiber | IIB | FUJ-2166-CSG-IXR-E-1 | NA | KLB-DC-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ2437 | 5G | 5G | 5G |  |  | 24.9513 | 56.1541 | OSP Ready | Existing Fiber | IIB | FUJ-2437-SCSG-SR7-1 | NA | FUJ-6001-AGG-ASR9912-1 | TBD |  | #N/A
| FUJ3877 | 5G | 5G | 5G |  |  | 24.9747 | 56.077 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 521446 | 8 Months
| FUJ2149 | 5G | 5G | 5G |  |  | 24.9876 | 56.3014 | OSP Ready | Existing Fiber | IIB | FUJ-2149-IBS-SAR-M-1 | NA | KLB-DC-SCSG-SR7B-1 | New CSG |  | #N/A
| FUJ3836 | 5G | 5G | 5G |  |  | 24.9913 | 56.0514 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 379134 | 8 Months
| SHJ3765 | 5G | 5G | 5G |  |  | 25.0022 | 55.6656 | OSP Ready | Existing Fiber | IIB | SHJ-3765-CSG-IXR-E-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| SHR2635 | 5G | 5G | 5G |  |  | 25.0084 | 55.9092 | OSP Ready | Existing Fiber | IIB | SHR-2635-CSG-IXR-E-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| SHJ1008 | 5G | 5G | 5G |  |  | 25.0179 | 55.8317 | OSP Ready | Existing Fiber | IIB | SHJ-1008-CSG-IXR-E-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| SHJ2594 | 5G | 5G | 5G |  |  | 25.0369 | 55.808 | OSP Ready | Existing Fiber | IIB | SHJ-2594-CSG-ASR920-LD-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| FUJ2686 | 5G | 5G | 5G |  |  | 25.0621 | 56.3564 | OSP Ready | Existing Fiber | IIB | FUJ-2686-CSG-ASR920-LD-1 | NA | KLB-DC-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ2996 | 5G | 5G | 5G |  |  | 25.0788 | 56.2976 | OSP Ready | Existing Fiber | IIB | FUJ-2996-CSG-ASR920-LD-1 | NA | FUJ-5002-SCSG-SR7-1 | TBD |  | #N/A
| FUJ3277 | 5G | 5G | 5G |  |  | 25.0928 | 56.2993 | OSP Ready | Existing Fiber | IIB | FUJ-3277-CSG-ASR920-LD-1 | NA | FUJ-5002-SCSG-SR7-1 | TBD |  | #N/A
| SHJ3586 | 5G | 5G | 5G |  |  | 25.0956 | 55.6619 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 817522 | 6 MONTHS
| FUJ3711 | 5G | 5G | 5G |  |  | 25.0969 | 56.2681 | OSP Ready | Existing Fiber | IIB | FUJ-3711-CSG-N540-LD-1 | NA | FUJ-5002-SCSG-SR7-1 | TBD |  | #N/A
| FUJ2971 | 5G | 5G | 5G |  |  | 25.111 | 56.2891 | OSP Ready | Existing Fiber | IIB | FUJ-2971-CSG-ASR920-LD-1 | NA | FUJ-2014-SCSG-SR7-1 | TBD |  | #N/A
| FUJ2698 | 5G | 5G | 5G |  |  | 25.1173 | 56.3331 | OSP Ready | Existing Fiber | IIB | FUJ-2698-CSG-ASR920-LD-1 | NA | FUJ-2013-SCSG-SR7-1 | TBD |  | #N/A
| SHJ2592 | 5G | 5G | 5G |  |  | 25.1283 | 55.8898 | OSP Ready | Existing Fiber | IIB | SHJ-2592-CSG-ASR920-LD-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| FUT3066 | 5G | 5G | 5G |  |  | 25.1333 | 56.2398 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 253179 | 4 Months
| FUJ3406 | 5G | 5G | 5G |  |  | 25.1426 | 56.2745 | OSP Ready | Existing Fiber | IIB | FUJ-3406-CSG-SAR-X-1 | NA | FUJ-2014-SCSG-SR7-1 | TBD |  | #N/A
| FUJ3060 | 5G | 5G | 5G |  |  | 25.1465 | 56.2455 | OSP Ready | Existing Fiber | IIB | FUJ-3060-CSG-IXR-E-1 | NA | FUJ-2398-SCSG-SRa8-1 | TBD |  | #N/A
| FUJ2141 | 5G | 5G | 5G |  |  | 25.1475 | 56.0279 | OSP Ready | Existing Fiber | IIB | FUJ-2141-CSG-SAR-8-1 | NA | FUJ-2437-PREAGG-SR7-1 | TBD |  | #N/A
| FUJ3706 | 5G | 5G | 5G |  |  | 25.1547 | 56.0109 | OSP Ready | Existing Fiber | IIB | FUJ-3706-CSG-N540-LD-1 | NA | FUJ-2398-SCSG-SRa8-1 | TBD |  | #N/A
| FUJ3227 | 5G | 5G | 5G |  |  | 25.1551 | 56.3502 | OSP Ready | Existing Fiber | IIB | FUJ-3227-CSG-SAR-X-1 | NA | FUJ-2022-SCSG-SR7-1 | TBD |  | #N/A
| SHJ2671 | 5G | 5G | 5G |  |  | 25.1675 | 55.8895 | OSP Ready | Existing Fiber | IIB | SHJ-2671-CSG-IXR-E-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| SHJ2591 | 5G | 5G | 5G |  |  | 25.1749 | 55.7367 | OSP Ready | Existing Fiber | IIB | SHJ-2591-CSG-IXR-E-1 | NA | SHJ-3612-SCSG-SRa8-1 | TBD |  | #N/A
| SHJ3336 | 5G | 5G | 5G |  |  | 25.1822 | 55.8118 | Possible | 2024 Fiber | MW | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG | 101369 | 3 MONTHS
| SHJ2991 | 5G | 5G | 5G |  |  | 25.1845 | 55.9232 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 385129.5 | 5 MONTHS
| SHJ3738 | 5G | 5G | 5G |  |  | 25.1855 | 55.6355 | OSP Ready | Existing Fiber | IIB | SHJ-3738-CSG-SAR-X-1 | NA | SHJ-2547-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ3562 | 5G | 5G | 5G |  |  | 25.1875 | 56.234 | OSP Ready | Existing Fiber | IIB | FUJ-3562-CSG-IXR-E-1 | NA | FUJ-5003-PREAGG-SRa8-1 | TBD |  | #N/A
| SHR3337 | 5G | 5G | 5G |  |  | 25.1932 | 55.8251 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 296692 | 4 MONTHS
| FUJ2152 | 5G | 5G | 5G |  |  | 25.1977 | 56.0346 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 694985 | 6 MONTHS
| SHJ3697 | 5G | 5G | 5G |  |  | 25.1987 | 55.8098 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 336257 | 4 MONTHS
| SHJ2634 | 5G | 5G | 5G |  |  | 25.2014 | 55.9166 | OSP Ready | Existing Fiber | IIB | SHJ-2634-CSG-IXR-E-1 | NA | SHJ-5001-SCSG-SR7B-1 | TBD |  | #N/A
| SHJ3667 | 5G | 5G | 5G |  |  | 25.203 | 55.9511 | OSP Ready | Existing Fiber | IIB | SHJ-3667-CSG-IXR-E-1 | NA | SHJ-5001-SCSG-SR7B-1 | TBD |  | #N/A
| SHJ2332 | 5G | 5G | 5G |  |  | 25.2267 | 55.9099 | OSP Ready | Existing Fiber | IIB | SHJ-2332-CSG-IXR-E-1 | NA | SHJ-5001-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ2143 | 5G | 5G | 5G |  |  | 25.2272 | 56.203 | OSP Ready | Existing Fiber | IIB | FUJ-2143-IBS-SAR-M-1 | NA | FUJ-5002-SCSG-SR7-1 | New CSG |  | #N/A
| FUJ2907 | 5G | 5G | 5G |  |  | 25.2335 | 56.0004 | OSP Ready | Existing Fiber | IIB | FUJ-2907-CSG-IXR-E-1 | NA | FUJ-2398-SCSG-SRa8-1 | TBD |  | #N/A
| FUJ2417 | 5G | 5G | 5G |  |  | 25.2436 | 56.3593 | Not possible | 2024 MW | MW | NA | NA | NA | New MW Link |  | 0
| FUJ2170 | 5G | 5G | 5G |  |  | 25.249 | 56.0804 | OSP Ready | Existing Fiber | IIB | FUJ-2170-CSG-IXR-E-1 | NA | FUJ-6001-AGG-ASR9912-1 | TBD |  | #N/A
| FUJ2151 | 5G | 5G | 5G |  |  | 25.2712 | 56.0338 | OSP Ready | Existing Fiber | IIB | FUJ-2151-CSG-IXR-E-1 | NA | FUJ-6001-AGG-ASR9912-1 | TBD |  | #N/A
| SHJ2550 | 5G | 5G | 5G |  |  | 25.274 | 55.7929 | OSP Ready | Existing Fiber | IIB | SHJ-2550-CSG-IXR-E-1 | NA | SHJ-5001-SCSG-SR7B-1 | TBD |  | #N/A
| SHJ2701 | 5G | 5G | 5G |  |  | 25.2782 | 55.7292 | OSP Ready | Existing Fiber | IIB | SHJ-2701-CSG-IXR-E-1 | NA | SHJ-5003-SCSG-SR7B-1 | TBD |  | #N/A
| KFN3946 | 5G | 5G | 5G |  |  | 25.2833 | 56.1999 | OSP Ready | Existing Fiber | IIB | KFN-3946-CSG-IXR-E-1 | NA | FUJ-5003-PREAGG-SRa8-1 | TBD |  | #N/A
| SHJ2664 | 5G | 5G | 5G |  |  | 25.2855 | 55.6625 | OSP Ready | Existing Fiber | IIB | SHJ-2664-CSG-IXR-E-1 | NA | SHJ-5003-SCSG-SR7B-1 | TBD |  | #N/A
| UAQ2811 | 5G | 5G | 5G |  |  | 25.2868 | 55.9991 | OSP Ready | Existing Fiber | IIB | UAQ-2811-CSG-IXR-E-1 | NA | SHJ-5001-SCSG-SR7B-1 | TBD |  | #N/A
| KFN3947 | 5G | 5G | 5G |  |  | 25.2873 | 56.1999 | OSP Ready | Existing Fiber | IIB | KFN-3947-CSG-IXR-E-1 | NA | FUJ-5003-PREAGG-SRa8-1 | TBD |  | #N/A
| SHJ2581 | 5G | 5G | 5G |  |  | 25.2912 | 55.5093 | OSP Ready | Existing Fiber | IIB | SHJ-2581-CSG-SAR-X-1 | NA | SHJ-2054-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ3639 | 5G | 5G | 5G |  |  | 25.2922 | 56.1208 | OSP Ready | Existing Fiber | IIB | FUJ-3639-CSG-SAR-X-1 | NA | FUJ-5002-SCSG-SR7-1 | TBD |  | #N/A
| FUJ2904 | 5G | 5G | 5G |  |  | 25.3041 | 56.1681 | OSP Ready | Existing Fiber | IIB | FUJ-2904-CSG-IXR-E-1 | NA | FUJ-5002-SCSG-SR7-1 | TBD |  | #N/A
| SHT2944 | 5G | 5G | 5G |  |  | 25.3042 | 55.6303 | OSP Ready | Existing Fiber | IIB | SHT-2944-CSG-SAR-X-1 | NA | SHJ-5003-SCSG-SR7B-1 | TBD |  | #N/A
| SHJ2475 | 5G | 5G | 5G |  |  | 25.3044 | 55.489 | OSP Ready | Existing Fiber | IIB | SHJ-2475-CSG-ASR920-LD-1 | NA | SHJ-2053-AGGR-SR7B-1 | TBD |  | #N/A
| SHJ1484 | 5G | 5G | 5G |  |  | 25.3051 | 55.4691 | OSP Ready | Existing Fiber | IIB | SHJ-1484-CSG-N540-LD-1 | NA | SHJ-2049-AGGR-SR7b-1 | TBD |  | #N/A
| SHJ1159 | 5G | 5G | 5G |  |  | 25.3159 | 55.4595 | Taawun | 2024 Fiber | MW | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG |  | 0
| SHJ3766 | 5G | 5G | 5G |  |  | 25.3204 | 55.523 | OSP Ready | Existing Fiber | IIB | SHJ-3766-CSG-ASR920-LD-1 | NA | SHJ-2053-AGGR-SR7B-1 | TBD |  | #N/A
| FUJ2905 | 5G | 5G | 5G |  |  | 25.3214 | 56.1609 | Possible | 2024 Fiber | MW | NA | FUJ5002 | FUJ-5002-SCSG-SR7-1 | New CSG | 162615 | 4 Months
| SHJ3515 | 5G | 5G | 5G |  |  | 25.3214 | 55.5112 | Not possible | 2024 MW | MW | NA | NA | NA | New MW Link |  | 0
| SHJ2643 | 5G | 5G | 5G |  |  | 25.3225 | 55.7396 | OSP Ready | Existing Fiber | IIB | SHJ-2643-CSG-ASR920-LD-1 | NA | SHJ-5003-SCSG-SR7B-1 | TBD |  | #N/A
| SHJ1264 | 5G | 5G | 5G |  |  | 25.3229 | 55.5172 | Not possible | 2024 MW | MW | NA | NA | NA | New MW Link |  | 0
| UAQ2812 | 5G | 5G | 5G |  |  | 25.3332 | 55.9624 | OSP Ready | Existing Fiber | IIB | UAQ-2812-CSG-IXR-E-1 | NA | RAK-2007-SCSG-IXR-R6D-1 | TBD |  | #N/A
| KFN3953 | 5G | 5G | 5G |  |  | 25.3448 | 56.3021 | OSP Ready | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| KFN3460 | 5G | 5G | 5G |  |  | 25.3452 | 56.3629 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 217215 | 6 MONTHS
| KFN3951 | 5G | 5G | 5G |  |  | 25.3473 | 56.2874 | OSP Ready | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| KFN3954 | 5G | 5G | 5G |  |  | 25.3499 | 56.3162 | Possible | 2024 Fiber | MW | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | New CSG | 50000 | 4 Months
| SHJ1262 | 5G | 5G | 5G |  |  | 25.3536 | 55.5183 | OSP Ready | Existing Fiber | IIB | SHJ-1262-CSG-IXR-E-1 | NA | SHJ-2035-SCSG-SR7B-1 | TBD |  | #N/A
| RAK3745 | 5G | 5G | 5G |  |  | 25.3592 | 55.9617 | OSP Ready | Existing Fiber | IIB | RAK-3745-CSG-IXR-E-1 | NA | RAK-2026-SCSG-IXR-R6D-1 | TBD |  | #N/A
| SHJ3209 | 5G | 5G | 5G |  |  | 25.36 | 55.4724 | OSP Ready | Existing Fiber | IIB | SHJ-3209-CSG-ASR920-LD-1 | NA | SHJ-2035-SCSG-SR7B-1 | TBD |  | #N/A
| SHJ3698 | 5G | 5G | 5G |  |  | 25.3608 | 55.3905 | OSP Ready | Existing Fiber | IIB | SHJ-3698-CSG-SAR-X-1 | NA | SHJ-2058-SCSG-IXR-R6-1 | TBD |  | #N/A
| AJM2108 | 5G | 5G | 5G |  |  | 25.3655 | 55.5339 | OSP Ready | Existing Fiber | IIB | AJM-2108-CSG-IXR-E-1 | NA | AJM-2459-SCSG-SR7B-1 | TBD |  | #N/A
| RAK3106 | 5G | 5G | 5G |  |  | 25.374 | 55.9752 | OSP Ready | Existing Fiber | IIB | RAK-3106-CSG-IXR-E-1 | NA | RAK-2026-SCSG-IXR-R6D-1 | TBD |  | #N/A
| SHJ2317 | 5G | 5G | 5G |  |  | 25.3778 | 55.6347 | OSP Ready | Existing Fiber | IIB | SHJ-2317-CSG-IXR-E-1 | NA | SHJ-5003-SCSG-SR7B-1 | TBD |  | #N/A
| FUJ2795 | 5G | 5G | 5G |  |  | 25.3827 | 56.1684 | Not possible | 2024 MW | MW | NA | NA | NA | New MW Link |  | 0
| RAK3357 | 5G | 5G | 5G |  |  | 25.3873 | 55.9722 | OSP Ready | Existing Fiber | IIB | RAK-3357-CSG-N540-LD-1 | NA | AUH-2122-SCSG-SR7B-1 | TBD |  | #N/A
| UAQ3472 | 5G | 5G | 5G |  |  | 25.3936 | 55.8308 | OSP Ready | Existing Fiber | IIB | UAQ-3472-CSG-IXR-E-1 | NA | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
| SHJ1522 | 5G | 5G | 5G |  |  | 25.3956 | 55.6379 | OSP Ready | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| KFN2793 | 5G | 5G | 5G |  |  | 25.3961 | 56.3515 | OSP Ready | Existing Fiber | IIB | KFN-2793-CSG-SAR-X-1 | NA | FUJ-2022-SCSG-SR7-1 | TBD |  | #N/A
| RAK2761 | 5G | 5G | 5G |  |  | 25.4015 | 56.0565 | OSP Ready | Existing Fiber | IIB | RAK-2761-CSG-N540-LD-1 | NA | AUH-2122-SCSG-SR7B-1 | TBD |  | #N/A
| KFN2832 | 5G | 5G | 5G |  |  | 25.4035 | 56.1495 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 597802 | 6 MONTHS
| AJM3817 | 5G | 5G | 5G |  |  | 25.4237 | 55.5708 | OSP Ready | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| KFN2681 | 5G | 5G | 5G |  |  | 25.4241 | 56.1519 | OSP Ready | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| UAQ2661 | 5G | 5G | 5G |  |  | 25.4252 | 55.5937 | Possible | 2024 Fiber | MW | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 159809.5 | 4 MONTHS
| UAQ2802 | 5G | 5G | 5G |  |  | 25.4298 | 55.7331 | OSP Ready | Existing Fiber | IIB | UAQ-2802-CSG-IXR-E-1 | NA | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
| AJM1345 | 5G | 5G | 5G |  |  | 25.44 | 55.5269 | Possible | 2024 Fiber | MW | NA | AJM2459 | AJM-2459-IBS-SAR-M-1 | New CSG | 126392 | 3 MONTHS
| KFN2616 | 5G | 5G | 5G |  |  | 25.4439 | 56.1272 | OSP Ready | Existing Fiber | IIB | KFN-2616-CSG-IXR-E-1 | NA | FUJ-6001-AGG-ASR9912-1 | TBD |  | #N/A
| UAQ2937 | 5G | 5G | 5G |  |  | 25.4464 | 55.6272 | OSP Ready | Existing Fiber | IIB | UAQ-2937-CSG-IXR-E-1 | NA | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
| RAK2745 | 5G | 5G | 5G |  |  | 25.4652 | 55.9808 | OSP Ready | Existing Fiber | IIB | RAK-2745-CSG-ASR920-LD-1 | NA | AUH-2122-SCSG-SR7B-1 | TBD |  | #N/A
| KFN2842 | 5G | 5G | 5G |  |  | 25.4721 | 56.3612 | OSP Ready | Existing Fiber | IIB | KFN-2842-CSG-SAR-X-1 | NA | FUJ-6001-AGG-ASR9912-1 | TBD |  | #N/A
| KFN2953 | 5G | 5G | 5G |  |  | 25.4793 | 56.1835 | Possible | 2024 Fiber | MW | NA | KFN2115 | KFN-2115-SCSG-SR7-1 | New CSG | 389266.5 | 8 Months
| UAQ2935 | 5G | 5G | 5G |  |  | 25.4955 | 55.6891 | OSP Ready | Existing Fiber | IIB | UAQ-2935-CSG-IXR-E-1 | NA | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
| UAQ3861 | 5G | 5G | 5G |  |  | 25.515 | 55.5828 | OSP Ready | Existing Fiber | IIB | UAQ-3861-CSG-N540-LD-1 | NA | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
| UAQ2932 | 5G | 5G | 5G |  |  | 25.5199 | 55.746 | OSP Ready | Existing Fiber | IIB | UAQ-2932-CSG-IXR-E-1 | NA | UAQ-2805-PREAGG-SR7-1 | TBD |  | #N/A
| UAQ1247 | 5G | 5G | 5G |  |  | 25.5224 | 55.5723 | OSP Ready | Existing Fiber | IIB | UAQ-1247-CSG-N540-LD-1 | NA | UAQ-DC-AGGR-SR7S-1 | TBD |  | #N/A
| RAK3105 | 5G | 5G | 5G |  |  | 25.5241 | 55.9064 | OSP Ready | Existing Fiber | IIB | RAK-3105-CSG-N540-LD-1 | NA | UAQ-2805-PREAGG-SR7-1 | TBD |  | #N/A
| UAQ2915 | 5G | 5G | 5G |  |  | 25.5246 | 55.5613 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 210264.5 | 5 MONTHS
| RAK2779 | 5G | 5G | 5G |  |  | 25.5339 | 56.0168 | OSP Ready | Existing Fiber | IIB | RAK-2779-CSG-N540-LD-1 | NA | AUH-2122-SCSG-SR7B-1 | TBD |  | #N/A
| RAK3122 | 5G | 5G | 5G |  |  | 25.5488 | 56.0342 | OSP Ready | Existing Fiber | IIB | RAK-3122-CSG-N540-LD-1 | NA | AUH-2122-SCSG-SR7B-1 | TBD |  | #N/A
| RAK2665 | 5G | 5G | 5G |  |  | 25.5533 | 55.8912 | OSP Ready | Existing Fiber | IIB | RAK-2665-CSG-IXR-E-1 | NA | UAQ-2805-PREAGG-SR7-1 | TBD |  | #N/A
| RAK6320 | 5G | 5G | 5G |  |  | 25.5659 | 56.0718 | OSP Ready | Existing Fiber | IIB | RAK-6320-CSG-IXR-E-1 | NA | FUJ-6001-AGG-ASR9912-1 | TBD |  | #N/A
| RAK2666 | 5G | 5G | 5G |  |  | 25.6104 | 55.8548 | OSP Ready | Existing Fiber | IIB | RAK-2666-CSG-IXR-E-1 | NA | UAQ-2806-PREAGG-SR7-1 | TBD |  | #N/A
| RAK2763 | 5G | 5G | 5G |  |  | 25.6803 | 55.9267 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 345884 | 6 MONTHS
| RAK2878 | 5G | 5G | 5G |  |  | 25.6907 | 55.9053 | OSP Ready | Existing Fiber | IIB | RAK-2878-CSG-SAR-X-1 | NA | RAK-2000-SCSG-SR7B-1 | TBD |  | #N/A
| RAK2659 | 5G | 5G | 5G |  |  | 25.6954 | 55.8776 | OSP Ready | Existing Fiber | IIB | RAK-2659-CSG-IXR-E-1 | NA | UAQ-2806-PREAGG-SR7-1 | TBD |  | #N/A
| RAK2600 | 5G | 5G | 5G |  |  | 25.7376 | 55.8882 | OSP Ready | Existing Fiber | IIB | RAK-2600-CSG-IXR-E-1 | NA | RAK-2000-SCSG-SR7B-1 | TBD |  | #N/A
| RAK2470 | 5G | 5G | 5G |  |  | 25.8226 | 55.9694 | OSP Ready | Existing Fiber | IIB | RAK-2470-CSG-IXR-E-1 | NA | RAK-2718-PREAGG-SR7-1 | TBD |  | #N/A
| RAK2858 | 5G | 5G | 5G |  |  | 25.8341 | 56.0055 | OSP Ready | Existing Fiber | IIB | RAK-2858-CSG-ASR920-LD-1 | NA | RAK-2718-PREAGG-SR7-1 | TBD |  | #N/A
| RAK3125 | 5G | 5G | 5G |  |  | 25.8456 | 56.0168 | OSP Ready | Existing Fiber | IIB | RAK-3125-CSG-ASR920-LD-1 | NA | RAK-2718-PREAGG-SR7-1 | TBD |  | #N/A
| RAK2690 | 5G | 5G | 5G |  |  | 25.86 | 56.013 | OSP Ready | Existing Fiber | IIB | RAK-2690-CSG-SAR-X-1 | NA | RAK-2727-SCSG-NCS57C3 | TBD |  | #N/A
| RAK2890 | 5G | 5G | 5G |  |  | 25.9594 | 56.0634 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 659527 | 6 MONTHS
| RAK2740 | 5G | 5G | 5G |  |  | 25.9685 | 56.094 | OSP Ready | Existing Fiber | IIB | RAK-2740-CSG-SAR-X-1 | NA | RAK-2727-SCSG-NCS57C3 | TBD |  | #N/A
| RAK2778 | 5G | 5G | 5G |  |  | 25.9688 | 56.0608 | OSP Ready | Existing Fiber | IIB | RAK-2778-CSG-IXR-E-1 | NA | RAK-2727-SCSG-NCS57C3 | TBD |  | #N/A
| FUJ1298 | BAU | 3G/4G | 3G/4G |  |  | 24.7808 | 56.1197 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 209435 | 4 Months
| FUJ1293 | BAU | 3G/4G | 3G/4G |  |  | 24.7905 | 56.1082 | Possible | 2024 Fiber | NA | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 169109 | 3 Months
| FUJ1497 | BAU | 3G/4G | 3G/4G |  |  | 24.8553 | 56.0037 | Possible | 2024 Fiber | NA | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 58380 | 2 Months
| FUJ3072 | BAU | 3G/4G | 3G/4G |  |  | 24.8666 | 56.2627 | Possible | 2024 Fiber | NA | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 469495.95 | 6 MONTHS
| FUJ1491 | BAU | 3G/4G | 3G/4G |  |  | 24.8992 | 56.105 | Possible | 2024 Fiber | NA | NA | FUJ2398 | FUJ-2398-SCSG-SRa8-1 | New CSG | 120567 | 3 Months
| FUJ1492 | BAU | 3G/4G | 3G/4G |  |  | 24.9133 | 56.1332 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 323277 | 5 Months
| FUJ3748 | BAU | 3G/4G | 3G/4G |  |  | 24.9346 | 56.1557 | Possible | 2024 Fiber | NA | NA | NA | NA | New MW Link | 235201 | 4 Months
| FUJ3928 | BAU | 3G/4G | 3G/4G |  |  | 25.0255 | 56.346 | Possible | 2024 Fiber | NA | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | New CSG | 51738 | 2 Months
| FUJ3315 | BAU | 3G/4G | 3G/4G |  |  | 25.0479 | 56.3618 | Possible | 2024 Fiber | NA | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | New CSG | 185354 | 3 Months
| SHJ6248 | BAU | 3G/4G | 3G/4G |  |  | 25.0642 | 55.6655 | Not Possible | 2024 MW | NA | NA | NA | NA | New MW Link |  | 0
| FUJ1577 | BAU | 3G/4G | 3G/4G |  |  | 25.0687 | 56.3551 | Possible | 2024 Fiber | NA | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | New CSG | 10355.95 | 2 Months
| FUJ1607 | BAU | 3G/4G | 3G/4G |  |  | 25.0869 | 56.124 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 221936 | 6 MONTH
| FUJ1250 | BAU | 3G/4G | 3G/4G |  |  | 25.1029 | 56.0602 | Not Possible | 2024 MW | NA | NA | NA | NA | New MW Link |  | 0
| FUJ1407 | BAU | 3G/4G | 3G/4G |  |  | 25.1364 | 56.2877 | CW Completed | 2024 Fiber | NA | NA | FUJ5003 | FUJ-5003-PREAGG-SRa8-1 | New CSG |  | 0
| SHJ1173 | BAU | 3G/4G | 3G/4G |  |  | 25.179 | 55.8036 | CW Completed | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ1391 | BAU | 3G/4G | 3G/4G |  |  | 25.2105 | 55.8917 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 367696.45 | 5 Months
| FUJ3055 | BAU | 3G/4G | 3G/4G |  |  | 25.2237 | 56.3004 | Not Possible | 2024 MW | NA | NA | NA | NA | New MW Link |  | 0
| FUJ3917 | BAU | 3G/4G | 3G/4G |  |  | 25.2307 | 56.3408 | Possible | 2024 Fiber | NA | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | New CSG | 56503 | 2 Months
| SHJ3657 | BAU | 3G/4G | 3G/4G |  |  | 25.232 | 55.6267 | Possible | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG | 83500 | 2 Months
| SHJ3668 | BAU | 3G/4G | 3G/4G |  |  | 25.2415 | 55.6484 | Possible | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG | 170500 | 2 Months
| SHJ1479 | BAU | 3G/4G | 3G/4G |  |  | 25.2501 | 55.6507 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ1275 | BAU | 3G/4G | 3G/4G |  |  | 25.2553 | 55.5885 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ3661 | BAU | 3G/4G | 3G/4G |  |  | 25.2567 | 55.6354 | Possible | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG | 155500 | 2 Months
| SHJ1664 | BAU | 3G/4G | 3G/4G |  |  | 25.2592 | 55.5918 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ6264 | BAU | 3G/4G | 3G/4G |  |  | 25.2621 | 55.5342 | Taawun | 2024 Fiber | NA | NA | SHJ2508 | SHJ-2508-SCSG-IXR-R6D-1 | New CSG |  | 0
| SHJ6246 | BAU | 3G/4G | 3G/4G |  |  | 25.2647 | 55.5874 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ3942 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.267 | 55.4821 | Taawun | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG |  | 0
| SHJ6255 | BAU | 3G/4G | 3G/4G |  |  | 25.2697 | 55.5863 | Taawun | 2024 Fiber | NA | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ2275 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.2751 | 55.51 | Possible | 2024 Fiber | NA | NA | SHJ2508 | SHJ-2508-SCSG-IXR-R6D-1 | New CSG | 68500 | 2 Months
| FUJ1125 | BAU | 3G/4G | 3G/4G |  |  | 25.2799 | 56.3712 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 218581 | 4 Months
| SHJ1680 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.2818 | 55.5065 | Possible | 2024 Fiber | NA | NA | SHJ2508 | SHJ-2508-SCSG-IXR-R6D-1 | New CSG | 22532.95 | 3 Months
| SHJ1390 | BAU | 3G/4G | 3G/4G |  |  | 25.2866 | 55.8828 | Possible | 2024 Fiber | NA | NA | SHJ5001 | SHJ-5001-SCSG-SR7B-1 | New CSG | 35500 | 1 MONTH
| SHJ1488 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.2979 | 55.4411 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 45500 | 1 MONTH
| SHJ1485 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3045 | 55.4567 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 72500 | 2 Months
| SHJ1621 | BAU | 3G/4G | 3G/4G |  |  | 25.3049 | 55.6047 | Possible | 2024 Fiber | NA | NA | SHJ5003 | SHJ-5003-SCSG-SR7B-1 | New CSG | 110500 | 2 Months
| SHJ1640 | BAU | 3G/4G | 3G/4G |  |  | 25.3056 | 55.4672 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 71403 | 2 Months
| SHJ1628 | BAU | 3G/4G | 3G/4G |  |  | 25.3058 | 55.4553 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 35500 | 1 MONTH
| SHJ1019 | BAU | 3G/4G | 3G/4G |  |  | 25.3063 | 55.458 | CW Completed | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG |  | 0
| SHJ1629 | BAU | 3G/4G | 3G/4G |  |  | 25.3078 | 55.4598 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 50500 | 2 Months
| SHJ1631 | BAU | 3G/4G | 3G/4G |  |  | 25.312 | 55.454 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 80500 | 2 Months
| SHJ1630 | BAU | 3G/4G | 3G/4G |  |  | 25.3121 | 55.4513 | Possible | 2024 Fiber | NA | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 55500 | 1 MONTH
| SHJ1401 | BAU | 3G/4G | 3G/4G |  |  | 25.3316 | 55.7307 | Possible | 2024 Fiber | NA | NA | SHJ5003 | SHJ-5003-SCSG-SR7B-1 | New CSG | 13974.95 | 3 Months
| SHJ1536 | BAU | 3G/4G | 3G/4G |  |  | 25.3349 | 55.6457 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 210500 | 2 Months
| SHJ1635 | BAU | 3G/4G | 3G/4G |  |  | 25.3417 | 55.5658 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 207084 | 2 Months
| SHJ1556 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3449 | 55.4013 | Possible | 2024 Fiber | NA | NA | SHJ2022 | SHJ-2022-AGGR-SR7b-1 | New CSG | 75500 | 2 Months
| KFN3955 | BAU | 3G/4G | 3G/4G |  |  | 25.3466 | 56.3303 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 323538 | 6 Months
| KFN1011 | BAU | 3G/4G | 3G/4G |  |  | 25.3512 | 56.3531 | Possible | 2024 Fiber | NA | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | New CSG | 114274 | 3 Months
| SHJ1214 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3599 | 55.4724 | CW Completed | 2024 Fiber | NA | NA | SHJ2035 | SHJ-2035-SCSG-SR7B-1 | New CSG |  | 0
| SHJ3317 | BAU | 3G/4G | 3G/4G |  |  | 25.3614 | 55.7026 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 462483.45 | 5 Months
| SHJ1516 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3644 | 55.3983 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | New CSG |  | 0
| AJM1667 | BAU | 3G/4G | 3G/4G |  |  | 25.3665 | 55.5703 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 13326.5 | 3 Months
| AJM1666 | BAU | 3G/4G | 3G/4G |  |  | 25.3677 | 55.5814 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 12089 | 3 Months
| AJM1682 | BAU | 3G/4G | 3G/4G |  |  | 25.3694 | 55.5886 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 25619 | 3 Months
| AJM1686 | BAU | 3G/4G | 3G/4G |  |  | 25.3707 | 55.5685 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 220869 | 4 Months
| AJM1587 | BAU | 3G/4G | 3G/4G |  |  | 25.3727 | 55.5664 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 450396 | 2 Months
| AJM1652 | BAU | 3G/4G | 3G/4G |  |  | 25.3731 | 55.5713 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 220620 | 5 Months
| AJM1563 | BAU | 3G/4G | 3G/4G |  |  | 25.3741 | 55.5962 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 65738.86 | 2 Months
| AJM1588 | BAU | 3G/4G | 3G/4G |  |  | 25.3741 | 55.5743 | Taawun | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG |  | 0
| AJM1395 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3789 | 55.4588 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG | 59908 | 2 Months
| SHJ2330 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3795 | 55.446 | Possible | 2024 Fiber | NA | NA | SHJ2515 | SHJ-2515-SCSG-SR7B-1 | New CSG | 80500 | 2 Months
| AJM1461 | BAU | 3G/4G | 3G/4G |  |  | 25.3831 | 55.5872 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | New CSG |  | 0
| AJM1386 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3878 | 55.4524 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG | 47188 | 2 Months
| AJM1388 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.3959 | 55.4403 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG | 91530 | 2 Months
| AJM1624 | BAU | 3G/4G | 3G/4G |  |  | 25.3999 | 55.6045 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 165264 | 2 Months
| AJM1626 | BAU | 3G/4G | 3G/4G |  |  | 25.4015 | 55.5876 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 225516 | 2 Months
| AJM1625 | BAU | 3G/4G | 3G/4G |  |  | 25.4048 | 55.5947 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 79819 | 2 Months
| AJM1392 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.405 | 55.4337 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG | 132157 | 2 Months
| AJM1611 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.4093 | 55.4329 | Possible | 2024 Fiber | NA | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG | 168701 | 2 Months
| AJM1254 | BAU | 3G/4G | 3G/4G |  |  | 25.4099 | 55.5425 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | New CSG |  | 0
| AJM1434 | BAU | 3G/4G | 3G/4G |  |  | 25.417 | 55.595 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 303944 | 2 Months
| AJM1665 | BAU | 3G/4G | 3G/4G |  |  | 25.42 | 55.5995 | Possible | 2024 Fiber | NA | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG | 44835.45 | 3 Months
| AJM1111 | BAU | 3G/4G | 3G/4G |  |  | 25.4357 | 55.5857 | Possible | 2024 Fiber | NA | NA | AJM2457 | AJM-2457-SCSG-IXR-R6D-1 | New CSG | 150720 | 3 Months
| KFN3464 | BAU | 3G/4G | 3G/4G |  |  | 25.4676 | 56.1433 | Possible | 2024 Fiber | NA | NA | RAK2722 | RAK-2027-CSG-IXR-E-1 | New CSG | 35500 | 1 MONTH
| UAQ1613 | BAU | 3G/4G | 3G/4G |  |  | 25.4711 | 55.6514 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 294210.95 | 5 Months
| UAQ1649 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.5188 | 55.5457 | Possible | 2024 Fiber | NA | NA | UAQ2012 | UAQ-2012-PREAGG-SR7-1 | New CSG | 65142 | 3 Months
| KFN1638 | BAU | 3G/4G | 3G/4G |  |  | 25.562 | 56.1946 | Possible | 2024 Fiber | NA | NA | KFN2115 | KFN-2115-SCSG-SR7-1 | New CSG | 167811 | 4 Months
| RAK6319 | BAU | 3G/4G | 3G/4G |  |  | 25.5804 | 56.1353 | Possible | 2024 MW | MW | NA | NA | NA | New MW Link | 381568 | 6 MONTHS
| KFN1566 | BAU | 3G/4G | 3G/4G |  |  | 25.593 | 56.3185 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 260500 | 3 Months
| RAK3537 | BAU | 3G/4G | 3G/4G |  |  | 25.6646 | 55.8518 | Possible | 2024 Fiber | NA | NA | RAK2028 | RAK-2028-CSG-IXR-E-1 | New CSG | 73984 | 2 Months
| RAK1494 | BAU | 3G/4G | 3G/4G |  |  | 25.6697 | 55.744 | CW Completed | 2024 Fiber | NA | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | New CSG |  | 0
| RAK1687 | BAU | 3G/4G | 3G/4G |  |  | 25.6886 | 55.957 | Possible | 2024 Fiber | NA | NA | RAK2026 | RAK-2026-SCSG-IXR-R6D-1 | New CSG | 106782.5 | 3 MONTHS
| RAK3786 | BAU | 3G/4G | 3G/4G |  |  | 25.6913 | 55.8899 | Possible | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | New CSG | 120918.65 | 2 months
| RAK3934 | BAU | 3G/4G | 3G/4G |  |  | 25.6962 | 55.9497 | Possible | 2024 Fiber | NA | NA | RAK2026 | RAK-2026-SCSG-IXR-R6D-1 | New CSG | 94109 | 2 months
| RAK1688 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.7 | 55.9102 | Possible | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | New CSG | 128105.45 | 6 MONTHS
| RAK1169 | BAU | 3G/4G | 3G/4G |  |  | 25.7055 | 55.9203 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | New CSG |  | 0
| RAK1663 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.7178 | 55.9194 | Possible | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | New CSG | 99584.65 | 4 MONTHS
| RAK1676 | BAU | 3G/4G | 3G/4G |  |  | 25.7608 | 56 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 314049.45 | 6 MONTHS
| RAK3858 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.7635 | 55.9231 | Possible | 2024 Fiber | NA | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | New CSG | 69938 | 2 months
| RAK1243 | BAU | 3G/4G | 3G/4G |  |  | 25.7776 | 56.0191 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 208013 | 2 months
| RAK1532 | BAU | 3G/4G | 3G/4G |  |  | 25.7896 | 55.9493 | Possible | 2024 Fiber | NA | NA | RAK2704 | RAK-2003-CSG-SAR-X-1 | New CSG | 51358.25 | 2 months
| RAK3151 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.7897 | 55.9373 | OSP Ready | 2024 Fiber | NA | NA | SLD on SPS | NA | New CSG |  | 0
| RAK3997 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.8076 | 55.9609 | Possible | 2024 Fiber | NA | NA | RAK2718 | RAK-2718-PREAGG-SR7-1 | New CSG | 77792 | 2 months
| RAK1393 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.8121 | 55.9912 | Possible | 2024 Fiber | MW | NA | RAK2718 | RAK-2718-CSG-IXR-E-1 | New CSG | 94455.5 | 2 months
| RAK3974 | BAU + 5G | 3G/4G/5G | 3G/4G/5G |  |  | 25.8301 | 55.9993 | Possible | 2024 MW | NA | NA | NA | NA | New MW Link | 234119.15 | 2 months
| RAK3354 | BAU | 3G/4G | 3G/4G |  |  | 25.8949 | 56.1395 | Not Possible | 2024 MW | NA | NA | NA | NA | New MW Link |  | 0
| AJM2117 | Migration | Migration | Migration |  |  | 25.3911 | 55.4837 | Possible | 2024 Fiber | MW | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | New CSG | 45000 | 6 Months
| AJM3982 | Migration | Migration | Migration |  |  | 25.3692 | 55.5763 | Taawun | 2024 Fiber | MW | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG |  | 0
| FUJ1014 | Migration | Migration | Migration |  |  | 24.8283 | 56.0507 | WIP CF 2023 | 2024 Fiber | MW | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 50000 | 2 Months
| FUJ1068 | Migration | Migration | Migration |  |  | 24.8185 | 56.0343 | WIP CF 2023 | 2024 Fiber | MW | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 170000 | 3 Months
| FUJ1230 | Migration | Migration | Migration |  |  | 25.2687 | 56.1651 | WIP CF 2023 | 2024 Fiber | MW | NA | FUJ5003 | FUJ-5003-PREAGG-SRa8-1 | New CSG | 245000 | 3 months
| FUJ2689 | Migration | Migration | Migration |  |  | 25.0906 | 56.3436 | Possible | 2024 Fiber | MW | NA | FUJ2014 | FUJ-2014-SCSG-IXR-R6D-1 | New CSG | 160000 | 6 Months
| FUJ2968 | Migration | Migration | Migration |  |  | 25.1745 | 56.351 | OSP Provisioned | 2024 Fiber | MW | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | New CSG | 15000 | 1 MONTH
| FUJ3073 | Migration | Migration | Migration |  |  | 25.0253 | 56.363 | Possible | 2024 Fiber | MW | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | New CSG | 200000 | 6 Months
| FUJ3274 | Migration | Migration | Migration |  |  | 25.1598 | 56.2542 | Possible | 2024 Fiber | MW | NA | FUJ5003 | FUJ-5003-PREAGG-SRa8-1 | New CSG | 108129 | 3 Months
| FUJ3407 | Migration | Migration | Migration |  |  | 25.1666 | 56.2855 | Possible | 2024 Fiber | MW | NA | FUJ5002 | FUJ-5002-SCSG-SR7-1 | New CSG | 65000 | 6 Months
| FUJ3409 | Migration | Migration | Migration |  |  | 25.174 | 56.3108 | CW Completed | 2024 Fiber | MW | NA | FUJ5002 | FUJ-5002-SCSG-SR7-1 | New CSG |  | 0
| FUJ3570 | Migration | Migration | Migration |  |  | 25.2719 | 56.2841 | CW Completed | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| FUJ3708 | Migration | Migration | Migration |  |  | 25.075 | 56.2493 | WIP CF 2023 | 2024 Fiber | MW | NA | FUJ5002 | FUJ-5002-SCSG-SR7-1 | New CSG | 375000 | 3 Months
| FUJ3835 | Migration | Migration | Migration |  |  | 24.8843 | 56.1875 | OSP Provisioned | 2024 Fiber | MW | NA | FUJ2437 | FUJ-2437-IBS-SAR-M-1 | New CSG | 15000 | 1 MONTH
| FUJ3915 | Migration | Migration | Migration |  |  | 25.2503 | 56.3405 | WIP CF 2023 | 2024 Fiber | MW | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | New CSG | 150000 | 2 Months
| FUJ3926 | Migration | Migration | Migration |  |  | 25.0984 | 56.322 | WIP CF 2023 | 2024 Fiber | MW | NA | FUJ2014 | FUJ-2014-SCSG-IXR-R6D-1 | New CSG | 160000 | 3 months
| KFN2469 | Migration | Migration | Migration |  |  | 25.3342 | 56.3513 | Possible | 2024 Fiber | MW | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | New CSG | 70000 | 2 Months
| KFT3098 | Migration | Migration | Migration |  |  | 25.5206 | 56.3656 | WIP CF 2023 | 2024 Fiber | MW | NA | KFN2678 | KFN-2678-CSG-IXR-E-1 | New CSG | 223166 | 3 Months
| RAK1048 | Migration | Migration | Migration |  |  | 25.6743 | 55.8115 | Possible | 2024 Fiber | MW | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | New CSG | 65000 | 3 Months
| RAK1066 | Migration | Migration | Migration |  |  | 25.7476 | 56.0067 | OSP Provisioned | 2024 Fiber | MW | NA | RAK6001 | RAK-6001-AGGR-SR7S-1 | New CSG | 15000 | 1 MONTH
| RAK1201 | Migration | Migration | Migration |  |  | 25.5413 | 55.9475 | Taawun | 2024 Fiber | MW | NA | RAK2722 | RAK-2027-CSG-IXR-E-1 | New CSG |  | 0
| RAK1203 | Migration | Migration | Migration |  |  | 25.5352 | 55.9603 | Taawun | 2024 Fiber | MW | NA | RAK2722 | RAK-2027-CSG-IXR-E-1 | New CSG |  | 0
| RAK1244 | Migration | Migration | Migration |  |  | 25.8001 | 55.992 | Possible | 2024 Fiber | MW | NA | RAK6001 | RAK-6001-AGGR-SR7S-1 | New CSG | 122005.4 | 2 months
| RAK3007 | Migration | Migration | Migration |  |  | 25.0226 | 55.9789 | Possible | 2024 Fiber | MW | NA | SHJ3612 | SHJ-3612-CSG-SAR-8-1 | New CSG | 550000 | 8 Months
| RAK3175 | Migration | Migration | Migration |  |  | 25.7803 | 55.9693 | Possible | 2024 Fiber | MW | NA | RAK6001 | RAK-6001-AGGR-SR7S-1 | New CSG | 110000 | 4 Months
| RAK3358 | Migration | Migration | Migration |  |  | 25.4971 | 56.0585 | Possible | 2024 Fiber | MW | NA | RAK2722 | RAK-2027-CSG-IXR-E-1 | New CSG | 110000 | 6 Months
| RAT2169 | Migration | Migration | Migration |  |  | 25.7128 | 55.944 | Taawun | 2024 Fiber | MW | NA | RAK2700 | RAK-2000-SCSG-SR7B-1 | New CSG |  | 0
| SHJ2597 | Migration | Migration | Migration |  |  | 24.8334 | 55.7829 | Possible | 2024 Fiber | MW | NA | SHJ3612 | SHJ-3612-CSG-SAR-8-1 | New CSG | 670000 | 6 months
| SHJ2948 | Migration | Migration | Migration |  |  | 25.3542 | 55.4836 | Possible | 2024 Fiber | MW | NA | SHJ2053 | SHJ-2053-AGGR-SR7B-1 | New CSG | 50000 | 4 Months
| SHJ3327 | Migration | Migration | Migration |  |  | 24.9086 | 55.8109 | CW Completed | 2024 Fiber | MW | NA | SHJ3612 | SHJ-3612-CSG-SAR-8-1 | New CSG |  | 0
| SHJ3546 | Migration | Migration | Migration |  |  | 25.3202 | 55.4423 | Possible | 2024 Fiber | MW | NA | SHJ2047 | SHJ-2047-SCSG-SR7B-1 | New CSG | 30000 | 4 Months
| SHJ3685 | Migration | Migration | Migration |  |  | 25.3216 | 55.4802 | Taawun | 2024 Fiber | MW | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG |  | 0
| SHJ3768 | Migration | Migration | Migration |  |  | 25.2573 | 55.6445 | Taawun | 2024 Fiber | MW | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG |  | 0
| SHJ3796 | Migration | Migration | Migration |  |  | 25.1853 | 55.8054 | Possible | 2024 Fiber | MW | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG | 120000 | 6 Months
| SHJ3901 | Migration | Migration | Migration |  |  | 24.883 | 55.7915 | Possible | 2024 Fiber | MW | NA | SHJ3612 | SHJ-3612-CSG-SAR-8-1 | New CSG | 350000 | 6 months
| UAQ1005 | Migration | Migration | Migration |  |  | 25.4733 | 55.6966 | CW Completed | 2024 Fiber | MW | NA | UAQ DC | UAQ-DC-AGGR-SR7S-1 | New CSG |  | 0
| UAQ1237 | Migration | Migration | Migration |  |  | 25.2961 | 55.9828 | WIP CF 2023 | 2024 Fiber | MW | NA | RAK2722 | RAK-2027-CSG-IXR-E-1 | New CSG | 300212 | 3 MONTHS
| UAQ1246 | Migration | Migration | Migration |  |  | 25.5879 | 55.5665 | Possible | 2024 Fiber | MW | NA | UAQ2012 | UAQ-2012-PREAGG-SR7-1 | New CSG | 150000 | 6 Months
| UAQ2925 | Migration | Migration | Migration |  |  | 25.3282 | 55.912 | OSP Ready | 2024 Fiber | MW | NA | SLD on SPS | NA | New CSG |  | 0
| FUJ1592 | Migration | Migration | Migration |  |  | 24.8768 | 55.9917 | Possible | 2024 Fiber | MW | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 135621 | 3 Months
| FUJ1422 | Migration | Migration | Migration |  |  | 24.9809 | 56.3385 | Possible | 2024 Fiber | MW | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | New CSG | 149617 | 4 Months
| RAK1168 | Migration | Migration | Migration |  |  | 25.7076 | 55.9316 | Taawun | 2024 Fiber | MW | NA | RAK2000 | RAK-2000-SCSG-SR7B-1 | New CSG |  | 0
| AJM0926 | Migration | Migration | Migration |  |  | 25.4098 | 55.4343 | OSP Provisioned | 2024 Fiber | MW | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG | 15000 | 4 Months
| SHJ0389 | Migration | Migration | Migration |  |  | 25.3348 | 55.3885 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2016 | SHJ-2016-SCSG-SR7B-1 | New CSG | 10000 | 1 MONTH
| SHJ0331 | Migration | Migration | Migration |  |  | 25.3363 | 55.3608 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | New CSG | 15000 | 1 MONTH
| SHJ0333 | Migration | Migration | Migration |  |  | 25.3685 | 55.3859 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | New CSG | 15000 | 4 Months
| RAK0536 | Migration | Migration | Migration |  |  | 25.6165 | 56.0136 | OSP Provisioned | 2024 Fiber | MW | NA | RAK2722 | RAK-2027-CSG-IXR-E-1 | New CSG | 50000 | 4 Months
| RAK0521 | Migration | Migration | Migration |  |  | 25.6827 | 55.7463 | WIP CF 2023 | 2024 Fiber | MW | NA | UAQ2018 | RAK-5001-CSG-SAR-8-1 | New CSG | 60000 | 2 Months
| FUJ0625 | Migration | Migration | Migration |  |  | 25.1278 | 56.2687 | Possible | 2024 Fiber | MW | NA | Kalba CLS | KLB-DC-SCSG-SR7B-1 | New CSG | 80000 | 6 Months
| SHJ0423 | Migration | Migration | Migration |  |  | 25.3089 | 55.5745 | Possible | 2024 Fiber | MW | NA | SHJ5003 | SHJ-5003-SCSG-SR7B-1 | New CSG | 80000 | 6 Months
| FUJ0631 | Migration | Migration | Migration |  |  | 24.8004 | 56.1276 | OSP Provisioned | 2024 Fiber | MW | NA | FUJ2433 | FUJ-2433-IBS-SAR-M-1 | New CSG | 15000 | 4 Months
| SHJ5498A | Migration | Migration | Migration |  |  | 25.3059 | 55.4425 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2047 | SHJ-2047-SCSG-SR7B-1 | New CSG | 10000 | 1 MONTH
| SHJ0314 | Migration | Migration | Migration |  |  | 25.314 | 55.3646 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | New CSG | 15000 | 4 Months
| SHJ0212 | Migration | Migration | Migration |  |  | 25.355 | 55.4045 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2022 | SHJ-2022-AGGR-SR7b-1 | New CSG | 15000 | 4 Months
| SHJ0361 | Migration | Migration | Migration |  |  | 25.36 | 55.3782 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2084 | SHJ-2084-SCSG-SR7B-1 | New CSG | 15000 | 4 Months
| SHJ0449 | Migration | Migration | Migration |  |  | 25.1774 | 55.8064 | Possible | 2024 Fiber | MW | NA | SHJ2547 | SHJ-2547-SCSG-SR7B-1 | New CSG | 70000 | 6 Months
| SHJ0445 | Migration | Migration | Migration |  |  | 25.3668 | 55.4054 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2019 | SHJ-2019-SCSG-IXR-R6D-1 | New CSG | 15000 | 4 Months
| SHJ0405 | Migration | Migration | Migration |  |  | 25.3566 | 55.4009 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2058 | SHJ-2058-SCSG-IXR-R6-1 | New CSG | 15000 | 4 Months
| SHJ0211 | Migration | Migration | Migration |  |  | 25.3537 | 55.4875 | Possible | 2024 Fiber | MW | NA | SHJ2053 | SHJ-2053-AGGR-SR7B-1 | New CSG | 130000 | 4 Months
| UAQ0754 | Migration | Migration | Migration |  |  | 25.5009 | 55.599 | OSP Provisioned | 2024 Fiber | MW | NA | UAQ-DC | UAQ-DC-AGGR-SR7S-1 | New CSG | 15000 | 1 MONTH
| AJM0871 | Migration | Migration | Migration |  |  | 25.4165 | 55.4958 | OSP Provisioned | 2024 Fiber | MW | NA | AJM2021 | AJM-2310-CSG-ASR920-LD-1 | New CSG | 15000 | 4 Months
| KFN0702 | Migration | Migration | Migration |  |  | 25.3714 | 56.3488 | OSP Provisioned | 2024 Fiber | MW | NA | KFN2620 | KFN-2108-IBS-SAR-M-1 | New CSG | 25000 | 1 MONTH
| SHJ0363 | Migration | Migration | Migration |  |  | 25.2995 | 55.4895 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2049 | SHJ-2049-AGGR-SR7b-1 | New CSG | 25000 | 1 MONTH
| SHJ0056 | Migration | Migration | Migration |  |  | 25.3087 | 55.3729 | OSP Provisioned | 2024 Fiber | MW | NA | SHJ2580 | SHJ-2580-PREAGG-SR7-1 | New CSG | 25000 | 1 MONTH
| KFN5750B | Migration | Migration | Migration |  |  | 25.3105 | 56.3455 | OSP Provisioned | 2024 Fiber | MW | NA | FUJ2022 | FUJ-2022-SCSG-SR7-1 | New CSG | 10000 | 1 MONTH
| FUJ0677 | Migration | Migration | Migration |  |  | 25.1619 | 56.3454 | CW Completed | 2024 Fiber | MW | NA | FUJ6001 | FUJ-6001-AGG-ASR9912-1 | New CSG |  | 0
| IAJ5826 | Migration | Migration | Migration |  |  | 25.4037 | 55.4484 | Possible | 2024 Fiber | MW | NA | AJM2121 | AJM-2121-CSG-ASR920-LD-1 | New CSG | 30000 | 6 Months
| IAJ5859 | Migration | Migration | Migration |  |  | 25.3931 | 55.4626 | CW Completed | 2024 Fiber | MW | NA | AJM6001 | AJM-0925-CSG-N540-LD-1 | New CSG |  | 0
| IAJ5842 | Migration | Migration | Migration |  |  | 25.394 | 55.5671 | Taawun | 2024 Fiber | MW | NA | AJM2450 | AJM-2450-IBS-SAR-M-1 | New CSG |  | 0
| AJM1253 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS OPEX | 25.4099 | 55.5314 | OSP Provisioned | Fiber Added 2024 | NA |  |  |  |  | 15000 | 2 Months
| FUJ1028 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 24.837 | 56.0272 | GSM Not Constrcuted | MW added 2024 | NA |  |  |  |  | 215000 | 5 Months
| FUJ1229 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.2648 | 56.1112 | Mountain area-Subject to Town planning approval | MW added 2024 | NA |  |  |  |  | 780000 | 8 Months
| FUJ1231 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 25.1564 | 56.298 | Not possible-ROW or planning not available to propose fiber route | Site is canceled | NA
| FUJ1325 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 25.0358 | 56.3269 | Taawun area | Fiber Added 2024 | NA
| FUJ1437 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 24.7806 | 56.1112 | Not possible-Area under construction & ROW not available-Near Hatta Dam | MW added 2024 | NA
| FUJ1442 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.0656 | 56.3479 |  | MW added 2024 | NA |  |  |  |  | 82000 | 4 Months
| FUJ1722 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du Solo | 25.068 | 56.35 |  | Already MW | NA |  |  |  |  | 15000 | 3 Months
| FUJ3410 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Colocation | Colocation | 25.2204 | 56.3536 | OSP Ready | Existing Fiber (Added) | NA
| KFN1151 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 25.3638 | 56.3377 | Not possible-Mountain area | MW added 2024 | NA
| KFN3631 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.4857 | 56.359 | GSM not found and location in Mountain | MW added 2024 | NA |  |  |  |  | 80000 | 4 Months
| KFN3844 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.3829 | 56.3181 | Taawun area | Fiber Added 2024 | NA
| KFN3847 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.3384 | 56.3431 | GSM not found and Corridor in Asphalt parking | Fiber Added 2024 | NA |  |  |  |  | 50000 | 4 Months
| RAK1167 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.7014 | 55.9685 | OSP Ready | Existing Fiber (Added) | NA
| RAK1227 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.7129 | 55.9438 | Taawun area | Fiber Added 2024 | NA
| RAK1312 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 25.9536 | 56.0534 | Inside RAK Maritime city, Port | MW added 2024 | NA |  |  |  |  | 400000 | 6 Months
| RAK1441 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.9081 | 56.0593 | CF 2023 Site-Work in progress (ECD: 20/Mar/2024) | Fiber Added 2024 | NA
| RAK1525 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.6061 | 55.9199 | Fiber route plan through MW site UAQ2815 | MW added 2024 | NA |  |  |  |  | 760000 | 6 Months
| RAK3849 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.7188 | 55.8255 | Not Possible-Corridor Issue | MW added 2024 | NA
| RAK3872 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.6804 | 55.8385 | GSM Not Constrcuted | MW added 2024 | NA |  |  |  |  | 220000 | 4 Months
| RAK3988 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.7183 | 55.9448 | GSM Not Constrcuted | MW added 2024 | NA |  |  |  |  | 195000 | 5 Months
| SHJ1506 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du Solo | 25.3599 | 55.4718 | GSM not found | MW, as site is temp | NA |  |  |  |  | 35000 | 3 Months
| SHJ3321 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.3369 | 55.4486 | OSP Provisioned | Fiber Added 2024 | NA |  |  |  |  | 20000 | 2 Months
| SHJ3656 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS OPEX | 25.2377 | 55.5853 |  | MW added 2024 | NA |  |  |  |  | 255000 | 4 Months
| SHJ3663 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.2615 | 55.6227 | High level area & GSM Not Constrcuted | MW added 2024 | NA |  |  |  |  | 230000 | 5 Months
| SHJ3764 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.2623 | 55.5828 | Taawun area | Fiber Added 2024 | NA
| SHJ3887 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.3541 | 55.5623 | GSM Not Constrcuted | Fiber Added 2024 | NA |  |  |  |  | 30000 | 3 Months
| SHJ6243 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 25.3441 | 55.476 | GSM Not Constrcuted | Fiber Added 2024 | NA |  |  |  |  | 54000 | 3 Months
| SHJ6244 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.3222 | 55.3582 | Taawun area | Fiber Added 2024 | NA
| SHJ6251 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.2724 | 55.5398 | GSM Not Constrcuted | Fiber Added 2024 | NA |  |  |  |  | 15000 | 2 Months
| SHJ6252 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Greenfield | Du CAPEX | 25.1959 | 55.8212 | No Access to Military Camp (Al Bata'eh) | MW added 2024 | NA |  |  |  |  | 470000 | 5 Months
| SHJ6260 | 2024 MainScope (2023 Carryforward) | 2024 MainScope (2023 Carryforward) | Macro | Site Share | SS CAPEX | 25.3147 | 55.4729 | Taawun area | Fiber Added 2024 | NA
| SHJ3136 | 5G Colocation | 5G Colocation | Macro |  |  | 25.3739 | 55.7888 |  | MW added 2024 | MW |  |  |  |  | 1250000 | 8 Months
| SHJ3880 | 5G Colocation | 5G Colocation | Macro |  |  | 25.0329 | 55.7435 |  | MW added 2024 | MW |  |  |  |  | 550000 | 6 Months
| FUJ1059 | 5G Colocation | 5G Colocation | Macro |  |  | 24.9289 | 56.2393 | Not Possible-Corridor Issue | MW added 2024 | MW
| FUJ2796 | 5G Colocation | 5G Colocation | Macro |  |  | 25.4473 | 56.197 | Dependancy from Y-2024 KFN2953 | MW added 2024 | MW |  |  |  |  | 850000 | 8 Months
| FUJ2797 | 5G Colocation | 5G Colocation | Macro |  |  | 25.5028 | 56.2139 |  | Fiber Added 2024 | MW |  |  |  |  | 70000 | 6 Months
| FUJ2903 | 5G Colocation | 5G Colocation | Macro |  |  | 25.1775 | 56.2456 | Not Possible-ROW not available & Etihad Rail Crossing | MW added 2024 | MW
| FUJ3262 | 5G Colocation | 5G Colocation | Macro |  |  | 24.8937 | 56.0899 |  | MW added 2024 | MW |  |  |  |  | 290000 | 7 Months
| FUJ3263 | 5G Colocation | 5G Colocation | Macro |  |  | 25.0791 | 56.0262 | Ministry Road crossing & Hard surface area | MW added 2024 | MW |  |  |  |  | 300000 | 8 Months
| KFN2951 | 5G Colocation | 5G Colocation | Macro |  |  | 25.3622 | 56.1636 | Dependancy from Y-2024 FUJ2905 & KFN2955, KFN6313 | MW added 2024 | MW |  |  |  |  | 290000 | 10 Months
| KFN2952 | 5G Colocation | 5G Colocation | Macro |  |  | 25.4135 | 56.1923 | Dependancy from FUJ2796 | MW added 2024 | MW |  |  |  |  | 800000 | 9 Months
| KFN2955 | 5G Colocation | 5G Colocation | Macro |  |  | 25.3392 | 56.1723 | Dependancy from Y-2024 FUJ2905 | MW added 2024 | MW |  |  |  |  | 370000 | 8 Months
| KFN6313 | 5G Colocation | 5G Colocation | Macro |  |  | 25.3512 | 56.1638 | Dependancy from Y-2024 FUJ2905 & KFN2955 | MW added 2024 | MW |  |  |  |  | 415000 | 9 Months
| KFN6316 | 5G Colocation | 5G Colocation | Macro |  |  | 25.4668 | 56.1888 | Dependancy from Y-2024 KFN2953 | MW added 2024 | MW |  |  |  |  | 260000 | 8 Months
| RAK2859 | 5G Colocation | 5G Colocation | Macro |  |  | 26.0403 | 56.0865 | Not Possible (Ras AlDara Border) | MW added 2024 | MW
| RAK3120 | 5G Colocation | 5G Colocation | Macro |  |  | 26.0489 | 56.0871 | Not Possible (Ras AlDara Border) | MW added 2024 | MW
| KFN1326 | 5G Colocation | 5G Colocation | Macro |  |  | 25.3633 | 56.1738 | Dependancy from Y-2024 FUJ2905 & KFN2955, KFN6313, KFN2951 | MW added 2024 | MW |  |  |  |  | 250000 | 10 Months
| KFN3777 | 5G Colocation | 5G Colocation | Macro |  |  | 25.5865 | 56.3563 | Access issue & Asphalt surface inside premises | MW added 2024 | MW |  |  |  |  | 250000 | 4 Months
| RAK1443 | 5G Colocation | 5G Colocation | Macro |  |  | 25.8421 | 56.0768 | Not possible-Jabel jais | MW added 2024 | MW
| AJM1620 | 2024 Buffer |  |  |  |  | 25.3966 | 55.4925 | 22-02-24: Kashif OSP Cost = 35K Timeline= 2 months | Fiber Added 2024 | [5 empty] | 35000 | 2 months

## Summary
Row Labels | Count of 2024 plan | Sum of OSP cost | Row Labels | Count of 2024 plan | Sum of OSP cost
2024 Fiber | 382 | 19178780.791 | 2024 Fiber | 382 | 19178780.791
2024 MW | 62 | 15488958.701 | Existing Fiber | 275 | 25000
Already MW | 1 | 15000 | Existing Fiber (Added) | 2
Existing Fiber | 275 | 25000 | Fiber Added 2024 | 15 | 289000
Existing Fiber (Added) | 2 |  | Grand Total | 674 | 19492780.791
Fiber Added 2024 | 15 | 289000
MW added 2024 | 31 | 9562000
MW, as site is temp | 1 | 35000
NA | 15
Site is canceled | 1
Grand Total | 785 | 44593739.492